Board Staff Interrogatories

Application for Extension to Mandated Time-of-Use Pricing Date for Regulated Price Plan Customers

Hydro 2000 Inc.

EB-2011-0259

Dated August 11, 2011

Board Staff question 1

Preamble

Hydro 2000 Inc. (“Hydro 2000”) filed an application dated July 4, 2011 with the Ontario Energy Board for a license amendment granting an extension in relation to the mandated date for the implementation of time-of-use (“TOU”) pricing rates for its Regulated Price Plan (“RPP”) consumers.

Under cover of a letter to all Ontario electricity distributors dated August 4, 2010, the Ontario Energy Board provided its determination of mandatory dates by which each distributor must bill those of its RPP customers that have eligible TOU meters using TOU pricing. Hydro 2000 has applied for an extension to its October 2011 mandated TOU pricing date and requested a new date of January 2012.

Hydro 2000 has stated that in its application that it has completed System Integration Testing (SIT) and started Qualification Testing (QT) in July 2011.

Hydro 2000 cited three reasons for requesting an extension.

The first reason was:

1. Customer Transition to TOU Rates

While Hydro 2000 has been preparing its customers for the introduction of TOU rates through published information and bills inserts, significant customer distress is expected when customers are suddenly faced with larger bills resulting, in part, from their lack of experience in managing electricity consumption in a TOU environment. A period covering a number of billing cycles is essential to enable Hydro 2000 to work with its customers to adapt to the new billing reality. Hydro 2000 plans to provide parallel billing information to its customers so they can modify their pattern of energy usage and thus mitigate the impact of potential bill increases.

Hydro 2000 files monthly reports with the Board on smart meter deployment and TOU pricing.1 Prior to its July 6, 2011 application, Hydro 2000 had not indicated it had concerns with customer transition or that its customers would experience “distress.”

On April 19, 2011 the Board released RPP electricity commodity prices that took effect May 1, 2011. The backgrounder accompanying the release of the RPP prices noted that “Though the electricity line on the bill has increased since last May, a comparison of May 2010 and May 2011 shows overall the total bill has remained relatively flat as a result of the introduction of the Ontario Clean Energy Benefit.”2

In the Board's decision denying extension applications based on bill impacts for PowerStream Inc. (EB-2011-0117) and Midland Power Utility Corporation (EB-2011-0133) the Board stated that “extraordinary” or “unanticipated circumstances” generally “relate to operational or technical issues which cannot be adequately resolved in time to meet the mandated date. The fact that there are bill increases for some customers (and decreases for others) is not extraordinary or unanticipated.”3

Questions

- Given the Board’s decision on the TOU extension applications of PowerStream Inc. and Midland Power Utility Corporation, please explain why Hydro 2000 should be granted an extension because of an expectation of “significant customer distress.”

Response:

Hydro 2000 installation of smart meters for residential and small commercial                (GS <50kW) was completed in August 2009.  General Service (GS >50kW) was completed in September 2010.  Hydro 2000’s smart meter implementation plan  from 2008 to 2010 focused primarily on meter installation and TOU system changes to meet TOU implementation targets.

Unlike, PowerStream Inc., Hydro 2000 has a very small staff of 2 employees in total.  The implementation of the smart meters themselves was completed by Hydro 2000 staff in order to keep costs to a minimum for our customers.  Hydro 2000 billing clerk retired in December 2010.  We are in the mist of training a new billing clerk.  There has been only one key staff the only one involved in the IESO testing which is, as you may be aware, intensive.  That key person is also involved in a Cost of Service which very time consuming.  After the Cost of Service filed I will have the time and resources to provide additional education to residential and in particular small commercial customers.  Hydro 2000 has been using all OEB information “stuffers” to help customers prepare for TOU pricing; however, it was plan that some town hall meetings was planned in both Service area that Hydro 2000 service.  On august 1, 2011 Hydro 2000’s website was launch that contains information and links for smart meter and TOU.  The website will be used to inform and educate our customers.

- Please explain in detail why Hydro 2000 did not raise this concern in its monthly reports filed prior to this application for an extension.

- Response:

As mentioned in response a) Hydro 2000 has minimal staff.  It was Hydro 2000’s intention to be completely compliant in meeting its TOU schedule.  All resources however, have been concentrating on the back office readiness.  When SIT and QT testing was completed with the IESO, the staff on this project required time to resume their day to day work.  This meant a delay in the town hall meetings mentioned above.

- Please state how many billing cycles Hydro 2000 proposes to provide parallel billing for customer transition purposes.

- Response:

Hydro 2000 Inc. has contacted its CIS provider and has decided that providing parallel billing for only 1200 customers transition purposes will not be possible without significant costs not only monetarily, but resource wise as well.

- Please state what Hydro 2000’s requested extension date would be in the absence of providing a period for customer transition.

Response:

Without the period of customer transition, Hydro 2000 believes that the extension date would still be January 1, 2012.  Hydro 2000 share lease the AMI with Cooperative Hydro Embrun and Renfrew Hydro from Ottawa River Power Corporation to reduce the cost to our customers, share resources, share experiences and knowledge’s.  Hydro 2000 as to work, plan in conjunction with the other 3 utilities.  On July 13, 2011 IESO had a webinar and announce to all the utilities to be compliant with Measurement Canada requirements on January 1st, 2012 we had to redo part of SIT and QT testing, another two to three weeks of work not plan.

- Please provide a description of all smart meter and TOU communications Hydro 2000 has issued to its customers over the last two years. Please explain why Hydro 2000 has failed to provide these customers with materials containing sufficient information to prepare them for TOU implementation.

Response:

Hydro 2000 has used all OEB ‘stuffers’ over the last two years.  Hydro 2000 then continued to use OEB stuffers each time these were made available.  We also had our website in place with links to the OEB and Ministry of Energy with the TOU information.  Hydro 2000 believes however, that its customers will require further education and will update its website with more information closer to the implementation of TOU pricing.  Hydro 2000 will have Town Hall meetings for all customers.  We will also advertise more information with our local media.

- Has Hydro 2000 performed analysis of the bill impact benefits to its customers with the implementation of TOU billing? Performed analysis of the bill impact benefits to its customers with the implementation of TOU billing? If so, please provide this analysis. If no such analysis has been conducted, please explain (1) why no analysis conducted, and (2) the basis of Hydro 2000’s expectation of “customer distress.”

Response:

- Hydro 2000 has not finalized its’ bill impact analysis, but is currently in the process of completing this.  The software that would allow us to perform this was purchased in October 2010, but has only been fully functional since June 2011.

- The basis of Hydro 2000’s expectations of ‘customer distress’ is information that has been provided by the OEB.  With week day on-peak periods taking place form 11:00am to 5:00pm in summer and from 7:00am to 11:00am plus 5:00pm to 7:00pm in the winter, Hydro 2000 is particularly concerned about our customers.  Hydro 2000 has a customer base that consists of many senior citizens and those on social assistance, where they are at home and using electricity during these hours.  Hydro 2000 is also concerned for our GS under 50KW customers who operate their small businesses during these peak times.  Hydro 2000 GS under 50KW are small businesses that drives their business from the Highway 17

traffic going through the village of Alfred and Plantagenet.  Those businesses will be the most affected by TOU because they mostly operate at noon and supper time.

- Please provide the details of Hydro 2000’s proposed TOU implementation schedule, including the specific dates customers will be converted to TOU billing and how many customers will be converted on each date.

Response:

Hydro 2000 has 5 billing cycles which are billed on a monthly calendar basis.  All of our customer base will be converted to TOU as of January 2012 or before and billed in February or before permitting that all testing is completed.

Board Staff question 2

Preamble

In its application for an extension, Hydro 2000 stated that a delay is required because:

2. Upgrade of the AMI System of Ottawa River Power Corporation

ORPC uses the Elster AMI system to collect the customers’ TOU energy usage data and deliver it to the IESO for central processing. Currently ORPC is using version 6.2, but must upgrade to version 7.5 to meet the requirement of Measurement Canada. This upgrade is planned for the summer period (July/August 2011). ORPC is carrying out the IESO implementation with (Cooperative Hydro Embrun), Renfrew Hydro and Hydro 2000. Therefore, version 7.5 conversion from ORPC has to be coordinated with all the utilities' SIT and QT testing. When we (Renfrew, Cooperative Hydro Embrun and Hydro 2000) have completed testing the conversion of the AMI system can be undertaken and then the system must be extensively tested before full implementation of TOU pricing.

Hydro 2000 files monthly reports with the Board on smart meter deployment and TOU pricing.4  Hydro 2000 did not indicate it had any concerns or issues regarding AMI upgrades in the monthly reports it has filed.

Questions

- Please explain in detail why Hydro 2000 did not raise this concern in its monthly reports prior to its application for an extension.

Response:

Ottawa River Power Corporation has to upgrade its AMI system to become compliant with Measurement Canada.  When Measurement Canada made their decision, Elster (ORPC’s and Hydro 2000’s meter provider) had to develop new software.  This was made available to us just recently.  Once again Hydro 2000 would like to emphasize that it had full intentions of complying with its TOU timeline.  Again, since Hydro 2000 is using the same resources as ORPC we have to wait till the resources are functional to comply with the TOU timeline.

Hydro 2000 was on track for its October deadline for TOU.  On July 13, 2001 when IESO announce that there were changing their software and method of transmitting data and we had 2 to 3 more weeks of testing to redo.  Hydro 2000 has to restart part of SIT and QT testing.  Hydro 2000 would have plan differently known this information before.  Maybe the Board should ask the question to IESO. Now Hydro 2000 has to do upgrade to it CIS billing and others software and re-start some testing.  This extra testing and some more software set-up are the caused for the delays and extra costs that could have been done at the same time that we did all our previous set-up and testing that we had plan.

- Please explain in detail why AMI upgrades require an extension to Hydro 2000’s TOU date and how they prevent Hydro 2000 from cutting-over to production and TOU billing.

- Response:

Since Hydro 2000 utilizes the same resources as ORPC, (to reduce the costs to                   and share resources to save time) we are unable to proceed with the TOU billing till the resources are available to us.

- Can Hydro 2000 implement TOU pricing using Ottawa River’s existing Elster version 6.2 AMI system?

Response:

Hydro 2000 would be able to implement TOU pricing using the existing Elster version 6.2, however, they would not be Measurement Canada compliant.  As mentioned above, Hydro 2000 has to wait for the new resources to be available at ORPC as we utilize the same systems.

- Please state and explain the contribution of Renfrew Hydro, Ottawa River and Cooperative Embrun’s TOU implementation to Hydro 2000’s requested extension date.

Response:

Ottawa River Power Corporation, Renfrew Hydro, Hydro 2000 and Cooperative Hydro Embrun made a decision when the Smart Meter Project began that the four utilities would collaborate.  We share consultants, software, and computer hardware.  This has saved time and money and intellectual resources.

- Please state the contribution of AMI upgrades to Hydro 2000’s requested extension date.

Response:

As stated in response b) The AMI upgrade would take 4 to 6 weeks including the time required to stabilize the network.

Board Staff question 3

Preamble

In its application for an extension, Hydro 2000 stated that a delay is required because:

3. Upgrade of the IESO System

Hydro 2000 will also have to re-complete SIT testing and QT testing after the IESO completes their system upgrade to version 7.2 that is expected in November 2011.

Hydro 2000 files monthly reports with the Board on smart meter deployment and TOU pricing.5   Hydro 2000 did not indicate it had any concerns or issues regarding IESO system upgrades in the monthly reports it has filed.

Questions

- Please explain in detail why Hydro 2000 did not raise this concern in its monthly reports prior to its application for an extension.

- Response:

- The IESO upgrade was just recently announced and is scheduled for January 2012.

- Originally, it was scheduled to upgrade in November 2011, this causing some delays

- with our implementation of TOU.  When this issue came to light, Hydro 2000

- once again decided it just did not have the resources.  Please see the response in     	1d) and 2a).

- Please explain in detail why the IESO system upgrades warrant an extension to Hydro 2000’s TOU date and how they prevent Hydro 2000 from cutting-over to production and TOU billing.

Response:

The IESO upgrade will require Hydro 2000 to once again complete mandatory testing with its limited resources.  Hydro 2000 had previously thought that it would send out its first TOU bills in November 2011 for October 2011 consumption.  With the IESO doing their upgrade in January 2012 this will conflict with a number of first time billing cycles.  We also have a new patch to be installed to our CIS which has the xml interface required to be able to bill TOU, which we have ordered.

- Please state the contribution of IESO system upgrades to Hydro 2000’s requested extension date.

Response:

Hydro 2000 estimates that the IESO upgrade will delay their TOU schedule by approximately 8-12 weeks, so that the first TOU bill is produced after the upgrade takes place.