## App.2-A_Capital Projects
[11 empty] | File Number: |  | EB-2012-0109
[11 empty] | Exhibit: |  | 2
Tab:
Schedule:
[11 empty] | Page: |  | 1
[11 empty] | Date: January 13, 2014 |  | July 17,2013
Appendix 2-A
Capital Projects Table
Projects | 2008 | Projects | 2009 | Projects | 2010 | Projects | 2011 | Projects | 2012 Bridge Year | Projects | 2013 Test Year | 2013 YTD Actuals | 2013 Forecast updated Budget
Reporting Basis | CGAAP |  | CGAAP |  | CGAAP |  | CGAAP |  | CGAAP | Reporting Basis | Modified CGAAP | Modified CGAAP | Modified CGAAP
Capital Project #1- Residential Seconary Services | 93448 | Capital Project #1- Residential Seconary Services | 112524 | Capital Project #1- Residential Seconary Services | 156047 | Capital Project #1- Residential Seconary Services | 118230 | Capital Project #1- Residential Seconary Services | 134156 | Capital Project #1- Residential Seconary Services | 110000 | 80260 | 97400
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
Capital Project #2 - Overhead Line Extensions | 263594 | Capital Project #2 - Overhead Line Extensions | 206127 | Capital Project #2 - Overhead Line Extensions | 354061 | Capital Project #2 - Overhead Line Extensions | 352871 | Capital Project #2 - Overhead Line Extensions | 179453 | Capital Project #2 - Overhead Line Extensions | 265000 | 102021 | 143300
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | -143717.02 | Capital Contribution: | -18132.78 | Capital Contribution: | -5171.29 | Capital Contribution: | -18816.99 | Capital Contribution: | 0 | Capital Contribution: | 0 | -11576.86 | -11577
Capital Project #3 - Underground Line Extensions | 330157 | Capital Project #3 - Underground Line Extensions | 236335 | Capital Project #3 - Underground Line Extensions | 483721 | Capital Project #3 - Underground Line Extensions | 327251 | Capital Project #3 - Underground Line Extensions | 351833 | Capital Project #3 - Underground Line Extensions | 280000 | 426249 | 417400
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | -311949.65 | Capital Contribution: | -528164.48 | Capital Contribution: | -90247.28 | Capital Contribution: | -176152.23 | Capital Contribution: | -322557.6 | Capital Contribution: | 0 | -1167.75 | -1168
Capital Project #4 -Overhead Transformers | 314189 | Capital Project #4 -Overhead Transformers | 202555 | Capital Project #4- Underground Transformers | 593583 | Capital Project #4 -Overhead Transformers | 83450 | Capital Project #4 -Overhead Transformers | 156725 | Capital Project #4 -Overhead Transformers | 45000 | 48145 | 52000
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | -5953.24 | Capital Contribution: | -1000 | Capital Contribution: | -13131.85 | Capital Contribution: | -8776.79 | Capital Contribution: | 0 | Capital Contribution: | 0 | -6771.5 | 0
Capital Project #5 - Underground Transformers | 617980 | Capital Project #5 - Underground Transformers | 277149 | Capital Project #5- Powerline Feeder Upgrades | 524514 | Capital Project #5 - Underground Transformers | 508860 | Capital Project #5 - Underground Transformers | 210587 | Capital Project #5 - Underground Transformers | 360000 | 175041 | 305900
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | -76089.18 | Capital Contribution: | -147735.61 | Capital Contribution: | 0 | Capital Contribution: | -57515.91 | Capital Contribution: | -64196.2 | Capital Contribution: | 0 | 0 | 0
Capital Project #6- New Subdivisions and Townhomes | 838213 | Capital Project #6 - Powerline Feeder Upgrades | 353641 | Capital Projects #6 - New Subdivisions and Townhomes | 265408 | Capital Project #6 - Powerline Feeder Upgrades | 489849 | Capital Project #6 - Powerline Feeder Upgrades | 692218 | Capital Project #6 - Powerline Feeder Upgrades | 450000 | 264649 | 611500
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: |  | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
Capital Project #7City/Ministry of Transportation Relocates | 103262 | Capital Project #7 - New Subdivisions and Townhomes | 1654016 | Capital Project #7 - Scada & Distribution/ System Upgrade to Windows | 246707 | Capital Projects #7 -New Subdivisions and Townhomes | 328556 | Capital Project #7 New Subdivisions and Townhomes | 841872 | Capital Project #7 New Subdivisions and Townhomes | 446100 | 1135131 | 547000
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | -37364.15 | Capital Contribution: | -6769.53 | Capital Contribution: | -3014.83 | Capital Contribution: | -4298.36 | Capital Contribution: | -3765.95 | Capital Contribution: | -178440 | -682862.28 | -250360
Capital Project #8 - Scada & Distribution Automation/Brantford General Hospital Automatic Load Transfer System | 179175 | Capital Project #8 - Scada & Distribution Automation/Reloser Installation | 96919 | Capital Project #8 - Annual Pole Replacements - General Yearly Rebuilds | 432011 | Capital Project #8 - Annual Pole Replacements - General Yearly Rebuilds | 613691 | Capital Project #8 - Annual Pole Replacements - General Yearly Rebuilds | 660709.0358 | Capital Project #8- Scada & Distribution Automation | 150000 | 52827 | 50000
[10 empty] | In-service date: | 2014-06-30
Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
Capital Project #9- Conversion of Lines from 4 & 8 Kv to 27 KvSystem - Applewood & Brier Park Subdivision | 1960631 | Capital Project #9 - Conversion of Lines from 4 & 8 Kv to 27 Kv System - Tranquility, Rosewood, etc. | 1402272 | Capital Project #9 - Annual Pole Replacements - General Yearly Rebuilds - Brantwood Park | 1537546 | Capital Project #9 - Annual Pole Replacements - General Yearly Rebuilds - Brantwood Park/Dunsdon Rebuild | 1468877 | Capital Project #9 - Annual Pole Replacements - General Yearly Rebuilds - Lynden Hill Estates | 1096018.7325 | Capital Project #9- Capacitor Study/Installation of Line Banks | 120000 | 46078 | 55800
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | -52497.06 | Capital Contribution: | -43454.25 | Capital Contribution: | -85022.4 | Capital Contribution: | 0 | Capital Contribution: | -213540.84 | Capital Contribution: | 0 | 0 | 0
Capital Project #10- Annual Pole Replacements - General Yearly Rebuilds | 471404 | Capital Project #10 - Annual Pole Replacements - General Yearly Rebuilds | 512324 | Capital Project #10-- Metering | 355369 | Capital Project #10 - Asset Management & Consultancy Software | 219196 | Capital Project #10 - Asset Management & Consultancy Software | 230987 | Capital Project #10- Ownership Transfers - Primary Services and older 27.6Kv Townhome Sites | 110000 | 11561 | 10000
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | 0 | Capital Contribution | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
Capital Project #11 - AM/FM GIS System Upgrade | 241944 | Capital Project #11 - Testing of G-Technology Version 9.4 | 70814 | Capital Project #11-- Wholesale Metering (Brantford TS) | 769365 | Capital Project #11 Upgrade to G-Technology Version 10 | 75249 | Capital Project #11 - Replacement of Vehicles | 123836 | Capital Project #11 Annual Pole Replacements - General Yearly Rebuilds | 390000 | 462978 | 434625
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
Capital Project #12 - Metering | 229050 | Capital Project #12 - Metering | 349517 | Capital Project #12- Replacement of Vehicles | 248832 | Capital Project #12 - Metering | 150239 | Capital Project #12 - Office Furniture & Computer Equipment | 106553 | Capital Project #12 - Asset Management Consultancy &Software | 150000 | 115606 | 170000
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: |  | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
Capital Project #13 -Replacement of Vehicles | 165750 | Capital Project #13 - Replacement of Vehicles | 312919 |  |  | Capital Project #13-- Wholesale Metering (Brantford TS) | 26781 | Capital Project #13 - Metering | 129614 | Capital Project #13 - Metering | 205000 | 81319 | 181160
[10 empty] | In-service date: | 2013-12-31
Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
[6 empty] | Capital Project #14 - Replacement of Vehicles | 309767 |  |  | Capital Project #14 - Replacement of Vehicles | 200000 | 149100 | 200000
[10 empty] | In-service date: | 2013-10-31
[6 empty] | Capital Contribution: | 0 | Capital Contribution: | 0 | Capital Contribution: | 0 | 0 | 0
[10 empty] | Capital Project #15 - Customer Services (CS) Requirements | 160000 | 0 | 0
[10 empty] | In-service date: | 2014-06-30
[10 empty] | Capital Contribution: | 0 | 0 | 0
[10 empty] | Capital Project #16 - City/MTO Relocation Overhead | 100000 | 23387 | 39800
[10 empty] | In-service date: | 2013-12-31
[10 empty] | Capital Contribution: | -25000 | 0 | -9950
[10 empty] | Capital Project #17- Tools, Shop, etc. | 25000 | 13339 | 25000
[10 empty] | In-service date: | 2013-12-31
[10 empty] | Capital Contribution: | 0 | 0 | 0
[10 empty] | Capital Project #18- Office Furniture & Computer Equip. | 77500 | 48799 | 29800
[10 empty] | In-service date: | 2013-12-31
[10 empty] | Capital Contribution: | 0 | 0 | 0
Capital Contributions | -627570 | Capital Contributions | -745257 | Capital Contribtuions | -196588 | Capital Contributions | -265560 | Capital Contributions | -605551 | Capital Contributions | -203440 | -702378.39 | -273055
Sub Total: | 5181227 | Sub Total: | 5041855 | Sub Total: | 5770576 | Sub Total: | 4807307 | Sub Total: | 4309010.7683 | Sub Total: | 3440160 | 2534111.61 | 3097630
Miscellaneous | -22289 | Miscellaneous | 88042 | Miscellaneous | -101275 | Miscellaneous | -226611 | Miscellaneous | 897460.2317 | Miscellaneous | 0 | -1.61 | 0
Total: | 5158938 | Total | 5129897 | Total: | 5669301 | Total: | 4580696 | Total: | 5206471 | Total: | 3440160 | 2534110 | 3097630
Notes:
1 Please provide a breakdown of the major components of each capital project. Please ensure that all projects below the materiality threshold are included in the miscellaneous line. Add more projects as required.
2 Amounts should be reported on a MIFRS basis for the adoption year and any subsequent years, only.
Note on M58: Phillip Chisulo: CoS Application had $200,000 it should be $160,000 confirmed with GMD on 10/8/2013 (email)
Note on N13: Phillip Chisulo: YTD Novermber 2013