## Appendix 2-AA
Appendix 2-AA
Distribution Capital Projects
Category | Job Type | NO. | PROJECT NAME | 2010 | 2011 | 2012 | 2013 | 2014 Bridge Year | 2015 Test Year | 2016 | 2017 | 2018 | 2019
System Access | 200 | 1 | New Subdivision - Lake Margaret, Phase 9 | 81487.36
System Access | 200 | 2 | New Subdivision - Orchard Park, Phase 3 | 71980.28
System Renewal | 215 | 3 | Voltage Conversion - Chestnut East of Fifth | 84699.85
System Service | 210 | 4 | Build New OH Powerline - Sutherland Line | 45076.34
System Access | 220 | 5 | Relocate Poles - Wellington - Princess to Elgin | 60325.95
System Access | 200 | 6 | New Subdivision - Shaw Valley, Phase 2A | 31895.78 | 256724.91
System Access | 200 | 7 | New Subdivision - Dalewood Meadows, Phase 4A | 151558.22 | 47.18
System Access | 200 | 8 | New Subdivision - Dalewood Meadows, Phase 4B | 92432.03 | 13334.79
System Access | 200 | 9 | New Subdivision - Misc | -592.32 |  | 8087.29 | 44790.64 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
System Renewal | 270 | 10 | Voltage Conversion - Misc. | 82120.33 | 102960.73 | 33413.92 | 28188.38
System Access | 202/204/240/230/231 | 11 | New Services Residential - Misc | 97509.91 | 66929.17 | 40098.25 | 71033.44
System Access | 205/241/242/231 | 12 | New Services Commercial - Misc | 66155.17 | 66670.93 | 68968.77 | 97132.92
System Access | 220 | 13 | Municipal Road Rebuilds - Misc | 41114.25 | 23546.85 | 11754.94 | 29400.64
System Renewal | 215/260 | 14 | Pole Replacement Program | 201630.28 | 36140.03 | 19585.11 | 25201.86
System Renewal | 215 | 15 | Voltage Conversion - Locust, Fifth to Third | 94208.82 | -3637.71
System Renewal | 215 | 16 | Voltage Conversion - Fourth, Myrtle, Forest, Erie | 170125.83 | 8347.23
System Renewal | 215 | 17 | Voltage Conversion - Forest, Third, Erie, Second | 145687.45 | 79028.45
System Access | 200 | 18 | New Subdivision - Orchard Park, Phase 4 |  | 130940.38
System Renewal | 215 | 19 | Voltage Conversion - Elmina/Churchill Area |  | 271108.18
System Renewal | 215 | 20 | Voltage Conversion - Dieppe, Dunkirk, Churchill |  | 254658.17
System Access | 205 | 21 | Upgrade Service - 84 Edward - School |  | 57405.48
System Access | 205 | 22 | Upgrade Service - 22 S. Edgeware - School |  | 82373.06
System Access | 200 | 23 | New Subdivision - Dalewood Meadows, Phase 5 |  | 37246.01 | 110144.55
System Renewal | 215/270 | 24 | Voltage Conversion - Meehan, Montgomery, Coyne |  | 185206.82 | 113168.95 | 837.75
System Renewal | 215/270 | 25 | Voltage Conversion - Parkview, Pinafore, etc. |  | 212723.1 | 305096.18 | 13262.3
System Access |  | 26 | Smart Meter Transfer |  |  | 3082487
System Access | 200 | 27 | New Subdivision - Shaw Valley, Phase 2B |  |  | 161795.97 | 23590.98
System Access | 200 | 28 | New Subdivision - Lake Margaret Estates, Phase 11 |  |  | 95968.65 | 762.62
System Access | 200 | 29 | New Subdivision - Dalewood Meadows, Phase 6 |  |  | 12115.46 | 190237.28
System Access | 200 | 30 | New Subdivision - Orchard Park, Phase 5 |  |  | 1352.15 | 119556.18
System Access | 200 | 31 | New Subdivision - Orchard Park South |  |  | 351016.64 | 3912.09
System Renewal | 215/270 | 32 | Voltage Conversion - Churchill & Chestnut Area |  |  | 140125.03 | 58
System Renewal | 270 | 33 | Voltage Conversion - Alma Kains North |  |  | 46472.69 | 145133.72
System Renewal | 270 | 34 | Voltage Conversion - Stokes & Manor |  |  | 325185.42 | 330.41
System Renewal | 270 | 35 | Voltage Conversion - McLachlin Place |  |  | 7826.59 | 135343.63
System Renewal | 270 | 36 | Voltage Conversion - Massey & Michener |  |  | 85828.86 | 3918.82
System Renewal | 270 | 37 | Voltage Conversion - Luton, McLarty, Dyer Area |  |  | 478 | 226098.44 | 211971.56
System Renewal | 270 | 38 | Voltage Conversion - Erie, Talequah to Park |  |  |  | 50859.76 | 34140.24
System Renewal | 270 | 39 | Voltage Conversion - Highview, Vanbuskirk & McCully Area |  |  |  | 379043.82 | 40956.18
System Renewal | 270 | 40 | Voltage Conversion - Steele St. |  |  |  | 68.03 | 114931.97
System Renewal | 270 | 41 | Voltage Conversion - Locke, Rosemount area |  |  |  | 471.29 | 700000
System Renewal | 270 | 42 | System Upgrade - Bush Line |  |  |  |  | 320000
System Renewal | 270 | 43 | Voltage Conversion - Mary St. East |  |  |  |  | 115000
System Renewal | 270 | 44 | Voltage Conversion - Warehouse, Park to Fairview |  |  |  |  | 35000
System Renewal | 270 | 45 | Voltage Conversion - Mandeville West of First |  |  |  |  | 28000
System Renewal | 270 | 46 | Voltage Conversion - Fairview, Sinclair & Talbot Area | [5 empty] | 298750
System Renewal | 270 | 47 | Voltage Conversion - Paulson, Gustin & Paddon Area | [5 empty] | 358750
System Renewal | 270 | 48 | Voltage Conversion - Confederation, Lakeview, Stirling Area | [5 empty] | 683750
System Service | 210 | 49 | Build New Powerline - Elmwood Ave | [5 empty] | 208750
System Renewal | 270 | 50 | Voltage Conversion - Hammond, Patricia, Inkerman, Daniel Area | [6 empty] | 790000
System Renewal | 270 | 51 | Voltage Conversion - Highview, Aspen, Chestnut, Croatia, Pol Area | [6 empty] | 800000
System Renewal | 270 | 52 | Voltage Conversion - Tecumseh, Montcalm, Brock, Alma Area | [7 empty] | 763335
System Renewal | 270 | 53 | Voltage Conversion - Park, Mary Bucke, Forest & First Area | [7 empty] | 463335
System Renewal | 270 | 54 | Voltage Conversion - Balaclava & S. Edgeware Area | [7 empty] | 303330
System Service | 210 | 55 | Build New Powerline - Centennial, Talbot to Wellington | [8 empty] | 305000
System Renewal | 270 | 56 | Voltage Conversion - Applewood, Lawrence, Butler, Dyer Area | [8 empty] | 700000
System Renewal | 270 | 57 | Voltage Conversion - Major Line West of Sunset Area | [8 empty] | 285000
System Renewal | 270 | 58 | System Upgrade - Edward, Gaylord, East side of Elgin Mall | [8 empty] | 230000
System Renewal | 270 | 59 | Voltage Conversion - First, Thompson, Glanworth, Ashton Area | [9 empty] | 511660
System Renewal | 270 | 60 | Voltage Conversion - Aldborough, Airey, Vanier Area | [9 empty] | 561670
System Renewal | 270 | 61 | Voltage Conversion - Aldborough, Pullen, Sparta, Parish Area | [9 empty] | 486670
|  | 62 | Asset Transfer - Restructuring |  |  | 1407734 | 69795
|  | 63 | GIS |  |  | 397908 |  | 150000 | 50000
|  | 64 | New Financial software |  |  | 353134
|  | 65 | Smart Meter Transfer |  |  | 185288
|  | 66 | Other |  |  | 37621 | 22888 | 28000 | 20000 | 20000 | 20000 | 20000 | 20000
|  | 67 | Computer hardward & software |  |  |  | 180898 | 116000 | 98000 | 131000 | 98000 | 120000 | 97000
|  | 68 | Fleet |  |  |  | 247083 | 264000 | 125000 | 60000 | 265000 | 20000
|  | 69 | Building, furniture & equipment |  |  |  | 17973 | 170000 | 170000 | 175000 | 15000 | 5000 | 5000
|  | 70 | SCADA | [5 empty] | 50000 | 50000 | 50000 | 100000 | 100000
71
72
73
74
75
|  |  | TOTAL | 1517415.53 | 1881753.76 | 7402655.42 | 2127870 | 2527999.95 | 2263000 | 2226000 | 2178000 | 1985000 | 1982000
Less Renewable Generation Facility Assests and Other Non Rate-Regulated Utility Assests (input as negative)
|  |  | TOTAL | 1517415.53 | 1881753.76 | 7402655.42 | 2127870 | 2527999.95 | 2263000 | 2226000 | 2178000 | 1985000 | 1982000
Note on H12: Judy Van Patter: Includes miscellaenous cost $-12,044 plus $1 to match actuals
Note on I12: Judy Van Patter: Includes miscellaneous cost $42,299 plus $1.66 to match actuals
Note on G13: Judy Van Patter: Includes difference unaccountable for Conversion work $63,068
Note on J40: Judy Van Patter: Budget $475,000 minus 2012 & 2013 costs - minus difference from Larry's estimates ($36,452)
Note on J41: Judy Van Patter: Budget $85,000 minus costs for 2013
Note on J42: Judy Van Patter: Budget $420,000 minus 2013 costs
Note on J43: Judy Van Patter: Budget $115,000 minus costs for 2013