REDACTED PUBLIC

ONTARIO ENERGY BOARD

| FILE NO.: | EB-2013-0321 |  |
| --- | --- | --- |
| VOLUME: DATE: | Technical Conference July 9, 2014 | REDACTED - PUBLIC |

EB-2013-0321

THE ONTARIO ENERGY BOARD

IN THE MATTER OF the Ontario Energy Board Act, 1998, S.O. 1998, c. 15, Sched. B;

AND IN THE MATTER OF an application by Ontario Power Generation Inc. pursuant to section 78.1 of the Ontario Energy Board Act, 1998 for an order or orders determining payment amounts for the output of certain of its generating facilities.

Hearing held at 2300 Yonge Street,

25th Floor, Toronto, Ontario,

on Wednesday, July 9th, 2014,

commencing at 9:30 a.m.

--------------------

TECHNICAL CONFERENCE

--------------------

MICHAEL MILLAR	Board Counsel

VIOLET BINETTE	Board Staff

RICHARD BATTISTA

CHARLES KEIZER	Ontario Power Generation (OPG)

CRAWFORD SMITH

COLIN ANDERSON

ANDREW BARRETT

DAVID CROCKER	Association of Major Power

SHELLEY GRICE	Consumers of Ontario (AMPCO)

PETER THOMPSON	Canadian Manufacturers & Exporters

E. BLANCHARD	(CME)

JULIE GIRVAN	Consumers' Council of Canada (CCC)

LARRY SCHWARTZ	Energy Probe Research Foundation

DAVID MacINTOSH

TAM WAGNER	Independent Energy System Operator (IESO)

PIPPA FEINSTEIN 	Lake Ontario Waterkeeper

RICHARD STEPHENSON	Power Workers' Union (PWU)

JAY SHEPHERD	School Energy Coalition (SEC)

MARK RUBENSTEIN

RUSS HOULDIN	Society of Engineering Professionals (SEP)

MICHAEL JANIGAN	Vulnerable Energy Consumers' Coalition (VECC)

--- On commencing at 9:30 a.m.	1

ONTARIO POWER GENERATION - PANEL 8	1

E. Gould, D. Reiner, G. Rose

Preliminary Matters:	1

Questions by Mr. Shepherd:	2

Questions by Mr. Crocker:	5

Questions by Ms. Blanchard:	32

--- Recess taken at 11:03 a.m.	53

--- On resuming at 11:23 a.m.	53

Questions by Mr. Battista:	55

Questions by Mr. Shepherd:	59

Questions by Mr. Battista:	60

--- On commencing in camera at 11:52 a.m.	68

Questions by Mr. Poch:	68

--- Luncheon recess taken at 12:34 p.m.	92

--- On resuming at 1:38 p.m.	92

Questions by Ms. Blanchard:	93

Questions by Mr. Shepherd:	97

--- Recess taken at 3:04 p.m.	149

--- On resuming at 3:22 p.m.	149

--- Whereupon the conference concluded at 3:52 p.m.	169

NO EXHIBITS WERE FILED IN THIS PROCEEDING.

UNDERTAKING NO. JT4.1:  with reference to REPORTS ENTITLED "SCOPE STRATEGY AND PLAN, 12/15/11," "OTHER ENGINEERING, 24 MAY, 2013, VBO OUTAGE STATUS, MDR WORK STREAMS ENGINEERING STUDIES", "DR engineering weekly tactical update" dated April 19, 2013; "DR engineering weekly tactical update"; "Engineering weekly tactical update," dated March 15th, 2013; "OPG proposal, org and labour resources review, A, organizational labour strategy," dated May 11, 2010:  A, to indicate where they are in the evidence; B, to produce them; or C, EXPLAIN WHY THEY CANNOT BE PRODUCED.	21

UNDERTAKING NO. JTX4.2 (IN CONFIDENCE):  TO PROVIDE THE TERMINATION PROVISIONS.	97

UNDERTAKING NO. JTX4.3 (IN CONFIDENCE):  TO PROVIDE MORE DETAIL ON HOW OPG ARRIVED AT THE 35 TO 45 PERCENT RANGE, AND HOW REASONABLE THE NUMBERS ARE.	115

UNDERTAKING NO. JTX4.4:  TO PROVIDE MORE BACKGROUND ON THE EXPERIENCE FACTOR AND HOW IT WAS DERIVED AND HOW IT WAS BENCHMARKED	121

UNDERTAKING NO. JTX4.5:  TO CONFIRM THAT NONE OF THAT $871 MILLION IS CURRENTLY INCLUDED IN THE REVENUE REQUIREMENT PROPOSED FOR THE TEST PERIOD.	143

Wednesday, July 9, 2014

### --- On commencing at 9:30 a.m.

# ONTARIO POWER GENERATION - PANEL 8

Eric Gould

Dietmar Reiner

Gary Rose

MR. MILLAR:  Good morning, everyone.  This is day two of the technical conference in EB-2013-0321, continuing with Mr. Crocker today.

Mr. Keizer, are there any preliminary matters?

# Preliminary Matters:

MR. KEIZER:  There are just a couple.  I believe Mr. Reiner has one correction to the transcript from yesterday.

MR. REINER:  Yes, there was a question asked by Mr. Poch yesterday regarding whether or not we had informed the government of the Modus reports and when that was, and I had answered that it was in early June.  It was -- we briefed the shareholder on the 25th of June and at that time left copies of all of the Modus reports with the shareholder.  In addition to that -- I think we pointed that out yesterday -- our shareholder does have their own adviser that has direct access to all information on the project and would have seen the reports that were issued prior to the June 26th reports and would have provided updates based on their view of those reports.

MR. MILLAR:  Is there anything else, Mr. Keizer?

MR. KEIZER:  And I believe Mr. Gould has a minor correction.

MR. GOULD:  I do have one minor correction.  Mr. Shepherd asked yesterday about an attachment.  It's attachment B to the fourth-quarter 2013 report.  It's a spreadsheet that shows the variances between release 4C and 4B.  That document, I believe that I said yesterday that that was something that we created.  That was a document that OPG created essentially at our request based on their information.  So when that document is released to you, then you understand where -- the genesis of that document.

MR. SHEPHERD:  Can I just follow up on that?

# Questions by Mr. Shepherd:

MR. KEIZER:  Sure.

MR. SHEPHERD:  So you said it was your document and Mr. Reiner said it was your document.

MR. GOULD:  We were mistaken.  It was -- it's in the format of both -- that OPG uses for its cost-estimating platform, and we had asked that OPG do this comparison.  That's all there is to it.

MR. SHEPHERD:  Okay.  So there is a spreadsheet just like this that has the 4B numbers in it and there is another one that has the 4C numbers in it, and they are both essentially identical to this, and this is just the difference between the two, right?

MR. GOULD:  Exactly.

MR. SHEPHERD:  So we can still get those 4B and 4C spreadsheets.  It's just that you are saying that when we get them you we shouldn't think they are yours.  They're --

MR. GOULD:  I just wanted to make sure that we were correct on the record.

MR. SHEPHERD:  I understand, thank you.

MR. MILLAR:  Anything else, Mr. Keizer?

MR. KEIZER:  Well, and I think there is, just in terms of one undertaking response, and I think it relates to the question of what work in -- it was related to what work was in the Modus report which was -- is OPG's work, and I think there was two charts, and I think that was in Undertaking 3.9, and so I think Mr. Gould is able to answer that question on the record this morning.

MR. GOULD:  So, yes, in response to Undertaking JT3.9 I went back -- I wanted to make sure that I was being fully accurate, so I went back through the report, and Mr. Shepherd identified two graphics that were created by OPG.  Those are correctly identified as OPG's work product.

There is also a chart that we have looked at multiple times in this hearing that's on page 16, and you will see in that table that refers to the campus plan budget -- it's under paragraph B, "overall cost impact" -- you will see that the footnote refers to the fact that these numbers are current forecast amounts provided by the DR team.

So that, like every other number that would be within this document, would be sourced from the project, but in terms of your question, Mr. Shepherd, I can state for the record that that is the only thing -- those are the only elements within this report or any of our reports consistently through that would have been provided by OPG.

MR. SHEPHERD:  So this chart on page 16 of the June 26th report, the chart is yours, but the numbers are OPG's, or did they just simply supply you with the chart?

MR. GOULD:  No, the chart is ours.

MR. SHEPHERD:  Okay.

MR. GOULD:  And the numbers would have to come from OPG, because we don't have numbers for this project independent of OPG.

MR. SHEPHERD:  Okay.  But we heard several times Mr. Rose being asked about this 552 million and saying it's close but it's not exact because it's not his number, it's your number, but this is actually his number then.

MR. GOULD:  The numbers that are in this chart reflect the documents that are represented here.  So if you went back to the 4C estimate you would see that set of numbers.  If you went to the current forecast as of that time you would see that set of numbers.

MR. SHEPHERD:  So then let me ask Mr. Rose:  Several times you said these weren't your numbers, so are these your numbers?

MR. ROSE:  Based on the clarification that these are numbers from the release 4C estimate they are our numbers.  I haven't validated personally that these are in alignment with 4C, but obviously I respect the advice and direction from Mr. Gould that they are our numbers.  What I did say is that they are certainly within the range that I would have expected to see for the FNIP projects.

MR. SHEPHERD:  Fine, thank you.

MR. KEIZER:  That's it, thanks.

MR. MILLAR:  Thank you.  Mr. Crocker?

# Questions by Mr. Crocker:

MR. CROCKER:  Thank you.  I would like to continue with questions on the third-quarter 2013 report, Exhibit 1 to the June 26th, 2014 report.  And I would like to start this morning on page 23, please, under the heading "engineering".

In that first paragraph you describe the stresses on the engineering reporting, and you say, sort of a couple lines into that paragraph talking about the engineering:

"Its metrics and tracking methods of engineering product were in the embryonic stage.  It appeared the engineering was significantly stressed, behind schedule.  However, the engineering team's performance indicators did not reflect this stress."

And my question is exactly what you mean by that, and why were they not -- are you saying that they were not fully or accurately reporting?

MR. GOULD:  What I'd say is that this was very early on in the project.  We are talking here about essentially the beginning of the engineering effort for the refurbishment project, and that's what's referred to in this paragraph.

So they are very early on.  It's certainly common in the industry that it would take time for metrics like this to develop.  You don't typically see metrics on something this -- something of this nature right off the bat that are entirely accurate.  Every project has its own reasons for developing different metrics that show you what you need to know about that effort.

So I think we say here that this is in the embryonic stage, and I think that is what we are referring to.

MR. CROCKER:  Have they improved their reporting techniques and the way they are reporting, et cetera?

MR. GOULD:  Yes, they have.

MR. CROCKER:  How so?  How have they done that?

MR. GOULD:  So in the past year since we made this observation, we have seen a sizeable increase in the amount of reporting that's coming out of the engineering team.  There is a weekly engineering meeting -- there was a weekly engineering meeting prior to this report, but in that meeting there is now much greater and much more intense focus on performance metrics.

There are performance metrics being developed -- or that have been developed that are being tracked on a weekly basis in the context of those meetings and elsewhere within the project for each of the major project bundles and for each of the subset pieces of engineering within those project bundles.

So whereas a year ago when we were putting this report together you would not have had clear line of site visibility to that level of detail, now I believe you do, sir.

MR. CROCKER:  And why is it important?

MR. GOULD:  It's important so that -- because engineering gets the project off to the essential start.  You need to get engineering done and have it be accurate on time so that you are off to a good start, and you also want to make sure that your engineering product is of sufficient quality so that you don't have significant issues once you get into the construction phase.

MR. CROCKER:  Who reviews the -- to whom is this engineering reporting done, and how is it responded to?

MR. GOULD:  So the meetings that I discussed that are held on a weekly basis every Friday are chaired by the vice-president of engineering, Mr. Neil Mitchell.  Mr. Mitchell, I believe, reports to Mr. Reiner.

So there is -- within the project team there is project executive attention on the flow of engineering and -- or the pace of engineering.  And in those sessions, there is absolute accountability that we have seen from the top down within the project, to ensure that they are meeting schedule.

MR. CROCKER:  The bottom of the next page, you say in the second last line on the page:

"OPG planned to prepare the modification design requirements packages with in-house internal resources, but OPG could not complete the volume of work and the number of MDRs required without additional engineering help.  The engineering team therefore contracted with OSS vendors..."

"OSS" stands for outside something, I assume, outside -- what is the SS of OSS?

MR. REINER:  "OSS" stands for owners support services.

MR. CROCKER:  Okay.  "...to complete the development", et cetera.  Why wasn't OPG able to do this internally?

MR. GOULD:  Well, let me answer in part, and I think I can give the some of that question to Mr. Reiner.

So our observation was that OPG in planning this project and looking out over the risks of this project, decided to go to the EPC model for engineering, where the engineering would be procured from outside vendors.

At one time -- and we comment about this in subsequent reports -- at one time OPG had a very, very large in-house staff and had a lot of engineers that had been part of the Pickering restart, among other projects.  I certainly saw them for the Pickering restart.

The decision was made to scale back that staff, for a number of reasons that I was not here to validate.  I can only say that the staff that they have right now is managing the outside vendors so that this work can get done.

But I think there is another important point here.  Yesterday when we were discussing issues related to the campus plan, Mr. Shepherd asked a series of questions about the performance specification that was given for the early pilot projects.  And this, what is referred to here as the MDR packages, that was the major lesson learned for the overall project, that increasing the amount of definition within those early engineering packages that were given to the vendors was essential to achieve the appropriate result in the project.

MR. CROCKER:  That's not exactly an answer to my question, but I will take the answer.

Is the -- so instead of -- what you are saying is instead of doing this work internally, it was decided to do it externally but to supervise it with internal engineers?  I guess that is what you are saying here; correct?

MR. REINER:  That's -- maybe I will jump in here.  That's correct.  So under the quality programs that we have to adhere to, the design authority, which is a critical role -- that's ultimately the approval of the final the design that gets implemented -- that rests with OPG, so that approval is provided under our quality program.

Our strategy for the project is -- you know, we are not a construction company, we are not resourced with the engineering capability in-house to manage these large projects, and that is part of what led us to the EPC contracting model.  So we provide oversight and we use EPC contractors to do the work.

In the case of modification design requirements, which is essentially an input to the EPC contractor, we have augmented our capability with these owner support services contracts.  They are essentially engineering services.  We can access technical expertise; that technical expertise works under our direction, our supervision, our quality program, and they produce those requirements.

And, you know, there is a statement in here that that has led to increased costs of the development of MDRs.  I think if you look at it on a dollar-per-hour basis, that would be correct.  But what I would add to that is when I look at the costs for managing the overall project, I have to look at the long-term liability associated with permanent hires.  It's not just an hourly cost; it's a pension cost and a benefit cost as well.  When you roll all of that in and add to it the flexibility that a contracted service provides, where I can turn it on and off as required, it is a far more cost-effective way of executing the project the way that we have implemented this.

MR. CROCKER:  So was it a mistake, then, to try to do it internally at the start?

MR. REINER:  It -- I don't know -- what I would say here, again, is, you know, Modus has a view of the strategy.  The strategy from the outset was always to augment our engineering capability as needed.  We will -- we always fully mobilize the resources that are available to us and make most effective use of them, and then we augment that as needed, based on the volume of work.

I think the learning as we went through this is that the amount of effort needed to produce design requirements ended up being larger than was initially anticipated.  And that was a learning that, you know, we had -- we incorporated as we progressed, but that's what I would say there.

I don't know think there was any mistake made here.  It's a learning, and we adjusted according to the strategy that we had implemented.

MR. CROCKER:  Okay.  Have you attempted to quantify the increased costs on an hourly basis?  You volunteered earlier in your answer that on an hourly basis, there would be an increase of costs.  Have you made any effort to quantify what the increase costs would be?

And, secondly, did you let engineers go who had begun to work on this internally?

MR. REINER:  We have not let any internal staff go.  So our engineering group is still intact and are still working actively on the project.  So no internal staff have been let go.

However, we do adjust the augmented staff up and down as needed, and have done that.  And so when the specific package requires certain skills, it's staffed up.  When the package is done, it is reduced.

I would not call this any increased cost.  If you wanted to see an hourly comparison of what an engineering services provider charges for engineering services versus what we pay our staff, I think there is other information that's been made available through the hearing on what OPG pays its employees.  You know, there are standard pay scales that we pay our folks.  When we look at the cost for this -–

MR. CROCKER:  Let me just stop you there.

MR. REINER:  Yes.

MR. CROCKER:  You were the one -- number one, Modus says there will be an increased cost.  I didn't create that, number one.

And number two, you were the one who said there will be an increased hourly cost.  I didn't invent that either.

MR. REINER:  Yes.  No, there is an -- so the amount per hour that a contractor charges is different than the amount per hour we pay an OPG employee, and it's typically higher because the contractor has overheads and other costs associated with it, and our hourly salary doesn't include all of those overheads.  We have pension liabilities and benefit liabilities that are accrued elsewhere.

So that's why, on an hourly salary basis, the cost of a contractor is higher than the cost of an OPG employee.  So that, I will agree with.

Has that increased the cost of refurbishment?  And the answer to that, I will say, is no, it has not.  When we look at our costs for completing the definition phase work, which includes completing all of the engineering work, with the exception of these cost increases that we talked about on the facilities projects, on the campus-plan projects, we are still tracking to plan on our definition-phase work.

MR. GOULD:  If I can add something on top of that, sir, that I think is important.  So the words that we use here are that there will be increased costs for the development of the MDRs, but you cannot just look at the MDRs -- you can look at the MDRs as a single line item within the budget.  You can see what that cost is.  But the real issue here that we are talking about in this report is the impact that the MDRs were having on the project, and what we commented on here and elsewhere in our reports, is that the owner giving more definition to the contractors will result in better engineering quality down the road.  And the better engineering quality down the road means that the work will be easier to execute when you have several thousand people on-site with tools in their hands.

So there may be a cost today that increases relative to the development of these initial scope-definition documents, but that cost pays dividends over and over again during the life of a project if it's done well.

MR. CROCKER:  All right.  You go on on page 27, the second bullet, just to continue the discussion of this way of doing things.  You say:

"There have been OPG-caused delays in approval of the OSS vendor's work, and the team needs to eliminate such constrictions where possible."

What caused those delays?  And have the supervisory people eased up a little bit?

MR. GOULD:  So start with the end of the story first.  The engineering team, despite the struggles that we documented in this report, ultimately met its milestone for the production of this first tranche of MDP packages actually two to three weeks ahead of schedule.

So the issue there is, did they meet schedule?  Yes.  I think in this report, as in the rest of our reports, where you see that we are focusing intensely on something like this, we are very concerned that we are seeing some early warnings about the urgency required to complete work on time.

We raised those red flags, the project team responded, and the fact that they completed on time or actually ahead of schedule is evidence of that.

MR. REINER:  If I can add just a point to that.  A key change that we made to address this is we actually physically co-located the vendor's team and our team in the same place, and what that immediately did is it allowed for that interaction between the teams and allowed for the review cycles and the feedback to happen in real time.  That was the big change that helped us sort of shorten the time lines here.

MR. CROCKER:  The bullet below that you talk about audits.  There was a lot of talk about audits yesterday.  Are those the kind -- the audits that were discussed yesterday, are they the audit program that the next bullet discusses?

MR. GOULD:  Could you -- which page are you on, sir?

MR. CROCKER:  Still on page 27.  I am on the third bullet.

MR. GOULD:  Third bullet, okay.

MR. CROCKER:  I am just asking whether the audit program that you are recommending in that bullet is the audit program that you were talking about yesterday?

MR. GOULD:  Well, so yesterday I think the question came about a statement in our report that there was audit fatigue on the project, so I would say, no, that this type of audit is more of a normal course of business type audit within the nuclear oversight group, that they would look into the overall quality of the engineering.

MR. CROCKER:  Is this auditing -- this kind of auditing then being done?

MR. GOULD:  I will let Mr. Reiner -- I believe it is.  I will let Mr. Reiner answer that.

MR. CROCKER:  The follow-up question --

MR. REINER:  It is being done.

MR. CROCKER:  -- to that will be, is there the similar kind of fatigue that was described as Mr. Gould describes it?

MR. REINER:  This is a little different, I think, than the audit fatigue that was described, because this type of audit is more about the quality of work that we receive from the contractor, and so the nuclear oversight function that Mr. Gould talked about serves a purpose here, and they do those kinds of audits.  But we do -- we do in the project our own internal audits as well.

So the type of thing that we would do, for example, we require the contractor to demonstrate to us that qualified people are executing the work.  The qualification has to be documented in the system.  There has to be evidence that the people working on the job have been trained and have successfully completed their training.  That has to be logged and recorded, and those are the kinds of checks that we do.  And then the other quality assessment that occurs is --

MR. CROCKER:  Is that -- let me interrupt you again.  Is that new?  That seems like something that --

MR. REINER:  It isn't new.  It is something that is the normal course of business when a contractor performs work in order for us --

MR. CROCKER:  And why is Mr. Gould having to recommend it at bullet 3 that you do it, if it's being done normal in the course of business?

MR. REINER:  Yeah, I mean, I can't speak to why he recommended that, but what I will tell you, it is part of our course of doing business, that when we have contractors do work for us, we have to assess the quality of that work, and it happens in engineering directly as part of the review process.

It happens -- it's sort of once removed through nuclear oversight.  It also happens through our supply-chain organization.  I think what Mr. Gould may have been identifying is the volume of work that contractors are doing is increasing and therefore your ability to audit and stay on top of the quality issues needs to be there.

I don't foresee this as an issue.  We are dealing with this.  I don't see this as a problem.

MR. CROCKER:  All right.  If we can go forward to page 35 of the same report.  In the second bullet on that page, you describe the way in which you're proposing to approach the issue.  And then at the bottom of the page, the bottom of the bullet, you say, in the last three lines:

"Even the best in the industry avoid this scenario.  In our experience, limiting the transparency of the schedule risks, the value of the schedule is an essential planning and communication tool needed to hold the contractors accountable."

If the best in the industry avoid this scenario, why does OPG choose it?

MR. GOULD:  They are not.

MR. CROCKER:  Have I misread?

MR. GOULD:  No, you didn't misread.

MR. CROCKER:  All right.

MR. GOULD:  The way that OPG is approaching the schedule is in conformance with what's best in the industry.  They -- we examined this issue.  We had many intense discussions with the project team about this.  This is something that we believe very strongly about.

We believe that in some ways the approach that they set out to take would have flaws.  We raised those red flags probably two years before you'd ever see a problem because of it based on our experience in knowing schedules and knowing projects, and we came to -- through meetings with the project team -- came to a consensus opinion that some of the observations that we made here that were very critical would be changed, and the path that OPG is now going down we would say is in conformance with what's best in the industry.

MR. CROCKER:  So your summary paragraph at the end of these bullets, when you say "in summary, Modus sees significant risk associated with the plan for tracking, scheduling", et cetera, "and are sceptical that the end project OPG intends to create will be useful, or a useful tool, let alone a...", how has that changed?  How has -- point to me where I can see the changes.

MR. GOULD:  So if you bear with me for just one moment.

MR. REINER:  While Mr. Gould is looking for that, I can give you the OPG project perspective on this.

So this was an area, as Mr. Gould identified -- so I describe the process whereby all the observations and recommendations get discussed between our teams.  This is an area where we felt quite strongly that we have adopted best practices.  And we wanted the Modus team to revisit this area in particular, and reassess their views.

And as part of that, the outcome was there were some adjustments we made in our process, and I think the Modus team at the end concluded that, yes, this is an appropriate method of integrating.  We have got the right visibility into each of the schedules.

There has been -- there has been a lot of evolution in the scheduling area since this particular report was written.  An example that I will give you, so this CNC schedule, it's the coordinating and control schedule.  We have multiple contractors doing work and we have to have the ability to see how that integrates and where there are milestones that might conflict each other.  And so the visibility across that and those interferences become critical.

We have now got in process a meeting that's held monthly with all contractors.  The scheduling folks from the contractors' offices attend that meeting.  They speak to those specific schedules and their milestones.  Every other contractor in the room is able to hear the status of schedule and what their key milestones are.  We provide a view of the integration across the projects, and that's an opportunity for everybody to see what those interferences are, and for us and OPG to be able to identify:  Is there an issue that requires us to have a contractor change a plan or advance some work or delay some work?

And that's what happens in that forum at the coordination level, at the level 2 in the schedule.  And that has evolved since this report was written.

MR. GOULD:  So if I can direct your attention to Exhibit 2, to the main exhibit, which is our fourth quarter 2013 report, sir.

MR. CROCKER:  June 26th report?

MR. GOULD:  No, it's dated November 12th, 2013.  If you look at page -- the bottom of page 9, you will see a section there under Roman numeral IV, "Functional group update."  It's an A schedule, A period schedule.

So if you look at that, in this first paragraph we summarize many of the conclusions that were in the prior report, which was the initial project assessment from August 2013.  And then we talk about -- this document, what I was discussing earlier, the discussions that we had with the project team where we revealed our concerns to the project team, and on page 9 and through page 10, those five bullet points identify how they were proceeding with the recommendations that we made, and that our conclusion was that this was an appropriate methodology for proceeding with the project schedule.

So we documented -- we identified the issues in August, we had a number of discussions with the team, we went through all of these issues with the team, and then this report reflects the end result of those discussions and the pivot that we believe management took in association with our recommendations.

MR. CROCKER:  I think I will just leave the rest of my questions on this report, because they have been dealt with yesterday, and ask you to turn to attachment 1, the attachment with all of the reports indicated.

I just want to request from Mr. Keizer some of these reports.

MR. GOULD:  Oh, you are referring to the document list that's attached to the August report?

MR. CROCKER:  Yes.  So I am looking at page 1, and almost at the middle of the page it says:  "Scope strategy and plan, 12/15/11."

Could I ask that we have that report, please?

MR. KEIZER:  Sorry, I will just ask the panel, is that something we have already produced in evidence or is that -- do we know what that is?

MR. ROSE:  I would have to go back and validate exactly what that is and -- I don't recall if we produced it.  Do you, Dietmar?

MR. REINER:  We will check at break whether it's in one of the management plans.  It is possible that that one is covered in a management plan, but we will check that at break.

MR. KEIZER:  To the extent it isn't, we had a series of caveats that attached to the same kind of production yesterday with Mr. Shepherd in his request for documents.  I am assuming to the extent we undertake to do that, it would be subject to the same caveats.

MR. MILLAR:  Yes.  I am assuming the answer is that you will either, A, show him where it is in the evidence, B, produce it, or C, explain why you won't produce it.

MR. KEIZER:  That's fine.

MR. MILLAR:  That will be JT4.1.

UNDERTAKING NO. JT4.1:  with reference to REPORTS ENTITLED "SCOPE STRATEGY AND PLAN, 12/15/11," "OTHER ENGINEERING, 24 MAY, 2013, VBO OUTAGE STATUS, MDR WORK STREAMS ENGINEERING STUDIES", "DR engineering weekly tactical update" dated April 19, 2013; "DR engineering weekly tactical update"; "Engineering weekly tactical update," dated March 15th, 2013; "OPG proposal, org and labour resources review, A, organizational labour strategy," dated May 11, 2010:  A, to indicate where they are in the evidence; B, to produce them; or C, EXPLAIN WHY THEY CANNOT BE PRODUCED.

MR. CROCKER:  And if we could go to page 2 of that list, and the third report on that page, it's entitled:

"Other engineering, 24 May, 2013, VBO outage status, MDR work streams engineering studies."

MR. REINER:  That's one that I don't recognize, and I am going to have to rely on Mr. Gould identifying what it was that he looked at there, because there is no document number.  There is a description.

MR. GOULD:  We can certainly check that at the break.

MR. CROCKER:  Thank you.

On page 3 --

MR. MILLAR:  Is that another undertaking, Mr. Crocker?

MR. CROCKER:  We can do all of this in one undertaking or separate undertakings.

MR. MILLAR:  How many do you have?

MR. CROCKER:  I have four more.

MR. MILLAR:  Let's keep them all as part of the same undertaking.  That's probably easiest.

MR. CROCKER:  Okay.  On page 3, there are three weekly reports described there about a third of the way down the page:  "DR engineering weekly tactical update," dated April 19, 2013; "DR engineering weekly tactical update"; "Engineering weekly tactical update," March 15th, 2013.

They also aren't numbered.

MR. REINER:  These I do recognize.  So yeah, we can provide those.  They haven't been submitted as part of our evidence.

MR. CROCKER:  I just have one more on page 5, two-thirds of the way down the page, "OPG proposal, org and labour resources review," I guess, "A, organizational labour strategy," dated May 11, 2010.

MR. REINER:  We will look at this one at break as well, because that may be covered in our management plans as well.

MR. ROSE:  Yeah, based on the date of this being May 2010, it may have been an early document that ultimately got culminated into our program management plans.  So we would have to go back and verify that.

MR. CROCKER:  That's fine.

I have a few questions on the June 26th report.

On page 6, in the paragraph immediately above the heading "B: Timelines and key events," you talk about the construction, among other things, the construction and the use of a full-scale mock-up for re-tube and refurbishment replacement.  Do you see that?

MR. GOULD:  Yes.

MR. CROCKER:  This is probably small potatoes in the grand scheme of things, and if it is we can move on.  How much does that cost?

MR. ROSE:  I will need to verify exactly the cost, but I believe it was in the 35- to $38 million range, by memory.

MR. CROCKER:  Okay.  So not that small potatoes.

MR. REINER:  So, yeah, it will be in that range.  We can get you an exact number, so I would say it's not small potatoes, but let me maybe provide some characterization of it.

So part of our strategy for the refurbishment -- and the key lesson learned is the mock-up.  Every refurbishment that was done prior to the Darlington refurbishment found that with -- they did not have the type of mock-up that we have constructed and found that that created significant issues for them, so we are going to achieve a couple of things with this mock-up.  One is ensure that the tooling operates to the required specification before we deploy them on the reactor face.  Every refurbishment prior to Darlington had a burn-in period for tooling on critical path on the reactor face that caused them significant delays.

The other thing that we are going to achieve with this is training of employees.  In the other refurbishments -- and we see this sometimes in our own outages -- the first time an external contractor is ever in a plastic suit wearing the radiological protective equipment is on the job site, and there is a, you know, there is a burn-in period, a ramp-up period, that is required in order for them to get productive, wearing double rubber gloves, wearing plastic suits, breathing apparatus.  We are going to do all of that offline.  Everybody that will work on refurbishment in the reactor vault is going to rehearse on the mock-up.

MR. CROCKER:  They couldn't do that at home with the stove?

[Laughter]

MR. REINER:  We might try that.

If you look at when we are at peak in refurbishment, a Darlington unit being offline costs the company about a million dollars a day.  Our run rate at peak with the number of resources that we'll have on-site is going to be about another million dollars a day.

So at $2 million a day it doesn't take many days to have a mock-up pay for itself.  We believe that this is actually a very critical investment that will allow us to really manage the critical path on this job.

MR. CROCKER:  I was going to ask you as a follow-up question whether you have done an analysis of the return on that investment, but I gather you have.

MR. REINER:  Yes, we absolutely have.

MR. GOULD:  If I can, maybe I can add a little bit more perspective on this from another project.  It was a project in the States, in the United States, a steam generator replacement project that -- I was part of the team that provided oversight, and on that project the first unit -- there were two units that were replacing steam generators.  The first unit had the longest steam generator replacement outage of its type of that type of unit in history.

So the company involved devoted, not to the extent of this type of mock-up, but significant resources to develop a mock-up to mock up the exact conditions under which the workers would be working going forward, and they went from having the worst outage ever to the best outage ever, and they reduced their critical path on that project by 46 days just by doing the work in the mock-up.

So we have seen tangible results from using mock-ups under these circumstances in the past.  This is an extraordinary -- and the whole point of this paragraph was to show what OPG is doing to provide confidence behind RQE.

And, you know, sometimes -- sometimes in looking at the different elements we see -- you know, you get a little bit too close to the flame, you look at one individual element like you talked about with engineering and schedule that we raised before.

We see this as an extraordinary effort on the part of OPG to do a lot of advance planning, more advance planning than I have ever seen on a project of this type, well, well in advance of execution.

MR. REINER:  As Mr. Gould had identified, as part of establishing the release quality estimate, we will have tested every sequence of work that will take place on critical path during the refurbishment outages, and that is what is going to give us a very high degree of confidence on this schedule, because we will have tested the tools, we will have tested the abilities of the workers to utilize those tools, the setup, the tear-down, the actual execution of the work, that will all be done on the mock-up, and that will feed into the release quality estimate.

MR. CROCKER:  I wanted to talk, actually, a little bit about the release quality estimate.  You say, Mr. Gould, on page 8 of your report that mega-projects like this need clear, visible objectives, and the release quality estimate is one of those.

Exactly when -- exactly what do you mean when you describe a release quality estimate?  What has to come together for that to be meaningful?

MR. GOULD:  So let me start the answer and we can let the project team answer for itselves.  What we are looking for in the release quality estimate is high confidence behind the up-front engineering, high confidence in the schedule, high confidence in the cost estimate, and that the risks have been fully identified, the known risks have been fully identified and contemplated as part of the overall review of the project.

It really goes into those four major elements of the underpinnings of the job.  Everything really flows through those four things, so that there are no guarantees when you get into the execution of a mega-project of this type, but having that type of information available so that it's fully vetted, so that not just our team, but all of the external groups that are looking at this project that need to have this information can see it.

Those would be the objectives for the RQE, and it's really getting into the underpinnings of -- that it's not just a number.  They are taking several years over a progressive process to develop this number over time, and there are a lot of different activities that build towards that date.  It's important for us, and it's essentially part of our scope -- it is the main part of our scope to characterize that effort to the board of directors to give them confidence that RQE is not just a number that was pulled out of the air.

MR. CROCKER:  So is it the date which is the important objective, or is it the analysis which gets you to the confidence level that's the important objective?

MR. GOULD:  It's the analysis, it's not the date.

MR. CROCKER:  Okay.  On page 10 on this chart in the third box, you talk about gaps with the Long-Term Energy Plan.  What are the gaps?  What kind of gaps are we talking about?

MR. GOULD:  So if you want to go through the first-quarter report in detail, I am happy to do that, but we identified certain of those.  I think some of that gets into the closed session, so if you want to do that I am happy to do that, but that's --

MR. CROCKER:  No, we can wait.  But are there -- have those gaps closed?

MR. GOULD:  I don't know that I can comment on that until we go into closed session.

MR. CROCKER:  Okay.

MR. MILLAR:  Mr. Crocker, how are you doing for time?

MR. CROCKER:  I am almost done.

MR. MILLAR:  Okay.  Thank you.

MR. CROCKER:  And I would have told you that even if I weren't almost done.

[Laughter]

On the bottom of page 11 you talk about, also on this chart, shoulder-to-shoulder work?

MR. GOULD:  Yes.

MR. CROCKER:  Is the shoulder-to-shoulder work that you are talking about there the kind of circumstances that Mr. Reiner talked about earlier?

MR. GOULD:  Yes, the collaborative process, yes.

MR. CROCKER:  Okay.  On page 15, in the middle, you talk about the projects and modifications organization hadn't adopted procedures developed by the design refurbishment team.  This is just above the heading "1: Extent and condition of budget scheduling, campus."

Why was that the case, or why is that the case?

MR. GOULD:  Why did they not adopt the procedures?

MR. CROCKER:  Yes.

MR. GOULD:  So I will answer and I will see if Mr. Reiner wants to append to it.

What we found from the evidence is --

MR. CROCKER:  My guess in advance is that he will.

[Laughter]

MR. GOULD:  What we found from the evidences was that projects and modifications was set up as a different organization.

The refurbishment project has its own governance, and it's exactly as it says here.  The projects and modifications was an existing organization that was out ahead of refurbishment, had been in existence for I don't know how many years.  I won't speculate on that.

But they were already doing quite a bit of work within the plants, and so these initial projects were assigned to them because they were -- it was believed that they had the capability to proceed with that under their procedures.

So what we identify here is simply a fact.

MR. REINER:  Just to add to that, so the project and modifications organization, they -- prior to taking on some of this prerequisite work for refurbishment, their function was to execute the nuclear project portfolio work that -- the allocation of funds, the business cases, approvals of business cases, is done by the nuclear business and follows the processes, the business planning processes and the financial processes used in the nuclear business.

For refurbishment, we started from the outset in building systems and reporting capability and financial tracking capability that is more project-focused.

So an example would be, when you look at the operations business, annual costs become very important.  They are also important for a project because we have obviously got to be able to manage the cash flows associated with the project, but life-to-date and forecast to completion become far more important.

So we have built systems and capability around a large project model.

In the case of the projects and modifications organization, there weren't a lot of those kinds of projects in their history, so those systems, the systems that were used to do the tracking, were different.

We are correcting that.  We are in process, as we speak, of rolling out the exact same systems for reporting, for tracking, for doing earned value management on the work that the projects and modifications organization is doing that is being used on the refurbishment project.  And that is underway as we speak.  It's part of the corrective actions that we are implementing as a result of the increases in estimates that we have seen on the D2O storage project and the auxiliary heating system project.  So these are changes that are in process of being made.

MR. CROCKER:  Is there someone supervising this who is saying to the P&M group:  Get on board?

MR. REINER:  They now report to me, the projects and modifications group, so I take direct accountability for that.

MR. CROCKER:  You are telling them to get on board?

MR. REINER:  I am telling them to get on board.

MR. CROCKER:  One last question, and it was discussed yesterday to some extent, but on page 17 you are talking about the auxiliary heating project, the delay, at the bottom of the page, the delay in that project and how it might impact the vacuum building outage.

And I think my question is:  Which one of those two projects is going to get out of the way of the other?  And will that -- is that the way it will be -- the scheduling problem will be resolved, or will it be resolved in another way?

MR. REINER:  When you say which project will get out of -- you are talking auxiliary heating system and vacuum building outage?

MR. CROCKER:  Yes.

MR. REINER:  So the vacuum building outage creates an environment where the auxiliary heating system is required, because we are shutting down four units in the spring and we could be -- during that time period there could be a day of cold weather and we could have some event that might require the system to be available.

So the current schedule has the auxiliary heating system get out of the way of the vacuum building outage, in that it will get completed prior to the start of the vacuum building outage.  It's not going run concurrently; it will be in service prior to the start of the vacuum building outage.

MR. CROCKER:  And are you flexible with the scheduling of the vacuum building outage, that it can be delayed?

MR. REINER:  No.  There is some limited flexibility, but the vacuum building outage can't be delayed.  As a risk mitigation measure, if we needed to implement a risk mitigation measure, we would need to find a way to provide heating steam to the plant by other means, and the other means would be the construction boiler house.  We would ensure that that stays available to be the backup supply.

There are other backup alternatives that could be implemented, but the vacuum building outage is the one that's fixed.  The auxiliary heating system is the one that we would move.

MR. CROCKER:  Thank you.  I have nothing further.  Thanks.

MR. MILLAR:  Thank you, Mr. Crocker.  Ms. Blanchard?

# Questions by Ms. Blanchard:

MS. BLANCHARD:  I have a few questions on behalf of Canadian Manufacturers & Exporters, and I will try not to cover any ground that's already been covered extensively.  I am just going to start generally.

It's my understanding that the key purpose of the update is, one, to update the evidence relating to the campus plan, and secondly, to present the Modus reports for the first time.  So I would just like to confirm that the Modus -- none of the Modus reports were initially provided in the filing?

MR. REINER:  That's correct.

MS. BLANCHARD:  And with respect to the campus plan projects, my understanding is there are really two themes that come out of the update.

And the first one is that the variances from the initial budget and scheduling estimates that are identified in the May 2014 Modus report are not material, because they don't trigger changes to the test period payment amounts.

So one of the key statements in the updated evidence -- and we heard this yesterday following questions from Ms. Girvan -- is the variances are not considered material because they don't meet the threshold for triggering a change in the payment amount.

MR. ROSE:  Let me break that down in two ways.  I think you referenced the Modus report.  And so Modus would not comment on the materiality of our impact on our rates.

MS. BLANCHARD:  Right.

MR. ROSE:  They would impact on the materiality of the cost increase.  We look at every cost increase as being serious and material through our project management approach, but from a perspective of looking at the rate impact, the calculations were performed -- as Mr. Barrett had alluded to yesterday -- and that the impact on this rate period was not the material of those cost increases of the in-service amounts, the revised in-service amounts for this period.

MS. BLANCHARD:  Okay.  So if we go to the update at page 7, we see those calculations that you are referring to.  So that's Exhibit D2, tab 2, schedule 2, page 7, just above the "Oversight processes."

Those are the calculations that you are referring to?

MR. ROSE:  Page 7 provides the recalculated in-service amounts, per the latest filing.

MS. BLANCHARD:  Right, so there was an overall cost increase of 213 million, but these are not considered material for the purposes of this application because of the in-service timing?

MR. KEIZER:  I think it's because the revenue requirement increase associated with the in-service amounts are not material, based upon OPG's materiality threshold that they generally apply as part of updates.

MS. BLANCHARD:  Right, but if the timing of the in-service additions had been different, or the -- for example, the scheduling for the storage, the heavy water storage facility had been on track or in accordance with the earlier estimates, it might have been material for the purposes of this application?

MR. KEIZER:  Sorry, I think if it created an in-service amount that would have been higher and therefore triggered a higher revenue-requirement calculation, it could have crossed that materiality threshold and put it in rates, yes.

MS. BLANCHARD:  Right.  And so ultimately that 213 million will be seen likely in the next rate application?

MR. ROSE:  That is correct.  It will be in the application related to when it goes into service.

MS. BLANCHARD:  Thank you.  So as I understand it, the other -- the other takeaway from the update, really, is that the various red flags, as we have heard them called, identified in the May 2014 Modus report relating to the heavy-water storage facility and the auxiliary heating system to a lesser degree, the process of -- or at least the issues experienced there were invited to consider those a learning experience that could be reviewed in an effort to improve processes for the larger refurbishment.

MR. REINER:  That's correct.

MS. BLANCHARD:  And it's referred to in the June 26 report at the top of the page as sort of an unintended pilot project, so that is page 16 of 21 in the June 26 report, where Modus was really contextualizing the heavy-water storage and auxiliary heating plant projects in the larger scheme of the Darlington project.

MR. GOULD:  I don't know that it was unintended.  You used the word "unintended".

MS. BLANCHARD:  Well, the wording is the project was unfortunately used as a pilot project.

MR. GOULD:  Okay.  It resulted in being a pilot project, yes.

MS. BLANCHARD:  So I suggested "unintended", because presumably -- or was it intended to be a pilot for the larger project?

MR. GOULD:  I will let Mr. Reiner answer that.

MR. REINER:  We did -- we did run a pilot to test the EPC model.  There was a project run.  It was specifically a pilot project.  There were some learnings that came out of that, that they were incorporated into the management plans.

For the -- it was a smaller project, and it was executed at Pickering.  I can't remember the exact nature of it.  I think it might have been a heat exchanger replacement project.

For the Darlington refurbishment itself, this is the leading project.  It's the one that's furthest ahead, so it naturally becomes the learning project, and that's -- I think that's what is being described by Modus.

MR. GOULD:  I don't believe that OPG set out with the intent of having a cost overrun on those two projects, so the unintended part would be the cost overrun.

MS. BLANCHARD:  Okay.  But because of a timing it de facto became a pilot for the larger Darlington.

MR. REINER:  It has become a pilot in the sense that it has resulted in some learnings.  Those learnings are being applied to the larger project.  As you have seen in reviewing these reports, some of the learnings are applicable -- more applicable to the other campus-plan projects.  There were already changes in strategy from the outset on the larger refurbishment execution project.

So, for example, getting to engineering complete before establishing a definitive baseline cost and schedule, that's the concept around release quality estimate that has been built into the refurbishment from the start.

For the campus-plan projects it's a little different, because they are stand-alone projects on a much shorter time line.  That same approach wasn't built into those projects.  So the learning from D2O storage is being applied to the other campus-plan projects.

MS. BLANCHARD:  So -- so in terms of, you know, following the theme of learning -- and we have had a lot of discussion about budgeting, and as I understand it, you know, the two key concepts are budgeting and schedule, and those are the two risks that really have to be managed.  We have got an undertaking that we are going to have an updated chart, so an update to the chart that's currently provided in the application, so that's at page 6 of the updated evidence, and that's the chart that shows the current forecasted amounts.

And so the chart that's contained there in the update shows the evolution of the campus-plan projects in terms of budgeting over the last almost year since September filing, and so I think what would be helpful would be to also understand the evolution of scheduling over the same period.

So -- because right now, you know, we are seeing final in-service dates for -- that were provided in September, but it's not totally clear to me how the schedule has evolved in lock step.

And so it seems to me that it would be useful if, either in this chart or separately, we had a sense of how the scheduling for those campus-plan projects has evolved in the last year, because it sounds like it has kind of gone in and out a few times over that period, and I think the evolution of both of those processes would be useful for the process.

So whether that's incorporated into the updated chart or whether it's given separately, if we could have an expansion of what the actual scheduled milestones were in September 2013 relative to as currently forecasted, that would be helpful.

And I think I understood from your evidence yesterday that we are still waiting for the heavy-water storage to be presented to the board of directors?

MR. REINER:  That's correct.

MS. BLANCHARD:  So I don't know what the timing would be or whether the current scheduling is available for the heavy-water storage, but we would like to be able to look at those.

MR. KEIZER:  So just to clarify, what you want to see is what was the projected milestones for these campus-plan projects, let's say at the time we filed the application in September 2013.

MS. BLANCHARD:  Yes.

MR. KEIZER:  And what are the revised milestone dates as of now.

MS. BLANCHARD:  Yes.

MR. ROSE:  Is the focus on the in-service dates that you are looking for, so the fact that we show only partial amounts of the heavy-water storage project being in service in the test period -- in the rate period, are you looking for the actual -- the final in-service dates or the entire schedule of all the in-service dates for that project as compared to what it was in our original filing?

MS. BLANCHARD:  Yes, that would be very helpful.

MR. ROSE:  Okay.  We can -- I think we can build that right on to the JT3.5 request, I believe it was.

MS. BLANCHARD:  That would be helpful, or if it's easier to do it in another format that's fine, but...

MR. ROSE:  I mean, I think we already have the in-service dates for the -- the changes in the in-service dates for the items going into service listed here.  You know, I think the addition from yesterday's 3.5 is you want to understand the stuff that wasn't going into service and its cash flow --

MR. KEIZER:  No, she wants to understand that you had a certain milestone in-service date for each of these projects in September of 2013, and what are the current projected milestone in-service dates as of now.

MR. REINER:  Yes, yes.

MR. ROSE:  Okay.

MR. KEIZER:  So that she would be able to see what ones are delayed and which ones are on time; is that correct?

MS. BLANCHARD:  Thank you very much, Mr. Keizer.

MR. REINER:  Okay.

MR. MILLAR:  So will that be provided as part of the existing undertaking, or would you like to assign it a separate number?

MR. REINER:  I think we can do it as part of the existing undertaking and capture it all.

MR. KEIZER:  That's fine.  One less document for us to keep track of.

MS. BLANCHARD:  Thank you.

And so just continuing on the theme, so there has been some learning that's happened associated with the campus-plan projects, and we have seen some fairly significant variances, and I think we have heard that a lot of that has to do with issues relating to the initial scoping of the project relative to the scoping that's recently occurred.

So I am looking at the Modus comparison of the 4C estimate relative to the current forecast, and I understand that that might not be a perfect comparison, but at least for discussion purposes I am going to go there.  So it's at page 16 of the June 26 report, just because it's an easy representation of those variances.

So we are seeing the variance there on the water storage that goes from 110 million to approximately 276, you know, qualified, as we have heard.  And I understand, as I said, that a lot of that has to do with scoping, but I am assuming that in that number, there also may be other items.

And, Mr. Reiner, you mentioned yesterday, just for example, that to deal with this scheduling crunch around the vacuum building outage or around the commencement of the Darlington refurbishment, OPG might consider taking measures like, for example, making use of multiple shifts or using other tools to accelerate the schedule for the heavy water storage.

And so one of the questions I have got is:  Does that updated forecast contemplate that type of measure?

MR. REINER:  Yes, it will.  That updated forecast will look at -- I talked about an effort on our part to bring back the in-service date for that facility to August of 2016, so it will incorporate the measures required to the achieve that.

MS. BLANCHARD:  Okay.  And so has there been any effort to isolate costs that would be associated with that type of measure?

MR. REINER:  That's part of the work that is currently underway.

MS. BLANCHARD:  And given that those costs might be attributed to sort of the learning aspect or the pilot project aspect of these additional -- that these costs might be attributed to those -- whatever you want to call them -- hick-ups or speed bumps, has there been any thought given to removing those from the amount that's going to be included in the rate base?

MR. REINER:  I wouldn't characterize them as costs associated with learning.  I think one of the points that I was attempting to make yesterday is the issue that we have on the D2O storage project is an estimate was produced before the scope of work was understood.  It would be false to use that as the starting point.  That estimate is not reflective of the work.

The estimate that will be reflective of the work and schedule is the one that will be produced here, that we will update.

So the time period that we are working towards hasn't changed.  This isn't a learning thing; this is get the job executed, given the scope that we are dealing with in the period of time that we have available to us.

So I would not characterize these as learning costs.  These are part of the facilities that are needed to execute refurbishment.  It's part of the cost for the overall refurbishment.  So I don't believe that's a correct characterization of the costs.

MS. BLANCHARD:  Is there any sense that any part of the delays are attributable to the management issues that are identified in the May 2014 report?

MR. REINER:  We have made improvements in the engineering processes, for example, to streamline and shorten approvals.  Those sorts of benefits have been factored in.  Again, to -- you know, to call these learning costs or call these -- you know, the thing about a project like this, there isn't sort of a template on the table and:  Here is how it should be done and this is the schedule you should be following.  Now, let's see where you are and let's do a comparison and then we will try to distinguish what's learning, what's not learning.

To me, this is part and parcel of project management.  You look at the risks, you look at the challenges, you correct them and you move forward.

So that kind of a segregation, I wouldn't know how to do that and it is not something that we would contemplate.  I think what becomes important is, you know, how have we responded to the risks that have emerged, the risks that Modus has identified in their report, risks that we have seen, how have we responded and what actions have we taken in order to ensure that we can manage those risks inside the project envelope that we are talking about.

MR. GOULD:  If I could add something to that that I think will be helpful, I think you also have to look at the overall cost of the entire program, because as Mr. Reiner discussed, you have to look at the risk of that particular project within the overall scope of the work.  So what risk does completing D2O storage take off of the table for refurbishment, which is a much larger set of risks.

So all of that would have to be analyzed.  That's a long way off from even being in a position to do that.

MS. BLANCHARD:  Okay.  Well, maybe I will move on, then.  And so I am now on page 5 of the May Modus report.

And at the top of the page, Modus is commenting on some of the management -- problems with the management model employed.  And one of the items that's flagged is the use of inexperienced project managers.

So who were these people?  Were they -- were they internal OPG staff?

MR. GOULD:  Yes.

MS. BLANCHARD:  And they were not -- they were inexperienced how?  They were inexperienced because of the scale of the project, or they were -- what was meant by "inexperienced"?

MR. GOULD:  So I think you were on the right track.  As Mr. Reiner discussed, the projects and modifications organization was set up to do smaller modification and non-modification work within the operating plants.  And it, in some ways, is a different skill set to the approach a very large, complex new construction project from the ground up that are represented by these campus plan projects.

MS. BLANCHARD:  So is this group of project managers no longer participating -- are they not participating in the Darlington refurbishment?  They are going back to doing the smaller-scale projects?

MR. REINER:  No, these -- this group of -- I mean, we always -- people always move around, get reassigned.  We always look at career paths and development for staff, and if they are not suited for certain jobs we will encourage them to move into other jobs.

But in general, the project management that's in place is still in place.  What we have done is we have augmented it.  We have brought in a new and very senior construction -- large project construction-type director that can provide some of that experience that was lacking.  What we then do with our staff is part of their development is to work under some of these -- under the more experienced project managers and project directors, and to learn, because we want to develop their capability.  We are dealing with a project that's going to take until 2025 to close, and we do have to develop the capability and make sure we have succession plans in place and we have a stream of resources that are able to take these projects on.

So this is being built into our succession planning and development planning approach for project managers.

MS. BLANCHARD:  So is this new and experienced director, was that person already an OPG employee?

MR. REINER:  That person was not an OPG employee, is now an OPG employee.  It is one of the changes that were made that I think was identified.

We have a couple of others that were OPG employees.  OPG had seconded a couple of individuals to Atomic Energy of Canada for the Point Lepreau refurbishment.  Those folks are back on the refurbishment project, and they have taken on senior roles on the project, so we are making direct use of the experience that they gained there.  And they were -- they were former OPG employees, and we just ran them through a development process.

MS. BLANCHARD:  So it sounds like there has been some fairly significant new hires, and has all of that happened since May of 2014?

MR. REINER:  No, some of that happened much earlier on and would have started around -- the changes were starting to be made around mid-2013.  The new person that came on to take on that senior role arrived in early 2014.  I think it was around January -- it was in early 2014.

MR. GOULD:  And I think we document not only the new VP's arrival, but also that as of the time of this report many of these changes had already been -- had been jump-started, and some of the -- some of the new things that Mr. Reiner is talking about had already begun.

MS. BLANCHARD:  So the person that you are describing is a new vice-president?

MR. REINER:  Yes.

MS. BLANCHARD:  And that person replaced Bill Robinson?

MR. REINER:  No, that person -- that person replaced the former vice-president of the projects and modifications organization, which would have -- which would have been Mike Peckham.  Bill Robinson came in in May of 2013 to augment the project.  He came back from retirement, spent a year with us to help the project, and he came in to oversee the project, so that was a change that was made at the CEO, board level.

MS. BLANCHARD:  Okay.  I am going to switch gears a little bit and go to page 8 of the Modus report.  So one of the significant issues that's been flagged here at the second-last paragraph on page 8 is that the lack of accurate reporting deprived senior management and the board the option of revisiting the original BCS analysis in order to determine if building a new AHS facility continues to be the preferred option.

And that's particularly true in light of the fact that there were three competing options to building the AHS that were priced at less than 50 million.

So one question is, have these other options been reconsidered, or were they reconsidered after this report was produced?

MR. GOULD:  So you accurately summarized what -- or you accurately stated what's in the report, so we were just highlighting that as a red flag to OPG that they do need to revisit that, so in the updated BCS that was provided as part of the board materials for the approval of this project, I believe that those issues were reinvestigated.

MR. ROSE:  I am sorry, I am having a tough time following you.  You said page 8 of which report?

MS. BLANCHARD:  Of the May report, I apologize.

MR. ROSE:  And which paragraph are you referring to?

MS. BLANCHARD:  It's, I guess the third from the bottom.  There is some redacted language, and just above that there is a discussion about options that were priced

-- or options to building the auxiliary heating system.

MR. ROSE:  And, sorry, can you repeat your question specifically?  Now I found the place I can understand the context.

MS. BLANCHARD:  The question was whether those options had been reconsidered by the board as recommended by the report in May.

MR. ROSE:  Yes, so we would have -- in updating our business case we would have done an assessment of the options still available and considered whether a refurbishment of the existing construction boiler house was or was not an option.  That would have been considered in that business case.  The conclusion is it is not an option because of the size requirement of the new boiler house.

I know I took an undertaking yesterday to provide the latest copy of that, and you will see that analysis in that business case.

MS. BLANCHARD:  Thank you.  And so what would have triggered the recommendation to reconsider those options was the variance from the original budget estimate?

MR. GOULD:  That's correct, and what we are saying here is they had to go back to the board with revised business case, so they needed to go back and re-examine all alternatives, that it would be prudent on OPG's part to re-examine all alternatives going forward from that point, and as Mr. Rose just stated, they did do that.

MS. BLANCHARD:  Okay.  And so what kind of variance acts as a trigger?  Is it a variance that's above the bands described in your various class estimates or, you know, is there some kind of red line where this obligation or recommendation to reconsider is triggered?

MR. GOULD:  Well, let me just state my own belief about this.  Mr. Reiner may have a different one.  If you have gone to the board for approval and you need to go back to the board for additional funds, you need to re-examine the basis by which you are asking for additional funds.

So I don't know that there is a dollar amount that I would put on that, but if you had to go back and ask for more money, you probably should go with justification for why you are asking for it.

MS. BLANCHARD:  And that would include reconsidering options that would require, for example, cancelling contracts?

MR. GOULD:  It could, if that was the most prudent course at that time.

MR. ROSE:  To elaborate on that point, you asked what the threshold is.  For the business cases that we take to the board -- we are talking about the individual project business cases like the auxiliary heating system or the heavy-water storage -- anytime the variance is greater than 10 percent of the amount of the business case, we re-evaluate that business case and for incremental funding we would have to go back to our board.

We sometimes, as I talked to yesterday, that we have funding that was released in November of 2013 at the program level, and then we have individual business cases for the facility and infrastructure projects, so sometimes we are going to the board and we are providing them an update on the cost estimate, and the funding may already be released in our overall program, it's just a discussion of the allocation of that funding that's in there.  There are other times where we may require incremental funding.

MS. BLANCHARD:  Would there be any other triggers for this kind of reconsideration other than a variance in cost of 10 percent?

MR. REINER:  I suppose, hypothetically speaking, if you got into some -- I mean, ultimately the issues would manifest themselves in costs, but if you got into some technical complexity that just had you realize that what you are constructing is just not going to work, but the end result in that would be, you know, would come back to a cost impact.

MS. BLANCHARD:  Okay.  So Mr. Shepherd had asked for -- I guess, Mr. Shepherd, you originally asked for a copy of the agreement with SNC-Lavalin Aecon, and the suggestion was that a summary would be provided, and then later in the day there was some discussion about termination for convenience clauses, and it seems to me that it would be useful if those clauses could be produced specifically.

So I would like to add to that undertaking and say we would like the summary, but we would like to specifically see the termination for convenience clauses.

MR. SHEPHERD:  Let me just step in.  I'd like you to make that a separate undertaking.

MR. KEIZER:  For, sorry, sorry, what was that, Jay?

MR. SHEPHERD:  I don't want that added to mine.  I am happy with mine as it stands.

MS. BLANCHARD:  Okay.  So I'd like a separate undertaking to receive a copy of the termination for convenience clauses contained in the agreement with SNC-Lavalin and Aecon.

MR. KEIZER:  Can we actually -- well, it's 11.  Could we actually -- maybe if I have a chance to discuss it with the panel over the break, and then I could come back.

MS. BLANCHARD:  Sure.  And I actually have a related request, which is that I would also like to see those provisions of the contract which tie the contractor to scheduling estimates, if those are in the contract, if there are specific provisions of the contract that transfer scheduling risk to the contractor.

MR. KEIZER:  We will include that in the same discussion.

MS. BLANCHARD:  Thank you.

MR. MILLAR:  We should take a break.  Ms. Blanchard, how are you doing for time?  You are almost at 40 minutes now.

MS. BLANCHARD:  I had one last question and it's probably short.

MR. MILLAR:  Why don't we do the last question?  And then we may not have to return to Ms. Blanchard after the break.

MS. BLANCHARD:  So the last question is in your update you mentioned that your September filing contained an endorsement of OPG's commercial and contracting model by Concentric Energy Advisors.

And one question I had was:  Did Concentric get an opportunity to review Modus's report?

MR. REINER:  Yes, they did review Modus's reports.

MS. BLANCHARD:  So they reviewed them in September before they submitted the 2013 report?  They reviewed the August Modus report?

MR. REINER:  We had Concentric review, just recently, all of the Modus reports to see if that would change their views on the approach being taken by OPG management.

MR. KEIZER:  Sorry, just to clarify, though, my understanding, as well, is that they did see the Modus reports prior to rendering their opinion as of December 31st, 2013.

MS. BLANCHARD:  Thank you.

MR. SHEPHERD:  Can I just ask a follow-up to that before you take the break?

So are we going to get an update from Concentric on their review of the contracting strategy?

MR. KEIZER:  We are going to make Mr. Reid available for you to cross-examine.

MR. SHEPHERD:  Well, if he has new information, I think we need to see that in advance of his evidence.

MR. KEIZER:  My understanding is he does not have any new information to provide.

MR. SHEPHERD:  Well, he has read the Modus reports now.

MR. KEIZER:  My understanding is that his opinion has not changed as a result of reading the Modus reports.

MR. SHEPHERD:  Why isn't he here today?

MR. KEIZER:  We assumed that, quite frankly, he was self-contained in his own opinions, and so it wasn't related directly to the update.

MR. SHEPHERD:  Okay.  Thanks.

MR. MILLAR:  Let's take our break.  We are running behind schedule, so can we come back -- I guess we better make it 11:20.

### --- Recess taken at 11:03 a.m.

### --- On resuming at 11:23 a.m.

MR. MILLAR:  Okay.  Welcome back, everyone.  We will get started again.

We are now moving to Mr. Battista, who I think has the last questions that will go on the public version, and --

MR. KEIZER:  Sorry, Mr. Millar, can we, though, before -- when we break for lunch, because I am assuming that we are going to go through to the lunch hour, just before we break, maybe I could take five minutes and just update people on where we are with GEC's undertaking request.

MR. MILLAR:  Did you want to do that now?

MR. POCH:  Let's do it now.  Let's do it now.  It's fresh in our hands.

MR. KEIZER:  Yes, because otherwise...

So I think where we're at is, I -- and hopefully I can summarize this correctly, and I am sure that regulatory affairs from OPG will jump in and advise me if I have got it wrong -- that Mr. Poch asked us to do a calculation to see what the impact would be of taking, let's say $20 billion, spreading that over the various work packages, and what implications it would be in terms of contractor responsibility or OPG responsibility or otherwise.

Our view is that -- OPG's view is that to take the 20 billion is not a number we feel comfortable with, because we think it's an unrealistic one, but what we have in terms of trying to do to satisfy Mr. Poch's request is to put him in a position where he can calculate or extrapolate whatever scenario he wishes to do so.

And so what we would like to try to do is effectively, for the various work packages, to be able to identify what percentage is fixed cost, identify on a dollar basis, you know, for every dollar below the target price, this is the implication, and for every dollar above the target price, this is the implication; and that then he would be in a position to be able to extrapolate as to the consequences of whatever number of excess above the 10 billion that we are currently discussing.

So what we are attempting to do is put together that, and I have had a discussion with Mr. Poch, but I will allow him to speak for himself in terms of his feeling with respect to that.

MR. POCH:  Well, I don't see the problem with running hard numbers, but if that's OPG's preference, that's fine, we can try that, and in the end I will probably run some numbers and then put those to OPG witnesses in the main proceeding just for them to confirm the math.  I just don't want us to spend time in front of the Board doing math, but that's fine.

And perhaps in the next few days as they do that we will stay in touch and make sure that we can avoid any prolonged discussion before the Board later.

MR. KEIZER:  That would be fine, sure.

MR. MILLAR:  So this was the --

MR. POCH:  JT3.17.

MR. MILLAR:  That's right.  Okay.  So is everybody happy?

MR. POCH:  For now.

MR. KEIZER:  Under the circumstances, yes.

MR. MILLAR:  Okay.  So we will move to Mr. Battista now.  When he is finished we will have to go in camera, so we will take a very short break to set that up, but for now Mr. Battista.

# Questions by Mr. Battista:

MR. BATTISTA:  Yeah, I shouldn't be very long.  Some of my questions are really points in clarification.

In the material in the updated evidence, two terms are used interchangeably:  "Campus-plan projects" and "facilities infrastructure projects".  The latter is often mentioned in the original evidence.  The Modus report talks about the campus plan.

So that things are clear going forward, can we assume that they are exactly the same, or do they differ?  And if they differ, just identify what projects are excluded from that one generic statement versus the other?  Not to take up time now, if it's -- the answer is the same you can say so.  If it's not the same you can undertake to show where projects are included or projects are excluded through undertaking.

MR. ROSE:  So the facilities and infrastructure projects and the campus-plan projects are the same projects.

MR. BATTISTA:  So when we see those words we don't have to worry about --

MR. ROSE:  That is correct.

MR. BATTISTA:  Okay.  Thank you.

The other thing I just would like clarified, I guess, going forward, because today when we have been talking about business -- the cost estimates, we have been using business-case summary dates.  Now we are all talking about 4B, 4C, 4D.  It gets a bit confusing.

Just to confirm, is 4B the July 2009 business-case summary?

MR. ROSE:  4B would be our November 2012 --

MR. BATTISTA:  November 2012?

MR. ROSE:  -- business case, which was filed in the original evidence.  We go to our board annually, so release 4C went to our board of directors in November 2013, and we filed that in impact statement number 1.

MR. BATTISTA:  Right.  And then 4D would be November '14.

MR. ROSE:  4D would be November 2014.

MR. BATTISTA:  Okay.  So they are annual events.

MR. ROSE:  That's correct.  Until we get to RQE, which will be --

MR. BATTISTA:  October.

MR. ROSE:  -- October 2015.  RQE, that will be release 5, and it will cover the first unit.

MR. BATTISTA:  That's release 5.  Okay.

And then mention has been made that, in August, OPG's management will be going to its board of directors with a report or a cost estimate.  What exactly will be the content of that?

MR. ROSE:  So at the program level on the annual programs we provide the board of directors our latest information on each of the projects, including the -- generally the estimate for the BCSs that went before the board in that year.

So when we go -- so in release 4C, in November 2013, the estimate for the heavy water would have been equal to the business case that went to the board in that year.

We will update the business case for the heavy-water storage facility in August of 2014 and provide the board with a new estimate for that project and also discuss the impact on the overall program and the current release that we have that we are working with within -- that was released under 4C.

MR. BATTISTA:  So there will be no amendment to or adjustment to the 4D or November 2014 business-case summary for the whole project?

MR. ROSE:  4D?  Will we --

MR. BATTISTA:  Sorry, 4C.  Sorry --

MR. ROSE:  4C; that is correct.  4D will reflect the best information that we have at that point in time.

MR. BATTISTA:  Right.  But in August it is just the heavy-water unit.

MR. ROSE:  That is correct.

MR. BATTISTA:  Okay.  Thanks.

Okay.  I understand that the contract with Burns and McDonnell/Modus was awarded in February 2013.  Now, when did the request for proposal for that contract go out?

MR. GOULD:  Best as I recall, the request for proposal went out in the summer of 2012.  I can't remember the exact date.

MR. REINER:  If you require, we can get you an exact date as to when that was issued.

MR. BATTISTA:  Okay.  And was that described in the evidence that was filed in the fall?

MR. GOULD:  Our response was in the fall.

MR. BATTISTA:  No, I meant in --

MR. GOULD:  Oh, I'm sorry.

MR. BATTISTA:  -- the OPG evidence filed in the fall.

MR. KEIZER:  I don't believe so.

MR. REINER:  I don't believe we touched on the Modus arrangement or the process for engaging Modus.

MR. BATTISTA:  Okay.  I guess you didn't think it was material to the case?

MR. REINER:  I guess, just a clarification, the evidence that we did file in the fall included a program assurance plan.  That assurance plan does identify Modus and external oversight and the model that the project has employed.

MR. BATTISTA:  Okay.

# Questions by Mr. Shepherd:

MR. SHEPHERD:  Can I just ask a follow-up question, Richard?  You had the original Modus report before you filed your application; right?

MR. REINER:  The -- Modus provides a report -- Modus provided their first report to the board in August of 2013.

MR. GOULD:  Yes.

MR. REINER:  And provides a report at each nuclear oversight committee meeting.

MR. SHEPHERD:  Right.  So you had their initial -- what they call their initial project assessment report before you filed your application?

MR. REINER:  It -- the timing for the filing of the application -- I think we filed in very early September, late September.  The board review would have been around August.  I think we had it in hand, yes.

MR. SHEPHERD:  Okay.  The reason I am asking that is because the initial assessment report does specifically talk about your contracting strategies. and I would have thought that was relevant if you were asking for approval of your contracting strategies.  I don't know why you wouldn't have included it at least at some point.

MR. REINER:  Yeah, we had contemplated including, and have done so in the update, the concentric reviews of the contracting strategy, but fair point.

MR. SHEPHERD:  Thanks.

# Questions by Mr. Battista:

MR. BATTISTA:  Okay.  Thank you. In the update, D2, tab 2, schedule 2, at page 3 and at page 8, it's mentioned that concerns were identified by OPG regarding the heavy water storage and the HSS projects, and Modus was asked to come in and review that.

I guess just quickly, what were the nature of the concerns, and when were they initially communicated to Modus for investigation?

MR. REINER:  So the nature of the concerns were related to the schedules and the difficulties that were being encountered by both the contractor and the project management team in developing the schedules, and also the cost estimates.

So those were issues that were becoming apparent to management, and therefore OPG had asked Modus to do a specific deep dive into the campus plan projects.

MR. BATTISTA:  And what was the timing of that as to when you -- management became aware:  We got a problem, and calling -- adding it to the Modus contract, so to speak, to investigate?  What was the timing of that?

MR. GOULD:  First quarter of 2014.

MR. BATTISTA:  So management didn't have concern -- wasn't aware of these problems until January 1st, no earlier than January 1st, 2014?  Or...

MR. REINER:  We always provide and look at updates in schedules and forecasts and project status, so there was an awareness that the projects were having difficulty.

The kind of root cause that we asked Modus to do that started to look at what are the underlying issues that are contributing to these problems, the Modus report certainly provided insights into that.

MR. BATTISTA:  Were you aware of that before your 4C business case summary in November 2013?

MR. ROSE:  The 4C business case summary reflected the latest estimate that we had for both projects.

MR. BATTISTA:  Right?

MR. ROSE:  Which did not include any cost growth, so we were not aware of any cost growth.  We were aware of some early slippages on schedule, and we were assessing the impact of the schedule and its impact on the in-service dates.  The latest in-service dates, to our knowledge at that point in time, would have been included in the release 4C.

MR. BATTISTA:  Right.  So the concerns that prompted calling Modus in weren't strong enough or material enough for you to flag it in your report to your board of directors in November?

MR. REINER:  The magnitude of the cost increases were not understood at that point.

MR. BATTISTA:  So it became apparent between November and early January?

MR. REINER:  The -- yeah.

MR. BATTISTA:  Okay.  I would like to take you to page 9 of Exhibit D2, tab 2, schedule 2, the third paragraph.  And it explains, I guess, the reasoning for the problems with the projects and modifications.

And I was wondering, did OPG senior management view the campus plan or the infrastructure projects as a minor maintenance or modification type of activity?  Which was the -- you know, that's the kind of work that modifications was good at, so to speak.

MR. REINER:  Yes.  I mean, we didn't -- we viewed them as projects that projects and modifications could execute.

I mean, they are different and were recognized as different than minor modifications from the outset, because they are largely buildings and facilities versus systems.

But we had embarked on a strategy to utilize the projects and modifications organization on these prerequisite projects, and then to continue to use that organization to manage the balance of plant projects in refurbishment.  So this was sort of a ramp-up to prepare that organization to execute those projects.

So we did view it as something that was manageable by projects and modifications.

MR. BATTISTA:  Right.  I think yesterday you mentioned that heavy water storage, comparatively, is more complicated than re-tubing, because there has been a lot of history and a lot of sites on re-tubing, but this is one of the first heavy water storage initiatives.

So I was wondering if -- since you knew that, why would you give a maintenance kind of group the responsibility for something that was so novel and so new?

MR. REINER:  I mean, initially when we embarked on the project and what we had understood at the time, it was heavy water storage only, which -- you know, the complexity arose as the needs were understood and as the integration to the tritium removal facility was understood and all of the sort of life-cycle management-type improvements that were also being made to the tritium removal facility as part of this.

So as we understood what the scope of work was and the complexity that was actually inherent in that scope of work, that is when we recognized that the projects and modifications organization wasn't equipped with the tools that they currently had to be able to manage that.

Now, that's not to say that, you know, therefore this organization should not be used.  That gets back to the kinds of changes that we have implemented: augment the team with more expertise, make changes to processes, enhance the reporting, apply earned value management techniques.

So those changes were being implemented to support that effort.

MR. ROSE:  I think it's worth it to clarify, though, your characterization of the projects and modifications organization as just being a group that did maintenance projects is not -- I don't see that as the proper clarification and how we term maintenance to be.  The projects and modifications does support what we call maintenance overflow work in our outages, but they also do modification work on nuclear systems, and they have in the past done some facility projects within our fleet.

So it wasn't that they -- this was taking them out into a paradigm that they have never done.  We had experiences with them.  I think that the paradigm was the EPC model approach was relatively new, and then the complexity of the D2O with relation to the design, the seismic requirements, et cetera was what complicated the project.

So it wasn't that we went in blindly, giving them something that they had never -- you know, making that type of a leap.

MR. BATTISTA:  Yeah, but it does say here:

"PM was chosen to manage the project since the DR team was at an early stage of being organized."

So it sounds like you weren't ready to do it the right way, I guess, but so that is why projects and managements got it?

MR. REINER:  It isn't that we weren't ready to do it the right way.  I think we still view this as being the right way, and there are learnings that are being built in to ensure that we can manage this appropriately.

The Darlington refurbishment team was really focused on getting the work, the definition phase work done by the release quality estimate, and then to ramp up its construction capability in time for breaker open on the refurbishments.  So we didn't anticipate doing that kind of a ramp-up to manage construction-type work in that definition phase.

And I believe it was the right strategy to utilize an organization that had already -- that had that capability, and then to grow that and enhance it and make sure that it can be done in an effective way.

MR. BATTISTA:  On this area, just one last question.

Obviously there has been a bit of a hiccup -- well, to be, you know, kind about it.  What is the financial impact, if you had gone –- if this work had been done under the DR team initially versus the maintenance team, would the overall costs related to these campus projects come in at the same amount, or at a higher amount?

MR. REINER:  I would say the cost impact is probably pretty negligible.  There were some inefficiencies, and there's some churn that obviously results in cost, but the change in estimate is a result of scope of work not being understood.

The difference -- the difference would have been that before an estimate was tabled the scope of work would have been understood, and the estimate we would be talking about here for D2O storage would be a $300 million estimate, not a $110 million estimate.  That is what the difference would be.

It would still be part and parcel of the overall project envelope.  We wouldn't change -- we wouldn't have changed the project envelope as a result of that, because it is within our abilities to manage that.

MR. BATTISTA:  Right.  So is it -- in terms of the incremental costs as a result of the hiccup, though, are we talking 10 million, 50 million, 5 million?

MR. REINER:  Again, I want to clarify "hiccup".  "Hiccup" means the estimate was not right and now we are working to a correct estimate.  That is the hiccup we are talking about.

MR. BATTISTA:  So just to be clear, you are not incurring any incremental costs as a result in this switch.  You had an original plan using maintenance?  Now --

MR. REINER:  There may be some inefficiencies in terms of getting the engineering -- the interaction with engineering set up the right way and making sure the reviews get done in flight and we can cut time out of review cycles, but we are not talking about many millions of dollars.  We are talking small numbers.

The change is the scope of work, is the actual physical work.  What would not have changed is the seismic design requirement, which added a significant complexity, or the tritium-removal requirements in that facility, which added complexity.  That would not have changed.

MR. BATTISTA:  So ballpark, less than 5 million?

MR. REINER:  I would say, yes, you know, just ballpark off the top, definitely less than 5 million.

MR. BATTISTA:  Then I would like to take you to attachment 1 of the Modus report, so that's the June 26th item.  On page 7, on the table, the last event, second-quarter 2014, says:

"Revised BCSs, business case summaries, presented to the board of directors for approval."

When were these provided to the board of directors?  Like, in just this past -- which month?  Was it in June or May?

MR. ROSE:  It was provided to the board of directors in May.

MR. BATTISTA:  This was May.  Okay.  And this is just relating to those subsets of the campus-plan project; right?

MR. ROSE:  So each of our projects have a different schedule of going to our gate review boards and then our board of directors.  These three were the only ones that went to the board of directors in May 2014.

MR. BATTISTA:  Okay.  And I would like to take you to Exhibit D2, tab 2, schedule 2, page 6.  In the table for the heavy-water storage facility, the original dollars and schedule as filed show April 15th and an amount of 83 million going into the in-service, and then it was updated in February, still in-service in '15, and then based on the updated evidence that we received a few days ago the in-service becomes 19 -- January 2017.

I was wondering why there are still amounts going into service, let's say, for '14 and '15?  Like, what part of the storage facility is going to be used and useful?

MR. ROSE:  So there are -- and I know we discussed this yesterday, and it will be -- we will include this in the undertaking JT3.5, but it is related to buried services.  So the location that the heavy-water storage facility is going, there is buried services, operating services, today that needed to be relocated, so those services will be going into service, so we will be relocating, and they will be used and useful by operations immediately upon completion of those work programs.

MR. BATTISTA:  And as discussed yesterday, the revenue requirement currently being proposed by OPG assumes $83 million of rate base in the storage facility, and the new plan is for 15 million, because things are going to be moved forward and the project is going to almost double in cost, and I appreciate the methodological approach about materiality and impact on revenue requirement, but it is the case that right now in our cost-of-service application there is 83 million for the storage facility when only 15- is going into rate base, planned to go into rate base, truly in 2014.

Okay.  So that concludes my questions.

MR. MILLAR:  Thank you, Mr. Battista.

We are going to go in camera now, so we will just take a couple of minutes to get everything set up.

### --- On commencing in camera at 11:52 a.m.

MR. MILLAR:  Okay.  We are ready to continue.  Everyone in the room is either with staff, OPG, or has signed the undertaking.

Mr. -- oh, I'm sorry, Mr. Poch, you are going to begin.

MR. POCH:  Yes, thank you very much.

# Questions by Mr. Poch:

Gentlemen, when I left off with you last day, I think the last thing we touched on was the turbine control sub-project, which you indicated had been taken out of the Darlington refurbishment capital costs, would be dealt with in the future, would presumably therefore still be in the LUEC, but was part of the 179 that came out.

Can you turn to the August 13th report at page 19.  And there, just under the graphic, it says:

"The turbine generator scope grew by [redacted] million or [redacted] percent due to the addition of the turbine controls system and general scope finalization."

So I just wanted to get a -- is the difference between the [redacted] and the -- whatever part of the -- first of all,

what part of the 179 was the turbine control deferral?  And

then can you confirm to me the difference between the [redacted]

and that is because this escalation had yet to be built into the 10 billion, so it will also be dealt with in the future?

MR. ROSE:  My recollection of the turbine generator control system costs that were excluded and removed as part of the blue ribbon was approximately [redacted] for Unit 2 only.  We -- and that's for the execution costs on Unit 2, again, [redacted], subject to check, but I know that's the ballpark.

And the other three units, the costs for the other three units as well as the design for the turbine controls, remains within our base estimate.

MR. POCH:  Okay.  So it's only the unit -- so why would you defer Unit 2 and not defer the other out of the Darlington project costs?

MR. REINER:  There's a couple of factors that weigh into the decision for deferral.

There is still useful life left in the existing control system on Unit 2.  Unit 2 is coming down prior to really reaching end of life of that equipment, so that's one factor that weighed in.  So time value for money.

Another factor that weighed in is we did make also a conscious risk mitigation decision by deferring that particular upgrade in the first unit refurbishment.  From a project perspective, it's a good risk mitigation measure.

There have been complex -- there have been challenges encountered by each of the other refurbishments that have taken place that have done turbine generator control system upgrades.  The burn-in periods are longer than initially anticipated.  We wanted to have the opportunity to understand the design, do simulator testing, and really be in a position to focus -- to focus on that particular upgrade and dealing with it separate, outside of the first unit refurbishment.

MR. POCH:  All right.  So this is really an example of getting it out of the critical path because it has a lot of uncertainties --

MR. REINER:  Because it's got uncertainties.  And it shows up on critical path at unit start-up, typically.

MR. POCH:  Okay.  Can we turn to the November 12th attachment B?  That was the spreadsheet that was talked about at the outset this morning.

And can we just identify -- are the campus projects synonymous with the box there that says, I guess, "Included CS projects"?  I am sorry, just the "F&IP CS projects."

MR. ROSE:  So the campus plan projects encompass the "Infrastructure projects" line under the -- it says "DPP EPC," top quadrant of this table.  Refurbishment in-station.

It also includes facility and infrastructure projects, CR projects, "CR" meaning core refurbishment projects, projects that are necessary for the refurbishment outage.

MR. POCH:  Where is that, sorry?

MR. ROSE:  Just about a third down the page.  It is titled "Facilities and infrastructure projects, CR projects."

MR. POCH:  Yes.  So all of that section?

MR. ROSE:  That one line.

MR. POCH:  Oh, just the one line -- oh, I am sorry, yes.

MR. ROSE:  Yes.  And the F&IP CS projects near the bottom.

MR. POCH:  Right.  Where there are four lines?

MR. ROSE:  And I am going to correct myself.  The infrastructure projects refurbishment in-station are not considered campus plan facility infrastructure projects; these are projects that are being done as part of our shutdown and lay-up project, sorry.  I am thinking of the project manager.  I couldn't get to the name of the project The shutdown and lay-up component.

So the facility and infrastructure projects that we were referring to are spread on these two lines, "facility and infrastructure projects, CR" and "facility and infrastructure projects, CS," "CR" meaning needed for refurbishment, "CS" meaning in support of extended station life.

MR. POCH:  Okay.  Thank you.  Turning to the May 13th report, and attachment C, right at the back of your bundle, page 1 of that attachment, there is an indication there in the bottom box that with the exception of phase 1 engineering design and award, long-lead procurement, which was contracted on a fixed-price basis -- so this is referring to the D2O storage and drum handling.

I am just trying to get a fix.  You have indicated roughly 270 million overrun on your campus projects, a lot of it having to do with D2O.  And then this indicates that some of this was -- some of the engineering was on a fixed-price basis.

Have there been, to your knowledge, cost overruns on the fixed-price portion that aren't showing up in your 270, because your contractors are eating that?

MR. ROSE:  Not to my knowledge.  The fixed-price engineering is the fixed-price engineering.  If there is additional engineering required through the scoping, that would be added on.  But no, I don't believe there would be any expenditures beyond the fixed-price amount.

MR. POCH:  Okay.  And just while we are here, on the next page, on page 2, in the first block there, "[redacted] labour

material rentals," where there is, at least in percentage terms, a very high cost run-up of 535 percent, was any of that fixed?  Or is that all -- was that all target pricing cost-reimbursable?

MR. ROSE:  We believe that was all target price cost-reimbursable.

MR. POCH:  Okay.  And overleaf on page 3 -- not to argue the motion about what should be confidential or not -- I am just trying to understand, first of all, you give these numbers in -- boxed in red, the increase from 3,000 meters of piping to 14,000 metres, for example.

Why is that confidential?  I don't want to get into an argument about this.  I am just trying to wrap my head around what the concern there is.

MR. ROSE:  So I will just tell you the general basis for our redactions were based on commercial harm and/or harm to the vendor relationships that we have.  So where there was a clear deficiency in the vendor's performance or information that would put us at a commercial disadvantage for -- we redacted.

This was probably under the guise of performance, vendor performance.

MR. POCH:  All right.  So this would have been -- your assumption here is that this was indicative -- this was due to the contractor just not appreciating what needed to get done, and so they underestimated?

MR. ROSE:  The contractor not appreciating the complexity of the scope of this project at the time that they submitted their bid.

MR. POCH:  Okay.  Going to the June 26th report at page 10, I think this was just touched on earlier, but you indicated you couldn't answer in open session.  There was a box there where you refer to gaps in complying with the LTEP.

And I am wondering if -- Mr. Gould, I think it was you -- if you can just elaborate on that now.

MR. GOULD:  So this was a major topic of discussion for our report from November of 2013.  So perhaps it would be better to discuss it in the context of that report rather than --

MR. POCH:  Whatever you can --

MR. GOULD:  This is a summary of -- a very high-level summary of that report.

MR. POCH:  Fine.

MR. GOULD:  So if you want to go to that document, it's the --

MR. POCH:  Yes, fourth-quarter 2013 report?

MR. GOULD:  I'm sorry, it's the first-quarter 2014.

MR. POCH:  All right.  So that's the August -- I'm sorry, let's go to 2014.

MR. GOULD:  March 4th, 2014.

MR. POCH:  Yes.

MR. GOULD:  So beginning on page 3, there is a table, so first we discuss -- we discuss the approach that we took in the second paragraph of this report, where we looked at the principles set forth in the Long-Term Energy Plan and looked at ways of -- ways in which OPG was in compliance, and we also identify ways for strengthening OPG's planning for completion of the release quality estimate related to that.

So we -- in -- from pages 3 through 7 of this report we go through each of the relevant pieces of the Long-Term Energy Plan and our assessment of the project's compliance with that plan.

MR. POCH:  Okay.  So the gaps then that you in your cover report, you just mention the word "gaps", are the ones where you have actually said potential gaps in the various boxes here?  Is that what you are referring to?

MR. GOULD:  That's correct.

MR. POCH:  Okay.  We will come back to that in a minute, I think.

August 13th report at page 4.

MR. GOULD:  So I should put this one aside for now?

MR. POCH:  Yes, sorry to jump around.  It's just, this way I won't lose track.

MR. GOULD:  Page 24, you said?

MR. POCH:  Page 4.

MR. GOULD:  Page 4.

MR. POCH:  And I just wanted to make sure I understand what numbers we are working with here.

The point-estimate numbers you recite there, there's

the 2009 point estimate of [redacted] billion and change, and then

2012 third-quarter of [redacted] billion.

How does that compare to the point estimate?  Can we just -- sorry, Mr. Reiner, I imagine this is for you.  I thought the point estimate now associated with the 10 billion number was less than that.  Am I wrong?

MR. REINER:  The point estimate is in the business case that was filed as attachment 5 in D2-2-1 --

MR. POCH:  Yeah, just from memory I recall it was around [redacted].

MR. REINER:  No, no, it's in that same range.  I think it's --

MR. POCH:  Oh, okay.

MR. REINER:  -- I think it's pretty close to that number, actually.  Let me just pull it up here --

MR. POCH:  So by "point estimate" what do you mean?  The estimate without contingencies and without --

MR. REINER:  No, that does have contingencies included.  That would be a --

MR. POCH:  Ah.

MR. REINER:  -- high-confidence estimate.

MR. POCH:  Okay.  I'm sorry.  All right.  So the only thing that's not --

MR. REINER:  Without contingencies it would be down to the number that you were talking about --

MR. POCH:  Okay.  And so that's what was -- confusion of language here.

And does that number include management reserve or not?

MR. REINER:  No, that number doesn't include management reserve --

MR. POCH:  All right.  And management reserve is the difference between that and 10 billion, basically?

MR. REINER:  Right.

MR. POCH:  Okay.  And at page 53 of this same report there is a discussion of -- at the very bottom of that page there's -- and going over the next, there is discussion of this "perfect" reference plant which is -- comes freighted with ambiguity -- your words, Mr. Gould -- and you are referring there to -- I take it from context you are referring there to the references -- the use of the experience at Wolsong on schedule management; is that right?

MR. GOULD:  No, we are referring more generally to the use of Wolsong as a reference plant.

MR. POCH:  Okay.  And so just tell me your understanding of how Wolsong was used as a reference plant.

MR. GOULD:  Well, I think it's explained fairly well within the context of the report.  So if you want to go through any specifics, but my understanding is that Wolsong was used primarily for purposes of the class 4 estimate by the joint venture of SNC and Aecon --

MR. POCH:  Right.

MR. GOULD:  -- for purposes of preparing their class 4 estimate.

MR. POCH:  Right.  And you are -- your concern in plain language is that they have used that in an oversimplified fashion.  They haven't accounted for things that went wrong at Wolsong.  Is that right?  Perhaps you

can explain this [redacted] percent of it as as-built durations, so -- I am not familiar with the language there.

MR. GOULD:  So first off, our concern was that the approach that they took to the overall development of the class 4 estimate using Wolsong as the reference plant was an attempt to, in essence, get down to the absolute perfect version of the project that was performed at Wolsong as scaled up for the size of the -- the size differential for Darlington, and that without appropriate qualification around that estimate, that it could be -- it could lead to some misunderstanding about the nature of the estimate itself.

MR. POCH:  In other words, how realistic it is to simply apply this perfect Wolsong example.

MR. GOULD:  That's correct.

MR. POCH:  Okay.  And can you just tell us, what are the differences which you think need to get recognized, in broad terms, between the experience at Wolsong and what was to be anticipated here that they didn't recognize?  One of

these things is this [redacted] percent figure.  You can tell me

what that is.

MR. GOULD:  Let's start with that.  Let's go point by point, if we can.

So the [redacted] point -- the [redacted] percent refers to the amount

of time that -- in the review of Wolsong's as-built durations they looked at any inefficiencies that may have occurred on Wolsong and stripped that time out of the Wolsong duration.  It is the --

MR. POCH:  I see.

MR. GOULD:  So to get down to brass tacks --

MR. POCH:  So their perfect version --

MR. GOULD:  -- on what the unimpacted schedule for Wolsong would look like.

MR. POCH:  All right.  So they took Wolsong's schedule

and said, We can do it [redacted] percent faster because we can

eliminate some of the problems they had.

MR. GOULD:  No, that is not what they said at all.  What they --

MR. POCH:  Okay.

MR. GOULD:  -- said was, if you take Wolsong's schedule and take out any evidence of any inefficiency of a guy not showing up for work that day or a ship not coming in with an important part on the exact day that you need it, this is what you would get.

MR. POCH:  Okay.  And that was the wholly unrealistic -- part of the wholly unrealistic mile post that -- as you refer to it.

MR. GOULD:  What we are saying is -- what we are saying there is that you're -- in the attempt to strip it down, you create a mile post that can be misunderstood.

MR. POCH:  Okay.  And so may I summarize it that this -- the concern that you are getting at ultimately is this has led to -- may have led to some of the -- some underestimation by the contractors, and hence you're advising OPG to exercise more oversight to correct for that?  Is that --

MR. GOULD:  No, I wouldn't say that at all, sir.

MR. POCH:  Why is this an issue then?

MR. GOULD:  What we were looking at is, in a more broad perspective here, as I said yesterday, OPG has hinged itself to the AACE recommendations on how to classify cost estimates.  And what was done here and labelled a class 4 estimate by the contractor does not neatly fit into the AACE definition of a class 4 estimate.  So what we were attempting to do is to characterize the effort that was done by the contractor at class 4 for what it was, and just to call out for both the good and the bad, and in fact we say that they probably should have -- that OPG should look at this for what it is and not attempt to pigeonhole it as a class 4 estimate in the broader sense.

MR. POCH:  Okay.  All right.  I notice in that same box on page 53 there is a reference to the fact that the class 5 through class 3 estimates don't include contingency amounts, and that is another example you are citing of it not following the AACE recommended procedure; correct?

MR. GOULD:  That's correct.

MR. POCH:  I want to ask a little bit now -- I am going to move on to some references where you talk about monetizing risk and target pricing.  I assume that's related?

MR. GOULD:  Yes.

MR. POCH:  Let's look at the June 26th report at page 13.

And at the bottom of the page there you say:

"There is ambiguity in pricing risk for the RFR target price.  The contract monetizes contingency as part of the target price, not before."

MR. GOULD:  Yes.

MR. POCH:  And you indicate that, in "Status," that they have undertaken to -- SNC-Aecon has committed to modelling contingency in the 4D estimate, and I assume the earlier one we were talking about was the 4C estimate.

So I am wondering what the implications of -- in terms of the numbers that the OPG board has seen and this Board has seen, not including this monetization of contingency.

MR. GOULD:  Let me clarify that.  And perhaps Mr. Reiner or Mr. Rose would like to add on to it.

What the board has seen relative to this estimate is it was fully anticipated by the contract that the contingency would not be monetized until the negotiation.  What they have seen up until now, including in class 5 and class 4 in the prior releases, is OPG's assessment of contingency around this project.  So it's not devoid of contingency.

What we are saying here is to get a more refined number from the contractor, you should get -- it would be preferable to get the contingency monetized from the source.

MR. POCH:  Okay.  And then once that -- you get that contingency monetized, presumably it becomes part of a particular contractor bundle and would be -- there would be a corresponding reduction or -- in OPG's broader contingency allowance; is that fair?

MR. ROSE:  That's correct.  So what happens is we have a contingency set aside for our owner's assessment of their estimate and the risks associated with that project, obviously highly informed with the ongoing conversations and relationship we have with these vendors.

As we get to the target price, the target price will include an amount for contingency.  We'll transfer the allocatable amount and control it at the project level.

MR. POCH:  Okay.  And that -- from page 8 of your August 13 report, I take it that at that time you didn't expect SNC-Aecon to do that monetization until May 2015; is that still accurate?

MR. GOULD:  I think what we identified here was that this is a potential gap, and in August of 2013 we raised that issue.  And subsequent to that, my understanding is that Mr. Reiner and Mr. Rose would have gotten some agreement from the contractor that they will provide some input on this.

MR. ROSE:  At the project team level, there has been a big effort in understanding what the risks are.  You want to understand what the risks are early so that in the vendor's estimate they can actually put in their plan methodologies how to resolve those risks.  So you are not going to ultimately need the contingency.

That being said, we are now going through a process of understanding that contingency and doing an analysis collaboratively with the R&FR vendor, to get a much better perspective on their opinion of contingency and building that into our 4Delta estimate.

MR. POCH:  Let me take you to two references, then, to see how that gets followed on.

And one is the August 13th report at page 38, where it says:

"Making OPG's risk register the foundation of the project contingency analysis potentially transfers quantifying risk and the exercise of estimating contingency not only away from the cost estimating function, but from the contractor to the owner.  As yet, we have not had a chance to fully review how the items in the risk register are monetized and how contingency is actually calculated.  The opportunity to do so will come with our vetting of the 2014 business plan budget process."

So I want to just tie that to what we were just talking about.  Can you help me there?

MR. GOULD:  This is a broader context than just the SNC-Aecon contract.

MR. POCH:  Yes.  I understand.

MR. GOULD:  This is for the entire project.  So what we were advising as of that time was to ensure that you are getting as much information as you go forward from the contractors in evaluating and monetizing risks as possible.

MR. POCH:  Okay.  And on page 48 it says -- at the bottom it says:

"Once there is an agreement, the target costs with only be increased for those risks that were identified, unless the risk is an excusable event."

And that means identified in the risk register, I take it from if earlier sentence.

So it's not just a matter of getting a better fix on risk; this is the mechanism by which you are going to determine who is going to bear the risk; is that right?

MR. ROSE:  Yeah.  As part of the target price determination, the risks that are best controllable by -- the risks that are best controllable by the R&FR vendor, we will allocate contingency to them and manage and control.  There may be other risks associated with that project that we feel that we are in the best position to monitor and control, and/or we would rather be the party holding the contingency.

MR. POCH:  Right.  Okay.  And I take it that, Mr. Gould, in your experience, the more that goes in the risk register, the higher the target price is likely to be, because the contractor is being asked to bear more risk?  It's that simple?

MR. GOULD:  In general, that could be the case, but what we have seen in the last year since we made these observations is a significant reduction in the number of risks identified within this particular contract that we are talking about.

MR. POCH:  Leaving aside, of course, that you may have better understanding because your engineering is more complex, for example -- I understand all that.  I am just saying all else being equal, the more of the risks that gets put into the risk register and therefore into the contracts, the higher you would expect the target price you can negotiate with them would be?

MR. GOULD:  It creates ambiguity.  And what I would say to that is -- and I am not trying to parse words here.  I am just trying to explain.

What we have been looking for in our observation of the development of this risk register, in particular for the RFR contract, is the movement of what you would assume to be business as usual risk, that -- into the actual contract estimates, so that if the contractor is anticipating that they will spend that money, rather than have it lingering out there as a potential risk, let's -- that should be included in its base cost estimate, as opposed to on a register, and in the event that it occurs, then it has a whole lot of transaction costs associated with it, and all other kinds of things.

MR. POCH:  You are going to be maybe be in litigation for that matter, if it's not foreseen and --

MR. GOULD:  Well, you would certainly want to avoid that at all costs.

MR. ROSE:  Just let me add too from an owner's perspective, I think your point is that the vendor may be motivated to populate their risk register as high as they can to drive up the target price and maximize their opportunity for incentive.  I think that's maybe where you are going there.

We recognize that, and the effort to truly understand every single risk early, understand the ones that are included in their base cost as business as usual risks to ensure there is an additional opportunity for incremental revenues, and for the ones that are truly theirs to manage, that we want them to manage, give them the risks; the ones that are truly ours to manage, we hold that, so that it's not on the target price and give the opportunity for incremental incentive.

MR. POCH:  Right.  So the ones in the risk register -- I might have had it backwards -- the ones in the risk register are the ones where the target price can rise because you control them?

MR. ROSE:  The ones that are in the R&FR vendors' risk register would be included in their target price.  So if that risk didn't come to bear, theoretically they are less than the target price.  They have -- there is an incentive.

MR. POCH:  Right.  Okay.

MR. ROSE:  The risks that we carry are not in their target price.  And if they come to bear we may adjust their target price accordingly, but that is better for us to be in that control.

MR. POCH:  Okay.  Changing topics, June 26th report at page 14 says:

"With respect to the RFR class 3 estimate, OPG needs to hold the RFR contractor accountable for meeting the required schedule dates."

Were you there, Mr. Gould -- just saying the schedule date you are referring to is for the production of the class 3 estimate?

MR. GOULD:  Yes.

MR. POCH:  Okay.  And do I take it then that the contract that's in place at -- now prior to the final target price contracts being secured don't have in them explicit dates for production of these estimates as we go, these refined estimates and penalties and so on, for that analysis work?

MR. REINER:  They do have dates, and there is a schedule currently under the -- for the work that they are currently doing in this phase of the contract.

MR. POCH:  So --

MR. REINER:  I think what Mr. Gould was identifying -- so this is a little dated -- it was a huge amount of effort required to get this class 3 estimate completed.  What we saw --and as we were progressing through the development of the class 3 there were some early packages developed that gave us an opportunity to vet the methodology, but there was a big bow wave yet to come, and this was a heads-up to OPG, there's a bow wave, and you need to be cautious of the fact that a major project milestone may be missed.  Now, they did actually achieve the milestone, so this is now history.

MR. POCH:  Okay.  And just a couple more questions.  Yes.  If you turn to August 13th report at page 34, there Modus observes:

"In our view the contracts executed to date do not present clear and unambiguous rules to hold contractors accountable in schedule development.  They rely on the parties reaching mutual agreement on the schedule, which is a concept fraught with risk."

Et cetera.

What's the status of that?  Have you crystallized yet -- have you crystallized schedule milestones, you know, with penalties and so on in the contracts, or is that still work to be done, negotiations still to happen?

MR. ROSE:  There is two points here.

MR. GOULD:  Yeah, there's -- you kind of mixed two different pieces here.

MR. POCH:  Help me out.

MR. GOULD:  So this section of our report deals with the fact that we believe that the contracts themselves needed to have stronger identification of the precise scheduling and project controls requirements that the -- that OPG would require from their contractors.

So that was the basis of this comment.  And my understanding -- and I will let Mr. Rose comment on this -- is that because of the size and the representative value of the RFR contract, that -- and the fact that the RFR contract was very early out of the box for -- to advance the schedule for the overall project, the thought was that the methodology used for the RFR contract would be the basis for all the other contracts that OPG would enter into, and thus those requirements would emanate from the development of the RFR schedule.

MR. ROSE:  And that is correct.  I mean, our -- when we went into the R&FR contract, being the lead contractor, we ended up with a partner, SNC-Lavalin, that had good experience, and some of our early observations were, let's actually understand their experience and how they have developed schedules for large construction projects and ensure that we partner that together with our needs.

We went through that exercise, and we have now set a scheduling standard and a common work breakdown structure that's required for all of our contractors, and it's a part of the contracts that we issue.

MR. POCH:  So in other words, you are suggesting this concern that was at the outset has been rectified both in the particular contract for RFR with your main contract with SNC-Aecon, but also in all your other contracts you are now putting in place more explicit schedule milestones at the outset.

MR. ROSE:  Schedule standards, NWBS.  The milestones are a different part of that exercise, in accordance with the schedule standards and milestones.  There was a deliverable -- a milestone deliverable from the R&FR contract that required them to submit their schedule management plan, which we had the opportunity to vet and make sure that was in accordance with our needs.  We then applied that methodology and how they are going to do the schedule, the adapted methodology, which included our impact into it, to all of the other contractors that

come --

MR. POCH:  Let me just ask this.  By the time you get to your release quality estimates, will you actually have, not just a requirement that they provide schedules, but will you have schedules for all your contractors, for all the steps?

MR. REINER:  Yes.

MR. ROSE:  Absolutely, without a doubt.

MR. POCH:  All right.  Okay.  And then in the May 13th report at pages 19 and 20 there is a discussion at the bottom of page 19 starting there of RFR commercial risks, and first of all, this is your most recent report, other than the cover report, which takes this into account, or was this -- I guess this is just prior to your cover -- your June report, obviously, so it's May report.

Never mind that.  It's obvious from the dates.

You close that discussion, Mr. Gould -- your group closes that discussion with a comment that the -- you found some reluctance on the part of OPG people to consider modifying the contracts, which you obviously feel there would be appropriate to consider.

Where does that stand now?  Is that something that...

MR. REINER:  Maybe I can answer that.

MR. POCH:  Yes.

MR. REINER:  We have launched an initiative, and this is through our internal contract management organization and process, to have a look at the contract and just see if it aligns precisely with everything that we are trying to achieve.  I think one of the areas that Modus has highlighted where there may be some misalignment with the LTEP principles is the incentive structure that's built into the contract, drives towards the best outcome across four units, not necessarily the best outcome on the first unit.  There are unit-over-unit contractual improvements that are embedded in that contract.

That might put us in a position where we are misaligned with the LTEP, which says, you know, based on how well you do on the first unit we will make a decision on the second, so those are the things that we are revisiting, and we will embark in discussions with the R&FR contractor.  And as we -- in terms of where we stand on that, our timing for that is, as we get into the discussion around target price we would also discuss any amendments that would need to be made to the contracts at the same time, so this would all culminate with the release quality estimate.

MR. POCH:  Okay.  But there -- in that -- in the previous sentence is they refer to things like "whether a negotiated guaranteed maximum price once engineering is complete".  That would be a significant change to your target pricing approach; right?

MR. REINER:  That would be a significant change.  That's, you know, that's an observation -- I view that as an observation from Modus as something to consider.  We would not necessarily go down that path.

MR. POCH:  All right.  So that's still a consideration, but you are not saying -- at this point you are not ready to --

MR. REINER:  We are not saying at this point that we would go down that path, because a guaranteed maximum price, I mean, it is obvious what that would mean.  You'd pay a premium to achieve that.

MR. POCH:  Understood.

MR. REINER:  And we'd need to understand what that premium is and whether there is value in paying that.

MR. POCH:  Okay.  Thank you.  Those are my questions.

MR. MILLAR:  Thank you, Mr. Poch.  We are getting close to a lunch break, but Mr. Crocker, you had just a couple of minutes to do.  Would you like to get that in before lunch?

MR. CROCKER:  Mr. Poch stole my thunder and asked my question.  It had to do with gaps between the program plan and the Long-Term Energy Plan, and so I don't have any questions.

MR. MILLAR:  Okay.  So you have no questions?

Why don't we take our lunch break, then?  It's 12:30.  We will come back at 25 minutes to 1:00, and we will still be in camera -- I am sorry, to 2:00, not to 1:00.

### --- Luncheon recess taken at 12:34 p.m.

### --- On resuming at 1:38 p.m.

MR. MILLAR:  Good afternoon, everyone.  We'll get started again.  We are still in camera, and we will move now to Ms. Blanchard.

# Questions by Ms. Blanchard:

MS. BLANCHARD:  So I just have a few brief questions, and I am going to start with the update materials on page 1.  So this is OPG's update on the project.

The first question is, there is a statement at line 6 that the heavy-water storage and the auxiliary heating projects represent less than 5 percent of the total planned expenditures for the DRP, and I just wondered if you could clarify how that percentage was derived.

MR. ROSE:  The current projection for the D2O of 287 million plus the approved estimate for the auxiliary heating system, which I believe is $85 million, totals 380-ish million dollars.  It's less than 5 percent of the $10 billion.

MS. BLANCHARD:  Thank you.

MR. ROSE:  You're welcome.

MS. BLANCHARD:  My next question is on this range.  So we have seen reference to the 6- to $10 billion range.  It's referred to in this update report on page 5.  So that's the DRP cost range of 6- to 10 billion.  And I understand that that range has been in place since 2009; is that accurate?

MR. REINER:  The 6 to 10 has been in place since 2009, but we have lowered the 10.  The 10 billion in 2013 dollars would translate to 10.8 billion, roughly, and we have reduced the upper bound to 10 billion in 2013 dollars.

MS. BLANCHARD:  So just focusing on the lower end of the range for a moment, based on what OPG knows today, is there any reasonable scenario where 6 billion represents -- still represents a possible lower range?

MR. ROSE:  So the $6 billion, in 2009 we had a Monte Carlo, an S curve, on our 2009 business case, the P50 amount was approximately $6 billion, the P90 amount was about $10 million -- $10 billion.  So our probability of getting to $6 billion today would be well less than the 50 percent confidence.  We haven't done that assessment.  You know, our current estimate -- our high confidence estimate, P90, is our -- generally around our point estimate.  Our $10 billion is our high confidence beyond P90 level estimate.

The likelihood of us getting to $6 billion today based on the advanced planning that we have done and understanding of our scope is certainly different than it would have been in 2009, and a probability that would be less than 50 percent.

MS. BLANCHARD:  I have to admit that there was a fair amount of terminology in that answer that escaped me.

[Laughter]

But I guess, umm, I guess as a follow-up question I would ask, does OPG still think it's appropriate to show 6 billion as a possible outcome?

MR. REINER:  I can point you maybe in the direction of the updated business case that was filed with the 2-2-1, attachment 5.  On page 38 there is a -- there are a series of S curves that are the result of the analysis that Mr. Rose spoke about, and you will see how those have changed over time.

So if you took the same P50 to P90 point you will see that that starts to move upwards.  So it's the result of the Monte Carlo analysis and the mathematical modelling.  So probabilistically from a mathematical point of view, yes, there is that potential kind of an outcome.

We have been careful to talk about the project as a less-than-$10 billion project, rather than a 6- to $10 billion project.

MS. BLANCHARD:  Okay.  But you are still -- in your application materials you are still referring to a 6- to $10 billion project.  At page 5, line 6.

MR. REINER:  Yes, no, I see that, and I would -- I would say that that -- without clarifying exactly what that means, I wouldn't -- I wouldn't conclude from this that there is an outcome that could result in a $6 billion project.

MS. BLANCHARD:  Thank you.  That's all I have, actually, thank you.

MR. MILLAR:  Thank you, Ms. Blanchard.

Mr. Shepherd, are you ready to go?

MS. BLANCHARD:  Oh, actually, just before I go, I had a brief discussion with Mr. Keizer before lunch, and I am going to try to catch a plane now, and I just wanted to indicate for the record that Mr. Keizer and I spoke, and I am in agreement with what he will propose in terms of my requested undertaking.

MR. KEIZER:  So the response is that there was two aspects to the request:  The early termination provisions and also provisions -- a provision relating to the adherence to schedule.  So obviously the contract itself is confidential, and OPG can produce the early termination provisions, obviously, in a confidential basis.  They wouldn't be partly redacted, they would be wholly redacted, because they don't mean anything unless in its entirety.

With respect to the issue of adherence to schedule, that's not as simple, because there isn't just one provision like an early termination provision in a contract, and that weaves itself through all number of areas within this very voluminous contract, whether it's in, you know, incentive areas or whatever else.  So what we think, that aspects relating to that is captured within the summary of the contract that we are proposing to produce, and so my colleague is fine with us producing the early termination provisions on a confidential basis and providing the summary in response to the earlier undertaking question.

MR. MILLAR:  Okay.  So that's a new undertaking for the termination provisions?

MR. KEIZER:  Yeah, I don't know if we gave a number that time.  I am not sure if we did or not.

MS. BLANCHARD:  We might not have.

MR. MILLAR:  I don't think we did.

MS. BLANCHARD:  Yeah.

MR. MILLAR:  So we'll call it --

MR. KEIZER:  So anyway, we just wanted to clarify that.

MR. MILLAR:  Very good, so JT4.2, and that's just to provide the termination provisions --

MR. KEIZER:  Yes, in confidence.

MR. MILLAR:  -- in confidence, and the rest will be provided as part of Mr. Shepherd's undertaking.

MR. KEIZER:  Yeah, by way of the summary.

MR. MILLAR:  Yes.

UNDERTAKING NO. JTX4.2 (IN CONFIDENCE):  TO PROVIDE THE TERMINATION PROVISIONS.

MS. BLANCHARD:  Thank you.

# Questions by Mr. Shepherd:

MR. SHEPHERD:  I have questions on a number of areas.  I just came in at the end of that discussion, and I take it you were talking about the point estimate; is that right?

MR. REINER:  We were talking about the 6- to $10 billion range.

MR. SHEPHERD:  All right.  The current point estimate is the one in the business-case summary from December; right?

MR. REINER:  Yes.

MR. SHEPHERD:  And that's [redacted] billion?

MR. REINER:  Yes, and just -- and maybe one additional thing.  It's that estimate adjusted by the growth that we have identified in the campus-plan projects.

MR. SHEPHERD:  So now it's [redacted] billion.

MR. REINER:  It's -- let me turn to Mr. Rose on what our current estimate is.

MR. ROSE:  Yes, we have lifted that point estimate by $[redacted] million.

MR. SHEPHERD:  So it's now [redacted] billion; is that right?

MR. ROSE:  That is correct.

MR. SHEPHERD:  And is that -- that includes contingency of [redacted] billion; is that right?

MR. REINER:  That's correct.

MR. SHEPHERD:  And it includes management reserve of

[redacted] billion?

MR. REINER:  The management reserve would be the difference between the 10 billion and the revised point estimate.

MR. SHEPHERD:  Okay.  So it's [redacted] now.

MR. REINER:  It would be reduced, yes.

MR. SHEPHERD:  Okay.  And now, Mr. Gould, I guess you are the expert in estimates.  The -- or maybe I will ask Mr. Reiner first or Mr. Rose.  Is this a class 4 estimate?

MR. REINER:  This is a class 4, and in some cases a class 3 for some of the projects.

MR. SHEPHERD:  So then what are your upper and lower bounds on that number?  Do you have them?

MR. ROSE:  Sorry, the upper and lower bounds on the estimate, when we put together the estimate we -- in calculating the contingency we would look at the classification of each of the direct costs, so the -- of the

direct work, approximately $[redacted] billion of direct work,

we would look at the R&FR and understand its classification of estimate class 4, and we would apply the AACE bounds which are in the Modus report.

MR. SHEPHERD:  But they are a range, so that's why I am asking.  Where on the range is your confidence band?  Because you a range from, what, 20 to 50 -- no, 20 to 30 down and 50 to 100 up, something like that?

MR. ROSE:  So my understanding is how this is run is that for a specific – it's an aggregate, the contingency is an aggregate of all of the elements that make up this -- what we do we take an element, we add the range to it, so minus 50, plus 100 on a class 5 element.  Our contingency based on a Monte Carlo assessment that we do, and it's reported on a P 90 basis.

MR. SHEPHERD:  So I obviously misunderstood something. I thought the contingency was an amount that you expected to spend.  This is what Mr. Gould said yesterday, I think, that when you put a contingency into a number, that's an amount you expect to spend; you don't know what you are going to spend it on, but you expect to spend it, right?

MR. ROSE:  That is what contingency is.  That's correct.

MR. SHEPHERD:  So contingency is not the same as confidence band, is it?

MR. ROSE:  No.  Contingency, included in our contingency is a level of uncertainty.  I said -- I don't know it was this morning or yesterday -- that about [redacted] dollars' worth of our contingency is based on estimating uncertainty.

MR. SHEPHERD:  So that's only a [redacted] confidence band.  That would be a class 1 estimate?

MR. REINER:  You're -- I think you are double-counting things here.  You are applying [redacted] to 10 billion and that 10 billion includes the contingency.  So I think what you need to do is go to that business case breakdown and look at the direct project work, because those uncertainty bands apply to the direct project work.  And you will see that that 10 billion includes a number of costs and -- fixed costs.

For example, there are costs in there for CNSC fees, there are costs in there for what we essentially call tipping fees, fees that we have to pay for storing nuclear waste, there are insurance fees in there.

Those are fixed costs; they don't have those kinds of uncertainty bands associated with them.  When you break the estimate down, really what you are looking at is the direct project costs, and applying what Mr. Rose identified as the uncertainty bands around those direct project costs, and in that calculation coming up with a contingency number.

So it's not as simple as take 10 billion number and apply a 10 percent band.

MR. SHEPHERD:  No, I understand.  That is why I am asking the questions.  It's a technical conference.

I went to the business case summary, trying to get a list that said:  Here is a number.  Here is the low, here is the high for that number.  I couldn't find that.  Is that in there somewhere?

MR. ROSE:  No.  What we have presented is an aggregate of our contingency calculation of all of the scope elements.  We went through the Monte Carlo of that scope elements to understand the contingency impact.

MR. SHEPHERD:  Sorry, again I'm confused.  You keep talking about contingency, but I thought contingency was a budget item.  It's not an uncertainty item.  It is a budget item, right?  They are different?

MR. ROSE:  Contingency is the calculation of uncertainty within a project.  Some of it is estimating uncertainty, some of it is discrete risks.  It's uncertainties within a project, what we call, in the industry would call known unknowns.

We know that the cost may be a little bit higher than what I have projected it to be, but I don't know exactly what the amount is going to be.  It's in a range.

MR. SHEPHERD:  Mr. Gould, you talked about in your reports about monetizing uncertainty, contingencies, right?

MR. GOULD:  Monetizing risk, yes.

MR. SHEPHERD:  So I thought you said a number of times monetizing contingencies.

MR. GOULD:  Okay.

MR. SHEPHERD:  Didn't you say that?

MR. GOULD:  Yes.  I mean, I believe the contingencies should be monetized.  Is there a question?

MR. SHEPHERD:  And -- see, I guess I understood you to be saying identify what the risks are with more rigour than you are doing, and put numbers attached to those and include those in your budget.  That's the only way you have a really solid budget; is that -- am I understanding that right?

MR. GOULD:  So let's unpack that a little bit.

So at different levels you would have different approaches to how you would assess both your uncertainty band and your contingency.  So when you are at a class 5, with very little definition -- if you look on page 5 of our most recent report, June 26 report, it has the -- it has the table from the AACE.  So when you are at that stage, you could be -- it's certainly acceptable to be looking at risk from a very -- what's called a very stochastic formula, where you are looking at it in terms of high ranges, because you don't have a lot of project definition yet to pin any specific events.

As the estimate will mature for the project, and as the nature, the underlying nature of the estimate matures, then you can have a better and more specific idea of the specific risks that you may face, the known unknowns that Mr. Rose referred to.

MR. SHEPHERD:  Is there something different, technically is there something different between a contingency that you put in a budget and a confidence band that you put around your estimate?

MR. GOULD:  Well, the contingency should reflect the confidence band.

MR. SHEPHERD:  So they are the same thing, in effect?

MR. GOULD:  They should work hand in hand.  There are times when you make decisions -- there are times when a company will make a decision about the size of contingency, to make it either larger or smaller, depending on the nature of the project, that you may not incorporate the entirety of all of your potential uncertainties.  That's a decision that can be made.  And it's just one that needs to be vetted in the case of any particular estimate, to see if it's appropriate.

MR. SHEPHERD:  So when we look at these confidence bands, then, the what is it, AC triple-E?

MR. ROSE:  AACE.

MR. SHEPHERD:  AACE confidence bands, those are really the contingencies that you would have in a budget, and so you would expect to always come in at the top of that range?

MR. GOULD:  No, I would not say that.  I would say there is a reason why -- and if you look at the underlying materials behind this chart and the various studies that have been performed, there is a reason why these things are represented in ranges, so that it gives the owner or the project owner who has -- who is applying these standards or anybody who is applying these standards some room within a bandwidth to apportion the expected accuracy range of the estimate.

MR. SHEPHERD:  Here is how -- you can see I am confused, right?  Here is how I understood this, from past history with seeing construction contracts.

In a construction contract you identify the costs that you know you are going to have, and then you put in a contingency that's based on your experience of the types of things that are going to come up in that type of contract.

And that -- you expect to actually spend that money.  If you spend the whole contingency, you are on budget?

MR. GOULD:  Mm-hmm.

MR. SHEPHERD:  And then in addition to that, you then have a confidence band around your result, that you say:  That's my number, my number is $800 million, but it could be as low as 700 and as high as a billion?  That is different from the contingency, right?

Have I described it correctly?

MR. GOULD:  So I think that what you have just described is a much more mature estimate than the one we are currently talking about, so that -- I think that is where I know I am struggling.  I think that may be where you are struggling.

MR. SHEPHERD:  Okay.

MR. GOULD:  I think that ultimately where OPG is planning to achieve that level of accuracy, that is at the class 2 -- or at the RQE milestone in October of 2015.

MR. SHEPHERD:  So when -- like, the business-case

summary, for example, refers to the point estimate, the [redacted]

or whatever it is, as a high-confidence estimate.  That's high confidence for a class 4, right?  It's not high confidence as a layperson would see it.  You don't actually have high confidence, because you haven't yet done all your design; right?

MR. GOULD:  It's within the understanding of the industry, yes, that this classification system is something that is utilized for a reason so that there is a commonality of understanding, so when you say "class 4" you can go to this guideline and you can say, well, so a class 4 would represent something that has a maturity level of 1 per cent to 15 per cent, it's at the study or feasibility stage, the methodology employed would be equipment factored or parametric modelling for purposes of the estimate, and it would have an expected accuracy range with typical variation and low and high ranges of on the low side minus 15 to minus 30 per cent and on the high side plus 20 to plus 50 per cent.

So you can tether that to a common understanding.  It's not something that -- as we saw in -- with the SNC-Aecon contract, you have to look at the specifics of the estimate in order to understand how it gets applied.  Does that help?

MR. SHEPHERD:  Okay.  No, I understand.  I didn't realize that before.  I thought you could just take a number and say, okay, add 50 or deduct 15.

MR. GOULD:  No, it's not formulaic -- it's not a form -- it's a guideline.  It's not a formulaic -- it's not an arithmetic calculation.  It's something that requires understanding, vetting, and some decision-making for determination.

MR. SHEPHERD:  Okay.  And so in your -- in your, Mr.

Rose, $[redacted] billion current point estimate, there is built

in this AACE on certainty, but it's done on a line-by-line basis; right?

MR. ROSE:  On a line-by-line basis we take -- we put a range on a line item and we run a Monte Carlo to get to a P90 confidence and what that estimate item would be --

MR. SHEPHERD:  Okay.

MR. ROSE:  -- aggregated together into the contingency amount.

MR. SHEPHERD:  So do we have the list anywhere of the lower and upper bands of each of your numbers?

MR. ROSE:  Each of the -- well, it's based on the scope elements, the detailed scope elements, for every element of scope, so the 300-plus DSRs that we currently have in scope.

MR. SHEPHERD:  Each has a range.

MR. ROSE:  Correct, based on its classification of estimate of classification based on its progress of definition.

MR. SHEPHERD:  But when you talk to your board of directors you don't -- or your nuclear oversight committee, you don't say, Well, here is the list of 300, right?  You aggregate it into groups and say, Here is a group.  These are all class 4.  This is the low, this is the high, right?	MR. ROSE:  And I think that we would generally classify there is some class 5, there's some class 3, but generally we are in the class 4 range right now.  That is how we would characterize this.

MR. SHEPHERD:  But you can't take the full number and simply apply class 4 uncertainty bands to it.

MR. ROSE:  No.

MR. SHEPHERD:  You have to do each individual number.

MR. ROSE:  The way we have done it bottoms up based on the details that we have in our planning, we have done a -- done that exercise bottoms up and present it.

MR. SHEPHERD:  But that's not in the evidence anywhere.

MR. ROSE:  I am not certain if it's in the evidence or not.  I would have to review the BCS.  But generally speaking, the overall view of our current estimate is somewhere in that class 4 range.

MR. SHEPHERD:  Well, but I am not actually trying to catch you out here.  I am trying to actually understand it. The fact that it's all in the class 4 range doesn't help me figure out what the range is around the number or around the point estimate, right, because you have to calculate it on a line-by-line basis; true?

MR. ROSE:  That is how we have done it, yes.

MR. SHEPHERD:  Well, and that's the right way to do it, right, Mr. Gould?

MR. GOULD:  I would agree.

MR. SHEPHERD:  Okay.  So how can we then look at what the range is around the [redacted]?  How can we get that calculation?  There must be a calculation somewhere; right?

MR. REINER:  I mean, I want to take you back to page 34 in that business case, because that shows you the breakdown of the direct project work, and you will see that that totals $[redacted] billion, and --

MR. SHEPHERD:  Just let me get to page 34, okay?  Here we go.  Okay.  Mine is all blacked out, but I understand.  Okay.

MR. REINER:  Okay.  So that's the direct project work, so what Mr. Rose described inside each of those categories, R&FR, balance of plant, there are these Darlington scope request items.  The analysis is done.  The uncertainty bands are run based on class of estimate, and that output is collected in the line that you see that's identified as

contingency and management reserve, $[redacted] billion.  That's

where the output of that number is.  So that's where that range --

MR. SHEPHERD:  So then the total direct plus indirect work is your real point estimate.

MR. REINER:  I call the real point estimates the total, because until we get to release quality estimate and we have done sufficient analysis to understand precisely what do we need to retain in contingencies to deal with discrete risks and then what do we need to have in management reserve to deal with the unknown/unknowns, this is a methodology that will get refined as we work towards RQE, but you should -- yes, I think it is fair to look at that [redacted], as that is our estimate of the executable work, and that is part and parcel of our point estimate.

MR. SHEPHERD:  Okay.  I am going have to think about that.  I thought I understood it, and clearly I don't understand it as well as I thought I did.

All right.  Let me move to another area.  Let me start with -- and this is for you Mr. Gould, I think -- your fourth-quarter 2013 report, which is the one from November 12th, and I am looking attachment C.

MR. GOULD:  Yes, sir.

MR. SHEPHERD:  And maybe you can just describe what this document is briefly?

MR. GOULD:  So as I described in previous testimony, one of our key -- one key component of our role in providing oversight to the nuclear oversight committee is to review and characterize the ongoing effort to develop and mature the estimate.

So what this section of the report deals with with attachment C, these are some in-depth observations related to the work that we did to -- in the vetting of the business plan from 2014, also known as 4C or 4Charlie.

MR. SHEPHERD:  Yes.  So you actually looked at components of that totalling 64 per cent, right, of the estimate?

MR. GOULD:  Yes.

MR. SHEPHERD:  Right?

MR. GOULD:  Yes, that's what's indicated in attachment 1.

MR. SHEPHERD:  And that 64 per cent, that's not the same as the 67-million that you see in the second bullet, six DSRs in the BOP scope?  That 64 per cent is of the whole project.  The 67-million is of one component of the project.

MR. GOULD:  That's correct.

MR. SHEPHERD:  Okay.  And I just have a couple of questions on this.  You have -- in A1 you see -- you talked about a refresh of the basis of estimates.

MR. GOULD:  Yes, sir.

MR. SHEPHERD:  Give us some context on that.  What does that mean?

MR. GOULD:  So Mr. Rose described the bottoms-up effort that the project team utilized to develop the initial business plan for the project, and what we were looking at for the 4C, 4Charlie estimate was in essence a comparison or a variance from the previous year.  So anything that had changed, any new information that revised any of the estimates, those were used to in essence refresh the numbers from the prior year's business plan.

MR. SHEPHERD:  Okay.  Sorry, let me just be clear on this.  Are you talking about how you did your review or how 4C was actually created relative to 4B?

MR. GOULD:  That's how 4C was actually created.

MR. SHEPHERD:  Okay.  So this was not a new bottoms-up budget, it was an adjustment to an existing budget based on delta.

MR. GOULD:  That's correct.

MR. SHEPHERD:  Okay.  And that's quite a different way of budgeting; right?  It's --

MR. GOULD:  Well, it's not a budget, it's an estimate.

MR. SHEPHERD:  I'm sorry; estimating, yeah, that's right.  The -- you can do an estimate that you do from scratch in which you question everything or you can do an estimate saying let's assume for now that the last estimate was right and look at what new information we have.  And that is what this one is?

MR. GOULD:  Yes.

MR. SHEPHERD:  Okay.  I understand.

MR. GOULD:  I think that's a fair characterization.

MR. SHEPHERD:  On the next page, on page 2 of 5 of this material, you talk about how labour hours are adjusted, and tell me whether this is right.

You take gross labour hours, how long you think people will actually have to work and get paid, and you say:  Well, how much -– A, how much productivity will we get out of them while they are working?  And B, how much known wasted time are we going to have for height?  Because they have to walk up and down scaffolding, right?

Those are the two adjustments?

MR. GOULD:  I wouldn't call it -- well, those are two of the adjustments that you would look for in analyzing productivity.  There are a number of different types of adjustments, depending on the type of the project.

But what we are talking about here is -- what we are talking about here is specific to how this estimate, the underpinnings of this particular estimate, those were two of the labour hours that were –- are two of the factors that were associated with adjusting the labour hours for purposes of this estimate.

MR. SHEPHERD:  Well, okay.  So, sorry, I am just -- let me just be clear on this.

The way I read this, there is a productivity factor.  So you take the labour hours, you adjust them for a productivity factor?

MR. GOULD:  Mm-hmm.

MR. SHEPHERD:  And that does not include the height factor?

MR. GOULD:  No, in this case.

MR. SHEPHERD:  Height factor, then, is an additional adjustment?

MR. GOULD:  Yes, sir.

MR. SHEPHERD:  Those are the only two adjustments to the labour hours in this estimate?

MR. GOULD:  In this particular estimate.

MR. SHEPHERD:  There are others you can do, right?

MR. GOULD:  Absolutely.

MR. SHEPHERD:  Did you look at the range of [redacted]

percent productivity?

MR. GOULD:  Our team did, sure.

MR. SHEPHERD:  And what did you conclude about that?

MR. GOULD:  We were just reporting it here, that getting to -- in trying to understand the nature of the estimate, we weren't -- we didn't draw any specific conclusion about those numbers at that time.

MR. SHEPHERD:  You weren't assessing whether that was a good productivity or a bad productivity, or benchmarking or anything like that?  This is how you got the number?

MR. GOULD:  Yes.  It would be premature for us to get too deep into those factors, based on where this estimate was a year ago.

MR. SHEPHERD:  And, Mr. Rose, this is your estimate, right?

MR. ROSE:  This is our, OPG's, estimate.  That's correct.

MR. SHEPHERD:  Were you the one who actually did it, or is this somebody else?

MR. ROSE:  No, I wouldn't -– no.  Somebody in my organization would have done the estimate.  In fact, we have our estimating done by an external company that we have hired to do estimating for us.

We were a construction business.  We got out of the construction business.  We let all of our estimators go.  So we didn't have that expertise, so we hired it.

MR. SHEPHERD:  And now you are not getting back into the construction business.  In fact, you are going to be a general contractor, but --

MR. ROSE:  That's correct.  So we do not have the estimating expertise; we have hired the estimating expertise.  I have folks that supervise and understand and do QA reviews of the estimates that are put together by a third party.

MR. SHEPHERD:  Interesting.

MR. ROSE:  And that third party is co-located with us.  They interface with our project team, our project managers on a continuous basis.

MR. SHEPHERD:  Are they former Ontario Hydro employees?

MR. ROSE:  The estimators themselves are not.  We have a couple of folks that we recently brought in, actually, to help with the interface between the estimating group and the OPG, but they are not the estimators.  The estimators are from the industry.

MR. SHEPHERD:  Okay.  So have you benchmarked this [redacted] percent number?

MR. ROSE:  I haven't personally.

MR. SHEPHERD:  No, has your organization?

MR. ROSE:  I think it says here that we have compiled it over the past three years.  I am not certain that it has been benchmarked.  It's based on our experiences and the way the work has been performed at OPG.

MR. SHEPHERD:  So what you have done is you've gone back and looked at –- "you," I don't mean you personally.  I mean OPG has gone back and looked at past projects, and said:  From an empirical point of view, what has our actual productivity been on those projects, because we know we can deliver that, right?  That is what we have done; is that fair?

MR. ROSE:  That is what it says here:  "Have been compiled over the past three years while estimating projects..."

MR. SHEPHERD:  Well, it's your group that does it, right?  So...

MR. ROSE:  That is correct.  I don't know that it's been benchmarked.

MR. SHEPHERD:  Okay.  You don't think it has or you don't know?

MR. ROSE:  I don't know that it has been benchmarked.

MR. SHEPHERD:  Can you undertake to find out?

MR. ROSE:  I can undertake to find out.

MR. SHEPHERD:  What I would actually like is an undertaking to -- this is probably more to the point -- to give us some more details on this.  This is going to be a big issue, I think.  So more details on how you got to the numbers and how you've assessed how reasonable they are; can you do that?

MR. ROSE:  Yes.

MR. MILLAR:  JT4.3.

UNDERTAKING NO. JTX4.3 (IN CONFIDENCE):  TO PROVIDE MORE DETAIL ON HOW OPG ARRIVED AT THE 35 TO 45 PERCENT RANGE, AND HOW REASONABLE THE NUMBERS ARE.

MR. KEIZER:  And the numbers you're referencing is the [redacted] --

MR. SHEPHERD:  [redacted] percent.  That's right.

MR. MILLAR:  Mr. Keizer, these will be confidential responses, I take it?

MR. KEIZER:  I assume so, since they are tied to the confidential material.

MR. MILLAR:  It is our practice to mark those with an X, and I should have done this for the previous one as well.  So our previous undertaking will be JTX4.2 and the current one JTX4.3.

MR. SHEPHERD:  I guess -- and maybe you can't tell me until you do the undertaking, but my reaction to getting

[Page 116, lines 3 to 7 redacted]

MR. GOULD:  No.

MR. SHEPHERD:  Is there something unique about this, that -–

MR. REINER:  Maybe I can explain some of what weighs into this.  So I wouldn't read this as, you know, hours spent working.  This is productivity in relation to critical path of the job being executed.

In the re-tube and feeder replacement job, there is a significant amount of continuous training to be ready to execute in the field that takes place.  So the crews that do pressure tube removal, for example, they will spend a certain amount of time on the reactor face, removing pressure tubes.  They will spend as much time training and preparing and rehearsing for that.

In the nuclear environment, you then also need to factor in things like the briefings that need to take place because of the radiological environment.  So as conditions change, all of those other things that impact, potentially, the ability to be on tools doing the work, just in reflection of the earn environment.

So those sorts of things factor into these numbers.

MR. SHEPHERD:  So this is not taking long coffee breaks?  This is actually --

MR. REINER:  This is the no taking long coffee breaks.  This is training, this is pre-job briefs, this is showing up in the shift office at the beginning of the meeting and signing on to work permits and getting ready to execute work.  It's all of those factors.

MR. SHEPHERD:  And there is presumably lots of paperwork and stuff associated with this sort of job that takes away from the time people can actually be at the reactor face, right?

MR. REINER:  There is an element of paperwork.  To the extent possible for trades labour, we are automating that.

So for example, time sheets, you know, we are not requiring people to fill out time sheets.  There is going to be an automated process when people walk in and out; their entry time and exit time to the work site is going to be recorded, so that will take away from that sort of an exercise.

But there is project management that does do a lot of paperwork related to the job that --

MR. SHEPHERD:  That's not included in these productivity numbers?  Project management is separate?

MR. REINER:  Right.

MR. SHEPHERD:  Okay.  So this is the productivity you have assumed for BOP, which is balance of plan, right?

MR. GOULD:  Maybe I can answer that.  I don't know that it's limited strictly to balance of plan, sir.

MR. SHEPHERD:  It says for BOP, the productive information -–

MR. GOULD:  Oh, I am sorry, that specific note.  This entire section is about the overall basis --

MR. SHEPHERD:  No, understood, but what I am going for is --

MR. GOULD:  Oh, this productivity?

MR. SHEPHERD:  What is the productivity assumed for rest of the work?

MR. ROSE:  I don't know that.  We will take that as part of the undertaking.  My assumption would be that this productivity is -- maybe I shouldn't assume.  I'll leave it at that.  Let me take the undertaking and get back to you.

MR. SHEPHERD:  Okay.  Then the second thing is the height factors.  And again, this is empirical data, right?  You have gone out and you are looked at how much time do people spend climbing up and down, because it's actually a material amount of time that is, in a sense wasted?  It's not wasted, but you know what I mean, because they have to go up 30 feet to start work, right?

MR. GOULD:  There is also the element of -- there is also the element of hazard of working at that height as well.

MR. SHEPHERD:  No, understood.  So this is, again, empirical data that you have collected on how much time it takes; is that right?

MR. ROSE:  Again, it would be a similar -- it's empirical data on what the factors are that we would apply to our estimates.  It's not necessarily what it would actually take.  Right now it's based on our estimates, and until I go back and take the -- and understand the basis of that, I am not certain that it is informed by -- I mean, ultimately the estimate is based on our experiences of true productive work.

MR. SHEPHERD:  Yes.

MR. ROSE:  So -- but it is also going to be based on some industry metrics that we also bring into play.  We don't -- we use means data, we call it, like data sets on

-- industry data sets on factors that we may build in as well.

MR. SHEPHERD:  Okay.  So, now, this labour-hour calculation, in item 9 here, where you have the labour-hour calculation, am I right that what you do is you say, okay, it should take three hours to fix this thing, let's say, and so to [redacted]

[Lines 18 to 21 redacted]

[redacted]. Is that -- am I understanding that correctly?  Estimate, sorry.  I don't mean budget, I mean estimate.

MR. ROSE:  Yes, that is the basis for how it would be used; that is correct.

MR. SHEPHERD:  Okay.  Good.  In the -- on page 3 of this cost estimate review -- and I am assuming, Mr. Gould, that none of this stuff is benchmarked from your point of view, that you are observing things, you are not assessing -- you are not assessing the reasonableness of these things, you are just observing.

MR. GOULD:  No, we're not -- we didn't do this for that purpose.

MR. SHEPHERD:  I understand, I understand.

MR. GOULD:  Ultimately all of this will be assessed against the actual estimates that are provided by the contractors as well, so --

MR. SHEPHERD:  Oh, of course, of course.

MR. GOULD:  -- these are just the standards that were being utilized within OPG.

MR. SHEPHERD:  So on page 3 at the top of the page you have what you call an experience factor, and I am not sure whether this is a question for you, Mr. Gould, or it's a question for Mr. Rose, but if I understand this correctly, it's saying that if the work -- doing something on the first unit costs a dollar, then by the fourth unit you should be [redacted] percent more efficient; is that

fair?

MR. ROSE:  That is what it says, yes.  That is how it would be applied.

MR. SHEPHERD:  Okay.  So where does that come from?

MR. ROSE:  I don't -- again, I don't have the details of how that was put together, but, you know, it would probably be done in the same manner as the other ones are, based on experience from an estimating perspective and our own experiences.

MR. SHEPHERD:  Okay.  Well, because I would have assumed that the industry has some standards, some expectations, wouldn't it?

MR. GOULD:  This is very unique work, so you would have to apply a lot of different things into that level of experience.

MR. SHEPHERD:  Okay.  Well, so I wonder if you could undertake to give us some sort of more background, and this, I think, is a separate undertaking, more background on this experience factor and how you derived it and how it relates to -- and how you benchmarked it, if you did, and that sort of thing.  Do you understand what I am looking for?

MR. ROSE:  I am.  So experience factor, how it was derived, and how it was benchmarked.

MR. SHEPHERD:  Yes, thanks.

MR. ROSE:  Got it.

MR. MILLAR:  JTX4.4.

UNDERTAKING NO. JTX4.4:  TO PROVIDE MORE BACKGROUND ON THE EXPERIENCE FACTOR AND HOW IT WAS DERIVED AND HOW IT WAS BENCHMARKED

MR. SHEPHERD:  Where am I here?  All right.  Still on estimating, you had a problem with the project and modifications group with your estimating; right?  With their estimating, not your estimating, theirs.  And I am looking, for example, at Mr. Gould's report, second-quarter 2014.  This is the May 13th report.  And page 6, going over to page 7, you said:

"It appears these initial BSC estimates..."

That's the estimates from the business case summary.

"...were poorly characterized as part of a deliberate management strategy directed by the former VP of P&M."

And then you go on to say that it looks like they -- I am characterizing it -- like they told the contractors, Don't put in all the costs; assume everything is going to be perfect, because we don't want to have a high cost.  Is that fair?  Is that a fair characterization?

MR. GOULD:  What we saw from the evidence was that the former VP from projects and modifications believed that the costs of these projects could be constrained by sort of a top-down management style.

MR. SHEPHERD:  You can't spend more than X and find a way.

MR. GOULD:  That was what the evidence showed, and that's from talking to people within the organization.  That's essentially what they reflected.

MR. SHEPHERD:  So this -- and I have obviously misunderstood this -- this wasn't intended to be duplicitous in any way.  It was actually intended to be sort of tough management.

MR. GOULD:  I don't know what's in anybody's hearts and minds that I haven't talked to, but I would agree that that is a better characterization.

MR. SHEPHERD:  Okay.

MR. GOULD:  I don't think that they had the intent of hiding information.  I think that this was an attempt to rule with an iron fist.

MR. SHEPHERD:  Ah, so that's also a style that you can use in managing projects that works sometimes; right?

MR. GOULD:  It can, it can work.

MR. SHEPHERD:  I mean, this is part of how the company is dealing with SNC-Aecon right now, right?  Tougher, expecting more from them.  Is that fair?

MR. REINER:  Just so I understand your question, is this is how we are dealing with SNC-Aecon right now?

MR. SHEPHERD:  Sorry, what I mean is that you toughened up your approach to them.  You demanded more of them; is that fair?

MR. REINER:  We are demanding more transparency, and we are demanding visibility into their detailed planning.  This isn't, pound your fist on the table and say we want more.  That is not what we are talking about here with SNC-Lavalin.

The approach with SNC-Lavalin, SNC-Lavalin had initially -- so this is under a fixed-price contract on their tooling work.

MR. SHEPHERD:  Tooling work, yes.

MR. REINER:  So the price is locked in, milestones are established, you meet the milestone, you get paid, you don't meet the milestone, you don't get paid, very strong incentives, and the price is capped.

However, from an OPG project management perspective we want to understand what potential risks are inherent in the work.  The only way for us to determine that was to have visibility into the schedule that they were working to.  We had asked for visibility into that schedule, and they provided it.

When we had visibility into that schedule and we saw that there were challenges, we asked for, What are you doing about those challenges?  Show us what your recovery plans are, and they provided it, so it's not, demand more and let's sit back and see what happens.  It's, set clear expectations, make sure that they are understood, ensure that what they are doing meets the requirements, and then ensure that it's actually being fulfilled.

MR. SHEPHERD:  What I understood Mr. Gould's report to say, and I think you said the same thing yesterday, is that with SNC-Lavalin -- SNC-Aecon, AECL, whoever --

MR. REINER:  Just to clear the record, it's not Atomic Energy of Canada.

MR. SHEPHERD:  No, it's actually CANDU Energy, right?

MR. REINER:  And it's not CANDU Energy.  Our contract is with SNC-Lavalin.  CANDU Energy is a subsidiary company that SNC-Lavalin does own.  Any work that they do on this -- on this is done in a formal contractual way, so they are a subcontractor that has been contracted to provide some services to the project, but it is SNC-Lavalin that is running this project.  It is not AECL.  It is not CANDU Energy Inc.  CANDU Energy Inc. have some specific deliverables, and we see those, and it's the CANDU Energy Inc. management team, and they're managed by SNC-Lavalin, but that's only a very small subset of the -- of the job.

MR. SHEPHERD:  And you did that on purpose because you have used the same people before and have had some cost overruns, right, and so you wanted more control over the situation?

MR. REINER:  When we embarked on negotiating the contract, the contract -- the partners in the contract negotiations were SNC-Lavalin and Aecon.  They were the bidders, so it's not something we did -- we ran an RFP, and they were the bidders on the job.

As that bid was progressing, Atomic Energy in its former state was actually a bidder on this job as well.

As the process, the procurement process was making its way through to conclusion, the sale of CANDU Energy Inc. occurred, and SNC-Lavalin acquired CANDU Energy Inc., and as a result of that, the partnerships in the bidding process realigned.

So it's not something we had demanded.  It's the procurement process.  It's the partnerships that were formed as part of the procurement process.  SNC-Lavalin was always the prime in that particular consortium.

MR. SHEPHERD:  You had -– there's references here to the JV.  The JV is SNC and Aecon, right?

MR. REINER:  Yes.

MR. SHEPHERD:  And you hadn't actually selected SNC-Lavalin prior to their acquisition of AECL, right?

MR. REINER:  We were in the midst of the procurement process when that acquisition occurred.

MR. SHEPHERD:  So you hadn't made the selection yet?

MR. REINER:  So we had not made the selection.

MR. SHEPHERD:  Of course that strengthened their position, because now they had more expertise?

MR. REINER:  You would expect it would strengthen then their position because they've got technical expertise, absolutely.

MR. SHEPHERD:  All right.  I don't know how we got off over there, but --

MR. REINER:  I just wanted to clarify that the contract is not with AECL.

MR. SHEPHERD:  No, that was very useful, but now I have forgotten where I was.  I have actually forgotten where I was.

I will go to another subject.  I will remember eventually.  Let's talk about the class 3 estimate from SNC-Aecon.

You -- your reports, Mr. Gould, a number of times say they are way behind schedule, they are not doing enough work on this, they haven't got enough hours into it.  In fact, at one point you said they must have made a mistake because they couldn't possibly be this slowly along on it.

And you expressed a concern that because they really didn't have enough time anymore, that it was not really technically possible for them to do a good estimate by the deadline, that the estimate would not be very good; do you recall those?

MR. GOULD:  Yes.  From our earlier reports, that summarizes our concerns.

MR. SHEPHERD:  And that was right until the March report you were saying that, right?

MR. GOULD:  Yes.

MR. SHEPHERD:  Okay.  And then they did deliver on time, right?  Did they deliver, actually, the class 3 report on time?

MR. GOULD:  Yes, they did.

MR. SHEPHERD:  Okay.  And so have you looked at that yet?

MR. GOULD:  Yes.

MR. SHEPHERD:  Okay.  Did you look at it, then, before the Darlington refurbishment team, because they are still looking at it, right?  You are still looking at that estimate?

MR. REINER:  We obviously are, because this estimate is now the basis for the next -- for the next estimate for getting to a class 2, which we need to get to for RQE.

MR. SHEPHERD:  Well, my understanding was that in fact the -- you don't expect to complete your review of the class 3 estimate until August; is that right?

MR. REINER:  Yeah.  That's correct.

MR. SHEPHERD:  You say at attachment A to the May 13th report, under the "Risk of class 3 estimate," you say:

"Ultimate goal of delivery by August 2014 is acceptable."

So that's -- after you vetted it. you then go back to SNC-Aecon, say:  There's some things we don't like about it.  Right?

And then they have to deliver one that you are happy with by August?

MR. REINER:  No, we -- we have accepted the class 3 estimate that they delivered.

MR. SHEPHERD:  Well, then what does this mean?

MR. REINER:  If you give me a second to --

MR. KEIZER:  Where are you looking at, Jay?

MR. SHEPHERD:  I am looking attachment A to the May 13th report.

MR. REINER:  What that means is we had looked at -- at one point in time when the concern was raised, that there might be a problem achieving the delivery milestone for the class 3 estimate.

Mr. Gould and I actually talked about this specifically.  We had a look at our schedule, and we said:  In terms of contingency, what is the outlying date by which we could accept that class 3 and not affect the project?  That is where that August date came from.

MR. SHEPHERD:  Let me just stop you.  In terms of contingency, you don't mean dollar contingency, you mean schedule contingency?

MR. REINER:  Schedule contingency, in terms of not impacting the next phase of work, which is the development of the class 2 and starting to do the tool proving and the time trials of the tooling.  What is the latest by which we could accept the class 3?  That is what that August date refers to in that report.

And I have got to validate with Mr. Gould, but I believe that is what that date refers to.

MR. GOULD:  And that's reflected in the body of the report as well, I believe.

MR. SHEPHERD:  Here is what I am trying to understand.  By this time, this is already delivered, right?

MR. GOULD:  No.  Well, you have to reflect the timing of the generation of the reports and the meetings.  This is as -- this report was generated as of April 30th.

MR. SHEPHERD:  Okay.

MR. GOULD:  There was a tremendous amount of effort that went into the final stages of the estimate.  The actual -- the actual deadline for the acceptance was June 15th.  So...

MR. SHEPHERD:  June?

MR. GOULD:  Well, the initial submittal was May 15th, and then there were vetting activities that occurred out to June 15th.

MR. SHEPHERD:  This says:

"Completing thorough OPG review by May 15th will be challenging."

MR. GOULD:  This was the progression of the documents that they were presenting.

MR. SHEPHERD:  Now I am confused.  When was SNC-Aecon supposed to deliver this?

MR. ROSE:  Let me try and elaborate on the process a little bit.

So the process for preparing the class 3 estimate is that the JV prepared -- they prepare what we call a comprehensive work package, so they actually look at all of the work that needs to be done.  They had 180-plus comprehensive work packages.

MR. SHEPHERD:  That is what is referred to as a CWP?

MR. ROSE:  CWP, that is correct, yes.

So the first part of their estimating process is to develop this comprehensive work package to understand how the work was going to be performed, then they apply an estimate to that, and it gets grouped together into what we call estimating reports.  Okay?

So those reviews are going along throughout the March, April, early May period.  OPG staff are receiving, reviewing, commenting, participating in that process.

On May 15th all of those estimate reports were bundled and provided in to us in a summary estimate report for OPG's final review.

We then had a series -- we actually seconded people to the Oakville office for about three weeks, to do a deep dive in their estimate report and to deal with issues, resolve issues, get to a point of final submission on June 13th and our acceptance.

MR. SHEPHERD:  Okay.  So they were late by a month?

MR. ROSE:  No, they were not late by a month.  They submitted it on May 15th.  We used the month to do OPG review, as per our schedule.  The final milestone date was June 15th; they submitted it on June 13th.

MR. SHEPHERD:  I see.  Okay.

So in March, Mr. Gould, you said that SNC-Aecon was -- achieving the May 15th delivery of the class 3 estimate was significantly challenged; right?

MR. GOULD:  Yes.

MR. SHEPHERD:  What happened, then, between March and May to change that?  I mean, you said here:

"SNC-Aecon's class 3 estimate recovery plan actually assumes it will prepare CWPs at a rate 50 percent faster than its best single weak performance to date."

And you are obviously saying that's not reasonable, right?

MR. GOULD:  We were questioning whether that was possible.

MR. SHEPHERD:  But they were able to do it?  What happened?

MR. GOULD:  They were able to do it.

MR. SHEPHERD:  Do you know how this happened?

MR. GOULD:  They devoted a significant number of resources to get the work done.

MR. ROSE:  I would also say they started late; they had a learning curve; they got over that learning curve; they got the people in place; they got the production rate up.

They created a bow wave for OPG folks in reviewing and understanding and ensuring the quality of that, but we committed to make sure it was done.

I know Eric and I had conversations about -- you know, about whether or not we should give them more time to do it.  And our choice was no.  We wanted to -- we didn't want to give up on that date in the March and the May time frame.  We wanted to make sure that we performed effective oversight and helped them achieve that milestone.

MR. SHEPHERD:  So you expressed, Mr. Gould, a concern that the speed at which they would have to do this would -- and I'm quoting again -- "degrade the quality of the class 3 estimate".  In your view that didn't end up happening.

MR. GOULD:  At the end of the day, no, it did not.

MR. SHEPHERD:  Okay.  And you are satisfied now with the estimate that you have.

MR. ROSE:  We have accepted the estimate and approved it, so they are now off to preparing and planning and getting going on class 2 estimate.

MR. SHEPHERD:  And you said at one point, Mr. Gould -- and I don't have this here, but I know you said it -- that rather than wait for the class 2 estimate SNC-Aecon should be required or asked to do the -- to monetize the contingency in the class 3 estimate.  Do you recall that?

MR. GOULD:  I recall that we made a recommendation along those lines.

MR. SHEPHERD:  Is that what happened?

MR. GOULD:  So under the contract they are not required to do that.

MR. SHEPHERD:  I understand.

MR. GOULD:  But there is an -- my understanding is that there is an agreement with the parties that they will help OPG with a view of what that contingency looks like so that the next business plan can be appropriately monetized for contingency.

MR. SHEPHERD:  So where are you on that, Mr. Rose?

MR. ROSE:  So I spoke of this earlier this morning that there was -- throughout the early parts of this year there was a scrubbing of the risk register, getting -- you know, eliminating the business-as-usual risks, getting down to a -- the true set of true risks that would impact contingency.

Now that the class 3 is done, we are working with JV over the summer months to truly understand what their contingency is, and that will be input into our 4 delta release in November.

MR. SHEPHERD:  All right.  I want to go back to the May 13th report for a second and ask you a couple of things about the Black and Mac (sic) estimates, if you could.  And I am looking at -- right now at page 9.

MR. GOULD:  Yes, sir.

MR. SHEPHERD:  And I take it that this stuff that's blacked out, the confidential stuff, rather than going through it in detail, I take it that you are saying -- you are being [redacted]

[line 24 redacted]

MR. GOULD:  I would say that's a fair characterization.

MR. SHEPHERD:  And on page 10 -- and this is what I am getting to here -- near the bottom of that box you say:

[Lines 1 to 7 redacted]

And you go on to say all their estimates now are doubtful.  Do you still believe that?  Or has that been --

MR. GOULD:  Yes, and that is why they are being looked at very closely right now by OPG, and with us providing oversight.

MR. SHEPHERD:  And the key one here is that [redacted] million for the D2O; right	[redacted]

[redacted].

MR. GOULD:  Yes.

MR. ROSE:  That is correct.  That is the key estimate, yes.

MR. SHEPHERD:  And you are looking at that in detail right now.

MR. ROSE:  We have people right now working day in, day out with Black and Mac, with Modus folks, to ensure that we get the best estimate possible to be able to provide a good update to our board in August.

MR. SHEPHERD:  All right.  So I am looking at -- now at the supplementary report, the June 26th report.  And you have -- on page 16 you have the 200 -- it's actually [redacted] forecast; right?  But --

MR. GOULD:  Hang on.  Just one moment, please.

Yes, on the wrong tab.  Yes, sir.

MR. SHEPHERD:  And then I am looking at the same time at attachment C to the -- attachment C?  No.  Hang on.  Just give me a second.

Sorry, I am looking at -- yeah, at attachment C to the May 13th report, and if you look at page 2, you have -- what does EAC mean?

MR. GOULD:  Estimate at completion.

MR. SHEPHERD:  Okay.  So this is not actually at completion.  This is what you now think will be your final cost once you are finished.

MR. GOULD:  It's a projection of your final cost.

MR. SHEPHERD:  Okay.  Good.  So you have -- in this

top table you have an estimate for the D2O of [redacted] million.

How does that relate to the [redacted] million?

MR. GOULD:  So [redacted] million that we looked at on May

13th was the estimate that was presented as of that time, and recall my testimony a moment ago that you just asked me about, about the quality of the estimate?

MR. SHEPHERD:  Yes.

MR. GOULD:  We had some serious questions about the quality of the estimate, and between the April 30th time frame when this report was submitted and generated until June 26th there were a number of different -- a number of different vetting exercises as of that time to continue to look at the numbers.

MR. SHEPHERD:  What are the SIO projects?

MR. REINER:  SIOs are safety improvement opportunities.  There is a list of five projects.  They are tied to environmental assessment requirements.  They are also prerequisite projects that need to be completed prior to breaker open.

MR. SHEPHERD:  Are they in this list of [redacted] million

for D2O?

MR. REINER:  No.

MR. GOULD:  When you say "this list" what are you talking about?

MR. SHEPHERD:  The one on page 2 of attachment C to the May 13th report.

MR. GOULD:  No, this is just for D2O storage, sir.

MR. REINER:  That is just a single project, D2O storage.  The SIO projects are a separate set of projects.

MR. SHEPHERD:  They are separate.  Okay.

So do I understand correctly then that the [redacted] is what

Black and Mac came to you with; is that right?

MR. GOULD:  Came to OPG with.

MR. SHEPHERD:  Yes.  No, I --

MR. GOULD:  As of that time.

MR. SHEPHERD:  -- was speaking to you collectively.

And you have been working on that vetting it, and you are now at [redacted]  as of the 26th.

MR. ROSE:  The estimate that I have in -- that, you know, I keep saying it's OPG's estimate that we have, is [redacted].  That was --

MR. SHEPHERD:  [redacted].

MR. ROSE:  That was the estimate that we have in our D2-2-2 evidence and supporting document.

MR. SHEPHERD:  That was going to be my next reconciliation, so thank you.

MR. ROSE:  So we have -- you know, we have talked about a range.  We've got a number that we put out there, but we've also talked about a 2- to $300 million range because we are still working through the details of the D2O.

I am optimistic that the number that we will finally land on will be less than $[redacted] million.

MR. SHEPHERD:  Okay.  So --

MR. ROSE:  But it will be a right number.

MR. SHEPHERD:  So Black and Mac hasn't accepted your [redacted] yet.

MR. ROSE:  There are no changes approved on the estimate as of today.

MR. SHEPHERD:  All right.  So the official estimate then is still [redacted].

MR. ROSE:  The official estimate is still, my opinion, $110 million project.

MR. SHEPHERD:  Oh, good.  All right.

MR. ROSE:  We have not approved, to my knowledge, any change orders to change that estimate at this point.

MR. SHEPHERD:  Understood, but Black and Mac isn't going to do the work if you say, By the way, we are only going to pay you $110 million.

MR. ROSE:  Correct.

MR. SHEPHERD:  Okay.

MR. ROSE:  We also understand that.

MR. SHEPHERD:  So they think that they are going to

get [redacted] million, or that's going to be the total cost, of

which they are going to get some of it, right?

MR. ROSE:  I guess, quite frankly, I don't care what they think today.  We will ultimately agree on what the number is as an outcome of this exercise.

MR. GOULD:  Okay.  And let me just clarify something.

What you keep coming back to is the [redacted] million.  That was

the estimate that existed as of this date.  So like Mr. Rose said, there are literally meetings happening right now to further examine this number.  This is not a fixed-price proposal --

MR. SHEPHERD:  Oh, no, I understand, it is a cost plus contract, right?

MR. GOULD:  It was -- it was -- it was a -- it was their -- their best estimate at the time, and that is being vetted very thoroughly.

MR. SHEPHERD:  But what I was asking was -- and I understand what you are saying.  What I was asking was, Black and Mac hasn't yet said, No, a different number is fine with us, right?  They are still at [redacted], until you finish these discussions?

MR. ROSE:  I don't know what number Black & McDonald is at, but whatever number it is, it will be agreed to by both parties before it gets...

MR. SHEPHERD:  Now, just looking at this table on page 2, some of the things leapt out at me.  What is B&M -- B&M is Black and Mac, right?

MR. GOULD:  That's correct.

MR. SHEPHERD:  [lines 4 to 9 redacted]

MR. GOULD:  I think that while, again, this -- this estimate is a point in time from April 22nd, so let's not attribute too much significant to the actual number.

But in terms of looking at what an underlies that range of numbers, I think this goes to what Mr. Reiner was saying about this estimate all along, that what was in the original BCS was not for the scope that is being built.

MR. SHEPHERD:  All right.  The -- one thing here is OPG costs.  Just what's included in OPG's costs there?

I think this is for you, Mr. Rose.

MR. ROSE:  Generally would be OPG's oversight, project management, engineering oversight, any operations support, commissioning support.

MR. SHEPHERD:  These are allocations from your group, right?  Basically?  Or mostly?

MR. ROSE:  The OPG costs are our assessment of what it's going to cost to perform our role in having this project executed.

MR. SHEPHERD:  What I am saying is you don't have a separate group of people that you have hired for this $27 million; right?  It's part of your overall group?

MR. ROSE:  So some of the folks that -- this is the projects and modifications organization that is overseeing this project, so it is their cost to be on this project.  It is not, you know, the DRP cost.

But it is also costs from people from the station and/or engineering organizations that are brought in to do the owner's role.

MR. SHEPHERD:  So if this one is low by -- it was only -- the estimate was only a third of what you now expect it to be -- because this is your number, right?  The 27,846 is your number; it's not Black and Mac, is it?

MR. ROSE:  Eric, I am not certain the basis of the $27 million.  You'll have to respond to that.

MR. GOULD:  As of that time, that was the best estimate from the projects and modifications organization for the support of the scope of work that was being developed.

MR. SHEPHERD:  So, Mr. Reiner, then, they now report to you, right?  So you are presumably working with them to --

MR. REINER:  That's right.  That is not a contractor number; that is going to be an OPG number.

MR. SHEPHERD:  It's not necessarily the final number?  You are still working on it?

MR. REINER:  It's not necessarily the final number.

MR. SHEPHERD:  Okay.  Let me move to a different area, and that is -- and the best place -- oh, by the way, let me just clear something up first.

The May 13th report is your second quarter 2014 report, right?

MR. GOULD:  Yes.

MR. SHEPHERD:  If you go to attachment A -- which is your risk thing, right?  The histograms, right.  It's labelled "1Q 2014"; is that just a typo?

MR. GOULD:  That's a typo.

MR. SHEPHERD:  Okay.  I didn't want to go relying on it and then find out later:  Oh, no, it's the wrong one.

MR. GOULD:  It's a typo.

MR. SHEPHERD:  I want to ask some questions, just a couple of questions about how you re -- how you re-look at some of the costs and how you treat them.

I want to start with -- if you go to the fourth quarter 2013 report, we talked about this a little yesterday but we didn't have the numbers so we couldn't get into it.

You see page 6 of this report?  This is -- now, this is you, Mr. Gould, looking at the 4C cost estimate, but you see here that one of the opportunities for cost reduction that you are talking about is reallocating costs outside of the project; do you see that?  $871 million?

MR. GOULD:  Sorry, I'm on the wrong report.  You are on the June...

MR. SHEPHERD:  No, I am on the November, November 12th, page 6.

MR. GOULD:  I am sorry, I am sorry.

MR. SHEPHERD:  You see where that blacked out part is there?  That's 871 million?

MR. GOULD:  Yes, sir.

MR. SHEPHERD:  So what you are saying is even if you have to spend some of this, maybe it doesn't belong to the project; is that fair?

MR. GOULD:  That is what we are getting at here, yes.

MR. SHEPHERD:  Have you taken any action on this yet, Mr. Reiner, Mr. Rose?

MR. REINER:  We are looking at this.  I mean, we understand what those costs are.  I think I described that yesterday.  There is a portion of that cost that's associated with maintaining the equipment in the units that's currently being refurbished, and we are having a look to see what's the most appropriate way to capture and carry those costs.

MR. SHEPHERD:  And do you have any –- well, let me put it this way.  Right now all those costs are included in the Darlington refurbishment project, and none of those, that 871 million, are included in the revenue requirement for the test period; is that right?

MR. REINER:  I think this falls outside of the revenue requirement for the test period.  These are costs that are incurred during the period that the units are on outage, so starting in 2016 and ending in about 2024.

MR. SHEPHERD:  All right.  So what I am going to ask you to do, because -- and I accept your answer, I'm just -- it's $871 million.  I want to make sure I get it right.  I am going to ask you to undertake to confirm that none of that $871 million is currently included in the revenue requirement proposed for the test period.

MR. KEIZER:  That's fine.

MR. SHEPHERD:  Thanks.

MR. MILLAR:  JTX4.5.

UNDERTAKING NO. JTX4.5:  TO CONFIRM THAT NONE OF THAT $871 MILLION IS CURRENTLY INCLUDED IN THE REVENUE REQUIREMENT PROPOSED FOR THE TEST PERIOD.

MR. SHEPHERD:  Now, you don't yet have a report or an analysis or anything that says how much you're actually going to put where and when, right?  You are still working on it?

MR. REINER:  In relation to this cost, that's correct.  We don't yet have that.

MR. SHEPHERD:  Do you know when you are going to have that?

MR. REINER:  It would be a little early for me to say.  I think what we will do -- I mean, this is going to require sort of an internal approval.

Our plan would be to highlight this in the 4Delta estimate, so when the 4Delta estimate goes forward this November, that is where we would provide the breakout of that cost and then make a recommendation to our board on how that cost should get accounted for.

MR. SHEPHERD:  All right.  And the effect of that is if you reallocate some of it, is to make it easier to stay within your $10 billion, right?

MR. REINER:  No.

MR. SHEPHERD:  I am not suggesting something bad.

MR. REINER:  No, if this is gets reallocated, we would adjust our project estimate accordingly.

MR. SHEPHERD:  Okay.  If you could take a look at the first quarter 2014 report, which is -- no, sorry, the -- yeah, the first quarter, which is the March 4th report, at page 5.

It says -- this is -- Mr. Gould, tell me whether this is right.  This is your analysis of how the Darlington refurbishment team is complying with the Minister's requirements in the Long-Term Energy Plan, right?

MR. GOULD:  That's my earlier testimony, yes.

MR. SHEPHERD:  Okay.  So on page 5, you have -- in this section "Current initiatives," it says:

"OPG has fully examined the scope of the Unit 2 refurbishment project and redistributed or cancelled work based on OPG's regulatory commitments."

Tell us what that is, Mr. Rose, I guess, probably, or is it Mr. Reiner?  I don't know.

MR. ROSE:  I would actually like Eric to comment on it first, if you could.

MR. GOULD:  I want to make sure I am on the right page.

MR. SHEPHERD:  Page 5 under item 3:

"Entrench appropriate and realistic off-ramps in scoping."

So you have re-scoped the Unit 2 refurbishment, or OPG has.  And I understand some of the work has been cancelled, but some of it has been redistributed.  That is what I am interested in.

MR. GOULD:  Okay.  So what we say here is this is a comment that reflects the blue-ribbon panel process that we discussed quite a bit yesterday.

MR. SHEPHERD:  Sure.

MR. GOULD:  So there was some scope that was completely eliminated as being unnecessary.  There was some scope that was put back into life-cycle maintenance.  I think Mr. Reiner described that at length yesterday.

MR. SHEPHERD:  Okay.  And that was the 125 million or something?

MR. ROSE:  179-, $180 million range.  I would like to also add to that.  I mean, the blue ribbon was a specific review of scope through -- Mr. Reiner spoke about our inspection process, and there is certain things that were identified as scope, regulatory scope, depending on results of inspection that we would or would not have to do, so through those, the results of those inspection, we would -- we may have inspected something that was in good condition and did not need to be replaced, and through our integrated implementation plan that was submitted to the CNSC we would have submitted it that way and excluded that from scope.

MR. SHEPHERD:  So that 179 million is stuff that was in your business-case summary and has been removed from it, and you are still going to do the work, you are just not going to do it as part of this project; is that right?

MR. ROSE:  A subset of that 179 million was cancelled.  The balance of that would have been carried into our business case for future work after refurbishment.

MR. SHEPHERD:  But it's not part of your refurb --

MR. ROSE:  Not part of refurbishment, capital direct cost.

MR. SHEPHERD:  So did you reduce your point estimate for that?

MR. ROSE:  We did.  Mr. Reiner spoke of the fact that we reduced our point estimate by $800 million, our -- sorry, our high-confidence estimate, but our point estimate would have reflected the results of all of those analysis, so the scope would have been removed for the point estimate as well.

MR. SHEPHERD:  Okay.  But I thought this work was in your business-case summary that was approved.  Your 4C include that stuff, right?

MR. ROSE:  No, the scope was actually removed from our 4C.

MR. SHEPHERD:  Oh, it was already out.  Okay.

MR. ROSE:  It was already out.

MR. SHEPHERD:  Okay.  What are the AISC programs?  It is the next item down.

MR. ROSE:  AISC stands for the asset investment screening committee.  It's the committee that projects and modifications -- the projects that are executed for the balance of the nuclear organization go through.  So we control the projects, the funding for the projects, that are funded by the Darlington refurbishment program.  The asset investment screening committee manages the funding related to the portfolio in the nuclear part of our business.

MR. SHEPHERD:  So is this sort of the same type of thing?  This is then, you had some stuff that was in the Darlington refurbishment plan as part of its scope, and you've said, no, that's not really part of that any more.  These are now -- we are going to hand these over to AISC and that's their problem now?

MR. ROSE:  So the $180 million, the plant would look at it and say, How do I execute that work?  Do I execute it as part of our maintenance program?  Do I execute it as part of our station program?  Or do I execute it as a project within the AISC -- funded by the AISC portfolio?

MR. SHEPHERD:  I see, I see.  Okay.  And then the last question on this, and then I will be happy to take a break, is, you see it says -- just -- under "potential gaps" it says:

"Ensuring the scope that is provided for refurbishment though performed outside of the DR project is staffed, funded, and executable."

So this is your words, Mr. Gould.  Can you describe what that means?

MR. GOULD:  So what we were saying here is that the scope that was moved into the AISC program that was just discussed to ensure that if in fact it is needed for the plant, that the plant have preparation -- have the capacity to perform that work whenever it's been rescheduled.

Now, we see it as a benefit to the project, because it simplifies the project to get whatever work you don't have to do during that time frame.  The real issue here is if you don't need to perform the work for another ten or 15 years, so that OPG makes sure that they have the capacity to perform that work whenever it was required.

MR. SHEPHERD:  Well, this sounds like you are saying that some of those things still have to be done in order for you to proceed with the refurbishment; is that right?

MR. GOULD:  Some of the -- maybe Mr. Reiner should answer.

MR. SHEPHERD:  Yes, yes.

MR. REINER:  They are not prerequisites to refurbishment, so we can proceed with the refurbishment, but there are some items that -- from -- that our regulator, for example the Canadian Nuclear Safety Commission, will look at as being part and parcel of the life extension of Darlington.

So when they look in at the plant, they look at it as a station that we are planning to operate for another 30 years.  They are not concerned about how we manage the work, whether it's done through ASIC or through maintenance or through a refurbishment project.  They will look at it in totality.

So we have -- all of this work has been -- it's part of the scope request process that we have in place.  It's earmarked as either going into a maintenance program or being managed through the AISC portfolio, and it does get tracked so that we are able to demonstrate that we have met the regulatory requirements.

MR. SHEPHERD:  All right, all right.  Do you want to take a break?

MR. MILLAR:  How much longer are you going to be, Mr. Shepherd?

MR. SHEPHERD:  Not more than 30 minutes.

MR. MILLAR:  Okay.  Why don't we come back at 3:20.

### --- Recess taken at 3:04 p.m.

### --- On resuming at 3:22 p.m.

MR. MILLAR:  Okay.  Why don't we resume?  We are in the home stretch now.  Mr. Shepherd, back to you.

MR. SHEPHERD:  You said that with a hopeful tone in your voice?

MR. MILLAR:  I did.

[Laughter]

MR. SHEPHERD:  You are not finding this just riveting?

MR. MILLAR:  I am finding it riveting.

MR. SHEPHERD:  You had to say that, I know.

I want to ask you a question about the RWPB building.  What is that?  Remind me, please.

MR. REINER:  That's re-tube waste processing building.  So all of the reactor components that come out of reactors get --

MR. SHEPHERD:  This is the one we talked about yesterday, where you chop it up and put it in bins and leave it out for the trash collection.

MR. REINER:  Yeah.

[Laughter]

MR. SHEPHERD:  So to speak.  All right.  My impression is -- and I am looking now at the May 13th report, and if you see on page 19 of that report, there is a discussion of the RWPB building, Mr. Gould, in which you say that it's facing some of the same issues as D2O and AHS; you see that?

MR. GOULD:  Yes, I see that.

MR. SHEPHERD:  And -- but this is being done by SNC-Aecon, right?

MR. GOULD:  That's correct.

MR. SHEPHERD:  So this is not a problem with a contractor estimating badly or not being -- I thought you were managing these projects differently, Mr. Reiner?

MR. REINER:  I think -- so in terms of the challenges that that project faces in general, facilities that are built at the site -- and I went through this yesterday -- we are encountering the same challenges everywhere.

Soil tends to be contaminated, and that needs to be dealt with.  There are buried services that need to get relocated before foundations can be put into place.  And if anything during excavation gets dug up that isn't documented in a drawing somewhere, it needs to be dispositioned in some way to understand whether or not it's energized and presents some sort of a safety hazard.

So that project will undergo many of those same challenges.  Now, we believe --

MR. SHEPHERD:  You knew about all of those already, though, right?  These are not news?

MR. REINER:  Some of this is news, yes.  We know now, based on the fact that projects like D2O storage, the R&FR island annex -- which are all recent projects -- have encountered this.  So that learning is being incorporated.

I mean, it's news in the sense that it isn't something that we would have necessarily -- the extent to which we are having to deal with these issues isn't something we would have thought we would get at this sort of level.

There is a significant amount of construction waste that's buried at the site, and we encounter it every time we dig.

MR. SHEPHERD:  But didn't you know that?  That is what I am trying to --

MR. REINER:  Knew that when?

MR. SHEPHERD:  Like, before you even started this, didn't you know that Darlington was built there and there would be construction waste all over the place?

MR. REINER:  Not -- we didn't anticipate it to the degree that we are encountering this.  Like -- and I will give you an example.  The water and sewer project which is being built essentially offsite, that encountered the same kinds of challenges with buried -- with buried materials.

MR. SHEPHERD:  Okay.  So this –- when, Mr. Gould, then, when you are saying that RWPB is facing the same issues, you are not saying it's in as bad shape as D2O?  You are saying that the same technical issues are arising?

MR. REINER:  The same technical issues and the same challenges, you know.  That project will have to address those same challenges, and that is being built into our plans.

MR. SHEPHERD:  So is it going to be also over budget by a similar amount?

MR. REINER:  No.  We -- the -- now, the RWPB, it's a very -- the building itself is a very basic building.  It doesn't -- you know, we are currently looking at, but it won't have to meet the same kind of seismic requirement, for example, that the D2O storage facility needs to meet.  It's essentially going to be concrete slab on grade and a shell around the building.

So the building itself isn't a sophisticated building; it's a simple building.  What's inside the building is the sophistication, but that's part of the -- that's part of the tool set, the re-tube and feeder replacement tool set, the inside of the building.

MR. SHEPHERD:  This is the same one that SNC-Aecon is working on, that they are behind on?

MR. REINER:  Yes.  It's -- they are not behind on this.  SNC-Aecon, they are having challenges with one tool.  This is not a tool that they are behind on.

MR. SHEPHERD:  So they are responsible for the tooling project and they are way behind on it; isn't that true?

MR. REINER:  Well, we flagged them as being behind schedule on tooling, yes, but the reason they are behind schedule on tooling is one of the tools, the re-tube platform, which ends up being a fairly sophisticated tool -- it's the one in the reactor vault that moves up and down in front of the face of the reactor, that everything sits on -- they are having challenges with that particular tool, and that's what has set them behind schedule.

And so we are monitoring their progress on that.  They have a recovery plan in place to get back to their desired control schedule, which is what we are measuring their performance to -- they are hitting their contract milestones -- but back to their control schedule, that's what we are currently monitoring.  And we see them being -- based on the progress they are making on their recovery plan, they will be back on plan by around September timeframe.

MR. SHEPHERD:  All right.  Okay.  I am just looking for a reference, because I was sure I saw commentary from Mr. Gould on the problems with tooling and that the milestone would be missed.

Didn't you say that?

MR. GOULD:  Yes.

MR. REINER:  There were interim milestones that had slipped.  I think engineering completion, design completion for tooling was one of those, but the contract milestones haven't been missed.

MR. SHEPHERD:  Oh, so that is something different?

MR. REINER:  The contract milestones typically tie to -- they are rolled up at a higher level, is payment received for work done.

When we look at this project, the change we have made to this project as a result of the challenges that they were having with this particular tool, we now look at a much more granular -- we are seeing a level 2 schedule for the tooling work, and we are seeing that level 2 for the subcontractors.  We've got complete visibility into all aspects of that, so we can see how the subcontractors are performing relative to the milestones that SNC-Lavalin has set inside their schedules for their subcontractors.

MR. SHEPHERD:  And that, you don't have any control over that, right?  It's just...

MR. ROSE:  Sorry just to clarify Mr. Reiner's comment, we are actually seeing level 3 schedules, so more detail than what he was alluding to.

MR. SHEPHERD:  Yes.  You have more visibility, but you don't actually have control over the subcontractors, right?  That's SNC-Aecon?

MR. REINER:  That's right, and we don't -- it's an EPC contract.  We don't want control over them.

MR. SHEPHERD:  But it allows you to keep on top of your schedule, your overall project schedule?

MR. REINER:  Well, and it allows us to challenge them and demonstrate to us how they are staying on top of their schedule.

MR. SHEPHERD:  Now, when you talked about project and modifications, those were fixed-price contracts and you didn't really have any right to ask for visibility at all, right?  Under the contracts?

MR. REINER:  Are you referring to the facilities projects, D2O storage and --

MR. SHEPHERD:  Yes.

MR. REINER:  No, they are not fixed-price contracts.

MR. SHEPHERD:  No, but they were contracts in which you didn't have a right to have any control over them, right?

MR. REINER:  Well, in -- we don't -- we don't have a right to take control on any of the EPC work, because as soon as we do that, the liabilities for the work --

MR. SHEPHERD:  You take the risks?

MR. REINER:  We take all the risks, right.  So I think the contractor would be happy for us to do that in some cases, but -- so we have very careful about how to provide the oversight, in an intrusive way, but not in a way where we say we would like you to drop that tool and pick up that tool and do that work.

MR. SHEPHERD:  No, no, I understand that, but what I am trying to get at here is that originally when you did those contracts with ES Fox and Black and Mac, those contracts were, You go do it.  Let us know when you are done.

MR. REINER:  That's the way that the projects and modification organization was managing them initially, sort of a hands-off approach.  That is what Modus had identified, that the oversight wasn't at the level it needed to be.

MR. SHEPHERD:  Understood.  And then you changed that, and you actually didn't have a right under the contract to change it.  You just said, We are going to change it, right?

MR. REINER:  Yes, we changed that.  I mean, we have a -- we can provide oversight.  There is nothing contractually that prevents us from doing that.  We have the right to provide oversight.  What we can't do is give work direction, because that then moves risk.

MR. SHEPHERD:  No, but you can tell them you are unhappy, and --

MR. REINER:  We can tell them we are unhappy and we would like to see a demonstration of what's being done to, for example, deal with whatever issues or complexities they may be running into.

MR. SHEPHERD:  Right.  The -- I wonder if you can take a look at the May 13th report.  And I am looking -- this is at page 18.  And this is under the heading "work status, tooling, definition, and mock-up".  Do you see that?

MR. GOULD:  Yes.

MR. SHEPHERD:  And so here is what I am concerned with. In addition to JV -- that's SNC-Aecon, right? --

[Lines 24 to 26 redacted]

So can you help us understand, like, fill us in on that?

MR. GOULD:  So this, again, is the situation where we are looking at the reports from the contractors and we are trying to identify if there are any positive or negative trends, and as of that time that was the case,

[Lines 5 to 11 redacted]

MR. SHEPHERD:  Okay.  Well, let me understand this.

[redacted]

[redacted]            So that is not your number, right?  That's --

MR. GOULD:  Actually, it is.

MR. SHEPHERD:  -- [redacted]

[redacted]

MR. GOULD:  What we showed in -- what we did in this report was to look at their report and try and characterize it, and this is our characterization of the variance that they were showing.

MR. SHEPHERD:  Okay.  So it's their forecast.

MR. GOULD:  It's their forecast.  It's our characterization of their forecast.

MR. SHEPHERD:  -- [redacted]

[redacted]

MR. GOULD:  No.

MR. ROSE:  No, we are talking about the -- if I am correct, we are talking about the work that is being done in the definition phase, that is not fixed price.  The fixed-price components are the tooling and the mock-up, which are in the neighbourhood of 420 million in total.  We are talking about the definition-phase work which I want to say is less than $100 million from memory.

MR. SHEPHERD:  This is 100 million?  All -- the engineering --

MR. ROSE:  Yes, this definition-phase work that we are referring to here is less than $100 million --

MR. SHEPHERD:  Engineering, schedule and estimate development, and construction management planning, that is less than 100.

MR. GOULD:  Yes.

MR. SHEPHERD:  So you are thinking that you are going to have an         [redacted]             associated with this.

MR. GOULD:  That is what they were projecting at the time, so we raised a red flag that their productivity was showing that this was the result of their productivity at the time.  I think that we have seen some correction to that subsequent to this report, where in some cases the way that you earn -- the way a contractor earns its payments takes time to catch up.

So a deliverable is in process.  You may be 90 percent complete with a deliverable, but you don't get paid until you're 100 percent, but you have expended a tremendous amount of effort to get there.

MR. SHEPHERD:  There is a table here somewhere -- let me just see if I can find it -- that has -- it would be easier if we actually had the table to look at, I think.  Here it is.

In the fourth-quarter 2013 report, on page 2, there is a table that is headed up "SNC-Aecon monthly progress summary" -- I can't even say it -- which have in it planned earned actual, and this is just a three-month snapshot.

So can you tell us what planned, earned, and actual are?

MR. GOULD:  So the planned, which is signified by the blue columns here, would be what's in the current schedule, the number of man hours and the dollars associated -- in this case it's -- this is in dollars, so it's the dollars associated with the work effort on a planned basis.

So these blue bars -- these vertical blue bars represent what they had planned to do that's in the schedule.  So --

MR. SHEPHERD:  So is that how much work they should have had done?

MR. GOULD:  That is how much work they planned to have done.

MR. SHEPHERD:  And that's -- is that in the contract?

MR. GOULD:  Is what in the contract?

MR. SHEPHERD:  These numbers, are these in the contract?  This is the expected rate at which you are going to be doing this stuff.

MR. REINER:  These are not laid out in the contract as you see them here.  So this is a combination of tooling, mock-up, and definition-phase work, so it's a look at the schedule and what is loaded into the schedule.  The schedule meets the contract, the contract divides that work into components, tooling is all fixed price, so there is no change in price.  Mock-up was fixed price as well.  The definition-phase work is -- the 100 million that we talked about, that's target price, so that's essentially if they exceed target they work for no profit or overheads.

MR. SHEPHERD:  Okay.  All right.  So you have the planned items, and then you have -- in red you have "earned".  What does "earned" mean, and how is earned different from actual?

MR. GOULD:  "Earned" means that's the value of the work that is in place.

MR. SHEPHERD:  For that month?

MR. GOULD:  In this case for that month, but in general "earned" means the value of whatever the deliverable is to the person paying for it.

MR. ROSE:  So we use the term you have earned your plan.  I planned to spend $100 to deliver a widget.  I delivered that widget, so I earned $100.  It may have cost 90 or 110.

MR. SHEPHERD:  So let's just take July, for example.

[lines 26 to 28 redacted]

MR. GOULD:  That was their actual payroll to achieve that level of earning.

MR. SHEPHERD:  [redacted]

[redacted]

MR. GOULD:  Yes, which you will see in the next month --

MR. SHEPHERD:  That doesn't sound like a good idea.

MR. GOULD:  But, sir, you see in the next month there will be variations from month to month.  You will see in the next month that the earned value is actually considerably higher than the actual value.

MR. SHEPHERD:  Ah.

MR. GOULD:  So sometimes these things tend to even out over time.

MR. REINER:  There isn't -- so when you look at this from a project-management perspective, you don't look for a precise alignment of all three of those each and every month.  The earning rule, that gives you sort of an indicator, you know, have they underestimated the job, have they overestimated it, have they under-resourced it.  It gives you a forward look on, you know, how much work is left, how much work got done, how much budget got consumed in getting to that point, so you need to take those indicators and then look at trends, at what happens month over month, to see if problems are arising or if challenges are arising.

MR. SHEPHERD:  I would have thought your key number then would be your cumulative number; right?

MR. ROSE:  That was kind of -- my comment is that we tend to look at cumulative.  It gets rid of the ups and downs month over month --

MR. SHEPHERD:  And that's --

MR. ROSE:  And those ups and downs are --

MR. SHEPHERD:  -- (inaudible) anyway, right?

MR. ROSE:  Yeah, those good ups and downs are good indicators, because if you are not earning one month and that's a trend, obviously your cumulative would reflect that, but when you get into the actual costs specifically, sometimes it's to do with timing of billings, right, and ability to do accruals for those billings that have yet to hit your books, so you try to norm that up.  That is why again they are indicators, but it is the cumulative SPI, which is cumulative SPICPI earned plan, which are the focus areas for us in our reporting.

MR. SHEPHERD:  So this $100 million on this definition-phase stuff -- let's just -- let's call it $100 million just for argument's sake -- if they -- their target price is 100 million, let's say.  It's a target price contract?

MR. ROSE:  Their target price for the definition plan work is actually $102 million.

MR. SHEPHERD:  Okay.  So if they go 25 percent over, what does that do to them?  How does that work?

MR. ROSE:  Without -- I don't have the specifics of it, but if they went 25 percent over they would start losing their -- parts of their fee.  Their fee is at risk.

So different from the ESMSA that we talked about yesterday, the -- JV's fee for the entire definition phase is at risk, as well as their overheads.

MR. SHEPHERD:  Okay.  So I recall this discussion.  So if -- so if their costs are -- were forecast to be 100 and they are 120, they still get the 120 for their costs but the additional amounts that they were going to get to cover their general overheads and their profits are going to be eaten up?

MR. ROSE:  It starts to get reduced.  That is correct.  For the entire amount, so they could -- you know, if they got so far over, they would lose their fee and overheads up to the caps that we would have in the contract.

MR. SHEPHERD:  But it is only for the definition phase contract?

MR. ROSE:  For that definition phase.

MR. SHEPHERD:  That's not integrated with your other contracts with them?

MR. ROSE:  For the target price for the unit execution phase, no, it is a separate piece.

MR. SHEPHERD:  Each one is an island?

MR. ROSE:  Yes.  And I believe in the R&FR there is ability -- I can't recall correctly, but I thought there was some ability, unit over unit, to apply parts of the incentive as well.

MR. SHEPHERD:  So in the actual RFR, the big contract -– that's the big contract, right?  You haven't negotiated that yet, right?

MR. REINER:  So the terms and conditions under which the execution work would be done, those have been negotiated and agreed to.

What hasn't been agreed to is the target price.

MR. SHEPHERD:  Ah.  Which is the one that matters?

MR. REINER:  Yeah.  So the incentives, the disincentives, the liabilities, the warranties, the intellectual property rights, all of those things have been negotiated and agreed to.

MR. SHEPHERD:  The schedule also has to be negotiated, presumably?

MR. REINER:  The schedule has to be negotiated, and so the process is, you know, this is where we go through the mock-up to do the testing of tools, we do time trials, and then we establish a schedule on the basis of tool performance.

MR. SHEPHERD:  And that negotiation is this fall, right?

MR. REINER:  That negotiation culminates next fall in the release quality estimate, but it is year-long process, starting this fall as these tools arrive, to get to that point.

MR. SHEPHERD:  All right.  All right.

And so that contract is going to be a separate target price for each unit; is that right?

MR. REINER:  That's right.

MR. SHEPHERD:  So they are individual islands?  If they screw up on one they could lose all their profit, but they still get to make money on the next one, if they do it better?

MR. REINER:  [redacted]

[lines 4 to 14 redacted]

MR. SHEPHERD:  So for example, if you had an incentive for doing better, having a lower cost on unit -- on the second unit than the first one, then they could get that incentive two ways.  One is by going low on the second one and the other is going high on the first one.

So that is bad?

MR. REINER:  Right.

MR. SHEPHERD:  [redacted]

[lines 23 and 24 redacted]

MR. REINER:    [redacted]

[lines 26 and 27 redacted]

MR. SHEPHERD:  So I guess what I am saying is that the -- you have already agreed to some incentives now, right?

MR. REINER:  Yes.

MR. SHEPHERD:  And that is not part of your target price approach.  The target price is really a single concept, right?

MR. REINER:  Yes, yes.

MR. ROSE:  But just to clarify, the incentives, I believe, are based on the bands.

MR. REINER:  Yes.

MR. ROSE:  So the incentive for a $1.5 billion target price for the entire execution is a certain range.  The 1.6 is a certain range, right?  So we have --

MR. REINER:  It's a percentage, yes.

MR. ROSE:  A percentage, yeah.  So I think we have built that in, that flexibility in.

MR. SHEPHERD:  So then my last question is, again, on this contract stuff so I can understand it.

You have given SNC-Aecon the containment building and the steam generator contracts as well, right?

MR. REINER:  SNC-Aecon have also got the turbine generator contract, a piece of the turbine generator contract.  It's being done under two contracts, the OEM, which is the original equipment manufacturer, which is Alstom, they are doing  the --

MR. SHEPHERD:  They manufacture the turbines?

MR. REINER:  They are doing the engineering, the manufacture, they're doing the design work, as well as they will provide the components that need to be replaced.

SNC-Aecon will install the components in the field on the --

MR. SHEPHERD:  It's still a big contract?

MR. REINER:  It's still a sizable contract, yes.

MR. SHEPHERD:  And they also have the containment building contract?

MR. REINER:  And they have -- so they have got the re-tube and feeder replacement contract.  We have moved into that contract the re-tube waste processing building.

MR. SHEPHERD:  The one we were talking about earlier?

MR. REINER:  The one we were talking about.  And it's because that building, it's not about the building.  It's about the purpose that it serves, and it has a direct impact on critical path for that project.

MR. SHEPHERD:  Sure.  And so that's -- I thought I read somewhere that they also were getting a containment building?  Or is that something separate?

MR. REINER:  No.  You may have read -- there is a containment bulkhead that needs to be designed and fabricated and installed, and SNC-Aecon also have that containment bulkhead work.  And that essentially is a barrier to isolate the refurbishment unit from the operating units.

Again, because it's critical path element of the job, it didn't make sense to have another contractor take that on.

MR. SHEPHERD:  So the question I am driving at with these is all of those contracts are going to be separate target prices in which they can earn or be penalized, depending on how well they do on each of them.

MR. GOULD:  Yes.

MR. SHEPHERD:  So one of the problems you had with Niagara Tunnel –- or you didn't, but OPG did -– is that you got to a certain point where it's not in the contractor's interest to be around anymore, because they are just getting whacked too much, right?

And so in this case, because you have all these separate contracts, am I right in understanding even if they do badly on one, they can still make money by doing well on the other ones?

[Witness panel confers]

MR. REINER:  They –- okay.  They are -- I am just getting the clarification on the details.

These are being done as change orders to the contract, so it essentially increases the target price or fixed price, whatever component these fall into, of the existing contract.

So they are not separate contracts.  And so you are right, we could sort of run a risk of -- you know, if you are getting hit on pieces of work, it impacts one contract.

MR. SHEPHERD:  So they have one profit pot, if you like?  This is exactly -- you are going exactly where I was going with this.  They have one profit pot, and if they do badly on Unit 2, they could use it all up?

MR. REINER:  It is -- each unit is a separate profit pot.

MR. SHEPHERD:  Ah.

MR. REINER:  But the bulkhead and the re-tube waste process -- the re-tube waste processing building is getting added -- I believe it's into the definition phase work, since that's prerequisite work.  The bulkhead is -- there is going to be -- we are installing bulkheads four times, for each of the four units, and this gets --

MR. SHEPHERD:  One on each unit?

MR. REINER:  Yes.

MR. SHEPHERD:  All right.  So each unit is an island, a profit island, and the definition phase is a profit island, but with -- there is only the five of them, if you like, right now?

MR. REINER:  Right.

MR. SHEPHERD:  Okay.  That is all my questions.  Thanks.

MR. MILLAR:  Thank you, Mr. Shepherd.

I think that concludes our technical conference, so we are adjourned until -- oh, one final thing.  Mr. Keizer, OPG will remember to have a look through the transcript and see what, if anything, can be released publicly, as is the normal practice?

MR. KEIZER:  Yes, we will.

MR. MILLAR:  Thank you for that.

So we are adjourned until Monday.

### --- Whereupon the conference concluded at 3:52 p.m.