## OEB 39
APPENDIX B: Capital Summary Table (CAPEX)
|  | Phase 1: Approved Capital Spending |  |  | Phase 2: Approved Capital Spending | Total Phase 1 + 2 Capex Approved |  | Phase 1 + Phase 2: Actual/Forecasted Capital Spending |  |  |  |  | Variance
|  | CapEx |  |  | CapEx | CapEx | CapEx | CapEx
|  | A | B | C | D | E = C + D | F = A + B + E | G | H | I | J | K = G + H + J | L = J - E | M = K - F
Schedule Number | Segments | 2012 Approved Capex | 2013 Approved Capex | 2014 Approved Capex | Total 2014 Approved Capex | Total 2014 Approved Capex | Total Approved Capex (2012-2014) | 2012 Capex (Actual) | 2013 Capex (Actual) | 2014 Capex Actual (YTD Jun) | 2014 Capex IR Fcst as at Jul 2014 (Annual) | Total Fcst Capex (2012-2014) | Total 2014 Capex Approved vs Fcst | Total 2012-2014 Capex Approved vs Fcst
B1 | Underground Infrastructure | 28753593.4747 | 58942370.5771 | 0 | 77862605.3345 | 77862605.3345 | 165558569.3863 | 36897844.6222 | 55972976.07 | 41693861.9 | 107078682.0214 | 199949502.7136 | 29216076.6869 | 34390933.3273
B2 | Paper Insulated Lead Covered Cable - Piece Outs and Leakers | 80959.4105 | 5419014.0116 | 0 | 3546010.5231 | 3546010.5231 | 9045983.9453 | 137958.9162 | 1982810.24 | 2326773.02 | 5961330.1708 | 8082099.3269 | 2415319.6477 | -963884.6184
B3 | Handwell Replacement | 13651577.3414 | 16650487.821 | 0 | 18058550.0878 | 18058550.0878 | 48360615.2501 | 12385834.028 | 11870518.69 | 3964543.06 | 15515985.3569 | 39772338.0748 | -2542564.7309 | -8588277.1753
B4 | Overhead Infrastructure | 9070887.645 | 55876554.2466 | 0 | 26014949.4683 | 26014949.4683 | 90962391.3599 | 11587001.3268 | 40422400.68 | 28229413.86 | 64115890.069 | 116125292.0758 | 38100940.6007 | 25162900.716
B5 | Box Construction | 582983.5928 | 23041698.5604 | 0 | 14272480.8627 | 14272480.8627 | 37897163.0159 | 844593.9922 | 13840254.06 | 9700517.8 | 23028311.8022 | 37713159.8544 | 8755830.9395 | -184003.1615
B6 | Rear Lot Construction | 16357430.5751 | 29425563.4537 | 0 | 12511564.6475 | 12511564.6475 | 58294558.6762 | 15981483.2793 | 23199803.54 | 7352234.33 | 26420176.5398 | 65601463.3591 | 13908611.8923 | 7306904.6829
B9 | Network Vault & Roofs | 2838161.8224 | 18760753 | 0 | 2252876.1602 | 2252876.1602 | 23851790.9826 | 2810334.7549 | 10581486.95 | 1170158.85 | 1184990.9548 | 14576812.6597 | -1067885.2054 | -9274978.3229
B10 | Fibertop Network Units | 1475586.7223 | 7711049.566 | 0 | 7090273.7503 | 7090273.7503 | 16276910.0386 | 2136043.8758 | 6827977.91 | 1593611.76 | 4664806.2971 | 13628828.0829 | -2425467.4531 | -2648081.9556
B11 | Automatic Transfer Switches (ATS) & Reverse Power Breakers (RPB) | 0 | 3263231.972 | 0 | 249975.698 | 249975.698 | 3513207.67 | 0 | 1589636.32 | 221857.25 | 222710.4313 | 1812346.7513 | -27265.2667 | -1700860.9187
B12 | Stations Power Transformers | 375540 | 3482290.242 | 0 | 0 | 0 | 3857830.242 | 15711.1169 | 1535653.55 | 872788.37 | 2662970.3632 | 4214335.0301 | 2662970.3632 | 356504.7881
B13.1 & 13.2 | Stations Switchgear - Municipal and Transformer Stations | 1727686.564 | 13716823.824 | 0 | 3535555.2811 | 3535555.2811 | 18980065.6691 | 2431288.7202 | 5080787.44 | 3212294.12 | 9341092.836 | 16853168.9962 | 5805537.5549 | -2126896.6729
B20 | Metering | 4739113.6848 | 8404097.944 | 0 | 9539788.9275 | 9539788.9275 | 22683000.5563 | 5694382.6068 | 4723680.35 | 4906191.45 | 12556592.108 | 22974655.0648 | 3016803.1805 | 291654.5085
B21 | Externally-Initiated Plant Relocations and Expansions | 10163652.1871 | 24840090.4082 | 0 | 4551142.6782 | 4551142.6782 | 39554885.2735 | 9202793.5319 | 18566468.45 | 3871531.66 | 6456336.8287 | 34225598.8106 | 1905194.1505 | -5329286.4629
BXX | ICM Understatement of Capitalized Labour | 8315992.1377 | 0 | 0 | 0 | 0 | 8315992.1377 | 0 | 0 | 0 | 0 | 0 | 0 | -8315992.1377
Total ICM Projects (Excluding Copeland) |  | 98133165.1576 | 269534025.6266 | 0 | 179485773.4192 | 179485773.4192 | 547152964.2034 | 100125270.7712 | 196194454.25 | 109115777.43 | 279209875.7792 | 575529600.8004 | 99724102.3601 | 28376636.597
B17 | Copeland Transformer Station | 8500000 | 81000000 | 34600000 | 0 | 34600000 | 124100000 | 4066381.95 | 26716765.19 | 20570437.66 | 54510000 | 85293147.14 | 19910000 | -38806852.86
B18.2 | Hydro One Capital Contributions | 0 | 23000000 | 37000000 | 0 | 37000000 | 60000000 | 0 | 18602884.31 | 8850092.52 | 21200000 | 39802884.31 | -15800000 | -20197115.69
Total ICM Projects |  | 106633165.1576 | 373534025.6266 | 71600000 | 179485773.4192 | 251085773.4192 | 731252964.2034 | 104191652.7212 | 241514103.75 | 138536307.61 | 354919875.7792 | 700625632.2504 | 103834102.3601 | -30627331.953
B7 | Polymer SMD-20 Switches | 0 | 1529097.889 | 0 | 3974435.2083 | 3974435.2083 | 5503533.0973 | 0 | 841992.01 | 707571.75 | 1845736.5597 | 2687728.5697 | -2128698.6486 | -2815804.5276
B8 | SCADA-Mate R1 Switches | 0 | 1429363.5 | 0 | 4731844.0852 | 4731844.0852 | 6161207.5852 | 0 | 1902414.28 | 450326.41 | 1788283.1641 | 3690697.4441 | -2943560.9212 | -2470510.1412
B14 | Stations Circuit Breakers | 759658.244 | 551875.376 | 0 | 2628551.5866 | 2628551.5866 | 3940085.2066 | 219735.7435 | 1018290.97 | 86272.66 | 1808262.2877 | 3046289.0012 | -820289.2989 | -893796.2054
B16 | Downtown Station Load Transfers | 679134.7743 | 2137062.829 | 0 | 0 | 0 | 2816197.6033 | 52699.5398 | 2313353.3 | 418570.86 | 1287463.6038 | 3653516.4437 | 1287463.6038 | 837318.8403
B18.1 | Hydro One Capital Contributions | 1480000 | 0 | 0 | 2637024 | 2637024 | 4117024 | 26626762.2762 | 20489919.05 | 1037330.65 | 5881869.75 | 52998551.0762 | 3244845.75 | 48881527.0762
C1 | Operations Portfolio Capital | 64779882.385 | 81633674 | 0 | 103777475.1641 | 103777475.1641 | 250191031.5491 | 66672210.9982 | 93238524.19 | 41606556.77 | 98244254.3725 | 258154989.5607 | -5533220.7917 | 7963958.0115
C2 | Information Technology Capital | 22000000 | 15000000 | 0 | 15000000 | 15000000 | 52000000 | 23203817.71 | 17117590.78 | 5991045.65 | 16244100.68 | 56565509.17 | 1244100.68 | 4565509.17
C3 | Fleet Capital | 800000 | 2000000 | 0 | 2000000 | 2000000 | 4800000 | 786898.84 | 2160294.5 | 509380.81 | 2000000 | 4947193.34 | 0 | 147193.34
C4 | Buildings and Facilities Capital | 5000000 | 5000000 | 0 | 5000000 | 5000000 | 15000000 | 5134949.65 | 5713969.56 | 1347060.04 | 8253359.1208 | 19102278.3308 | 3253359.1208 | 4102278.3308
| Allowance for Funds Used During Construction | 1200000 | 1400000 | 0 | 7946500.5766 | 7946500.5766 | 10546500.5766 | 0 | 0 | 0 | 0 | 0 | -7946500.5766 | -10546500.5766
Total Normal Capital Budget |  | 96698675.4033 | 110681073.594 | 0 | 147695830.6209 | 147695830.6209 | 355075579.6182 | 122697074.7577 | 144796348.64 | 52154115.6 | 137353329.5386 | 404846752.9363 | -10342501.0823 | 49771173.3181
Total |  | 203331840.561 | 484215099.2206 | 71600000 | 327181604.0401 | 398781604.0401 | 1086328543.8216 | 226888727.4788 | 386310452.39 | 190690423.21 | 492273205.3179 | 1105472385.1867 | 93491601.2778 | 19143841.3651
Note on M5: Based on outlooks from September 2014 IOP reporting
Note on N5: Based on outlooks from September 2014 IOP reporting