## SEC09_SCEN_1B
APPENDIX A: Capital Summary Table (ISAs)
|  | Phase 1: Approved |  |  | Phase 2: Approved | Phase 1 + 2: Approved |  | Phase 1 + 2: Actual/Forecast |  |  |  |  | Variance
In-Service Additions
|  | A | B | C | D | E = C + D | F = A + B + E | G | H | I | J | K = G + H + J | L = J - E | M = K - F
Schedule Number | Segments | Total 2012 In-Service Additions | Total 2013 In-Service Additions | Total 2014 In-Service Additions | Total 2014 In-Service Additions | Total 2014 In-Service Additions | Total Approved In-Service Additions (2012-2014) | 2012 In-Service Additions Actual (Annual) | 2013 In-Service Additions Actual (Annual) | 2014 In-Service Additions Actual (YTD June) | 2014 In-Service Additions Forecast (Annual) | Total Forecast In-Service Additions (2012-2014) | Total 2014 In-Service Additions Approved vs Forecast | Total 2012-2014 In-Service Additions Approved vs Forecast
B1 | Underground Infrastructure | 12743887.7517 | 51882315.2531 | 23069761.047 | 36697785.1247 | 59767546.1717 | 124393749.1765 | 9346431.2188 | 62170498.82 | 10073883.34 | 76544982.647 | 148061912.6858 | 16777436.4753 | 23668163.5093
B2 | Paper Insulated Lead Covered Cable - Piece Outs and Leakers | 35882.2231 | 3343115.1453 | 2120976.0538 | 1418404.2092 | 3539380.263 | 6918377.6314 | 114629.42 | 151528.36 | 381747.51 | 6173557.1094 | 6439714.8894 | 2634176.8464 | -478662.7421
B3 | Handwell Replacement | 6050519.2474 | 17734624.8322 | 6516921.0828 | 7223420.0351 | 13740341.1179 | 37525485.1975 | 5412332.03 | 16613718.75 | 2338560.07 | 10894938.8782 | 32920989.6582 | -2845402.2397 | -4604495.5393
B4 | Overhead Infrastructure | 4020819.5963 | 39056807.4449 | 21869814.8505 | 14778610.7525 | 36648425.603 | 79726052.6441 | 1030915.64 | 33468212.89 | 12862467.96 | 49818727.9931 | 84317856.5231 | 13170302.3901 | 4591803.879
B5 | Box Construction | 258384.1272 | 14347887.5932 | 9018410.4328 | 5720007.9632 | 14738418.396 | 29344690.1164 | 21551.8306 | 5237684.66 | 2902317.94 | 18446628.6684 | 23705865.159 | 3708210.2725 | -5638824.9574
B6 | Rear Lot Construction | 7249780.8137 | 27016189.2634 | 11517023.9516 | 5004625.859 | 16521649.8106 | 50787619.8877 | 3489318.98 | 27225745.21 | 8354589.07 | 16700996.8775 | 47416061.0675 | 179347.0669 | -3371558.8202
B9 | Network Vault & Roofs | 1257902.3508 | 12998143.8407 | 7342868.6309 | 901150.4641 | 8244019.095 | 22500065.2864 | 0 | 12331413.75 | 2053794.78 | 2292543.0298 | 14623956.7798 | -5951476.0652 | -7876108.5066
B10 | Fibertop Network Units | 653486.6371 | 5515081.6171 | 3018068.0341 | 2836109.5001 | 5854177.5342 | 12022745.7884 | 958865.96 | 7059181.67 | 937025.29 | 5601513.8814 | 13619561.5114 | -252663.6529 | 1596815.723
B11 | Automatic Transfer Switches (ATS) & Reverse Power Breakers (RPB) | 0 | 1986018.6319 | 1277213.3401 | 99990.2792 | 1377203.6193 | 3363222.2512 | 0 | 1512188.31 | 286378.27 | 298175.46 | 1810363.77 | -1079028.1593 | -1552858.4812
B12 | Stations Power Transformers | 166443.1798 | 2328435.5315 | 1362951.5307 | 0 | 1362951.5307 | 3857830.242 | 0 | 353056.05 | 988747.86 | 2901842.737 | 3254898.787 | 1538891.2063 | -602931.455
B13.1 & 13.2 | Stations Switchgear - Municipal and Transformer Stations | 765728.2121 | 9158170.6229 | 5368698.8809 | 1414222.1124 | 6782920.9933 | 16706819.8283 | 0 | 0 | 3209347.38 | 3610839.3316 | 3610839.3316 | -3172081.6617 | -13095980.4967
B20 | Metering | 2100423.6525 | 7753464.3653 | 3289323.611 | 3815915.571 | 7105239.182 | 16959127.1998 | 0 | 7127527.68 | 3405748.54 | 10823665.609 | 17951193.289 | 3718426.427 | 992066.0892
B21 | Externally-Initiated Plant Relocations and Expansions | 4504634.9765 | 20776815.7691 | 9722291.8497 | 1865990.4147 | 11588282.2644 | 36869733.01 | 1935764.03 | 7366316.01 | 26379.58 | 17795321.9378 | 27097401.9778 | 6207039.6734 | -9772331.0321
BXX | ICM Understatement of Capitalized Labour | 3685733.009 | 4630259.1287 | 0 | 0 | 0 | 8315992.1377 | 0 | 0 | 0 | 0 | 0 | 0 | -8315992.1377
Total ICM Projects (Excluding Copeland) |  | 43493625.7771 | 218527329.0391 | 105494323.2959 | 81776232.2853 | 187270555.5812 | 449291510.3973 | 22309809.1093 | 180617072.16 | 47820987.59 | 221903734.1602 | 424830615.4295 | 34633178.579 | -24460894.9678
B17 | Copeland Transformer Station | 0 | 0 | 124100000 | 0 | 124100000 | 124100000 | 0 | 2079863.71 | 1301431.49 | 1302031.49 | 3381895.2 | -122797968.51 | -120718104.8
B18.2 | Hydro One Capital Contributions | 0 | 0 | 60000000 | 0 | 60000000 | 60000000 | 0 | 0 | 0 | 0 | 0 | -60000000 | -60000000
Total ICM Projects |  | 43493625.7771 | 218527329.0391 | 289594323.2959 | 81776232.2853 | 371370555.5812 | 633391510.3973 | 22309809.1093 | 182696935.87 | 49122419.08 | 223205765.6502 | 428212510.6295 | -148164789.931 | -205178999.7678
B7 | Polymer SMD-20 Switches | 0 | 930616.2508 | 598481.6382 | 1589774.0833 | 2188255.7216 | 3118871.9723 | 0 | 842296.18 | 0 | 1509369.8867 | 2351666.0667 | -678885.8349 | -767205.9057
B8 | SCADA-Mate R1 Switches | 0 | 869917.1859 | 559446.3141 | 1892737.6341 | 2452183.9482 | 3322101.1341 | 0 | 1880474.65 | 25339.67 | 25339.67 | 1905814.32 | -2426844.2782 | -1416286.8141
B14 | Stations Circuit Breakers | 336688.4334 | 758844.0435 | 216001.1431 | 1051420.6346 | 1267421.7777 | 2362954.2546 | 219735.75 | 901957.19 | 186683.34 | 496289.4694 | 1617982.4094 | -771132.3083 | -744971.8452
B16 | Downtown Station Load Transfers | 300999.3976 | 1678761.9731 | 836436.2327 | 0 | 836436.2327 | 2816197.6033 | 0 | 32877.24 | 1326598.32 | 1327798.32 | 1360675.56 | 491362.0873 | -1455522.0433
B18.1 | Hydro One Capital Contributions | 0 | 1480000 | 0 | 2637024 | 2637024 | 4117024 | 5475623.17 | 2612403.86 | 0 | 1757138.41 | 9845165.44 | -879885.59 | 5728141.44
C1 | Operations Portfolio Capital | 28999447.3836 | 87751163.6544 | 29662945.3469 | 49290826.0928 | 78953771.4398 | 195704382.4778 | 39928028.2215 | 79394518.94 | 30759137.69 | 99433818.348 | 218756365.5095 | 20480046.9083 | 23051983.0317
C2 | Information Technology Capital | 9253446.2362 | 21469477.0075 | 6277076.7563 | 11250000 | 17527076.7563 | 48250000 | 7558731.8 | 20282466.53 | 6235077.42 | 17485167.7443 | 45326366.0743 | -41909.012 | -2923633.9257
C3 | Fleet Capital | 288354.49 | 760516.4588 | 1751129.0512 | 2000000 | 3751129.0512 | 4800000 | 799291.61 | 441103.9 | 1833039.27 | 3719177.33 | 4959572.84 | -31951.7212 | 159572.84
C4 | Buildings and Facilities Capital | 3757853.3777 | 2897017.0813 | 3345129.5411 | 5000000 | 8345129.5411 | 15000000 | 1396328.71 | 6160806.76 | 38486.13 | 7210426.88 | 14767562.35 | -1134702.6611 | -232437.65
Total Normal Capital Budget |  | 42936789.3184 | 118596313.6552 | 43246646.0237 | 74711782.4449 | 117958428.4686 | 279491531.4422 | 55377739.2615 | 112548905.25 | 40404361.84 | 132964526.0584 | 300891170.57 | 15006097.5899 | 21399639.1277
Total |  | 86430415.0955 | 337123642.6943 | 332840969.3196 | 156488014.7302 | 489328984.0497 | 912883041.8395 | 77687548.3708 | 295245841.12 | 89526780.92 | 356170291.7086 | 729103681.1995 | -133158692.3411 | -183779360.6401