## App.2-AB_Capital Expenditures
[21 empty] | File Number: |  | EB-2015-0004
[21 empty] | Exhibit: |  | B
[21 empty] | Tab: |  | 5
[21 empty] | Schedule: |  | 1
[21 empty] | Page: |  | 1
[21 empty] | Date: |  | ORIGINAL UPDATED: June 29, 2015
Appendix 2-AB
Table 2 - Capital Expenditure Summary from Chapter 5 Consolidated Distribution System Plan Filing Requirements
First year of Forecast Period: | 2016
CATEGORY | Historical Period (previous plan1 & actual) | [17 empty] | Forecast Period (planned)
| 2011 |  |  | 2012 |  |  | 2013 |  |  | 2014 Q2 |  |  | 2014 Actual |  |  | 2015 |  |  | 2016 | 2017 | 2018 | 2019 | 2020
| Plan | Actual | Var | Plan | Actual | Var | Plan | Actual | Var | Plan | Actual | Var | Plan | Actual | Var | Plan | Actual2 | Var
| $ '000 000 |  | % | $ '000 000 |  | % | $ '000 000 |  | % | $ '000 000 |  | % | $ '000 000 |  | % | $ '000 000 |  | % | $ '000 000
System Access | 30.2 | 31.6 | 4.636% | 34.5 | 30.9 | -10.43% | 36.9 | 37.7 | 2.168% | 40.7 | 39 | -4.177% | 40.7 | 35.5 | -12.78% | 35.3 |  | -100% | 36.3 | 35.2 | 35.1 | 35.8 | 36.6
System Renewal | 26.7 | 27.8 | 4.12% | 27.4 | 29.6 | 8.029% | 23.4 | 29.5 | 26.07% | 32.8 | 37 | 12.8% | 32.8 | 37.4 | 14.02% | 40 |  | -100% | 41 | 31.8 | 36.5 | 36 | 35.7
System Service | 25.5 | 26.7 | 4.706% | 21.5 | 21.4 | -0.4651% | 25.1 | 23.9 | -4.781% | 23.1 | 21.8 | -5.628% | 23.1 | 19.3 | -16.45% | 20.8 |  | -100% | 22.2 | 34 | 29.5 | 30.5 | 33.3
General Plant | 20.6 | 10.2 | -50.49% | 35.9 | 27.2 | -24.23% | 43.6 | 40.5 | -7.11% | 22.8 | 18.7 | -17.98% | 22.8 | 32.8 | 43.86% | 20.9 |  | -100% | 45.9 | 48.1 | 18.3 | 18.7 | 14
TOTAL EXPENDITURE | 103 | 96.3 | -6.505% | 119.3 | 109.1 | -8.55% | 129 | 131.6 | 2.016% | 119.4 | 116.5 | -2.429% | 119.4 | 125 | 4.69% | 117 | 0 | -100% | 145.4 | 149.1 | 119.4 | 121 | 119.6
System O&M | N/A | N/A | -- | N/A | 24.9 | -- | N/A | 25.2 | -- | N/A | 27.1 | -- | N/A | 27.3 |  | 29.5 | N/A | -- | 30.9 | N/A | N/A | N/A | N/A
Notes to the Table:
1. Historical “previous plan” data is not required unless a plan has previously been filed
2. Indicate the number of months of 'actual' data included in the last year of the Historical Period (normally a 'bridge' year):
Explanatory Notes on Variances (complete only if applicable)
Notes on shifts in forecast vs. historical budgets by category
See section 3.4 of the DSP (B-1-2)
Notes on year over year Plan vs. Actual variances for Total Expenditures
See section 3.4 of the DSP (B-1-2)
Notes on Plan vs. Actual variance trends for individual expenditure categories
See section 3.4 of the DSP (B-1-2)