Board staff summary tables

Table 1a– Capital Expenditure Pacing (original application)

| Capital Expenditure Category | 2015 | 2016 | 2017 | 2018 | 2019 | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | $ thousand |  |  |  |  |  |
| System Access (net) | 4,084 | 2,685 | 2,475 | 2,340 | 2,350 | 13,934 |
| System Renewal | 4,883 | 4,932 | 4,472 | 4,761 | 4,851 | 23,899 |
| System Service | 2,868 | 2,830 | 4,670 | 4,645 | 3,050 | 18,063 |
| General Plant | 1,675 | 1,180 | 755 | 730 | 510 | 4,850 |
| ALL CAPITAL PROJECTS | 13,510 | 11,627 | 12,372 | 12,476 | 10,761 | 60,746 |
| Annual Capital Projects % of 5 Year Total | 22% | 19% | 20% | 21% | 18% | 100% |
| Source: data from Appendix 2-AA Capital Projects Table 20150129; OEB Staff calculations |  |  |  |  |  |  |

Table 1b – Capital Expenditure Pacing (June 23 update)

| Capital Expenditure Category | 2015 | 2016 | 2017 | 2018 | 2019 | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | $ thousand |  |  |  |  |  |
| System Access (net) | 4,084 | 2,685 | 2,475 | 2,340 | 2,350 | 13,934 |
| System Renewal | 5,943 | 4,932 | 4,472 | 4,761 | 4,851 | 24,959 |
| System Service | 2,418 | 1,380 | 5,820 | 18,395 | 4,050 | 32,063 |
| General Plant | 1,675 | 1,180 | 755 | 889 | 510 | 5,009 |
| ALL CAPITAL PROJECTS | 14,120 | 10,177 | 13,522 | 26,385 | 11,761 | 75,965 |
| Annual Capital Projects % of 5 Year Total | 19% | 13% | 18% | 35% | 15% | 100% |
| Source: data from Appendix 2-AA Capital Projects Table 20150623; OEB Staff calculations |  |  |  |  |  |  |

Table 2a – System Service Capital Expenditure Pacing (original application)

| System Service Capital Expenditure - Detail | 2015 | 2016 | 2017 | 2018 | 2019 | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | $ thousand |  |  |  |  |  |
| Thornton TS Capacity - HONI Contributions | 1,500 | 1,500 |  |  |  | 3,000 |
| Wilson TS Capacity - HONI Contributions |  |  | 1,000 | 1,000 | 1,500 | 3,500 |
| MS9 - 44kV/13.8kV Substation | 750 | 1,000 | 3,250 | 2,000 |  | 7,000 |
| MS9 Proposed OH distribution feeders |  |  |  | 1,000 | 1,000 | 2,000 |
| Subtotal – New Load | 2,250 | 2,500 | 4,250 | 4,000 | 2,500 | 15,500 |
| Annual New Load as % of 5 Year Total | 15% | 16% | 27% | 26% | 16% | 100% |
| Misc. System Service | 618 | 330 | 420 | 645 | 550 | 2,563 |
| Total System Service | $2,868 | $2,830 | $4,670 | $4,645 | $3,050 | $18,063 |
| Annual SS as % of 5 Year Total SS | 16% | 16% | 26% | 26% | 17% | 100% |
| SS as % of Total Capital Projects for Year | 21% | 24% | 38% | 37% | 28% | 30% |
| Source: data from Appendix 2-AA Capital Projects Table 20150129; OEB Staff calculations |  |  |  |  |  |  |

Table 2b– System Service Capital Expenditure Pacing (June 23 update)

| System Service Capital Expenditure - Detail | 2015 | 2016 | 2017 | 2018 | 2019 | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | $ thousand |  |  |  |  |  |
| TS Capacity - HONI Contributions | 1,350 |  | 5,400 | 6,750 |  | 13,500 |
| MS9 - 44kV/13.8kV Substation |  |  |  | 7,000 |  | 7,000 |
| MS9 Proposed OH Distribution Feeders |  |  |  | 4,000 | 3,500 | 7,500 |
| Subtotal – New Load | 1,350 | 0 | 5,400 | 17,750 | 3,500 | 28,000 |
| Annual as % of 5 Year Total New Load | 5% | 0% | 19% | 63% | 13% | 100% |
| Misc. System Service | 1,068 | 1,380 | 420 | 645 | 550 | 4,063 |
| Total System Service | 2,418 | 1,380 | 5,820 | 18,395 | 4,050 | 32,063 |
| Annual SS as % of 5 Year Total SS | 8% | 4% | 18% | 57% | 13% | 100% |
| SS as % of Total Capital Projects for Year | 17% | 14% | 43% | 70% | 34% | 42% |
| Source: data from Appendix 2-AA Capital Projects Table 20150623; OEB Staff calculations |  |  |  |  |  |  |