## 2-AMPCO-3
2-AMPCO-3
|  |  |  | Forecast Installs (Units) |  |  | Actual Installs (Units)
Segment |  | Assets | Unit of Measure | Non-Linear Units | Linear Units | Total Units | 2012-2014 ISA Quantities (Forecasted Jobs) | 2012-2014 ISA Quantities (Analogous Jobs) | 2012-2014 ISA Quantities
B1 | Underground Infrastructure | Primary Cable | M | 0 | 601275 | 601275 | 447044.664 | 112861 | 559905.664
|  | Submersible Transformers | EA | 976 | 0 | 976 | 473 | 78 | 551
|  | SF6-Insulated Pad-mounted Switchgear | EA | 78 | 0 | 78 | 84 | 45 | 129
|  | SF6-insulated Vault-installed Switchgear | EA | 133 | 0 | 133 | 154 | 12 | 166
B2 | PILC Cables | Piece Out and Leakers 1 | EA | 299 | 0 | 299 | 0 | 0 | 0
B3 | Handwell Replacement | Handwells3 | EA | 7165 | 0 | 7165 | 7756 | 0 | 7756
B4 | Overhead Infrastructure | Poles | EA | 5570 | 0 | 5570 | 5689 | 175 | 5864
|  | Transformers2 | EA | 156 | 0 | 156 | 1490 | 27 | 1517
|  | Conductor | M | 0 | 204000 | 204000 | 226070 | 5351 | 231421
|  | Switches2 | EA | 138 | 0 | 138 | 308 | 30 | 338
|  | Porcelain Insulators1 | EA | 3403 | 0 | 3403
B5 | Box Construction | Poles | EA | 2364 | 0 | 2364 | 1949 | 20 | 1969
|  | Switches | EA | 260 | 0 | 260 | 115 | 12 | 127
|  | Transformers | EA | 496 | 0 | 496 | 525 | 42 | 567
|  | Conductor | M | 0 | 129105 | 129105 | 135989 | 6653 | 142642
B6 | Rear Lot Construction | Poles | EA | 216 | 0 | 216 | 211 | 0 | 211
|  | Switches | EA | 17 | 0 | 17 | 58 | 0 | 58
|  | Transformers | EA | 302 | 0 | 302 | 340 | 17 | 357
|  | Conductor | M | 0 | 13665 | 13665 | 31169 | 0 | 31169
|  | Cable | M | 0 | 89979 | 89979 | 80343 | 3410 | 83753
|  | Underground Civil Work | M | 0 | 37421 | 37421 | 51508.55 | 4199 | 55707.55
B9 | Network Vaults & Roofs | Vaults - Decommissioned | EA | 3 | 0 | 3 | 17 | 9 | 26
|  | Vaults - Complete Rebuild | EA | 19 | 0 | 19
|  | Vaults - Roof Rebuild | EA | 9 | 0 | 9
B10 | Fibertop Network Units | Network Units | EA | 104 | 0 | 104 | 145 | 40 | 185
B11 | Automatic Transfer Switches & Reverse Power Breakers | Automatic Transfer Switches | EA | 12 |  | 12 | 27 | 0 | 27
|  | Reverse Power Breakers | EA | 2 |  | 2
B12 | Station Power Transformers | Transformers | EA | 10 | 0 | 10 | 5 | 8 | 13
B13 | Stations Switchgear | MS Switchgear | EA | 10 | 0 | 10 | 0 | 2 | 2
|  | TS Switchgear | EA | 4 | 0 | 4
Note:
1Actuals data does not track this asset.
2Forecast only includes amounts filed in Phase 2 as no forecasts were filed in Phase 1; actuals includes all 2012-2014 data.
3Forecast only includes amounts filed in Phase 2 as no forecasts were filed in Phase 1; actuals includes all 2012-2014 data. Data in Actuals for financial statements was only tracked discretely starting from 2013.