## Budget EXAMPLE
RPP Roadmap Pilot Project Detailed Budget (Proposal Section 3.1B)
Example Load Control Pilot Project
Applicant Company | [9 empty] | PLEASE NOTE: 1.) Example content is only to demonstrate format. 2.) The "Rate/Cost" X "Units" must match the value in the "Total Contribution (All Funders)" column. 3.) Do not include OEB reviews (such as M&V plan review) as an in-kind contribution.
Click red triangles on cells for important notes that will help you accurately complete this template.
Task Areas | Activities | Due Date | Service Provider | Rate/Cost | Units | Funding (OEB) | Local Distribution Company (LDC) (Cash/In-Kind) | Partner (Cash/In-Kind) | Total Contribution (All Funders)
Milestone 1: Pilot Project Preparation
Task 1: Develop M&V Plan
| Develop detailed M&V Plan | Month 1 | Applicant/3rd party | 70 | 15 |  | 550 | 500 | 1050
| Review detailed M&V Plan with OEB | Month 2 | Applicant | 70 | 2 |  | 140 |  | 140
Task 2: Load Control Installation
| Develp installation plan | Month 2 | Applicant Company | 70 | 5 | 200 | 150 |  | 350
| Acquire load controls | Month 2 | Load Control Co. | 400 | 10 | 4000 |  |  | 4000
| Load control installation | Month 3 | Installation Co. | 100 | 12 | 1200 |  |  | 1200
0
Task 3: Measuring Results | [8 empty] | 0
| Data collection (12 months) | Month 9 | Applicant Company | 60 | 100 |  | 6000 |  | 6000
| Data analyis and weather normalization | Month 13 | Applicant Company | 70 | 40 | 1400 | 1400 |  | 2800
Task 4: Reporting | [8 empty] | 0
| Draft report on results | Month 14 | Applicant Company | 70 | 6 | 420 |  |  | 420
0
Total | [5 empty] | 7220 | 8240 | 500 | 15960
Note on C6: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on D6: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on E6: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on H6: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on I6: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on J6: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on A7: Group your activities by milestones; the date by which you expect the task will be completed. Project funding is provided to correspond with milestone dates and deliverables.
Note on A8: Include tasks as described in Section 3. Add or remove rows as necessary.

## Budget
RPP Roadmap Pilot Project Detailed Budget (Proposal Section 3.1B)
Hydro One RPP Roadmap Pilot
Hydro One Networks Inc. | [9 empty] | PLEASE NOTE: 1.) Example content is only to demonstrate format. 2.) The "Rate/Cost" X "Units" must match the value in the "Total Contribution (All Funders)" column. 3.) Do not include OEB services (such as M&V plan review) as an in-kind contribution.
Click red triangles on cells for important notes that will help you accurately complete this template.
Task Areas | Activities | Due Date | Service Provider | Rate/Cost | Units | Funding (OEB) | Local Distribution Company (LDC) (Cash/In-Kind) | Partner (Cash/In-Kind) | Total Contribution (All Funders)
Milestone 1: OEB Approval of Submission
0
0
0
Total | [5 empty] | 0 | 0 | 0 | 0
Milestone 2: Pilot Launched
|  |  | [Product or Service Provider] | [$/hr] or [$/unit] | [hours] or [units] |  |  |  | 0
0
Task 1: Administration | Administrative Support | 2017-04-30 | Support staff | 5400 | 5 | 27000 |  |  | 27000
| Adminstration - Professors |  | Professors | 3000 | 5 | 15000 |  |  | 15000
| OEB testimony support |  | Professors | 10000 | 1 | 10000 |  |  | 10000
| Supplies & Equipment |  | Software/Hardware/Supplies | 4000 | 1 | 4000 |  |  | 4000
Task 2: Conjoint | Design |  | Professors | 14000 | 1 | 14000 |  |  | 14000
| Research Support |  | Student Support | 1000 | 1 | 1000 |  |  | 1000
| Study |  | follow a panel | 15000 | 1 | 15000 |  |  | 15000
| Consultant Support |  | Sawtooth Support | 32000 | 1 | 32000 |  |  | 32000
Task 3: Rate Design | Rate Determination |  | Professors | 6000 | 1 | 6000 |  |  | 6000
|  |  | Student Support | 1500 | 1 | 1500 |  |  | 1500
| Focus Groups |  | incentives & rooms etc. | 15000 | 1 | 15000 |  |  | 15000
Task 4: Sample Selection | Research Support |  | Student Support | 4000 | 1 | 4000 |  |  | 4000
Task 5: Registration Platform Design | Research Support |  | Student Support | 3200 | 5 | 16000 |  |  | 16000
Task 6: Co-ordinationg Recruitment & Vendor Setup | Coordiantion |  | Field Project Coordinator | 7500 | 5 | 37500 |  |  | 37500
Task 7: Recruitment | Support |  | part-time assistants | 17000 | 1 | 17000 |  |  | 17000
| Survey Fees |  | $15 ($20-control) per participant | 40675 | 1 | 40675 |  |  | 40675
| Survey Platform |  | Research Now | 2000 | 1 | 2000 |  |  | 2000
Task 8: Equipment & Installation | Equipment |  | IHD/thermostats/TES | 552650 | 1 | 552650 |  |  | 552650
| Installation |  | various installers | 395650 | 1 | 395650 |  |  | 395650
| Vendor Support |  | various vendors | 175000 | 1 | 175000 |  |  | 175000
Task 9: Model Specification and Analysis | Analysis |  | Professors | 5600 | 5 | 28000 |  |  | 28000
|  |  | Professors |  | 1 | 0 | 5000 |  | 5000
Task 10: Data Transfer & IT Support | Data Transfer |  | Hydro One IT/ Inergi | 100000 | 1 | 100000 |  |  | 100000
[6 empty] | 0 |  |  | 0
Task 11: Marketing and Recruitment | Recruitment Letters and Eblasts |  | Hydro One / Context Creative | 52000 | 1 | 52000 |  |  | 52000
| Website Development |  | Hydro One / Context Creative | 55000 |  | 0 |  |  | 0
| Participant Educational Material Development |  | Hydro One / Context Creative | 10000 | 1 | 10000 |  |  | 10000
| Letter and Educational Material Postage |  | Canada Post | 0.5 | 152000 | 76000 |  |  | 76000
| Customer Support |  | Hydro One | 45000 | 1 | 45000 |  |  | 45000
| Recruitment Management |  | Hydro One | 50000 | 1 | 50000 | 30000 |  | 80000
[6 empty] | 0 |  |  | 0
Total | [5 empty] | 1741975 | 35000 |  | 1776975
Milestone 3:Interim Report Submitted to OEB
|  |  | [Product or Service Provider] | [$/hr] or [$/unit] | [hours] or [units] |  |  |  | 0
Task 1: Administration | Administrative Support | 2017-10-31 | Support staff | 9000 | 6 | 54000 |  |  | 54000
| Administration - Professors |  | Professors | 2500 | 6 | 15000 |  |  | 15000
| Supplies & Equipment |  | Software/Hardware/Supplies | 1500 | 1 | 1500 |  |  | 1500
Task 2: Ongoing Field Support | Research Support |  | Student Support | 3600 | 6 | 21600 |  |  | 21600
| Coordination |  | Field Project Coordinator | 6000 | 6 | 36000 |  |  | 36000
| Vendor Support |  | various vendors | 125000 | 1 | 125000 |  |  | 125000
| Support (participant field support) |  | part-time assistants | 3000 | 1 | 3000 |  |  | 3000
| Project Management |  | Hydro One | 38000 | 1 | 38000 |  |  | 38000
Task 3: Rebates | Participant Rebates |  | 2835 participants | 342500 | 1 | 342500 |  |  | 342500
| Delivery of Mockbills |  | 2835 participants | 44100 | 1 | 44100 |  |  | 44100
Task 4: Data Warehousing | data warehousing |  | storage of data | 4500 | 6 | 27000 |  |  | 27000
Task 5: Prepartation of Interim Report | Research Support |  | Student Support | 5375 | 2 | 10750 |  |  | 10750
| Analysis |  | Professors | 3250 | 6 | 19500 |  |  | 19500
Task 6: Model Specification and Analysis | Analysis |  | Professors | 5000 | 6 | 30000 | 5000 |  | 35000
| Research Support |  | Student Support | 2100 | 6 | 12600 |  |  | 12600
0
0
0
0
0
0
Total | [5 empty] | 780550 | 5000 |  | 785550
Milestone 4: Billing System Update Complete
|  | 2018-05-01 | [Product or Service Provider] | [$/hr] or [$/unit] | [hours] or [units] |  |  |  | 0
Task 1: Billing System Infrastructure Upgrade* | Billing system changes |  | Hydro One | [5 empty] | 0
| Bill Format editing |  | Hydro One | [5 empty] | 0
| Bill Settlements |  | Hydro One | [5 empty] | 0
| Staff Training |  | Hydro One | [5 empty] | 0
| TOU Portal Update |  | Hydro One | [5 empty] | 0
| Project Coordination |  | Hydro One | 5600000 | 1 | 5600000 |  |  | 5600000
0
0
0
Task 2: Integration with IESO/MDMR ** | Integrate with IESO MDMR System |  | Hydro One / IESO | 4000000 | 1 | 4000000 |  |  | 4000000
0
0
* Preliminary figures - detailed budget to be delivered by Jan 2017 | [8 empty] | 0
** Preliminary figure - estimate includes IESO costs | [8 empty] | 0
0
0
Total | [5 empty] | 9600000 | 0 |  | 9600000
Milestone 5:In-Field Testing Complete
|  |  | [Product or Service Provider] | [$/hr] or [$/unit] | [hours] or [units] |  |  |  | 0
Task 1: Administration | Administrative Support | 2018-11-30 | Support staff | 5700 | 13 | 74100 |  |  | 74100
| Adminstration - Professors |  | Professors | 2300 | 13 | 29900 |  |  | 29900
| Supplies & Equipment |  | Software/Hardware/Supplies | 12000 | 1 | 12000 |  |  | 12000
Task 2: Ongoing Field Support | Research Support |  | Student Support | 3600 | 12 | 43200 |  |  | 43200
| Coordination |  | Field Project Coordinator | 5250 | 12 | 63000 |  |  | 63000
| Vendor Support |  | various vendors | 295000 | 1 | 295000 |  |  | 295000
| Support (participant field support) |  | part-time assistants | 5000 | 1 | 5000 |  |  | 5000
| Project Management |  | Hydro One | 120000 | 1 | 120000 | 15000 |  | 135000
| Customer Support |  | Hydro One | 70000 | 1 | 70000 | 15000 |  | 85000
Task 3: Rebates | Participant Rebates |  | 2835 participants | 342500 | 1 | 342500 |  |  | 342500
| Delivery of Mockbills |  | 2835 participants | 44100 | 1 | 44100 |  |  | 44100
Task 4: Data Warehousing | data warehousing |  | storage of data | 4500 | 12 | 54000 |  |  | 54000
Task 5: Interim & Final Surveys | Survey Platform |  | Research Now | 2000 | 2 | 4000 |  |  | 4000
| Survey 2 & 3 fees |  | $25 ($30) per participant (control) | 84800 | 2 | 169600 |  |  | 169600
Task 6: Model Specification and Analysis | Analysis |  | Professors | 5000 | 12 | 60000 | 5000 |  | 65000
|  |  | student support | 1500 | 12 | 18000 |  |  | 18000
0
0
0
0
0
0
Total | [5 empty] | 1404400 | 35000 |  | 1439400
Milestone 6: Final Report Submitted to OEB
|  |  | [Product or Service Provider] | [$/hr] or [$/unit] | [hours] or [units] |  |  |  | 0
Task 1: Administration | Administrative Support | 2019-05-01 | Support staff | 5000 | 5 | 25000 |  |  | 25000
| Adminstration - Professors |  | Professors | 2500 | 5 | 12500 |  |  | 12500
| Supplies & Equipment |  | Software/Hardware/Supplies | 2000 | 1 | 2000 |  |  | 2000
0
Task 2: Project Management | Project Management |  | Hydro One | 30000 | 1 | 30000 |  |  | 30000
[6 empty] | 0 |  |  | 0
Task 3: Final Report | [5 empty] | 0 |  |  | 0
| Coordination of Data and Analysis |  | Field Project Coordinator | 4500 | 6 | 27000 |  |  | 27000
| Vendor provision of data etc. |  | various vendors | 75000 | 1 | 75000 |  |  | 75000
| Environmental and Grid Impact Assessment |  | external consultant | 50000 | 1 | 50000 |  |  | 50000
| Research Support |  | Student Support | 8000 | 6 | 48000 |  |  | 48000
| Analysis & Write-up |  | Professors | 15000 | 6 | 90000 | 5000 |  | 95000
0
0
0
0
0
0
0
0
Total | [5 empty] | 359500 | 5000 |  | 364500
|  | Project Total |  |  |  | 13886425 | 80000 |  | 13966425
Note on C6: List the expected date of completion for this task. Should match Timeline tab of this Excel file.
Note on D6: Please list/describe the product or service provider that will be paid for performing this task. If your service provider is not confirmed, provide a generic name/description.
Note on E6: Regardless of whether or not the supplier is known at this point, you must provide a rough estimate of the rate you expect you will pay for the good or service of this task/cost item, otherwise, there would be no basis for your request.
Note on H6: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on I6: Please specify the name of the funder or contributor, as well as if the contribution is in cash or in kind amount. There should be separate columns for cash and in-kind amounts if a partner provides a contribution in both forms. If there are additional partners, please add columns.
Note on J6: You should check to make sure that the total contribution for an activity matches the cost for each activity (i.e., that all costs are covered by contributions)
Note on A7: Group your activities by milestones; the date by which you expect the task will be completed. Project funding is provided to correspond with milestone dates and deliverables.
Note on A13: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on A48: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on A73: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on A91: Include tasks as described in Section 3. Add or remove rows as necessary.
Note on A116: Include tasks as described in Section 3. Add or remove rows as necessary.

## Work Plan
RPP Roadmap Pilot Project Work Plan (Proposal Section 3.1B)
Hydro One RPP Roadmap Pilot
Hydro One Networks Inc.
Project Month # (Maximum project length is 36 months)
Task Area | Activity/ Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| Year | Project Month # (Maximum project length is 36 months) 1: 2016; Project Month # (Maximum project length is 36 months) 4: 2017; Project Month # (Maximum project length is 36 months) 16: 2018; Project Month # (Maximum project length is 36 months) 28: 2019
| Month | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Project Length | bar: 2016 O to 2019 F
Conjoint | bar: 2016 N to 2017 F
Design
Customers Complete Conjoint Survey
Conjoint Analysis
OEB Approval | bar: 2016 O to 2016 D
Pilot Design | bar: 2016 N to 2017 J
Website
Final Rates Analysis for Pilot
Procurement: Technology Vendors & Installers
Develop Participant Agreements
Recruitment | bar: 2017 F to 2017 M
Develop Recruitment Communication Material
Deliver Recruitment Communication & Finalize Participants
Installation | bar: 2017 A to 2017 M
Billing System Updates | Year Month: Budgeting / Planning
System Updates
Testing / QA
Go live with Customer billing
Pilot Duration
Risk-Free Period
Recruitment Survey
Risk Period
Interim Survey
Final Survey
EM&V | Year Month: Pilot Final Analysis

## Measuring Results
RPP Roadmap Pilot Project - Measuring Results (Proposal Section 4A)
Hydro One RPP Roadmap Pilot
Hydro One Networks Inc.
Click red triangles on cells for important notes that will help you accurately complete this template.
Ultimate Outcome | Project/ Intermediate Outcome | Immediate Outcome | Activity/Deliverable | Performance Indicator | Method of Measurement | Target Results | Target Completion Date/Month
Pilot participants have incorporated effective energy management into their daily energy usage decisions. | Pilot participants choose rate plan well suited to their lifestyle and ability to shift usage | Pilot participant education on rate options | Development of education material | Website launched | Number of participants switching from their initial rate choice | 85% remain on initial rate choice for duration of pilot | 2017-11-01
| Pilot participants see value in choice of rate structure | Participants indicate satisfaction with control over their rate structure | Initial participant survey | Participant survey response shows desire to have choice with respect to electricity rates | Survey results | 70% of participants indicate preference to have choice in rate structure | 2017-06-30
|  |  | Final participant survey | Participant survey response shows improved preference to have choice with respect to electricity rates | Survey results | 80% of participants indicate preference to have choice in rate structure | 2019-04-01
| Pilot participants shift out of the peak | Participants shift consumption from peak to off-peak periods | Final Report: Analysis of shifting & measurment of price elasticities | (i) Percentage kWh shifted (ii) price elasticitiy | Statistical Analysis: Econometric panel analysis (difference in difference specification & CES formulation), using counterfacutal estimation | Reliable estimates of shifted consumption & elasticities with 95% confidence bands | 2019-04-30
| Pilot participants see value in integrating energy enabling technologies with dynamic pricing | Participants with more information feedback & enabling techologies shift more kWh relative to those without such technoligies | Final Report: Analysis of shifting & price responsivness as function of information feedback and enabling technogies | (i) Percentage kWh shifted (ii) price elasticitiy as a function of information feedback and enabling technologies | Statistical Analysis: Econometric panel analysis (difference in difference specification & CES formulation), using counterfacutal estimation | Reliable estimates of shifted consumption & elasticities attributable to feedback & enabling technologies with 95% confidence bands | 2019-04-30
Hydro One billing system has ability to deliver billing based on complex, dynamic rate options | Pilot participants receive bills from Hydro One based on their dynamic rates | Pilot participants receive bills from Hydro One based on their dynamic rates | Hydro One bill based on new rate structures delivered to participants beginning May 2018. | Bills delivered | Number of bills delivered | 100% of participants receive bill from Hydro One based on their new rate structure beginning for the period May 2018. | 2018-06-30
Hydro One billing system has ability to deliver billing based on complex, dynamic rate options | Pilot participants receive bills from Hydro One based on their dynamic rates | Pilot participants receive bills from Hydro One based on their dynamic rates | Hydro One bill based on new rate structures delivered to participants beginning May 2018. | Bills delivered | Number of bills delivered | 100% of participants receive bill from Hydro One based on their new rate structure beginning for the period May 2018. | 2018-06-30
Note on B6: This should match the Intermediate Outcomes described in section 3 of the proposal template.
Note on C6: This should match the Intermediate Outcomes described in section 3 of the proposal template.
Note on E6: Deliverables are tangible products that are created as the result of an activity. Some activities may not result in a deliverable but are nevertheless important (e.g., participant recruitment)
Note on F6: Measuring results requires a performance indicator to be established for EACH project activity/deliverable as well as plan for how and when it will be measured.
Note on G6: The method of measurement should be chosen to reflect the data required, the level of accuracy needed and the difficulty of collecting it. Frequency of measurement should be included if it occurs more than once.
Note on H6: Results should match what you hope to achieve, not the minimum or maximum possible.
Note on I6: This date should match the dates provided in the budget. If the activity happens on a recurring basis, the date should indicate the first time that the activity takes place. You may choose to write Month 8 rather than a specific date to ensure the proposal does not need to be updated if project start date is delayed.