## Task_Table
| Man Hrs | Start Date | Finish | Project Manager | Notes | Summary of Linemen Hour Allocations 2017 |  |  | Assume 3% Sick Leave
CAPITAL
[7 empty] | Working Days | Total Hours | Vacation/Sick | Trng/NM | Ops/Mtnc | Capital | Hrs Remaining
Pole Replacements (40) | 700 | April | Dec |  |  | January | 22 | 704 | 61 | 36 | 608 | 10 | -11
Pole Top Tx Replacement Program (15) | 135 | April | Dec |  |  | February | 19 | 608 | 61 | 164 | 408 | 10 | -35
Padmount tx Upgrades (2) | 25 | July | July |  |  | March | 22 | 704 | 61 | 52 | 608 | 10 | -27
Underground Conductor System Upgrades (2) | 75 | July | Aug |  |  | April | 20 | 640 | 61 | 68 | 151 | 355 | 5
Underground Secondary Upgrades | [5 empty] | May | 22 | 672 | 16 | 56 | 121 | 485 | -6
[6 empty] | June | 22 | 704 | 40 | 36 | 231 | 535 | -138
MS-1 Breaker Replacement | 150 | May | Sept |  |  | July | 20 | 640 | 40 | 36 | 221 | 500 | -157
Hunter Gate Subdivision | 350 | June | Sept |  |  | August | 22 | 704 | 40 | 36 | 221 | 486 | -79
Smart Grid- Feeder Monitoring | 150 | June | August |  |  | September | 20 | 640 | 40 | 28 | 221 | 375 | -24
Tools & Equipment |  | May | Sept |  |  | October | 22 | 704 | 140 | 36 | 221 | 317 | -10
Argyle St Rebuild | 640 | April | Sept |  |  | November | 22 | 704 | 132 | 116 | 255 | 275 | -74
Raglan St N Rebuild | 700 | May | Dec |  |  | December | 20 | 640 | 120 | 116 | 120 | 75 | 209
[6 empty] | Total | 253 | 8064 | 812 | 780 | 3386 | 3433 | -347
Vehicle Replacement | 40 | Oct | Dec
Line Extensions | 160 | June | Dec |  |  |  |  | est. | 568 total vacation
System Upgrades | 160 | June | Dec |  |  |  |  | est. | 244 total sick leave
URD Installations | 32 | April | Nov
Battery Bank Upgrades |  | June | July
Substation Security/Lighting | 16 | June | July
Meters | 100 | Jan | Dec
TOOLS
RECURRING CAPITAL ITEMS |  | METERING
TOTAL CAPITAL LABOUR | 3433
PREVENTATIVE MAINTENANCE
Pole Testing- Resistograph/Polux | 350 | June | October
Vegetation- Tree Trimming | 1600 | January | April
Substation Inspections | 96 | June | June
Feeder Inspections- 3 yr |  | part of poletesting and vegetation work
Power Transformer- Oil Sampling | 10 | June | June
Guy Guard Survey- snowmobile areas |  | part of regular inspections above
Customer Requests | 600 | April | Dec
Electrician Requests | 250 | April | dec
Battery Maintenance
Gang Switch Inspection and Maintenance | 64 | April | Dec
|  | April | April
Thermovision Inspection |  | Included above
Regulators Inspection | N/A
Padmount Switch Inspection |  | Included above
Padmount Transformer Inspection |  | Included above
Dissolved Gas Analysis |  | Included above
Recloser Maintenance | 32 | May | October
Recloser Inspection |  | Included above
Cable Condition Testing (VLF)
TOTAL PM LABOUR | 3002
CORRECTIVE MAINTENANCE BACKLOG
Trended Maintenance @ 50% | 384
NON-MAINTENANCE
APPOINTMENT
AWAY ON BUSINESS (AOB) | 32
BEREAVEMENT | 32
FAMILY COMPASSIONATE LEAVE | 32
VOLUNTEER TIME
Stand By
Transportation
Vehicle Inspection | 220
Storm Assistance | 32
Training
Block 1 for meter tech | 80
Block 2 for meter tech
MV-90 Course
Tantalus Trainiing
Equipotential Grounding & Bonding, Course and Instructor Cost only
Equipotential Grounding & Bonding (16hrs Labour only)
Hot Line Refresher Training
TDG/WHMIS | 32
Safety Meetings 12/year 2hours | 96
First Aid/CPR 8hr | 32
First Aid 2 day 8hr
Pole Top Rescue 5hr May | 20
Fall Arrest 4hrs | 64
Work Protection Code 4hr
Safety Rule Book 8hr
Arc Flash Training 4hrs | 16
Rigging/Slinging 4hr
Confined Space 8hr
Emergency Response training 2hrs
Fire Extinguisher 2hr
Work Methods, SOP's
EMS 8hr | 32
PPE Refresher 2hr | 8
Flu Shots and Wellness 1 hr
OH&S Cmte (4 mtgs/yr) | 8
TOTAL NM Lineworker LABOUR | 388

## Raw Data Budget
Gross Resource |  |  | 672 | 640 | 704 | 704 | 672 | 672 | 704 | 672 | 704 | 704 | 672 | 704 | 8224
Type | Item | hours | January | February | March | April | May | June | July | August | September | October | November | December | Total
0
Capital |  | 720 | [12 empty] | 0
Capital | Pole Replacements (40) | 700 |  |  |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 60 | 700
Capital | Pole Top Tx Replacement Program (15) | 135 |  |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 135
Capital | Padmount tx Upgrades (2) | 25 | [6 empty] | 25 | [5 empty] | 25
Capital | Underground Conductor System Upgrades (2) | 75 | [6 empty] | 40 | 35 |  |  |  |  | 75
Capital | Underground Secondary Upgrades | [13 empty] | 0
Capital | [14 empty] | 0
Capital | MS-1 Breaker Replacement | 150 |  |  |  |  | 30 | 30 | 30 | 30 | 30 |  |  |  | 150
Capital | Hunter Gate Subdivision | 350 | [5 empty] | 90 | 90 | 90 | 80 |  |  |  | 350
Capital | Smart Grid- Feeder Monitoring | 150 | [5 empty] | 50 | 50 | 50 |  |  |  |  | 150
Capital | Tools & Equipment | [13 empty] | 0
Capital | Argyle St Rebuild | 640 |  |  |  | 250 | 250 | 140 | [6 empty] | 640
Capital | Raglan St N Rebuild | 700 |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 700
Capital | [14 empty] | 0
Capital | Vehicle Replacement | 40 | [9 empty] | 20 | 20 |  | 40
Capital | Line Extensions | 160 | [5 empty] | 10 | 30 | 30 | 30 | 30 | 30 |  | 160
Capital | System Upgrades | 160 | [5 empty] | 10 | 30 | 30 | 30 | 30 | 30 |  | 160
Capital | URD Installations | 32 | [9 empty] | 32 |  |  | 32
Capital | Battery Bank Upgrades | [13 empty] | 0
Capital | Substation Security/Lighting | 16 | [7 empty] | 16 |  |  |  |  | 16
Capital | Meters | 100 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 100
Capital | [14 empty] | 0
Total Capital |  |  | 10 | 10 | 10 | 355 | 485 | 535 | 500 | 486 | 375 | 317 | 275 | 75 | 3433
Preventative Maintenance | Pole Testing- Resistograph/Polux | 350 | [5 empty] | 70 | 70 | 70 | 70 | 70 |  |  | 350
Preventative Maintenance | Vegetation- Tree Trimming | 1600 | 600 | 400 | 600 | [9 empty] | 1600
Preventative Maintenance | Substation Inspections | 96 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96
Preventative Maintenance | Feeder Inspections- 3 yr | [13 empty] | 0
Preventative Maintenance | Power Transformer- Oil Sampling | 10 | [5 empty] | 10 | [6 empty] | 10
Preventative Maintenance | Guy Guard Survey- snowmobile areas | [13 empty] | 0
Preventative Maintenance | Customer Requests | 600 |  |  |  | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 40 | 600
Preventative Maintenance | Electrician Requests | 250 |  |  |  | 30 |  | 30 | 30 | 30 | 30 | 30 | 70 |  | 250
Preventative Maintenance | Battery Maintenance | [13 empty] | 0
Preventative Maintenance | Gang Switch Inspection and Maintenance | 64 | [10 empty] | 64 |  | 64
Preventative Maintenance | [14 empty] | 0
Preventative Maintenance | Thermovision Inspection | [13 empty] | 0
Preventative Maintenance | Regulators Inspection | N/A | [12 empty] | 0
Preventative Maintenance | Padmount Switch Inspection | [13 empty] | 0
Preventative Maintenance | [14 empty] | 0
Preventative Maintenance | Padmount Transformer Inspection | [13 empty] | 0
Preventative Maintenance | Dissolved Gas Analysis | [13 empty] | 0
Preventative Maintenance | Recloser Maintenance | 32 | [11 empty] | 32 | 32
Preventative Maintenance | Recloser Inspection | [13 empty] | 0
Preventative Maintenance | Cable Condition Testing (VLF) | [13 empty] | 0
Total PM |  |  | 608 | 408 | 608 | 108 | 78 | 188 | 178 | 178 | 178 | 178 | 212 | 80
Corrective Maintenance | Trended Maintenance @ 50% | 384 |  |  |  | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 40 | 384
0
NON-MAINTENANCE | APPOINTMENT | [13 empty] | 0
NON-MAINTENANCE | AWAY ON BUSINESS (AOB) | 32 | 8 |  |  | 8 |  |  | 8 |  |  |  |  | 8 | 32
NON-MAINTENANCE | BEREAVEMENT | 32 |  | 8 |  |  | 8 |  |  | 8 |  |  | 8 |  | 32
NON-MAINTENANCE | FAMILY COMPASSIONATE LEAVE | 32 |  |  | 8 |  |  | 8 |  |  |  | 8 |  | 8 | 32
NON-MAINTENANCE | VOLUNTEER TIME | [13 empty] | 0
NON-MAINTENANCE | Stand By | [13 empty] | 0
NON-MAINTENANCE | Transportation | [13 empty] | 0
NON-MAINTENANCE | Vehicle Inspection | 220 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 220
NON-MAINTENANCE | Storm Assistance | 32 | [11 empty] | 32 | 32
Total NM |  |  | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 20 | 28 | 28 | 48 | 348
Training | Metering | 160 |  | 80 | [8 empty] | 80
Training | Hot Line Refresher Training | [13 empty] | 0
Training | TDG/WHMIS | 32 |  |  |  | 32 | [8 empty] | 32
Training | Safety Meetings 12/year 2hours | 96 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96
Training | First Aid/CPR 8hr | 32 |  | 32 | [10 empty] | 32
Training | First Aid 2 day 8hr | [13 empty] | 0
Training | Pole Top Rescue 5hr May | 20 |  |  |  |  | 20 | [7 empty] | 20
Training | Fall Arrest 4hrs | 16 |  |  | 16 | [9 empty] | 16
Training | Work Protection Code 4hr | [13 empty] | 0
Training | Safety Rule Book 8hr | [13 empty] | 0
Training | Arc Flash Training 4hrs | 16 |  | 16 | [10 empty] | 16
Training | Rigging/Slinging 4hr | [13 empty] | 0
Training | Confined Space 8hr | [13 empty] | 0
Training | Emergency Response training 2hrs | [13 empty] | 0
Training | Fire Extinguisher 2hr | [13 empty] | 0
Training | Work Methods, SOP's | [13 empty] | 0
Training | EMS 8hr | 32 | [11 empty] | 32 | 32
Training | PPE Refresher 2hr | 8 | [11 empty] | 8 | 8
Training | Flu Shots and Wellness 1 hr | [13 empty] | 0
Training | EMS Awareness 2hr | 8 | [11 empty] | 8 | 8
Training | PPE Refresher 2hr | 8 | [11 empty] | 8 | 8
Training | Flu Shots and Wellness 1 hr | 4 | [11 empty] | 4 | 4
Total Training |  |  | 8 | 136 | 24 | 40 | 28 | 8 | 8 | 8 | 8 | 8 | 88 | 68 | 432
Vacation/Sick | Vacation/Sick | 812 | 61 | 61 | 61 | 61 | 16 | 40 | 40 | 40 | 40 | 140 | 132 | 120 | 812
|  | 9131 | 1369 | 1225 | 1401 | 1166 | 1297 | 1601 | 1511 | 1483 | 1245 | 1245 | 1381 | 702

## Working DayHours
|  | January | February | March | April | May | June | July | August | September | October | November | December
BUDGET | Working Days | 21 | 20 | 22 | 21 | 22 | 21 | 22 | 21 | 22 | 22 | 21 | 22 | 257
| Working Hours | 672 | 640 | 704 | 704 | 672 | 672 | 704 | 672 | 704 | 704 | 672 | 704 | 8224
ACTUAL | Working Days | 21 | 20 | 22 | 22 | 21 | 22 | 24 | 21 | 22 | 22 | 21 | 23 | 261
| Working Hours | [12 empty] | 0