## Table #3(d) - Total
IR #3(d)
Sub-account | Project Cost Category | Budget - As Stated in Application | Incurred prior to September 2008 | Incurred October 2008 to October 22, 2010 | Incurred October 23, 2010 to September 7, 2015 | Incurred September 8, 2015 to August 26, 2016 | Incurred August 27, 2016 to October 31, 2016 | Total Costs Incurred | Percentage Incurred Through October 31, 2016 | Percentage Forecasted to be Spent by Filing LTC | Total Project Budget
1 | Engineering, design and procurement activity costs | $20M | 0 | 5250 | 1665297.6665 | 134708.9223 | 52525.6641 | 1857782.253 | 9% | 31% | 19925278.45
2 | Permitting and licensing costs | part of $14M | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1850000
3 | Environmental and regulatory approvals costs, including costs of mitigating project impacts | $10M | 0 | 0 | 3077217.5439 | 848979.3164 | 370157.2726 | 4296354.1329 | 51% | 84% | 8467121.27
4 | Land rights acquisition costs and landowner engagement/negotiation costs (excluding Aboriginal Engagement costs) | part of $14M | 0 | 0 | 40000 | 28673.62 | 3521.72 | 72195.34 | 7% | 27% | 985000
5 | Aboriginal engagement and communication | part of $18M | 0 | 213170.865 | 1457010.3795 | 657192.3826 | 45850.054 | 2373223.6811 | 51% | 77% | 4654955
6 | Community and other stakeholder engagement costs (excluding landowner and Aboriginal engagement costs) | part of $14M | 0 | 3274.95 | 708916.96 | 377420.0352 | 66863.2199 | 1156475.1651 | 48% | 66% | 2425277.52
7 | Costs for regulatory activities and filings, including legal support | part of $14M | 0 | 4501.2 | 457021.5167 | 105786.6616 | 50665.6229 | 617975.0012 | 36% | 82% | 1724760
8 | Interconnection study costs | included in Sub-account 1 | 0 | 0 | 0 | 53361.1041 | 0 | 53361.1041 | 17% | 38% | 323361.1
9 | Accounting, administration and project management costs | $8M | 0 | 671463.1367 | 4089838.5803 | 1790008.1664 | 313948.7165 | 6865258.5999 | 63% | 73% | 10960200
10 | Aboriginal land-related costs | part of $18M | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 46% | 710000
11 | Aboriginal participation, mitigation of project impact and local distribution planning | part of $18M | 0 | 216296.905 | 980003.7295 | 913980.9302 | 5437.5 | 2115719.0647 | 15% | 38% | 13684809
12 | Contingency costs incurred in excess of budgeted costs | part of $14M | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 3498198.7308
13 | Development activity costs not reflected in other sub-accounts | part of $14M | 0 | 2251 | 471716 | 7478.0605 | 0 | 481445.0605 | 50% | 97% | 957478.06
14 | Start-up costs (partnership formation) | $7M | 0 | 0 | 2713133.07 | 958685.06 | 353.85 | 3672171.98 | 57% | 89% | 6394457
Grand Total |  | $77M | 0 | 1116208.0567 | 15660155.4464 | 5876274.2593 | 909323.6202 | 23561961.3825 | 31% | 54% | 76560896.1308