REDACTED

PUBLIC

ONTARIO ENERGY BOARD

| FILE NO.: | EB-2016-0152 | Ontario Power Generation Inc. |
| --- | --- | --- |
| VOLUME: DATE: BEFORE: | 2 February 28, 2017 Christine Long Ellen Fry Cathy Spoel | REDACTED - PUBLIC Presiding Member and Vice-Chair Member Member |

EB-2016-0152

THE ONTARIO ENERGY BOARD

Ontario Power Generation Inc.

Application for payment amounts for the period from

January 1, 2017 to December 31, 2021

Hearing held at 2300 Yonge Street,

25th Floor, Toronto, Ontario,

on Tuesday, February 28, 2017,

commencing at 9:33 a.m.

----------------------------------------

VOLUME 2

----------------------------------------

BEFORE:

CHRISTINE LONG			Presiding Member and Vice-Chair

ELLEN FRY				Member

CATHY SPOEL			Member

MICHAEL MILLAR	Board Counsel

IAN RICHLER

VIOLET BINETTE	Board Staff

LAWRIE GLUCK

JANE SCOTT

RUDRA MUKHERJI

CHARLES KEIZER	Ontario Power Generation Inc.

CRAWFORD SMITH	(OPG)

BARBARA REUBER

JOHN BEAUCHAMP

CHRIS FRALICK

IAN MONDROW	Association of Major Power

SHELLEY GRICE 	Consumers of Ontario (AMPCO)

VINCE DeROSE	Canadian Manufacturers & Exporters (CME)

MICHAEL BUONAGURO	Consumers Council of Canada (CCC)

JULIE GIRVAN

BRADY YAUCH	Energy Probe Research Foundation

LARRY SCHWARTZ

KENT ELSON	Environmental Defence (ED)

DAVID POCH	Green Energy Coalition (GEC)

SCOTT WALKER	Ontario Association of Physical Plant Administrators (OAPPA)

RICHARD STEPHENSON	Power Workers' Union (PWU)

MIKE McLEOD	Quinte Manufacturers' Association

MARK RUBENSTEIN	School Energy Coalition (SEC)

JAY SHEPHERD

BOHDAN DUMKA	Society of Energy Professionals (SEP)

RON TOLMIE	Sustainability Journal

MICHAEL JANIGAN	Vulnerable Energy Consumers Coalition

--- On commencing at 9:33 a.m.	1

Preliminary Matters	1

ONTARIO POWER GENERATION - PANEL 1A, Resumed	2

J. Lyash, D. Reiner, Previously Affirmed

Cross-Examination by Mr. Mondrow	2

--- Recess taken at 11:19 a.m.	66

--- On resuming at 11:40 a.m.	66

Cross-Examination by Mr. McLeod	89

Cross-Examination by Mr. DeRose	96

Cross-Examination by Mr. Janigan	109

### --- Luncheon recess taken at 12:49 p.m.	109

### --- On resuming at 1:58 p.m.	109

Cross-Examination By Mr. Tolmie	132

Cross-Examination by Mr. Elson	146

--- Recess taken at 3:37 p.m.	165

--- On resuming at 3:55 p.m.	165

Questions by the Board	165

ONTARIO POWER GENERATION - PANEL 1B	177

L. Saagi, G. Rose, Affirmed;

D. Reiner, Previously Affirmed

Examination-in-Chief by Mr. Keizer	177

--- On commencing in camera at 4:27 p.m.	182

Cross-Examination by Mr. DeRose	182

--- On resuming public session at 4:59 p.m.	202

Procedural Matters	202

--- Whereupon the hearing adjourned at 5:00 p.m.	203

Exhibit No. K2.1:  VECC compendium	109

Exhibit No. K2.2:  Environment Defence compendium	146

Undertaking No. J2.1:  To advise how much of the $2.2 billion has already been approved by the Ontario Energy Board for recovery	5

Undertaking No. J2.2:  To advise re the working schedule, what P level does that working schedule correspond to	17

Undertaking No. J2.3:  To determine the revenue-requirement impact moving from a p90 to a p50 in this application	29

Undertaking No. J2.4:  To advise precisely where in the evidence there is an expert that says P90 is an appropriate allocation	33

Undertaking No. J2.5:  To advise whether the government was provided with a specific unit 2 number in addition to the total DRP number	36

Undertaking No. J2.6:  To provide a final in-service date updated and an updated column H, 2016 actuals for the projects that are in-service	45

Undertaking No. J2.7:  To advise what the major changes of scope were in the project between January 2016 and today	62

Undertaking No. J2.8:  To advise where the hockey stick contingency curve is in the evidence	68

Undertaking No. J2.9:  To provide a full list of those projects that will have use beyond the unit 2 refurbishment but that are being charged to rates or close to rate base at the same time as the unit 2 expenditures are being close to rate base in 2020	76

Undertaking No. J2.10:  To provide an updated status report once it's provided to the board	83

Tuesday, February 28, 2017

### --- On commencing at 9:33 a.m.

MS. LONG:  Good morning, everyone.  Please be seated.

Mr. Keizer, are there any preliminary matters?

# Preliminary Matters:

MR. KEIZER:  Yeah, there actually are two preliminary matters.  The first relates to the undertakings.  You may recall yesterday there were three documents that OPG agreed to disclose before the appearance of panel 1B, and there was concerns about their confidential status.

So what we have done this morning is distributed to people in the hearing room that had signed the undertaking by giving them full copies of the documents in confidence in sealed envelopes.  So they have them.

We are working on the redactions, and so we hope to be in a position to file redacted copies with the Board tomorrow along with, in sealed envelopes, according to protocols, the unredacted version.  So that would be formally filed.

But the parties that did need them for purposes of preparation, I believe, do have them, and if they don't, they can speak to us at the break to make sure that they have received the appropriate documents.

MS. LONG:  And do you have a copy for the Panel?

MR. KEIZER:  Yes, we did provide that this morning as well --

MS. LONG:  Thank you.

MR. KEIZER:  -- so you have that.

That's the first preliminary matter.

The second is, yesterday during cross, I believe, by Mr. Poch, and I also believe by Mr. Yauch from Energy Probe, there were two questions which prompted the view that they were best answered by the regulatory panel, which, just to clarify whether that's panel 2 or panel 5, our view is, based on the questions, that panel 5 is best appropriate to deal with the questions that were asked, and we just want it to be clear so that people could deal with that accordingly.

I believe Mr. Poch's questions related to the issues of prudence and I think Energy Probe related to the CRVA.

MS. LONG:  Mr. Poch, you have taken to note of that?

MR. POCH:  I have, thank you.

MS. LONG:  Okay.

MR. KEIZER:  But, other than that, I have no other preliminary matters.

MS. LONG:  Any other matters, Mr. Richler?

MR. RICHLER:  No.

MS. LONG:  Okay.  Then we will start with you, Mr. Mondrow.

# ONTARIO POWER GENERATION - PANEL 1A, Resumed

Mr. J. Lyash,

Mr. D. Reiner; Previously Affirmed.

# Cross-Examination by Mr. Mondrow:

MR. MONDROW:  Good morning, Madam Chair.  Thank you.

Good morning, gentlemen.  As you know, I'm counsel for AMPCO on this matter and, in particular, in respect of the DRP, which is what you're here to talk about, so I look forward to our conversation.

I want to start with you this morning to talk a little bit about the planning process for the DRP, and I've been struck, I must say -- I'm a relatively late arrival to this proceeding, but I've been struck over the last few weeks trying to catch up to all of you on the amount of evidence dedicated to describing the planning and the project control processes, and I know, Mr. Lyash, you talked about that yesterday.

And so I just want to start on that topic, and just to set the context for that, I would like to ask you to turn to Exhibit D2, tab 2, schedule 4 of your prefiled evidence, and starting at page 1, under the overview section, I'm just going to read this to you.  It says right upfront:

"To ensure successful execution of the Darlington refurbishment program, OPG made a major investment in planning during the definition phase.  This has enabled OPG to establish detailed scope and a high-confidence schedule and cost estimate, thereby minimizing the risk of scope creep, schedule delays, and resulting increases in cost."

And this exhibit, it says, goes on to describe that extensive planning effort.

And in the very next subsection, the Subsection 2.1 of this document is headed "Investment in Planning," and I won't read this all to you, but I just want to make sure that we have the road map for the planning activities.  And this first paragraph under Section 2.1 tells us, I believe, that the first phase of planning, the initiation phase, started about ten years ago in 2007 and ran until 2009, and it was a preliminary assessment of the feasibility of DRP, and it got Board approval, as I understand it, at the end of 2009.

Mr. Reiner, that's correct?

MR. REINER:  Yes, that's correct.

MR. MONDROW:  And then we moved to -- well, you moved to the definition phase, and that was about five years long, and than ran from 2010 to 2015, and if I'm not mistaken, the culmination of that phase would have been the release quality estimate, or the RQE that's been discussed, that was approved in December 2015, I believe.

MR. REINER:  That's correct.

MR. MONDROW:  And then, if we look at line 23, still on this page 1 of this planning evidence, there is a note that the life-to-date expenditures to the end of 2015 includes extensive planning work carried out during the initiation phase and definition phase, and there's a number quoted of $2.2 billion inclusive of interest and escalation.

Do we have somewhere on the record in this proceeding how much of that $2.2 billion has already been approved by the Ontario Energy Board for recovery?  Do you know?

MR. REINER:  I believe that is -- that is in --

MR. MILLAR:  Microphone.

MR. REINER:  I believe that is in evidence.  I would have to get back to you on exactly where you can find that, but I believe that has been included, yes.

MR. MONDROW:  That would be appreciated.  And I'm hoping that that evidence also has both the amounts and the dockets, the OEB dockets, in which those amounts were approved.  So I'm happy to leave that with you.  Maybe we'll get an undertaking just to track it.  And if the dockets aren't there, if someone could add those, that would be appreciated, but my expectation is that it is there.  I just haven't been able to locate it.  So that would be great.

MR. RICHLER:  That would be Undertaking J2.1.

Undertaking No. J2.1:  To advise how much of the $2.2 billion has already been approved by the Ontario Energy Board for recovery

MR. MONDROW:  Thank you, Mr. Reiner.  And then the amount of the 2.2 billion that's not covered by that undertaking that you're going to provide is being sought for recovery, of course, in this application.

MR. REINER:  Yes.

MR. MONDROW:  So that will bring us up to date.

And if we just stay in this Exhibit D2, tab 2, schedule 4 and we look at page 2, there's a figure here.  It's at one of these built-up bar graphs, Figure 1, and it provides a summary of life-to-date, definition-phase spending to December 2015 in billions of dollars, and I just want to spend a minute with these various items.  And what I'm trying to understand, gentlemen, is which of these items are kind of squarely planning expenditures and which are actual program expenditures.  So -- and what I'm trying to do is establish an understanding of how much you spent in order to really get your collective heads around this project and what's going to be required, which is the basis for your confidence that you're going to be able to execute it to budget and/or under budget and on time.

So if we look at the first bar, the RFR mock-up and tooling, it seems to me that that would have legitimately been a preparatory step to allow you to properly plan the execution of the project.  Would that be fair?

MR. REINER:  Yes, that's correct.  Part of our planning effort was about ensuring that we can do the necessary training that's required to execute the work and, also, in terms of establishing the fidelity that we need in the execution schedule.  That was a key contributor to establishing that schedule.

MR. MONDROW:  Okay.  And then the next item, the turbine generator parts, is that actually just a pre-order of parts that you would need, that you are going to be needing, or will need as you proceed through execution, rather than preparation investment?

MR. REINER:  It's a combination.  There are some included in this phase.  Our expenditures associated with long lead materials, so materials that need to be ordered well in advance because of the lead time that's required.  But there is also an element in this associated with what specifically is required in terms of parts to actually execute the scope of work.

MR. MONDROW:  That's a good distinction.  Thank you, Mr. Reiner.  So I gather that, unless there was a long lead time or some availability risk with the parts, you wouldn't order them farther in advance than you needed to, so if you pre-ordered them this far in advance, you wanted to be sure that you had them when needed.

MR. REINER:  Yeah.  That's correct.  The general philosophy that we built into the planning and one that is, again, based on a key lesson learned, one of the things that have caused prior refurbishments to go beyond their scheduled duration is the availability of parts for execution.

So we established a mechanism to ensure that we have a minimum window.  In general, we selected six months as the window.  Our goal was to have parts available on-site six months prior to the requirement for installation.  And then when you work backwards from that and you look at manufacturing time and all the lead times, engineering associated with fabricating certain parts, that determines the schedule by which you then begin the order process.

MR. MONDROW:  Thank you.  The next part, the $500 million in vendor/EPC definition-phase planning, clearly that's a straight planning investment?

MR. REINER:  That's a straight planning cost, yes.

MR. MONDROW:  Then we have the next two bars, and we're going to come back to these, and others have talked to you about these two categories of projects, the facility, the infrastructure, and the safety improvement.  Those are projects that, as I understand it, you determined needed to be done early, prior to the start of the unit 2 refurbishment.  But not they're not necessarily planning investments.  Is that a --

MR. REINER:  So there is a planning element in the facility and infrastructure project.  So, for example, what we needed to ensure is that, as the construction workforces arrive at site, we have an efficient flow in and out of the site so that we don't impact productivity during execution and that we also do not disrupt the operations of the power plant.  So there's a very clear segregation between operation staff that have to make their way in and out of the site versus the workforces that will come in to do the construction work.  So there was a significant amount of work related to this that went into the design and establishment of that infrastructure that ensured that we could productive execute that field construction work.

I'll just add that, on the safety improvements themselves, as part of our environmental assessment and the integrated implementation plan, we talked previously at the last hearing about the Canadian Nuclear Safety Commission regulatory requirements associated with extending the life a of a nuclear plant.  There are a series of safety enhancements that were required in order to provide us the licence to operate the plant in its second life, and those safety improvements are associated with that element of the project.

MR. MONDROW:  That's very helpful.  Thank you.

Then we've got the $400 million, obviously, again, strictly a definition-phase and planning investment there?

MR. REINER:  Yes.  And that is the OPG-related cost.  The previous one, the vendor/EPC, that's the contractor cost.

MR. MONDROW:  And then we've got interest, and we total it up.  So that's helpful.  Thank you.

That brings us to the filing date of this evidence, which was May, the end of May 2016.  And then breaker opening was, as I recall -- October 15th, I think, was the auspicious date.

MR. REINER:  That is correct.

MR. MONDROW:  And you talked about that yesterday, and that's formally the start of the execution phase?

MR. REINER:  That is where unit 2 gets disconnected from the power grid, and we begin to shut down unit 2 and essentially start the critical path for execution of unit 2.

MR. MONDROW:  And do you continue, or have you continued planning expenditures between the breaker open and today?

MR. REINER:  Yes.  There are still some outstanding definition-phase, planning-related items, and those will carry on in 2017.  There are still some project milestones related to definition-phase work that are still in the process of being completed, and they tie primarily to the retube and feeder replacement project work.

MR. MONDROW:  So are those costs in addition to the 2.2 billion figure that's provided here in the evidence?

MR. REINER:  They would be in addition.  The 2.2 here, I believe, are actual life-to-date costs, so these have not been incurred yet.  They would be in addition to.

MR. MONDROW:  Could you -- not necessarily on the spot, but could you tell us, by way of undertaking, if it's easier, how much more cost is in this category of planning so that we can get a full picture of the planning investment?

MR. REINER:  Maybe, if I may, we could take that question in panel 1B, because we will have additional resources there that can get into the details of the numbers, and we can likely answer your question.

MR. MONDROW:  That's fine.  I've marked it down, so I'll come back to you on that.  Thank you.

So with all that, Mr. Lyash, on a scale of one to ten, how -- ten being the most prepared, how prepared is OPG for this project?

MR. LYASH:  I'm not going to use the scale of one to ten, because it's an arbitrary --

MR. MONDROW:  Well, you have to.  That's the rule.  Didn't anyone tell you about the rule?

MR. LYASH:  In that case, can you please define numbers one through ten, the critical attributes that I can use as the --

MR. MONDROW:  Fair enough.  However you want to answer the question.

MR. LYASH:  I think the preparations were very well done.  If I compare it to my personal experience, this is as robust a planning and preparation activity as I've seen for a project of this nature.  But probably more importantly, the assessments that we've had done all the way through, whether those were by outside parties or our own internal audits, which I view as having been very aggressive and very critical, give me confidence that we're well prepared to undertake this.

MR. MONDROW:  I would define that as a ten, just for your reference.  But I'm not giving evidence here.

MR. LYASH:  I'll cede to your judgment.

MR. MONDROW:  Thank you very much.  And all of that gives you confidence, Mr. Lyash -- and you said this a few times yesterday -- that you will be able to complete -- OPG will be able to complete the DRP on time and within budget?

MR. LYASH:  Yes.  That is not to ignore the fact that the projects are very difficult and carry significant risk, so very challenging, but I think the company is well positioned at the outset to execute.

MR. MONDROW:  All right.  And I will come back to some of those challenges.  I know you've talked about it, and I will try not to repeat that.  But I will have some areas to discuss with you in a few minutes.

But if I asked that same question about your confidence level but asked you to assume that you didn't have the P90 contingency for cost and schedule, what would your confidence level be in that scenario?

MR. LYASH:  I'm sorry.  Can you ask that again?  I didn't hear the first part of the question.

MR. MONDROW:  If I asked you the same question, how confident are you that you can complete on time and under budget, but didn't have a P90 schedule and budget; you had your planning schedule and budget, how confident would you be in that case?

MR. LYASH:  I'm not sure what you're referring to as the planning schedule.

MR. MONDROW:  Mr. Reiner talked about that yesterday actually.

MR. LYASH:  The planning schedule?

MR. MONDROW:  The schedule you're actually working to.

MR. LYASH:  Oh, the working schedule.

MR. MONDROW:  I'm sorry.  I misspoke.  Let's call it the working schedule.

MR. LYASH:  As we discussed yesterday, there is risk in any project, and risk has to be managed as part of the project, so schedule and cost contingency, a very active risk management program.

My confidence has, in part, to do with the aggregate of all that upfront work, the preparation, the development of the cost and the schedule, the risk register.  In selecting what kind of contingency to apply to that, one implied by a P50 or a P90, I think you have to make some additional judgment to select the right one to provide the requisite level of confidence.

In this case, I think P90 is the right selection.  I think that, as you move away from that to some lower probability, you are, by its nature, reducing your confidence in your ability to execute.  And so the farther you move from what we think is the right balance point, P90, from that point in a lowering direction -- say P50 or P25 -- the less likely you are to be successful.

We chose a working schedule that is more aggressive than P90, which I believe is an industry best practice, for a few reasons.  One is such that, if risks aren't realized, you can take advantage of that pull forward in schedule as you work your way through so that you can keep the project moving toward an early conclusion.

The other is so that you can measure project performance against a more aggressive set of objectives and, by doing that, have earlier indications of performance or productivity issues and a more straightforward approach to mitigating them before they impinge on the high-confidence schedule.

MR. MONDROW:  Let me pick up on a couple things I think you've said, Mr. Lyash.  You said you chose a working schedule that was more aggressive than the P90 schedule.  Does that mean you developed a P90 schedule first and then worked back and developed a working schedule from that?

MR. LYASH:  The schedule development question, the details on that, are probably better for panel 1B.

MR. MONDROW:  But you've got overall responsibility for this project; you signed off on a schedule, a working schedule.  Is it your understanding that working schedule was a back-cast from a P90 schedule?  Is that how it worked?

MR. REINER:  It is not a back-cast.  It's actually the opposite.  So the methodology that was used to develop the schedules, in fact, we took efforts to build it up from a P0, a zero-risk perspective, and then build it up from there.

Now, that is a very difficult thing to do, and so I wouldn't call it precisely that.  In the working schedule currently, I mean, there is the work done by the contractors; there is a 50 percent confidence associated with the risks that the contractors carry inside that working schedule.

So it is a bottom-up where we land on a working schedule, and then we do a risk analysis of all the things that could go wrong on that working schedule to determine what additional amount of time do we need to carry in contingency to mitigate those risks and based on a probabilistic assessment.  So it is that calculation that then gets you to the P90.

MR. MONDROW:  Right.  I understand.

So, Mr. Lyash, with that colour, and if your answer to my first -- the first time I asked about your confidence, and you described how confident you are, if that's a ten, without the P90, if you move back to a P50, does that mean you're about -- between one and ten, you're at a five for confidence that you can do this under budget and on schedule?

MR. LYASH:  Well, I think the working schedule is certainly possible to achieve, but significantly less likely to achieve than the working schedule plus the schedule contingency, which is the P90.

MR. MONDROW:  Okay.  So, Mr. Reiner, a P50 schedule, as I understand it, means that the odds are about fifty-fifty that you'll come in under schedule, at a high level.

MR. REINER:  Mathematically, a P50 suggests that, yeah, it's a roll of the dice.  You might be ahead of schedule; you might be behind schedule, and it's equal probability.

MR. MONDROW:  And is that your working schedule?  Is that a P50 schedule?

MR. REINER:  The working schedule is not a P50 schedule.  If -- it actually lands -- so the working schedule, given it's a bottom-up assessment of, if everything went correctly exactly as planned, how long would it take to execute that schedule.  There are, as I said, elements of risk for contractor work that are in there, but there is no risk -- there's a significant amount of OPG work in this schedule as well, for example, about a year of the critical path rests with OPG, the front end, to do the defuelling and all the interfaces associated with islanding the unit and, on the back end, bringing the unit back in-service.

So all of the risks associated with that sit in the P90, so there a combination in the working schedule.  If I were to align it with a probability level, it is something less than a P50.

MR. MONDROW:  Okay.  You produced -- and I'm sorry I don't have the number with me, but I saw it last night.  There is an interrogatory response that describes a calculation that the Monte Carlo simulation that was used for this probability analysis produced schedules and cost levels at -- right from 1 to 99 along a curve.

So I'm assuming you know what your working schedule is.  I'm assuming that you could tell us what P50 or what P -- sorry, what P level that working schedule corresponds with.  Could you do that?  Not necessarily on the spot, but can that be done?

MR. REINER:  I'd have to take that back to have a look if that could be done.

MR. MONDROW:  Could you do that, both for schedule and cost?

MR. RICHLER:  We'll call that J2 point --

MR. MONDROW:  Well, that's fine.  So the undertaking will be to -- let me be clear, because I just said schedule and cost, and cost isn't actually relevant to this question.  So you've got a working schedule, and my question is:  What P level does that working schedule correspond to?  And you've undertaken to (a) see if you can give me that number, and if you can, you'll give me the number.  Is that -- that's appropriate?

MR. REINER:  Yeah, that's fine.

MR. MONDROW:  Okay.  Thanks.

MR. RICHLER:  J2.2.

MS. LONG:  J2.2?

Undertaking No. J2.2:  To advise re the working schedule, what P level does that working schedule correspond to

MR. MONDROW:  So, Mr. Reiner, I assume my next question here is P50, what you actually planned to spend, and based on your previous answer, I think you're going to say, no, that's not exactly right.  P50 is not what you actually planned to spend.

MR. REINER:  What we planned to do is execute the project within the high-confidence estimate.  And that is why currently we're still forecasting that the cost at completion of unit 2 is going to be 4.8 billion and the cost of completion of the four units is going to be $12.8 billion.  And, at this stage, it's too early for us to determine whether we are going to -- there hasn't been enough time yet expended in execution to know whether that -- there is a risk there.  We don't see that.

Certainly, in the early execution, we were ahead of the working schedule in defuelling; and in bulkhead installation, we were behind, slightly behind, the allotted time for doing that work.  So, in aggregate, we're roughly on the working schedule currently.  But it is still very early days at this stage.

MR. MONDROW:  You've got a working schedule.  Have you got a working budget?

MR. REINER:  There is only one budget.  It's the budget that was released to the project as part of the unit 2 execution estimate.

MR. MONDROW:  That's the P90 budget?

MR. REINER:  That's the P90 budget, yes.  And the way it is segregated is there are elements of that that are held in contingency that are not budgeted for projects, and then there is an element that is budgeted for project work that is held by the project management team.

MR. MONDROW:  If I took -- and the contingency portions of those budgets are -- and we're going to come back to this, but they're pretty clear on the evidence.  So if I took the budget for unit 2 and I took out the contingency line item for unit 2, would I get a number that you are at least as likely to come in under as you are to come in over?

MR. REINER:  No, you would not.

MR. MONDROW:  Why not?

MR. REINER:  You would not, because the -- so the budget -- the baseline budget would be associated with that -- the budget without contingency would be associated to the schedule without contingency.

MR. MONDROW:  Right.

MR. REINER:  Which is -- which is, as I indicated earlier, you know, we will see if we can come up with a probability level for that, but it is less than P50.

MR. MONDROW:  Okay.  So, when you do that, could you give us a budget associated with that schedule?

MR. REINER:  So we'll look to see if we can actually do that.  This is sort of a backwards derivation of a schedule that was built from the bottom up.  We will see if we can do that.

MR. MONDROW:  What is your working schedule for unit 2?

MR. REINER:  In terms of?

MR. MONDROW:  For unit 2, for completion of unit 2.

MR. REINER:  Completion of unit 2?  It's 35 months, 1,071 days.

MR. MONDROW:  And your P90 is 40 months; right?

MR. REINER:  And the P90 is 40 months.

MR. MONDROW:  So can we just add to Undertaking J2.2 that, if you can derive a P50 schedule, you will also consider and, if possible, provide a budget associated with that schedule?  Is that okay?

MR. REINER:  So just --

MS. LONG:  I'm not sure I understand, Mr. Mondrow.  You've lost me a little bit.  So you're asking him to take the contingency out, and so contingency on schedule and contingency on budget out, and that's what you're interested in?

MR. MONDROW:  I'm interested in -- kind of.

MS. LONG:  Maybe you can --

MR. MONDROW:  That's perhaps a clear way to put it, but let me see if I can come at this from the other side of the question.

Mr. Reiner, we've been talking about a -- I've been trying to determine a schedule that you're at least as likely to come in under as over, so your actual expectation, in my language.  And I'm also trying to determine whether there is a budget like that that you are at least as likely to come in under as you are over, all in respect of unit 2.

MR. REINER:  So just -- maybe I'll repeat back, and you can tell me if I've got it.  You are looking for a P50 schedule and a P50 cost estimate for unit 2?

MR. MONDROW:  Yes, let's do that.

MR. REINER:  Okay.  So we'll take that back and see if we can do that.  At this point, I couldn't tell you how much work that that would require.  There is no P50 schedule.  There is a working schedule and a P90 schedule, and the working schedule is less than the P50 probability.  So what you're looking for to us derive is what would a 50 percent probability schedule look like.

MR. MONDROW:  If it's easier, let's look at it this way:  You have a working schedule; you have a P90 schedule.

MR. REINER:  Yes.

MR. MONDROW:  You have a P90 budget.

MR. REINER:   Yes.

MR. MONDROW:  Can you give me a budget associated with the working schedule?  That may be easier.

MR. REINER:  Okay.

MR. MONDROW:  Why don't we amend undertaking J2.2, Madam Chair, if that's okay with you?  That sounds like the most straightforward exercise and perhaps more relevant to your deliberations.

MS. LONG:  But that would not be a P50 schedule, as I understand it.

MR. MONDROW:  It would not.

MS. LONG:  I think what you're saying to me is that it would be less than P50, if you backed out contingency, timing, and contingency cost.

MR. MONDROW:  Maybe, Mr. Reiner, just to complete this analysis, or what I'm trying to analyze, if you could add  -- if it's possible without too much work, to add the P level to the working schedule in the response.  That would be helpful so that we can understand how far off it is from a P50.

MR. REINER:  I think that was your question in the previous undertaking.

MR. MONDROW:  It was.  So we can do this all under J2.2, now that I've clarified it with your assistance.

MS. LONG:  Are you clear on that, Mr. Reiner?  Mr. Keizer?

MR. KEIZER:  I just want to make sure that we have it.  So we're determining what P level the working schedule is and what cost level is --

MR. MONDROW:  Associated with the working schedule.

MR. KEIZER:  And that's it?

MR. MONDROW:  Let's do that.  That would be fine for me.

MS. LONG:  Okay.  So that's the amended J2.2.

MR. MONDROW:  Thank you for your assistance, Madam Chair.

Now, Mr. Lyash, if you obtain approval from this Hearing Panel for the test period payment amounts that you're requesting, which is at a P90 contingency level, as I understand it, and then you ultimately come in under budget on unit 2, I think you said yesterday the difference between the approved revenue requirement and your actual expenditure in respect of the unit 2 refurbishment and your actual expenditure on the unit 2 refurbishment would go in the CRVA for disposition, and ultimately back to ratepayers.  Is that right?

MR. LYASH:  That's correct.

MR. MONDROW:  In that scenario, you will have, by definition, overcollected during the test period; right?

MR. LYASH:  Yes, I would assume so.

MR. MONDROW:  And, indeed, with a P90 contingency level, that's the likely result, isn't it?  That's 90 percent probable?

MR. LYASH:  First of all, I'm not sure how the CRVA will be cleared or when.  So with respect to how that plays out in the particular test period, I can't say.

The P90, I think we have to always keep this in a broader context.  We have done our best and used the best available tools and expert judgment to build a model of probability and risk whose purpose it is to identify and manage those risks very actively all the way through the project to produce the best possible result.

The output of that, we call P90; that's what the tool produces.  But the project considerations are larger than that.  And so there is a significant amount of judgment to be applied, and the selection of what the appropriate basis for the project is depends on the nature of the project.  A very short-duration project, fairly straightforward, you may select as the planning basis a much lower model output as a reasonable measure of success, because it's unlikely that unanticipated complexities will arise.  It's unlikely that the passage of longer period of time would create issues.

And so my personal view is that, while the output of the tool is a P90, I wouldn't say that, in the end, the project result would be less than that nine out of ten times, because to do so would be to ignore all the other factors we have to manage.  And I think this is shown true particularly on megaprojects where the selection of a less conservative planning basis contributes to a delta in performance.

MR. MONDROW:  P90, Mr. Lyash, there is a 90 percent probability you are going to come in under budget; right?  By definition, that's what P90 means?

MR. REINER:  May I make a comment?

MR. MONDROW:  I would like an answer first, and then you can expand on it.

MR. LYASH:  With respect to the Monte Carlo analysis and that element of our project planning, yes.

MR. MONDROW:  So the odds are you're going to overcollect in the test period?  There is no other possible mathematical result than to answer yes to that question?

MR. REINER:  I'm going to --

MR. MONDROW:  Sorry, but I think Mr. Lyash is about to acknowledge that, mathematically, that is correct.

MR. KEIZER:  When you say overcollect in the test period, the evidence is that, if you come under, it gets recorded in the CRVA.  So I think there is, and I'm not -- I think if there's questions about how that CRVA amount gets calculated and the recovery of the revenue requirement over the period that's attributable to the ratepayer as a result of coming in under, I don't necessarily believe that you can assert that there is a full overcollection.

So you can ask your question, but you may also want to raise the question with respect to the CRVA with the appropriate panel to ensure the record is clear as to what the implications are in clearing that account and the treatment of the ratepayer.

MR. MONDROW:  Thank you, Mr. Keizer.  You've given Mr. Lyash some time to think about his answer.  But that's not what I asked.  I asked about collection.  We both know that putting overcollection in a variance account and refunding it has nothing to do with how much you collect.

Mr. Lyash, during the test period, odds are you're going to overcollect if you get the approvals you've asked for, by definition?

MR. LYASH:  I don't agree.

MR. MONDROW:  Why don't you tell me why you don't agree with that?

MR. LYASH:  First, as I've said, this risk modelling in the Monte Carlo is one of a number of elements of how you think about planning and executing the project.  But even if I just focus on this analysis and the P90 output, that is a result that was created on a four-unit basis, not on a single-unit basis.  That is a four-unit Monte Carlo analysis.

Secondly, risks aren't realized in the probability or percentages that are calculated in the model.  Any particular risk is given a probability and then a consequence, and the sum of those is placed into the contingencies.  Risks don't occur in pieces or percentages; they occur in whole.  And when they occur in whole, they bring the entirety of that cost with them.  And so it is -- while the tool is very useful, because it's a four-unit analysis and because risks occur in large chunks, not in percentages, I don't agree that you can use the P90 Monte Carlo analysis all by itself to extend to the notion that the project will be under budget 90 percent of the time for a single unit.

MR. MONDROW:  I appreciate your answer.  I respect that answer.

You allocated 40 percent of your DRP contingency to unit 2; right?

MR. LYASH:  Correct.

MR. MONDROW:  And you're telling me now that you do not expect to come in under budget on unit 2 at P90?

MR. LYASH:  My expectation is to hit the P90.  I would be very happy if we come in under budget, and I would be very pleased if those funds accumulate into the CRVA.  But that is not our planning basis.

MR. MONDROW:  You expect that all the risks that went into the Monte Carlo as inputs are all going to materialize, and you're going to hit P90?

MR. LYASH:  No.  Because all risks materializing would be a far greater number.

MR. MONDROW:  It would be a P100?

MR. LYASH:  Yes.  Which is a substantial amount of additional money and schedule than a P90.

MR. MONDROW:  Indeed, it's probably a hockey stick type curve; right?

MR. LYASH:  Right.

MR. MONDROW:  So you're near the top of the curve, but there's a lot of upside after 90?

MR. LYASH:  There certainly is.

MR. MONDROW:  Have you produced a graph of that curve anywhere?

MR. REINER:  I believe, if you go into the evidence and you look up the information that was provided for the release quality estimates, there is a business case document in there, and there are graphs associated with that in that document.

MR. MONDROW:  Okay.  Apparently we've seen that.  Thank you very much.  I will check that out.

I can take you to the evidence, but maybe I don't have to, just to short-circuit it.  There is an interrogatory response, AMPCO 70, and my understanding is that, at P50, the total DRP project cost is reduced by $400 million.

Mr. Reiner, is that familiar to you?  Would you rather go to the response?

MR. REINER:  If that is directly out of the interrogatory response, then yes.

MR. MONDROW:  Let's do that.  So this would be Exhibit L4.3, schedule 2, AMPCO 070.  And we see there in this chart total project cost, billions of dollars.  At P50, it's 12.4, and that compares to the 12.8 at P90, I think.  Is that right?

MR. REINER:  Correct.

MR. MONDROW:  Okay.  So $400 million less project cost at a P50 for the entire DRP; right?  That's just math.

MR. REINER:  That's just the outcome of the modelling.

MR. MONDROW:  Right.

MR. REINER:  Yes.

MR. MONDROW:  I just mean, 12.8 minus 12.4 is --

MR. REINER:  Oh, and that's just -- yes, exactly.  That's just subtraction.

MR. MONDROW:  Okay.  And so, at a P50, would you still allocate 40 percent of that saving, which would equate to 160 million to unit 2?  Would that be a way for me to determine, if I wanted to argue this Hearing Panel should work with P50, that the unit 2 should be reduced -- the unit 2 revenue requirement should be reduced by $160 million?  I know you don't agree with the argument, but would that be a mathematically appropriate way to couch the argument?  The allocation proportion remain the same?

MR. REINER:  I'd have to give that some thought, whether that is -- whether that is precisely true, whether the allocation would occur precisely that way.

MR. MONDROW:  If you could do that, I would appreciate that.  And feel free to say you don't agree with the premise.  I fully expect that in your answer --

MR. KEIZER:  Is that a question maybe that you could also maybe, instead of us taking an undertaking, put it to panel 1B?  And if we can answer it there, that may save having to do an undertaking.

MR. MONDROW:  Well, this way at least -- we cannot --

MS. LONG:  Why don't we mark it as an undertaking, but I would like panel 1B to address it, because I think the panel is interested in hearing that in live evidence rather than through an undertaking response.  We may have some questions about that.

MR. LYASH:  Just to be clear about the question, and there may be some issues with the premise, but it wouldn't be the difference between 12.8 and 12.4.  It would be the difference between 1.7 and 1.4 if you're asking specifically about contingency.

MR. MONDROW:  Sorry, if you're asking specifically about --

MR. LYASH:  About contingency changes.  I think you mentioned contingency versus total project cost.  The contingency difference is 300 million.  The project cost is 400 million difference.

MR. MONDROW:  The difference being interest and escalation?

MR. LYASH:  I think that's probably the difference, but I'm not sure.  I'm just not sure which one you were asking about --

MR. MONDROW:  Okay.  So account interest and escalation, we sort of counted everywhere, but I take your point, Mr. Lyash, and when we come back on panel 1B, we'll make sure to clarify that.  Thanks.

MR. RICHLER:  Mr. Mondrow, I should have given an undertaking number.  It's J2.3.

MR. MONDROW:  Thank you.

Undertaking No. J2.3:  To determine the revenue-requirement impact moving from a p90 to a p50 in this application

MS. LONG:  So, sorry, Mr. Mondrow, is the nub of your question, if you take -- if you go from P90 to P50 on the contingency level, is it OPG's view that it should be divided equally, let's say, when you look at all four units?  And that means -- I mean, is that what you're looking for with respect to unit 2?

MR. MONDROW:  I'm looking for the revenue-requirement impact in this application moving from a P90 to a P50.  So that would be --

MS. LONG:  Right.  Just based on unit 2, though.

MR. MONDROW:  Unit 2 is the only unit they're --

MS. LONG:  Right.  Okay.

MR. MONDROW:  -- asking for revenue requirement.  Yes.

MR. REINER:  Yeah.  The -- and I'll just repeat back as well so I'm clear.  So the $400 million number that you identify here in the mathematics, you're looking for the amount that would be allocated to unit 2?

MR. MONDROW:  Well, kind of.  So you've already allocated 40 percent of contingency on a total --

MR. REINER:  Yes.

MR. MONDROW:  -- DRP basis --

MR. REINER:  Yes.

MR. MONDROW:  -- to unit 2?

MR. REINER:  Yes.

MR. MONDROW:  P90.  So I'm assuming a proportional allocation if we move to P50 --

MR. REINER:  -- P50, does that allocation still hold?

MR. MONDROW:  And you may conclude --

MR. REINER:  Yeah.

MR. MONDROW:  -- not, and if not, I would be interested --

MR. REINER:  Yeah.

MR. MONDROW:  -- in why not.  So I think we have an undertaking number, but we've agreed we're going to talk about it --

MS. LONG:  Well, let's just mark it so we don't lose it --

MR. MONDROW:  Yeah, yeah.  I would appreciate --

MS. LONG:  -- and -- but we'll deal with it on 1B.

MR. MONDROW:  So that's J2.3 then.  Thank you very much.

Mr. Reiner, there's something else I want to ask you about from your testimony yesterday, and I'm sorry; I actually didn't receive the transcript last night.  I think I've corrected that this morning.  So I don't have a reference for you, but I'm sure you will remember.  You mentioned a few times yesterday morning in particular the expert support that you have on the record already for your P90 selection and why that's appropriate.  I think Schiff Hardin you referred to a couple of times.

I must admit I haven't seen any of those experts say P90 is the right selection.  I have seen them talk a lot about your methodology and how you conducted the analysis appropriately and Monte Carlo is appropriate for this kind of project, et cetera, et cetera, but I didn't see anyone say, "We agree with P90."  Is that what you intended to say yesterday?

MR. REINER:  So what the experts have told us is that the -- so I think we had said yesterday there is no prescribed method of contingency allocation to projects that you can go to and say, "Hey, this is my project, and this is the number that goes with it."

The nature of a megaproject and the decision we made in OPG to utilize a P90 confidence level given the nature of the project, the experts looked at that, and the conclusions provided were that it's an appropriate allocation of contingency given the nature of the project.  So P90 is an appropriate contingency allocation.

MR. MONDROW:  Okay.  Can you take an undertaking to tell me, perhaps with the assistance of some of your colleagues, where precisely in the evidence there is an expert that says P90 is an appropriate allocation?  Because I didn't see that anywhere, and I may just have missed it, so if you're pretty confident about that, I would like to understand the basis for that position.  Could we have an undertaking for that?

MR. REINER:  I believe, in the Pegasus testimony, there is some information that talks about the reasonableness of P90; that that is seen to be a reasonable allocation of contingency.

MR. MONDROW:  That's interesting, because that's the piece I read most carefully, and I didn't read it that way, so I would actually like a cite from you for where you believe Dr. Galloway said that.  Could you undertake to give me that?

MR. REINER:  Okay.

MR. MONDROW:  And any other piece of evidence.  I'm not going to limit you to Pegasus, but you seem pretty sure about this, and I just haven't seen it, so I would like to understand the basis for that position.

MS. LONG:  So, in any of the expert reports you're looking for that, Mr. --

MR. MONDROW:  Any of the evidence, but I assume expert reports, yes.  I'm sorry.  Any of the expert reports, because it's external validation of that --

MS. LONG:  I assume that's what you're looking for.

MR. MONDROW:  Thank you.  J2.4?

MR. RICHLER:  Yes.

Undertaking No. J2.4:  To advise precisely where in the evidence there is an expert that says P90 is an appropriate allocation

MR. MONDROW:  Thank you, Mr. Reiner.  And I don't want to put you on the spot today, so take that away and you can let me know where you've seen that.  I know we all see things that we remember, and I would be curious where that is.

Can I go to Exhibit D2 -- still on contingency, D2-2-7, so it's Exhibit D2, tab 2, schedule 7, page 7.  I'm looking at chart 1.

And if you have that, Mr. Reiner, there are two columns there on contingency.  Well, there's three --

MS. LONG:  Mr. Mondrow, could you just wait --

MR. MONDROW:  Oh, I'm sorry.

MS. LONG:  -- until we get it in front of us.  Thank you.

MR. MONDROW:  Sorry.

MS. LONG:  We have it now.  Thanks.

MR. MONDROW:  I did provide these yesterday.  I understand sometimes it takes some time to find.  It's not --

MS. LONG:  I know it's a hard job to get those documents up, so we appreciate it.  Thank you.

MR. MONDROW:  It was only late last night, I must confess, so completely understandable.

So I'm looking at D2, tab 2, schedule 7, page 7.  It's chart number 1 --

MR. REINER:  Yes.

MR. MONDROW:  -- Mr. Reiner, and there are, apart from the "Total" column, two separate columns on contingency.  And I know you answered a couple interrogatories on this.  I looked at those answers.  I still don't quite get it.  I wonder if you could just explain the difference between project contingency and program contingency.  Maybe take the RFR, which we all are focused on, as an example and just explain what the difference is there.

MR. REINER:  So, in general, project contingency is contingency that is allocated specifically to a project bundle, and program contingency would be something that would cut across all projects and is not directly allocated to a project, is held at program level.  So, for example, radiation protection support would be something -- there is a risk associated with that.  It is attributable to RFR but would be held at a program level.

MR. MONDROW:  And so, if we look at project execution operations and maintenance, I didn't understand that category to be -- to have specific projects under it.  I thought it was a kind of a project management office.  Am I wrong on that?

MR. REINER:  So the -- there are operations and maintenance.  There is an allocation of operations and maintenance effort to projects specifically.

MR. MONDROW:  Ah.

MR. REINER:  And there is also -- if you look at the project in its entirety in the defuel phase, that is all work executed by operations and maintenance.  And in the return-to-service phase, that is all work largely executed by operations and maintenance.

MR. MONDROW:  At the program level, the contingency would relate, I assume, more how the projects interact with each other as opposed to the risk inherent in an isolated project.

MR. REINER:  Yes.  And I think that's generally the allocation here.  If it's specific to a project, it sits in the project.  We can get into this in more detail on panel 1B.  Panel 1B will be able to drill down into the specifics on what's in program level versus project level.

MR. MONDROW:  That will help me prepare for that.  Thank you very much.

One more question on this table:  Unallocated program contingency, what's that?

MR. REINER:  Unallocated is something that isn't specifically allocated to a piece of work.  So, for example, there is a -- if you look at the resources between the execution of unit 2 and unit 3, the resources diminish, and then they ramp back up again.  We call that the trough between units 2 and 3.  It may have been referenced that way in our evidence, and there are risks associated with ramping those resources back up.

So the availability of the resources, the training that goes with it, the costs associated with doing that, there is an element of risk.  That would be an unallocated risk, because its a not attributable to any specific project activity.  It's just the nature of the program, the way the schedule is structured.

MR. MONDROW:  Does some of that get allocated to unit 2, ultimately?  I guess only if you call on it.

MR. REINER:  Again, I would ask -- we can deal with that on panel 1B, what the exact allocation is into the unit 2 contingency.  I believe there is information that's been provided that breaks the unit 2 contingency down into the same categories.

MR. MONDROW:  Okay.  I'll come back to that.  Thanks.

Mr. Lyash, when OPG obtained government approval for the DRP, was there a total cost number that you provided to the government?

MR. LYASH:  We provided the government the RQE in obtaining approval to proceed.

MR. MONDROW:  And would you have provided the government with a specific unit 2 number in addition to the total DRP number?

MR. LYASH:  I can't recall whether that -- the focus was on RQE for the 12.8 billion.  I can't recall whether we included the unit 2 number in that approval process or not.  We can certainly check.

MR. MONDROW:  Can you check?  J2.5?

MR. RICHLER:  Yes, J2.5.

Undertaking No. J2.5:  To advise whether the government was provided with a specific unit 2 number in addition to the total DRP number

MR. MONDROW:  Thank you.   I'm going to go through some detail here, Mr. Reiner, just to understand, and this is on unit 2 contingency included in the application there. I think they're different numbers, and I'm not sure why that is.  So let's just do this chronologically and take a couple of minutes to do this.

So if we can start at D2, 2-8, please, page 9.  So this is Exhibit D2, tab 2, schedule 8, page 9, chart number 4.  This is for the Darlington unit, so the 2020 revenue requirement and service amounts that you're requesting in this application.

As of the filing date of this evidence, which I guess is May 2016, you had a contingency amount, if you look at the second-last row on this table, of $694.1 million, so  just remember that number for a minute.

Now I'm going to take you to Mr. Rubenstein's compendium from yesterday, which is Exhibit K1.2, page 19.  I was struck with this yesterday.  There is a unit 2 cost summary, which is an appendix to a board of directors report, the date of which was August 2016, and I can take you back to the date in a minute.  But just relative to the May 2016 number we just looked at, in August 2016 on this chart here, page 19 of K1.2, there is an RQE contingency number of 689.5 million, and that compares to the 694.1 million.

I don't understand why that's a different number.  Do you?

MR. REINER:  So you're referring to row 17 on that table, the difference between the RQE number and the current U2EE number?

MR. MONDROW:  I'm referring to the difference between the RQE on this table and the prefiled number in your prefiled evidence, which I thought was also an RQE number.  I may be wrong.

MR. REINER:  We would have to undertake to get you an answer to that.  I don't have the answer off the top precisely.  I think the 1B panel may have that answer, so maybe we can come back on the 1B panel.

MR. MONDROW:  Okay.  I know it's only $5 million, but it seems like a reasonable question.

MR. REINER:  I see the delta that you're talking about.

MR. MONDROW:  I made a note to come back to that, if you want to make your own note.

And then as you pointed out, we have, really for this Hearing Panel going forward, the current U2EE contingency number of 677.5 million.  That's the current number and the number you mentioned yesterday, I believe, Mr. Reiner?

MR. REINER:  Yes, that's correct.

MR. MONDROW:  Okay.  And why was the unit 2 contingency reduced to 677.5?

MR. REINER:  The release quality estimate was an estimate at a point in time at the end of 2015.  And the unit 2 estimate is the budget that we released for unit 2 in 2016, and it is just a reflection of the continuation of the work that was done in getting ready for unit 2 execution and in refining some of the estimates that were still at a higher class and having progressed some of the engineering work and the details that feed into that estimate.  So that reduced the amount of contingency that we required at the time of the release of funds to the project.

MR. MONDROW:  Okay.  And you've now removed the water facility from the approvals requested in this application.  Will that reduce the unit 2 contingency request at all?

MR. REINER:  That does not reduce the unit 2 contingency request.

MR. MONDROW:  I assume there was contingency associated with that facility originally?

MR. REINER:  There was an allocation of contingency that was allowed for within the project itself.  And so, based on the outcome of the analysis that is now underway to understand what is the exact completion date and estimate to completion for that project, that will inform us on whether that amount of contingency is sufficient to cover any cost increases.

There was also a contingency amount held as program level for the whole suite of facility and infrastructure and safety improvement projects.  Based on current estimates where they stand, we have allocated all of that contingency to projects.  If there is a requirement for additional contingencies to be utilized to execute the tool storage, that would come out of the refurbishment program contingency.

MR. MONDROW:  Thank you for that.  But just stepping back, the D20 facility had a budget with a contingency?

MR. REINER:  Yes.

MR. MONDROW:  And some portion, perhaps all the D20's facilities costs were actually allocated to unit 2 for the purposes of this application?

MR. REINER:  No.  Those costs -- so the 4.8 billion is a unit 2 cost, and then initially in the application, there was a cost identified for the early in-service, the facility and infrastructure and SAO projects, and it's in that number.

MR. MONDROW:  Okay.  And the contingency amount, I think it was 1.7 million overall for the project, 40 percent of which was included in this application.

MR. REINER:  Yes.

MR. MONDROW:  I think I asked you the wrong question.  Thank you for your clarification.  So the $677.5 million of contingency, that is the current contingency amount before this Hearing Panel.  That's -- is that just a unit 2 contingency, or is that -- that's just a unit 2 --

MR. REINER:  That is a unit 2 contingency, yes.

MR. MONDROW:  So there is additional contingency before this Hearing Panel for approval other than the 677.5 because of the early in-service projects that haven't closed to rate base yet that you're going to close at the same time as unit 2?

MR. REINER:  Yes.  So whatever the actual costs are for those projects when they close, that will determine how much of that program-level contingency was actually consumed for those projects.

MR. MONDROW:  So if I look at the updated -- and we're going to do this at the end of my questions -- at the updated approvals requested, you have got revenue-requirement numbers for each year.  Those numbers are net of the removal of the D20 facility from this application.  Is that right?

MR. REINER:  Yes.

MR. MONDROW:  Those are the final numbers as of today that you're asking for approval?

MR. REINER:  They are the final numbers as of today, yes.

MR. MONDROW:  And "as of today" means after taking D20 out?

MR. REINER:  After removing D20 storage from the application, yes.

MR. MONDROW:  Good enough.  Thank you.

Mr. Reiner, I think the evidence now reveals that, in respect of the early in-service projects, there has been some schedule delay on some of the projects.

MR. REINER:  Yes.

MR. MONDROW:  We'll get into details with panel 1B, but that is correct; right?

MR. REINER:  That is correct.

MR. MONDROW:  Okay.  And do any of those projects impact the critical path for the unit 2 refurbishment?

MR. REINER:  Those projects do not.  There were commitments that were made in our integrated implementation plan to the Canadian Nuclear Safety Commission in relation to some of those projects.  We do have a change control mechanism that is built into the tracking of those regulatory commitments which we have executed to notify the Canadian Nuclear Safety Commission that we are going to be late on a couple of those commitments.

But they do not -- those are systems that will be in-service to support the licence that we require to obtain for continued operation of Darlington, but they do not actually impact critical path on execution of refurbishment.

MR. MONDROW:  Okay.  Is there somewhere in the evidence a description or an illustration or some combination of what the critical path is for unit 2?

MR. REINER:  Yes, I believe so.  There is a layout.  We walked through it yesterday at a very high level in its large blocks, and there is also what we call a level 1 schedule, which provides a level of detail.  I believe it's an attachment to the evidence that speaks to the schedule.

MR. MONDROW:  So if we look at K1.1 from yesterday, there was this foldout sheet, which is -- this was Board Staff's compendium at page -- I guess it would be nine.

MR. LYASH:  Yes, that is the one.

MR. MONDROW:  And so if I'm looking at this gorgeous diagram, I must say -- matches my tie, Mr. Keizer -- is the red bar here the critical path?

MR. REINER:  The red bar is the critical path, yes.

MR. MONDROW:  And some of these other coloured bars which have arrows coming in and out of the red bar, I assume some of them would impact the critical path if they were delayed?

MR. REINER:  So those are -- those arrows indicate logic ties back to critical path, so those activities would need to be completed prior to getting to that point on critical path.  And so they do have -- they do have a potential of impacting critical path if they run behind schedule.  That's correct.

MR. MONDROW:  So anywhere where I see an arrow directly from a project that's not highlighted in red to the red bar, that would be a critical path interface of that other project with the critical path?

MR. REINER:  That would be an interface where there is a requirement to have that activity done --

MR. MONDROW:  Right.

MR. REINER:  -- in order to proceed to the next step on critical path.

MR. MONDROW:  Okay.  So thank you for that.  We can study that for panel 1B, use that as a reference.

Just let me ask you:  Are there any of the early in-service projects, the facilities and infrastructure projects, the safety improvement opportunity projects, that have critical-path relationships?

MR. REINER:  The -- what I would say on D20 storage, I mean, D20 storage is required in order to allow for two units of refurbishment to be executed simultaneously, so we do need that facility before we get into that point in the schedule.  So that would be at the point in time where unit 3 and unit 1 overlap.

MR. MONDROW:  Is that the only one from that group of SIO and F&P projects -- or F&I projects, sorry?

MR. REINER:  If you point me to the list of projects that --

MR. MONDROW:  Sure.

MR. REINER:  -- you're looking at, then I can just take a look and let you know.

MR. MONDROW:  Sure.  So I'll tell you the list I use.  Let me see here.  Let's start with Exhibit D2, tab 2, schedule 8, page 9, my notes tell me.  Oops, that can't be right.  Sorry.  Sorry, just give me a minute.

Maybe if we go to AMPCO response 30, that would be a better place for me.  So I will have to take you into the interrogatory responses, and I will give you the exhibit number.  So it's Exhibit L-4.3, schedule 2, AMPCO 030.  Okay.  Sorry, maybe there's -- sorry for the confusion.

Maybe there's an even better place, and this will save me a question later on, actually, so why don't we go to Exhibit D2, tab 2, schedule 10, table 2.  It's Exhibit D2, tab 2, schedule 10, table 2.  It says schedule 10 of this exhibit, table 2.  It's Adobe page 135 of 331, PDF page 135.  Oh, sorry, I've got it broken up in the next exhibit.  Schedule 10.  There we go.  Thank you.

So here we have a list of projects, Mr. Reiner, that's actually called ongoing projects from EB-2013-0321, and my question was:  You talked about the water storage facility, and whether any of these other projects have critical-path impacts.

MR. REINER:  We talked about the heavy water storage facility already.  The water and sewer project is complete.  The Darlington energy complex is also complete.  The retube and feeder replacement island support annex is complete.  The refurbishment project office is complete.  The electrical power distribution system is complete.  The third emergency power generator is not yet in-service, but is expected to be in-service before the end of the month.  It does not have a critical-path impact on unit 2.  The containment filtered venting system also is expected to be in-service by end of March, and it does not have a critical-path impact on unit 2.

MR. MONDROW:  For the projects not yet in-service but expected to be in service shortly, do we have updated costs?  Do you have updated costs, updated from this table?

MR. REINER:  I believe we do have updated costs.

MR. MONDROW:  I don't want to take the time now to go through each of them.  I think that's a panel 1B discussion perhaps.  But I wonder if, for table 2 and table 3, which lists further ongoing projects, whether we could get updated in-service and cost information prior to panel 1B.  Would that be possible?

MR. REINER:  Yes, we can provide that.

MS. LONG:  So an updated column H?

MR. RICHLER:  J2.6.

Undertaking No. J2.6:  To provide a final in-service date updated and an updated column H, 2016 actuals for the projects that are in-service

MR. MONDROW:  For both schedule and dollars.  So a final in service date updated, and an updated column H.

MS. LONG:  D and H.

MR. MONDROW:  Thank you.  I'm told 2016 actuals for the projects that are in service; I assume that's what we'll get.  Okay, Mr. Reiner?

MS. LONG:  Are you asking for that as an undertaking, or asking that be addressed by panel 1B?

MR. MONDROW:  I am asking for that as an undertaking, so we have the information in order to explore the variances with panel 1B, if there are material variances.

MR. REINER:  Yes.

MR. MONDROW:  Okay?

MR. REINER:  Yes.

MR. MONDROW:  Thank you.

MS. LONG:  Is that 2.6?

MR. RICHLER:  Yes, that's J2.6.

MR. MONDROW:  If I could have a moment?  I didn't want to ask redundant questions.  Thank you.

Mr. Reiner, you talked a few minutes ago about some contingency updates because you now have, a little further along in execution, more information.  That makes sense as you go.

I assume, gentlemen, and Mr. Lyash in particular, that, in 2019, you'll have greater certainty on unit 2 schedule and cost than you do today?

MR. LYASH:  Yes.  I would expect we should be closing in on completion of the unit at that point.

MR. MONDROW:  And I just want -- you had some discussion yesterday about your midterm update.  I know the original proposal for the midterm update was to adjust rates for 2020 and 2021, if required, based on an updated nuclear production forecast.

Your nuclear production forecast, Mr. Reiner, is it a P level determination, or is it just kind of a conventional forecast?

MR. REINER:  I would have to ask that you take that question to the nuclear panel.  I'm not in -- I don't have the background needed to be able to talk about how the nuclear production forecast is done, and I believe the nuclear panel is prepared to talk to that in detail.

MR. MONDROW:  Do you know if there was a Monte Carlo simulation done on that nuclear production?

MR. REINER:  I don't know.

MR. MONDROW:  Okay.  I made a note to come back to that.

So the midterm review is going to look at an updated nuclear production forecast.  You're now also going to seek a prudence review for the heavy water facility at the midterm, Mr. Lyash?  That's the plan at the moment?

MR. LYASH:  Correct.

MR. MONDROW:  You're going to be updating the Board annually on the DRP, as I understand it.  That's part of your filing proposal?

MR. LYASH:  Yes.  We plan to file an annual report with a cost schedule and performance information.

MR. MONDROW:  And to the extent there are material changes between now and then, that would be an appropriate subject for the midterm review, I assume?

MR. LYASH:  I would assume so.

MR. MONDROW:  The CRVA clearance, is that -- I think, Mr. Lyash, you said a few minutes ago that you're not sure how and when that's going to be clear.  I thought that was a midterm review issue, but maybe I am mistaken about that.  Is that a midterm review issue?

MR. KEIZER:  It is a midterm review issue.

MR. MONDROW:  Okay.  So we're going to do that at the midterm as well.  All right.

Mr. Lyash, you'd agree with me, I trust, that there is a real concern in this province about consumer electricity costs?

MR. LYASH:  I agree.

MR. MONDROW:  You're acutely aware of that, I would imagine.

MR. LYASH:  Yes.

MR. MONDROW:  And you'd agree with me that OPG has a significant role to play in respect of electricity cost control, not the only agency, but certainly a major player?

MR. LYASH:  Yes, I agree.

MR. MONDROW:  In fact, your recent proposal for regulation change in respect of rate smoothing, about which we are all waiting with bated breath, as you are, I'm sure, for more detail, is a proposal specifically to address cost impacts on electricity consumers in Ontario?

MR. LYASH:  Yes.

MR. MONDROW:  Mr. Lyash, are you cognizant of the fact that this Board has a very strong focus, in particular of late, on building incentives into rate approvals in order to reward and encourage efficiencies in the entities regulated by the Board?

MR. LYASH:  Yes, I'm aware of that, and we have undertaken to build that into the application that's pending before the Board currently.

MR. MONDROW:  Right.  Your application in this docket includes express efficiency incentives in some areas, but not in respect of the DRP.  You went over this yesterday, but that's a correct understanding, no express incentives in respect of the DRP?

MR. LYASH:  In the application that is pending, correct, other than those that I have described yesterday.

MR. MONDROW:  Okay.  And you talked about that, and you did talk about how the company is incented to do well on this project, and you were very clear about that a few times yesterday.  But I'm still not sure why you wouldn't  -- given that emphasis and given the sensitivity about costs, why you wouldn't build some sort of express incentive into the biggest project in electricity in provincial history.  Can you help me with that?

MR. LYASH:   Well, I'm not sure what type of incentive you're postulating, so I'll have to make some assumptions in answering the question.  We have done what we think is a very strong job of planning and preparing to execute it with very well based cost schedules and defensible contingencies.  I'm not sure what incentive you would suggest is applied, but perhaps if I assume your proposal was to somehow apply a lower capital investment number as an incentive for the company to hit, then I think you have to take great care in doing that, because the objective here is to deliver the maximum value to the customers over the 30-plus-year life of Darlington.  It's a very long-term investment.

And in terms of sensitivity to how much value the customer gets over that period of time, two of the factors that are very substantial are capacity factor and production costs, total generation cost.  Achieving those numbers don't always perfectly align with lowering your capital or OM&A cost in a project.  And so I'm always very cautious about the type of behaviours and incentive it's designed to produce and whether those behaviours really are in the best interests of the customers or not.  Lowering capital cost by extending the schedule and having customers absorb lower replacement power costs, lowering capital costs in a way that adversely impacts system capacity factor in the long term, lowering capital costs in a way that adds in ongoing O&M costs, that balance, I think you have to be careful to maintain it.

So your answer (sic) is why not a hard incentive on capital.  I that's your question, those are my thoughts on why that is not necessarily an appropriate thing to oppose on this project.

MR. MONDROW:  That's very helpful.

I gather, Mr. Lyash, that you don't want to skimp and save at the expense of robust longer-term performance and safety?

MR. LYASH:  That's correct.

MR. MONDROW:  And, in your perspective, it's important to keep an eye on that longer-term value when evaluating the approvals requested in this application for the first chunk of the DRP?

MR. LYASH:  Yes.

MR. MONDROW:  So, essentially, it's we're going to spend what we have to spend to get this right.

MR. LYASH:  We're going to get this right, and we're going to spend as little as possible in doing so.

MR. MONDROW:  And your incentive for that is to get it right?

MR. LYASH:  The incentives are as I described yesterday, yes.

MR. MONDROW:  Right.  So you made some assumptions about what I might have in mind.  So bearing in mind you have a variance account or you're asking for a variance account, if this Board approved a P50 contingency budget and schedule rather than a P90 contingency budget and schedule -- I guess it's the other way around, schedule and associated budget -- given that you have variance account treatment, would that be an appropriate way to control -- communicate the importance of cost control without putting you in a position where you have to sacrifice robustness or safety on this project?

MR. LYASH:  The Board can certainly decide to select a different probabilistic basis for unit 2.  I'm not sure what the basis for that number would be, but that's certainly something that the Board could do.  I wouldn't take away from that an incentive to lower costs beyond that which I already have.  The cost would be the lowest number we can produce to achieve the result we're looking for.

So, in my mind, that's just a question of what the Board cares to examine, not in a cost incentive for us.

MR. MONDROW:  So that's heartening, Mr. Lyash, as long as you're at the helm there, that you feel the same pressure either way, but I guess the difference is, if you get a P50 approval, if you spend more than that, you need to justify the prudence of that at the time.

MR. LYASH:  I think -- as we said, I think the -- what we are saying is that what we've done -- and the $4.8 billion number that we've established is a reasonable number based on industry best practice for a project of this complexity and nature, and that is the standard against which we think the project should be measured.

A different standard could certainly be established, but that 4.8 billion is the standard that we think demonstrates reasonableness on the part of OPG.

MR. MONDROW:  The Board set your payment amounts based on a P50.  Those payment amounts are more likely mathematically to match your actual costs at the end of the day.

MR. LYASH:  Well, I don't agree that just pure mathematics is the way to make this decision.

MR. MONDROW:  Okay.  I understand.

I did want to ask you one question about some of the testimony you gave yesterday on incentives, and one of the incentives you mentioned is the link between compensation amounts and performance on this project.  Do you recall that testimony?

MR. LYASH:  I do.

MR. MONDROW:  And we're a bit puzzled by that, because my understanding is you're asking for an envelope, but compensation obviously is determined on an annual basis.  So how do you bridge that timing difference for compensation purposes?

MR. LYASH:  Well, this is perhaps better -- better for the compensation panel 4 to take up since it's a direct question to them.  But compensation has certainly got base salary; it's got elements of incentives.  The company has goals.  Those goals extend beyond the current calendar year.  Managers are assessed on their performance, not only in obtaining annual goals, but achieving the goals in the business plan.  And those goals in the business plan, as you might guess, are heavily weighted around refurbishment.

MR. MONDROW:  Do you have annual milestones that you and your other senior management team have to meet in order to --

MR. LYASH:  We do.

MR. MONDROW:  -- get compensated?

MR. LYASH:  Yes.

MR. MONDROW:  And those would be kind of schedule and cost milestones on the DRP?

MR. LYASH:  Yes.  Yeah.

MR. MONDROW:  So isn't that how you bridge the gap?  You actually have broken the overall envelope for both schedule and costs down into milestones which include milestones within each compensation year?

MR. LYASH:  Correct.

MR. MONDROW:  Okay.  And, presumably, that's how your portion of the compensation is evaluated.

MR. LYASH:  As an example -- and I think the compensation committee or the compensation panel can go into this in detail -- in 2015 -- or 2016, there were specific management goals for the number of channels defuelled, because that was the end for the completion of the campus plan and SIO projects, and those milestones for '16 were numbers taken directly down from the project plan and budget.

MR. MONDROW:  Okay.  Thank you.

The break is about 11:30, Madam Chair?  Is that...

MS. LONG:  11:15.

MR. MONDROW:  11:15.

MS. LONG:  Do you have about 15 minutes more or...

MR. MONDROW:  I wish I could say that with a P90 confidence level.  I cannot.  But I'll certainly do a break at 11:15, and I'll be able to --

MS. LONG:  Let's break at 11:15.

MR. MONDROW:  That would be P100 at 11:15 for a break.  That, I can manage.

Mr. Lyash, your contractors will have built contingency into their contract fees; right?

MR. LYASH:  Yes.

MR. MONDROW:  Do you know what contingency levels they use?

MR. LYASH:  This is a panel 1B question in detail, but generally we have visibility into contingencies for those contracts that are, for example, target price, not for those that are fixed price.

MR. MONDROW:  Right.  So the fixed-price contracts you assume have contingency, but you don't know how much they budgeted for contingency?

MR. LYASH:  Correct.

MR. MONDROW:  The target-price contracts, there's actually an express contingency amount built in is my understanding.

MR. LYASH:  There is, generally speaking, an open-book approach on the target price, so we have visibility into the contractor's cost and contingency.  And, again, panel 1B can go through this in quite a lot of detail.

MR. MONDROW:  Okay.  Fair enough.  And I won't go into too much more detail with you gentlemen, but I do want to check conceptually something, but I want to reference a number to do so.  If you could look at Exhibit -- these are the interrogatory responses again, so it's Exhibit L, tab 4.3, schedule 2.  I'm pretty sure it's AMPCO 072.  And we asked about -- well, my colleagues asked about some of this.  So it's Exhibit L, tab 4.3, schedule 2, AMPCO 072.  There we go.

And if we look at the response to part F, we see that the contingency amounts for the RFR, EPC, and the turbine generator EPC agreements are set out there at 371 million and 28.4 million respectively, Mr. Reiner, so those would be the express contingency amounts for these two contracts; right?

MR. REINER:  That's correct.

MR. MONDROW:  And these numbers and others like them would be in addition to the contingency being requested by OPG; right?

MR. REINER:  Yes.  That is correct.

MR. MONDROW:  So the overall contingency request before this Panel is actually a P90-plus.  It's something more than P90, isn't it?

MR. REINER:  No.

MR. MONDROW:  No?  Why not?

MR. REINER:  So these numbers are embedded in the -- so they essentially are a P50 for the contractor.  We don't double-count contingency, so if the contractor has contingency to cover a specific task and the execution of that task, we don't layer on top of that another amount of contingency to cover that same risk.  That's with the contractor to manage.  Our contingency looks at the risk that sit with OPG and that sit with the program and are on top of what the contractors would have embedded in their costs.

MR. MONDROW:  If I'm understanding you correctly  -- and that's comforting for me, thank you -- you calculate your P90 based on the OPG responsibilities excluding, for example, these two EPC contracts.  Is that correct?  Excluding the contractor responsibilities under these?

MR. REINER:  So the details of that calculation, I would ask that we defer to 1B, because that panel can go through the details and explain to you how the mathematics is done to get to our P90.

MR. LYASH:  I think it is --

MR. MONDROW:  Sorry, Mr. Lyash.  So for today's purposes, the answer is you're not double counting, and we can explore 1B how that result is obtained.  Sorry, I interrupted you.

MR. LYASH:  I was going to emphasize that we can see the contingency in the contractors and don't double that up in developing the OPG contingency.

MR. MONDROW:  Okay.  We'll come back to that.

I want to move to the topic of scope for the DRP and to do so, hopefully clearly, I want to start at Exhibit D2.2.5, in particular page 3.  And in particular -- that's fine, what's on the screen, because, in particular, I want to just emphasize two process bodies or mechanisms that I understand OPG employed in order to ensure that it defines the scope of the DRP with confidence, Mr. Lyash, and precision.

So this evidence talks about your project scope review board, and if we look at line 10 on this page, the responsibility of that organization was primarily whether the proposed scope needed to be included in the DRP or could be performed through normal station work processes, bracket, or was required at all, close bracket.

So that's one entity.  And if we look down starting at line 20 on the same page, we see reference to what I gather is a separate and distinct entity, the Darlington Nuclear Refurbishment Scope Review Panel, so review on the first entity essentially, also referred to as the blue ribbon task force, which was formed in late 2013 to form a detailed review of all scope requests that the PSRB intended.

If we look at the footnote on that page 3, which is in reference to the blue ribbon task force, we're told that the objective of that task force was to ensure only scope requests required to support the refurbishment of Darlington units are included in the approved DRP scope.  So that's pretty comprehensive, and you can agree with that.  But I'm not actually asking you a question.  I wanted to set that context for the questions I have to come.

So if we -- unless you want to comment on that at all, but you don't have to.  Okay.  So I'm going to move on.

If we can go to D2, tab 2, schedule 2, page 13, attachment 2 – sorry, D2, tab 2, schedule 2, attachment 2, page 13, just to identify this document.

So this is the Darlington Refurbishment Charter, and if we scroll down a little bit, we see, Mr. Reiner, that you have senior sign-off on this document; right?

MR. REINER:  Yes.

MR. MONDROW:  Okay.  And if we look at page 4 of the document -- so, for that, you need to look in the page boxes at the top right corner under the "Internal Use Only."  Those are the page numbers I'm referring to, and if we go to page 4, we see the revision dates.

The first issue date here was June 2008, and the final so far date for this document is much more recent.  It's January 2016.  I'm reading that right, Mr. Reiner?

MR. REINER:  That's correct.

MR. MONDROW:  And you've been involved in this document throughout that time period?

MR. REINER:  I was not involved with revision 0 and revision 1, but was with revision 2 and 3.

MR. MONDROW:  So sometime between 2009 and 2014?

MR. REINER:  Yes.

MR. MONDROW:  So if we look at page 9 of the document, we see a heading, "DRP scope," and if we look at the paragraph following the bullet list, I want to read that.

"A program scope review board --"

We just looked at that.

"-- with supporting governance was put in place to approve the technical scope of the DRP.  The technical scope for the DRP was initially confirmed in May 2012."

You were involved at that point, Mr. Reiner?

MR. REINER:  Yes.

MR. MONDROW:  "Since that time, as a result of

engineering studies and analysis, results of planned inspections and completion of regulatory submittals, including the integrated safety review and environmental assessment, scope has been finalized."

So, clearly, as of January 2016, the scope of the DRP had been finalized.  That was the latest sign-off date we looked at a minute ago; right?

MR. REINER:  That's -- yes, that's correct.  Now, I will say that doesn't -- this doesn't necessarily finalize 100 percent of the scope.  There are elements of scope that we've identified that do still require inspection work, and that inspection work can't be conducted until the unit is shut down and defuelled, because we require access to certain parts of the plant that we don't have access to currently in order to establish that precise scope.

MR. MONDROW:  That's helpful.  Let's break that down.  Between January 2016 and now, there have been some changes in scope?

MR. REINER:  Yes.

MR. MONDROW:  And is there some sort of continuity schedule in the evidence that isolates what those changes have been and what the cost implication that might have on the project?

MR. REINER:  So, in terms of cost implications, where you would see that in the evidence is the difference between the unit 2 execution estimate and the release quality estimate.  We talked earlier about how contingency has changed.  You'll see there are some variations in the numbers, so that's a reflection of the progression of that work.

MR. MONDROW:  But is there actually a continuity piece that tells us what has changed between this -- remember, this followed all of that careful scoping exercise.  What I'm trying to do is understand -- and I understand why things might change.  You described that, and you'll describe that a little more, I expect, in the coming moments.  But I'm trying to isolate what has changed between the time of this approval and essentially now.  Is there some piece of evidence that tells us that, that collects all of that comprehensively?

MR. REINER:  You're talking about the precise changes in scope, whether that has been submitted?

MR. MONDROW:  Yes.

MR. REINER:  I would have to see -- I would have to ask whether we have submitted all of that detail of scope change in the evidence.  Certainly, internally, we have a process for tracking all scope, and the scope has been tracked since the initiation phase of the project.

MR. MONDROW:  I would say at a project level.  I'm not interested if you needed a different screwdriver.  I know I'm vastly oversimplifying, but I don't want that kind of detail.  But projects moving in and out is what I'm interested in.  Could you undertake to see if you can produce a kind of a continuity schedule of some sort on those scope changes between the filing -- well, between this date --

MR. REINER:  When you say "this date"?

MR. MONDROW:  January 2016 was the last sign-off on this document, so between your sign-off and today.

MR. REINER:  This document isn't -- this isn't a scope document; right?  It's a project charter is what this document is.

MR. MONDROW:  Right.  And it says the scope was finalized as of then.  I appreciate that changes as the project progresses, and I'm trying to get a sense of what is still changing.

MR. REINER:  So you're looking between January 2016 and what point in time?

MR. MONDROW:  Today.

MR. REINER:  What the major changes of scope were in the project?

MR. MONDROW:  Right.  Is that possible?

MR. REINER:  I think we can undertake to do that.

MR. KEIZER:  It's just not clear to me that the January date may be the best date, but we'll see what we can figure out.

MR. MONDROW:  I wonder --

MR. RICHLER:  Sorry, that will be J2.7, Mr. Mondrow.

Undertaking No. J2.7:  To advise what the major changes of scope were in the project between January 2016 and today

MS. LONG:  I think what Mr. Mondrow is looking for is when the scope was finalized and how it's changed up until the time -- well, today's date.  Is that fair?

MR. MONDROW:  That's right --

MS. LONG:  Okay.

MR. MONDROW:  -- Madam Chair.  Thank you.

MS. LONG:  Can I just ask you a question, Mr. Reiner?

MR. REINER:  Yes.

MS. LONG:  When you talk about scope change, and you've told us that, obviously, you know the scope will change because you're going to get in and do certain investigations, and it may lead to future work that you don't know about because you haven't gone in yet to see.

MR. REINER:  Yes.

MS. LONG:  Does something like that, then, require a scope change?  I mean, is it built in that you have identified five areas where you need to go in and do an assessment, and there may be a scope change or there may not.  You may go in and see nothing needs to be done.  Is that built in already?

MR. REINER:  That is -- so the processes for executing that are all built in, and it's done through our change control process.  In terms of where it is captured in schedule and contingency, there are contingency items identified for contingent scope where we have not -- we have not yet identified a need to execute a certain piece of work, but we're holding in contingency some dollars in the event that that is needed.  And some of the schedule contingency is also attributed to that.

So. if a scope of work needs to be executed that has the potential to impact schedule, that's what schedule contingency would then cover.  So, when we break down all the details, that is covered in the project, and there's a very prescriptive process that we run internally where we have -- we do reconstitute periodically the scope review board, because, at times, there are large items that may move in and out of scope.

Primary heat transport pump motors was one example like that.  They were in scope at one point in time.  The reliability of those motors didn't allow the performance to reach the refurbishment time period, and so they were removed from scope, and so that decision-making and that tracking is all recorded, and processes are in place to do that for every line item of scope.

And the reason for that is because we do have to precisely establish a schedule for executing that, and we want to be confident that we've got the costs covered in our contingency or in our base cost, so it was a very prescriptive process for doing this.

MR. LYASH:  And just to add, that will continue over the refurbishment.  So, as we open up systems, as we get in, as we inspect, we'll find repairs that couldn't have been anticipated.  Those repairs will be scoped, added.  There will be a cost impact, the schedule impact.  The contingency is used to fund those efforts if they can't be mitigated and accomplished under the base budget.

MS. LONG:  Okay.  I'm sure we will hear more about that in schedule (sic) 1B, but I am interested, I guess, in how you balance, obviously, the documentation and being able to move ahead with doing things in a timely basis.

Mr. Mondrow has asked you for an extension of a chart showing how scope changes, but I think the Panel is very interested in how you balance being able to move quickly on issues and being able to make sure that there is correct oversight.  So you can address that in panel 1B.

MR. MONDROW:  Thank you, Madam Chair.

I know it's break time.  I just want to finish one question on scope if I could.  And so we got Undertaking J2.7, which is to kind of provide continuity on the scope changes, and I also said, I just want to be clear, and associated costs, so whether the costs have come out of the program or been added to the program in consequence of those scope changes, if you have that information available.

MR. REINER:  Yes.  And you also said you don't want all the details.  You're looking for the big -- the large items; right?

MR. MONDROW:  Yes.  That's fine.

MR. REINER:  So we'll make an assumption on what kind of a materiality threshold that would be --

MR. MONDROW:  Just tell us what that assumption was.

MR. REINER:  Yes.

MR. MONDROW:  Thank you.

And just one -- so, Mr. Reiner, you mentioned a minute ago why, I think it was steam generators, if I'm not mistaken, came out of scope, something about --

MR. REINER:  Heat transport --

MR. MONDROW:  -- heat transport.

MR. REINER:  -- pump motors.

MR. MONDROW:  Pump motors, because they weren't available in time to keep them in scope, or...

MR. REINER:  So the initial -- the initial plan was for some of the heat transport pump motors to be replaced during the refurbishment of the plant.  In actual fact, what has transpired over the course of time is the reliability of those motors deteriorated significantly, and we have had failures.  And so that's an item that had to be addressed by the station outside of refurbishment.  It was required just to keep the plant running.

MR. MONDROW:  Sooner rather than waiting --

MR. REINER:  Sooner, sooner rather than later.

MR. LYASH:  Couldn't wait for refurbishment.

MR. MONDROW:  Couldn't wait.  Right.  Okay.

All right.  Let's leave it at that, Madam Chair, and I'll regroup over the break.  Thank you.

MS. LONG:  Thank you, Mr. Mondrow.

We're going to take 15 minutes.

### --- Recess taken at 11:19 a.m.

### --- On resuming at 11:40 a.m.

MS. LONG:  Mr. Mondrow?

MR. MONDROW:  Thank you, Madam Chair.

Mr. Lyash was kind enough to point out to me on the way out of the room that I exceeded my P100 schedule, which we both thought was a mathematical impossibility.  So I apologize for that.

I am conscious of those that are following me in your schedule, Madam Chair.  I have gone through my questions and taken a number out.  I'm estimating up to another 30 minutes, and, with your leave, I will continue and try to finish my examination.

MS. LONG:  That's about 30 more minutes than we had estimated.

MR. MONDROW:  I think I'm at the top of my estimate, yes, so that's 30 more minutes than estimated.  I have looked at the schedule with Board Staff.  I believe there is some play in it for today to finish this panel, and I don't think it will jeopardize that.  It may mean that someone on panel 1B doesn't proceed today.  I know Mr. DeRose needs to, because he is going home.

MS. LONG:  Yes, he does.

Mr. McLeod, you're good to go on Thursday?

MR. MCLEOD:  Thursday is perfect.

MS. LONG:  That's fine for you.  Okay.  I would suggest, Mr. Mondrow, on a go-forward basis, maybe having a compendium would help speed things up.  We are spending a bit of time looking for documents, and I appreciate it's hard to do.

MR. MONDROW:  I appreciate that.

MS. LONG:  We're going to give you the indulgence today.  But on a go-forward basis, that may help.

MR. MONDROW:  I take your point.  I made the mistake of giving you my planning estimate rather than my probability estimate.  I will not make that mistake again. But I will pay attention to that.  Thank you.

With that background, Mr. Reiner, we talked together about the hockey stick contingency curve, you will recall, before the break, and you said it was in the evidence.  Apparently we can't find it, and I wonder -- and it doesn't have to be now, but I wonder if you could just identify for us, perhaps over the lunch break, where that is.

MR. REINER:  We can do that.  I believe it was actually in the 2013 business case that was filed in the previous hearing.  It's in that business case that you can see that S-curve.

MR. MONDROW:  Perhaps, Madam Chair, just to keep the record straight, if Mr. Keizer doesn't mind, we'll get an undertaking number to identify where that is.  If it's not on the record, then we can thereby put it on this record.  I'm happy to do that over lunch.

MS. LONG:  Just a minute, please.

MR. KEIZER:  We'll hopefully clarify over lunch; we can do it on the record.

MS. LONG:  All right.

MR. RICHLER:  J2.8.

Undertaking No. J2.8:  To advise where the hockey stick contingency curve is in the evidence

MR. MONDROW:  Thank you very much.  Because none of us are techies, we're all fascinated with the heavy water facility.  So even though it's out of the application, you've had some questions on it.  I have very few questions on it, which I would like to ask you.

So my understanding is unit 2 has now been drained, Mr. Reiner, of the heavy water.

MR. REINER:  It hasn't.  The draining has begun; it is not yet completely drained.

MR. MONDROW:  And the water that's been taken out is sitting in -- obviously, it is sitting in an appropriate storage facility at the moment?

MR. REINER:  That's correct.

MR. MONDROW:  And that facility has the capacity to receive the rest of the unit 2 water?

MR. REINER:  The station is equipped with storage capability, and as part of normal operations, there is a requirement to be able to facilitate one unit of heavy water in storage capacity.  With the project utilizing that storage, it does present some operations risk in terms of utilizing that storage capability, so we have implemented a mitigation plan to allow the project to make use of that capability.

MR. MONDROW:  What's the operations risk?

MR. REINER:  So if a unit were required to drain for whatever reason, to drain heavy water due to some maintenance-related issue that needed to be resolved, then we are potentially in a risk situation to accommodate that water.  The existing facilities are not equipped to handle two units' worth of heavy water.

MR. MONDROW:  And is that the point of the D20 facility that you're proceeding with, as I understand it?

MR. REINER:  Yes.

MR. MONDROW:  To handle more than one unit's worth of water?

MR. REINER:  Yes.  You had asked me previously is there a critical-path impact, and that would be the critical-path impact.

MR. MONDROW:  When units 3 and 4 overlap?

THE DEPONENT:  When three and one overlap.

MR. MONDROW:  What's the time expectation for that?  Do you recall?

MR. REINER:  That happens midway through unit 3, so around about 2021-2022, in that time frame.

MR. MONDROW:  Thanks.

MR. REINER:  The easiest place to read that is in the schedule section of the evidence.  There's a high-level schedule there that shows you where that overlap occurs.

MR. MONDROW:  I'll remember that.  That's perfect.  Thanks.  So let me at least leave heavy water.

Can you go with me, please, to -- I'm going to explore for a few minutes the costs that are being included in your request for relief in this application, but that relate perhaps more broadly to the DRP.  I know you've explained why that is, and I want to explore that explanation a bit.  So to do that, I would like to go to Exhibit D2, tab 2, schedule 1, page 3.

These, I believe, are the two categories of the so-called early in-service projects.  The category I want to talk about are the safety improvement opportunity initiatives, and if you go to Exhibit D 2, tab 2, schedule 1, page 3, at the bottom is one place where those SIO projects are talked about.  And starting at the very end of line 17, the justification, I believe, that you're giving for including the full cost of those projects in the revenue requirement relief at 2020, so unit 2 expected in-service, is stated as follows:

"The SIO are useful to OPG's current and future and current nuclear operations independent of whether the DRP is completed."

As I understand it, Mr. Lyash, that's the essential reason why OPG says the full costs of those SIO projects should be included at the time the first unit goes into service, rather than allocated across the various in-service dates for the four units.

MR. LYASH:  That's correct, when the SIO projects go into service.  For example, this month, when we place the containment filter vent system in-service, it will be a significant safety improvement for all four units, including those currently operating.

MR. MONDROW:  Am I correct that, but for the refurbishment, these SIO initiatives would not have been required?

MR. LYASH:  What I would say is to obtain the ten-year licence, which was an important risk mitigator, ten years covering -- allowing regulatory stability over the entire pendency of the refurb.  The requirements from the CNSC were to install the safety improvement opportunities, so they're embedded in that risk mitigation strategy.

MR. MONDROW:  Okay.  Then if we go to page 4, the second category of these early in-service projects is the facilities and infrastructure projects.  And if we look at line 1 on page 4, it says:

"The FNIP are projects that do not involve refurbishment of units, but which are necessary to enable execution of the unit refurbishments."

And if we look at line 7 on that page:

"The FNIP are expected to remain useful to OPG's current and future nuclear operations, independent of whether the DRP is completed."

Am I correct, Mr. Lyash, that those projects would not have been required if there had not been a mandate to refurbish?

MR. LYASH:  Certainly -- I'm not clear whether they might have been required in the future, but in the present time, they were necessary to refurbishment of all four units, including the first unit.

MR. MONDROW:  And they will support continued operation of the Darlington nuclear site beyond the refurbishment schedule?

MR. LYASH:  Yes, they will continue to be used beyond refurbishment.

MR. MONDROW:  If I can take to you Exhibit D 2, tab 2, schedule 5, page 6.  And we'll go back in a minute to page 5, where there is a list of specific projects, but I just want to look at this paragraph starting at line 4:

"Because the scope is not the same for each unit, the cost will not be the same for each unit.  Unit 2 is expected to be the most costly unit to refurbish because it includes more scope than the subsequent units, and due to station configuration and various requirements that are common across the station many engineering changes and other supporting scope is only required for unit 2 as they would already be in place for the remaining units."

So this paragraph refers, at least in part, as I understand it, to those two categories of early in-service projects which you need to complete in order to refurbish unit 2 but which will continue to serve the balance of the DRP program and, indeed, the Darlington nuclear facility beyond refurbishment of unit 2.  Is that fair?

MR. REINER:  That is -- yeah.  That's partially correct.  There are also specific in-station elements of scope that do not need to be repeated once they've been executed for unit 2.  They relate to -- because Darlington is an integrated multi-unit station, there are systems on unit 2 specifically that are required to operate the remainder of the power plant.  And we have had to make modifications to those systems in order to island unit 2 and not impact the operation of the plant.  So that work does not need to be repeated in subsequent units.

MR. MONDROW:  Right.  And you talked about that yesterday, and we'll come back to some of those details with the next panel.  But if we just go up to page 5 of this same exhibit, if I look at line 16, it says:

"Some examples of projects completed during the Unit 2 outage that are not completed for other units include..."

And then there's a list.  And I'm not going to take you through the list at the moment.  But my question is:  Given the language some examples, is there someplace where we can find a full list of those projects that will have use beyond the unit 2 refurbishment but that are being charged to rates or close to rate base at the same time as the unit 2 expenditures are being close to rate base in 2020?  Is there a list of those that we can see somewhere?  And if you want to take an undertaking, that's fine.

MR. REINER:  Yeah, we can address that in panel 1B.  I would say that is probably appropriate to pose that question for panel 1B.

MR. MONDROW:  Well, so my question is slightly different, Mr. Reiner.  What I would like to have is a list of those so that --

MR. REINER:  Yes.

MR. MONDROW:  -- we can look at those and ask questions about those when we get to panel 1B.  So if we could have the list in advance, which is why I asked for the undertaking, that would be helpful for me.  Can we do that?

MR. REINER:  I think we can undertake to --

MR. KEIZER:  Well, I think what we can do is look to see if we can find an evidence reference for -- I mean, sorry, just so I clarify your question, you want a list of projects -- other than when it says, some examples of projects, you want anything else that's over and above the some, basically.

MR. MONDROW:  Right.  Exactly.  And a list of references would be fine.  So we can make sure that we cover them all off as relevant when we get to panel 1B.

MS. LONG:  I'm not sure I understand what you mean, a list of references.  Are you looking for references in the evidence?

MR. MONDROW:  Well, so Mr. Keizer said, "Well, rather than a list of projects, we can give you a list of references."  I just need a list so that I know I have a comprehensive picture of the projects that are going to be if OPG's request is granted by your Panel, Madam Chair, put into rates effective 2020, and usefulness which extends beyond the unit 2 refurbishment.  That's what I'm looking for so that I can explore the relationship between those projects and the longer program.

MS. LONG:  Mr. Keizer?

MR. KEIZER:  Well, we'll do our best to get what we can.  I mean, there is a lot of projects, some of which are very small.  There's 560 specific projects, according to the evidence that appears on the screen, but -- so whether we can actually have them all ready for the appearance of panel 1B, which may be on this afternoon, I find that doubtful.

MR. MONDROW:  I won't be on this afternoon.  But let me be clear, Madam Chair.  I'm not looking for a list of 560 projects.  We can do -- I'm trying to think of how to make this manageable for you.  You've been dealing with programs, I guess, rather than individual projects.

So if you look at -- Mr. Reiner, if you look at this list of examples, that's the level of detail I'm interested in.  If there are major items not on this list that fall into this category, that's what I'm after, if that helps.

MR. REINER:  Okay.  What we would then propose to do is we'll, again, make a materiality assumption here in terms of what signifies major, and we'll come up with a list.

MR. MONDROW:  That's fine.  If it wraps around this list and anything like it, that would be perfect.  Thank you very much.

MR. REINER:  Yes.  Thank you.

MR. MONDROW:  So I don't know if we got a number.

MR. RICHLER:  J2.9.

MS. LONG:  J2.9.

MR. MONDROW:  Thank you.

MS. LONG:  Point 9.

Undertaking No. J2.9:  To provide a full list of those projects that will have use beyond the unit 2 refurbishment but that are being charged to rates or close to rate base at the same time as the unit 2 expenditures are being close to rate base in 2020

MR. MONDROW:  Mr. Lyash, I understand -- I recall, and someone actually wrote this down for me -- that this morning you said in answer to some of my -- some of our discussion that this project, being the DRP, is, quote, as robust as you have seen -- as I have seen for a project of this nature, close quote, as robust as I have seen for a project of this nature.

And the question I would like to ask you about that is:  What other projects were you thinking of that are of this nature that you've seen to compare this project to?

MR. LYASH:  Yeah.  And we were discussing planning and preparation --

MR. MONDROW:  Yes.

MR. LYASH:  -- the degree of effort that went into the project before the commencement of execution on unit 2, the breaker open.  And so, as I make that statement, I'm comparing it to a range of new builds, from very large gas-fired combined cycle, super-critical coal, nuclear power up rates, plant life extensions, and nuclear new build.

MR. MONDROW:  And some of those are listed in the Pegasus evidence and other pieces --

MR. LYASH:  Some of them are, yes.

MR. MONDROW:  Just while we're on the topic of Pegasus, Dr. Galloway mentions in her evidence -- and I can give you the reference for this -- some U.S. precedent for regulatory commissions allowing costs to go into rate base before a project is complete.  And that puzzled me a bit, because I don't think you're asking for that.  My understanding is you're asking on a forecast basis to put the unit 2 costs into rates when unit 2 goes into service in 2020.

MR. LYASH:  That's correct.

MR. MONDROW:  But you're not asking in this application for the inclusion in rates of any costs for facilities that will not at the time those costs are included -- facilities that are not in rate base at that time.

MR. LYASH:  That's correct.

MR. MONDROW:  Okay.  Unless, of course, you get approval here and you fall behind schedule on unit 2, in which case you would have approval for costs for facilities that aren't ready to rate base; right?

MR. LYASH:  I'm sorry.  Could you say that again?

MR. MONDROW:  If you got the approvals you requested in this case, which include rate-basing -- which includes rate-basing $4.8 billion in 2020, and unit 2 is not ready until 2022, that approval will have costs approved for rates for facilities not yet in-service; right?

MR. LYASH:  Yes.  And when you asked me about Dr. Galloway's comments, I think that is -- the way I understood that is approval for collecting revenues against a project that would not go in-service in the test period.  So we're not asking for that.  There are cases where very long-term, expensive projects that are in-service outside the test period are included in rates.

Here what we're asking for is what is, not unique, what is done with -- across various jurisdictions with transmission construction or generating station construction within the test period of major assets coming into service, and it's asked to come into rate base --

MR. MONDROW:  Right.

MR. LYASH:  -- at that time.

MR. MONDROW:  And, indeed, the way you calculate the rate impact of that is -- and the evidence makes some assumptions about the timing for rate-basing of those costs --

MR. LYASH:  Correct.

MR. MONDROW:  -- in 2020, some in February, some later in the year, as I recall.

MR. LYASH:  Yeah.  That's correct.

MR. MONDROW:  Okay.  But in the event you got the approvals you sought here and something came off the rails, even at P90, and unit 2 wasn't in-service in 2020, unless you came back to this Board, you would have rates that included collection for assets not in-service, so you would have to come back to the Board; right?

MR. LYASH:  Yes.  Or if the project comes into service early or late, then those would be accumulated, as I understand it, to the CRVA and dispositioned as part of that process.

MR. MONDROW:  Okay.  That's fine.

Two questions following up on some of your testimony yesterday, and I'm going back down into, not the weeds, but at least the trees here.

I believe you told Mr. Rubenstein yesterday that there was a November quarterly OPG board meeting.  Do you recall that, Mr. Reiner?

MR. LYASH:  Yes.

MR. MONDROW:  Mr. Lyash?  Okay.  And there has not been a board meeting since then?

MR. LYASH:  That's correct.

MR. MONDROW:  When is the next one scheduled for?

MR. LYASH:  It begins next Wednesday.

MR. MONDROW:  And will there be a DRP status report at that meeting?

MR. LYASH:  Yes, there will.

MR. MONDROW:  When will that be available?

MR. LYASH:  That will be issued to the Darlington Review Committee, the subcommittee of the board, sometime early next week.

MR. MONDROW:  Could we get an undertaking to file that once it's been issued?

MR. KEIZER:  I guess my concern is that, you know, the -- I think we've filed schedules related to what we had, and that's part of the undertaking from the November meeting, I believe, if I'm correct.  But my concern is that we continue to file the quarterly arrangements with respect to the board.  I'm not quite sure what it's to reflect.  I mean, the request here is based upon -- and we understand the current status of the project, based on the testimony that's been given.

We also are looking out on a forecast which goes over a series of years, based on the plan and execution.  And the report that's given isn't in respect of, for example, such as RQE, where there is a definitive decision made by the board; it's purely for information.

So I'm not quite sure why or what it leads to since it really doesn't lead to any other information that's already been put on the record in respect of the project and also doesn't lead to any formal deliberations by the board that is impactful in respect of the project, such as RQE.

MS. LONG:  What if Mr. Mondrow was to make the argument that this panel is talking about oversight?  This, to me, seems to go to the heart of oversight, what senior management is reporting to the board as to the status of this project.  Am I wrong on that?

MR. KEIZER:  I think we've been clear with respect to the nature of the reporting.  I guess I go to the purpose of it.  I guess I struggle with, you know, at some point our evidence goes in, but every meeting that happens, we end up putting more and more information in which already is a vast record.  I'm not sure what it actually gains, given the fact that the information in respect of the project is being given here by the people who are leading the project as to live witnesses.

In terms of the oversight, the nature and content of it, I think, certainly can be described.  But I'm in your hands; obviously you determine what is relevant.  But I get concerned about, you know, more and more just for sake of disclosure when, in fact, the evidence in respect of it is already either available through the examination of these witnesses and is simply just an interim update on, like, anything that would have happened with RQE, or as the description of the project already given.

MS. LONG:  Maybe we'll ask Mr. Mondrow why he needs it.

MR. MONDROW:  Madam Chair, I don't have any precedence on whether the report is going to have anything relevant or not, unlike Mr. Keizer, it appears.  So it may be there is nothing in the update that causes any concern or prompts any questions, but obviously I wouldn't know that until I saw it.

We're in the middle of a proceeding.  There is a principle of having the most current useful information before the Board.  We've got some tens of thousands of pages of disclosures, of various reports over time.  We're sitting here with the OPG witnesses this week and in coming weeks, and it seems to me if the reports are innocuous, it validates everything is on course, and if the report has something of interest, we have an opportunity to ask about it, and you have an opportunity to consider it prior to your approval.

So it seems to me that that's relevant if it's not onerous to produce this.  I was actually going to ask for two things.  One is quarterly OPG board meeting report, and there is a Darlington Refurbishment Committee, which meets monthly, as I understand it from yesterday's testimony, and I wanted to get a copy of the latest report for that.

If we don't have the information disclosed while the witnesses are here to get information from them, I'm not sure what questions to ask them.  That's what the disclosure allows parties to do is determine what areas might be relevant for the Board that further information could be examined or the witnesses could be asked to clarify.  That's the whole point of disclosure from the outset.  Why we would cut it off now is a bit of a puzzle to me.

I understand, once your decision is made, you've made your decision.  But you are in the process of doing that now, and I would have thought this was helpful.  But if it's not helpful, I'm in your hand.

MS. LONG:  I agree it would be helpful, so I would like you to file that.

MR. KEIZER:  The only question is I don't know what the status of the report is, given the board is meeting next week.  So that's the only question we --

MS. LONG:  I don't expect we would get it before the board saw it.  But once it is provided to the board, I would expect it to be filed.

MR. KEIZER:  Thank you, Madam Chair.

MR. MONDROW:  That would be?

MR. RICHLER:  J2.10.

Undertaking No. J2.10:  To provide an updated status report once it's provided to the board

MR. MONDROW:  To be clear, as I alluded to a minute ago, this was the report to the quarterly board meeting, and I did mention a minute ago -- I didn't get your evidence on it, Mr. Lyash, but I understand there is a monthly Darlington Refurbishment Committee report; is that right?

MR. LYASH:  No.  Let me just make sure we all have the right context.  We've got a rather layered and robust oversight process.  If I focus on the board for a minute, the board of directors has established a committee of the board, the Darlington Refurbishment Committee, with independent directors who are charged -- that committee's sole responsibility is the oversight of the Darlington refurbishment program.

The board meets nominally quarterly.  The Darlington Review Committee meets quarterly, in advance of the full board.  They tour the site, look at projects and progress, and then the leadership team provides a report to that refurbishment committee in their committee meeting, and then the DRC, that committee, reports to the full board on the status of the project quarterly.

We elected to -- in order to maintain that refurbishment committee, their level of engagement in oversight at yet a slightly higher level, we do a monthly conference call with the Darlington Refurbishment Committee of the board to update them on what has transpired in the last month and what is planned in the upcoming month.  So that conference call happens, for example, in month 1, in month 2, and then in month 3 is the DRC visit to the site, the committee meeting, and the full board at which we present a report.

MR. MONDROW:  The conference call would include the leads of all the various work streams?

MR. LYASH:  Yes.  It includes the senior management team, myself, Mr. Reiner, the program leads presenting --discussing with the board, as I said, what performance has been experienced in the last month and what the next month lookahead is.

MR. MONDROW:  And all of that is eventually rolled up to the quarterly report to the board?

MR. LYASH:  In a manner.  The relevant issues are in the quarterly report.  The intent of the monthly meeting is to help the DRC members maintain a very high level of understanding of the flow of DRC so that, when they sit as a committee, they have that as a basis.

MR. MONDROW:  Thank you very much.

Thank you, Madam Chair, for your indulgence.  Those are my questions.

Thank you, gentlemen.

MS. LONG:  Thank you.

MR. MONDROW:  Was there something else?

MR. LYASH:  I was going to add that these same things that we discuss on a quarterly basis, this level of detail is -- if you look at our proposal for the annual report to the OEB, it's a parallel set of information.

MS. LONG:  Thank you.

MR. KEIZER:  Just to be clear in terms of what we're providing then is the -- and whether we have the capability of doing so is the DRC report for March?

MR. LYASH:  For March, yes.

MR. KEIZER:  Once presented to the board of directors?

MR. LYASH:  Yes.  And I think, Charles, just one thing:  We ought to consider -- the board should see that first, and then I want to be careful about whether there are any fiduciary issues between that and our MD&A that gets issued coming out of the board.

MR. MONDROW:  Does that report include a Modus update?

MR. LYASH:  Pardon me?

MR. MONDROW:  Does that quarterly report to the board include an update from Modus?

MR. LYASH:  The report we provide does not.  Burns & McDonnell provide their report separately from the management team.

MR. MONDROW:  To the board?

MR. LYASH:  To the Darlington Refurbishment Committee.

MR. MONDROW:  And that separate report is not attached to the board report?

MR. LYASH:  No -- well, it's not attached to the management report to the DRC.

MS. LONG:  Can I be clear?  There is a management report to the DRC.  Then there is the DRC report to the full board, and then Burns & McDonnell does a separate report to the board -- or to the DRC.

MR. REINER:  To the DRC.

MR. LYASH:  Management provides a report to the DRC, and that's the report we've been discussing, as far as I understand.  The board retains an independent consultant, Burns & McDonnell, who reports independently to the board  -- independently to the DRC in the DRC meeting and then in camera with those directors.  The DRC then provides an oral report to the board of directors in the full board meeting.

MR. KEIZER:  And layered on to that is the aspect Mr. Lyash references, which is the MD&A, which is the disclosure document that OPG makes for Securities Act purposes.  So there's a bridge of time between it going to the Board and then ultimately being disclosed within the context of that document under the Securities Act.

MR. MONDROW:  In the meeting next week, there will be a written DRC report released to the board.

MR. LYASH:  Released to the Darlington refurbishment committee of the board.

MR. MONDROW:  And in your understanding, that's the undertaking that you provided, subject to your disclosure and obligation concerns?

MR. LYASH:  Correct.

MR. MONDROW:  And a companion or an input into that report to the DRC is the periodic, what I call the Modus report.

MR. LYASH:  No.

MR. MONDROW:  No.

MR. LYASH:  Burns & McDonnell is an independent contractor reporting directly to the Darlington Refurbishment Committee of the board.  They do not report through management --

MR. MONDROW:  Right.

MR. LYASH:  -- and so their report is not filtered or any way incorporated into management's report.  It's provided independently directly to the Darlington Refurbishment Committee of the board.

MR. MONDROW:  The Darlington Refurbishment Committee of the board, next week, will receive, among other things, two documents.  One the report that you've undertaken to provide subject to your disclosure concerns and confidentiality perhaps -- disclosure concerns, I suppose, and the other is a Burns & McDonnell report?

MR. LYASH:  Yes.

MR. MONDROW:  Okay.  So could we get that undertaking which we've been given, which is J2.10, if I'm not mistaken, to cover both of those documents?

MR. KEIZER:  I look to the Chair's ruling, and Madam Chair has indicated that you deem it to be relevant, so subject to their availability and subject to confidentiality aspects, obviously, and subject to timing for it being disclosed to the committee itself and the committee's reviewing and report to the board, if that's --

MS. LONG:  Yeah.  I think you understand what we want, Mr. Keizer.  I think I will leave it to you to figure out timing --

MR. KEIZER:  Yes.

MS. LONG:  -- based on when the DRC receives it and has time to digest it, and you can deal with confidentiality and security issues, and you'll raise that with us next week if those pose any problems.

MR. KEIZER:  Yes, Madam Chair.

MS. LONG:  Okay.

MR. MONDROW:  And, again, Madam Chair and gentlemen, thank you very much.  I'm done.

MS. LONG:  Okay.  Thank you.

Mr. McLeod.

# Cross-Examination by Mr. McLeod:

MR. MCLEOD:  Thank you, Madam Chair.

Panel, I represent the Quinte Manufacturers' Association, which is a group of manufacturers and processors in eastern Ontario.  And one of the things that we're particularly concerned about is -- many manufacturers are -- are cost control and business processes and policies and procedures.

Your testimony over the last day and a half now has been really helpful in particular.  What we were just talking about with respect to the DRC is of concern to us, so, actually, I'm going to take you through just now is the Charter, so that's at Staff IR 222, which is Exhibit L, tab 10.4, schedule 1.

And the dialogue we had just now has been helpful, but I would like to just go through a few more things which I think might help just clarify things for us.  If we look at the Charter -- I'm looking at page 1 of the Charter right now -- it talks -- and I'm looking at item 1, or paragraph 1, section 1, I guess, external independent oversight.  And (a) talks about:

"The committee reviews and approves the retention and compensation of qualified advisers."

Et cetera.

The next paragraph in (b) talks about:

"In carrying out its responsibilities for oversight of external experts and/or independent oversight, the committee reviews --"

And then it talks about:

" -- results and/or major findings from external assessments of the Darlington refurbishment project and management's proposed remediation programs and plans."

It reviews it.  Then what does it do?  That's my question.  What happens?  Where does it go?

MR. LYASH:  So the refurbishment committee reviews a wide range of activities, so, in this paragraph, for example, the feedback from Burns & McDonnell, as we have discussed, the Darlington Construction Review Board, which generally reports its findings to myself and Mr. Reiner, also has the opportunity to present periodically those results directly to the Darlington Review Committee.

The Nuclear Safety Review Board that looks at impacts on operating units, the World Association of Nuclear Operators, who does independent assessments, each of these independent assessments are provided to the board so they can consider and be cognizant of them, as are project -- as are internal audits in the company and audits done under our quality assurance program by the nuclear oversight organization.

So each of these streams of oversight activities has visibility to the Darlington Refurbishment Committee of the board.  Likewise, the expectation is that management provides full and accurate information on project performance to the DRC, with an emphasis on any gaps or performance deficiencies, that we make those visible.  It's actually part of the Burns & McDonnell mission to verify that management is providing complete and accurate information on performance, especially gaps.

That's put before the board, and the expectation of the board is that the management team identify for any gap what mitigation, what recovery, what remediation plans are necessary, either specific or programmatic in nature, to close that gap.

MR. MCLEOD:  Okay.  So when they've completed the review, what triggers it then to go forward?  Because it sort of stops there.  It says, "Okay.  They review it."  Is there an obligation then to bring it forward?  Is there a determination by them whether or not they bring it forward?

MR. LYASH:  Bringing it forward to the board --

MR. MCLEOD:  To the full board?

MR. LYASH:  Full board?  Yeah.  That determination is made by the Chair and the committee members.

MR. MCLEOD:  Okay.  Great.

MR. LYASH:  But the general expectation from the board is that any material issue with respect to refurb identified or discussed in the Darlington Refurbishment Committee is reported out at the full board.

MR. MCLEOD:  Okay.  Perfect.  Thank you.

Now, paragraph 3, or item 3, talking about the execution phase, again, the committee reviews and makes recommendations.  I see that.  And then, under (b), where it's talking about execution phase, progress, and safety scope, budget, and performance, is the DRC the first group to flag where there's problems for the board?

MR. LYASH:  No.  There is -- without going into a long description, there is a substantial and layered set of performance reporting, gap identification, and corrective action that rolls from the individual projects to the bundle to the project management team to the executive committee of the company, with myself as the Chair of that.  And it's the obligation of the management team, if there is a material issue, regardless of when it occurs, that that be raised to the board of directors, and I would do that directly with subsequent review by the DRC.

MR. MCLEOD:  And that would -- to me, that would make sense as an operational thing moving up to the governance level, so we're just trying to figure out:  There's so much information, enormous amounts of information.  How do you kind of manage this and make sure the board is properly informed of what's going on in the entire project.

So now I'm going to take you to the back part of the Charter, and I'm just looking at authorities, because the authorities for us sometimes becomes kind of critical.  And in the delegation of authority it says a couple of interesting things:

"The committee may not delegate its oversight responsibilities."

Okay.  It may or may not.

"The committee may delegate to a sub-committee."

Which could be yourself, Mr. Lyash, or -- and then here is where the concern comes in:

"Any employee of OPG."

Can you just explain what that means, if you wouldn't mind?

MR. LYASH:  Let me take a second to read the statement.

MR. MCLEOD:  Sure.

MR. LYASH:  Okay.  So I would comment that the way not to read that is in sort of the literal sense, any employee, meaning any engineer, any accountant, any lawyer.  But there may be occasions where the committee wants to delegate some activity to the chief executive officer.  There may be a situation where it's more appropriate to delegate an activity to the chief audit officer directly from the board, task the chief audit officer independent of the CEO to undertake some effort and report on some issue.  My sense of what's meaning here is that the -- of this is that the committee should not delegate its oversight responsibilities generally.  It should retain those, but it might delegate particular and specific sets of activities to be undertaken by individuals in the organization.

MR. MCLEOD:  Okay.  This is really helpful.  The reason I'm looking at this, not that it matters specifically for this, but outside my role here as being president of a corporation, these things become very important, especially when the committee a is committee of the board.  This wording sometimes gets us a little bit concerned, because you don't know how -- if something goes sideways on us.

It kind of goes back to what I think Mr. Mondrow was getting at and what the Modus reports do in reporting directly to the board.  That's where these kind of things would get captured, I think.  Is that correct?

MR. LYASH:  Yes.

MR. MCLEOD:  Perfect.  I guess the other circumstance I want to clarify:  Under what circumstance can you think of -- and I am not holding you to these, but just as an example -- where that delegated authority may go?  You mentioned audit, for example.

But if we're looking at -- let's suppose one of the project packages starts going sideways or something, and the board is advised of it and there's concerns raised at the board, how does this -- I'm trying to figure out the process for how it works so that it's managed and controlled.

MR. LYASH:  It's difficult to think of a hypothetical, because I don't have a practical example here.  The DRC hasn't moved to delegate activities of this nature.  They have tasked out independent and outside consultants to do reviews, as in Burns & McDonnell.

A hypothetical might be, if there is action or decision that needs to be taken in the flow of the refurbishment that's very timely in nature, where a decision has to be made, a contract written, an allocation of resources above what is otherwise my delegation limit of authority has to be made between meetings, it may require that the DRC to consider that in a special call and delegate the authority to move forward to me because of the urgency of the timing.  That's a hypothetical.

MR. MCLEOD:  Fair enough.  That's fine; I'm happy with that.

Now, the Infrastructure Ontario rep who sits on here, would he or she see that?

MR. LYASH:  Yes, the shareholder has contracted Infrastructure Ontario and put an independent representative who reports to the shareholder on the DRC.  That member functions as any other DRC member, except for engagement in voting on a decision.  Otherwise, they have full and open access to all the information and attend any activity scheduled for the DRC.

MR. MCLEOD:  I may be confused on this, but I think when I read in here that the board -- and correct me if I'm wrong -- does see the Infrastructure Ontario person's report, maybe not necessarily in the briefing of the Minister.

MR. LYASH:  Not necessarily.  The Infrastructure Ontario individual reports directly to the Minister, so we may or may not see any written report that is shared with the Minister of Energy from Infrastructure Ontario.

The practice is that -- to date is that, if there are concerns from that representative, he voices them in the DRC meeting, and they're addressed as any other concern or issue that might rise to the committee.  Also, following the board of directors meeting, the chair of the DRC and the Infrastructure Ontario representative hold a briefing of the Minister of Energy to share the results of the DRC meeting, at which point they talk about their independent assessment.

But directly to your question, we may or may not see what goes between the Minister and Infrastructure Ontario.

MR. MCLEOD:  Would it be fair for me to say, then, the discussion that goes on is reasonably transparent?

MR. LYASH:  Yes.  I have no reason to believe that the IO representative has concerns we don't know about.  The practice is to be very transparent.

MR. MCLEOD:  Thank you, that's helpful.  Those are my questions.

MS. LONG:  Thank you.

Mr. DeRose?

MR. DEROSE:  Thank you very much.

# Cross-Examination by Mr. DeRose:

MR. DEROSE:  Panel, my name is Vince DeRose, and I'm here on behalf of Canadian Manufacturers & Exporters.  The benefit of coming to the end of the group is I've narrowed my questions down to one area, and I'm going to remove us out of the weeds where we have been for most of the morning and take us to the 10,000-foot level again, because one of the concerns CME has is actually not with the Darlington refurbishment.

CME has publicly stated since 2010 that it supports Darlington refurbishment.  CME's concern is with maintaining Energy Board oversight of the project as it proceeds and just trying to understand exactly when and where the Board will be reviewing what has occurred.

If I could pull up -- I've given – so Exhibit D2, tab 2, schedule 8, this is a chart that Mr. Mondrow took you to this morning, and I think I'm going to use it as an aid to try and walk through some scenarios so we can understand exactly when and if the Board would have any further approval or scrutiny of the costs in the future.

First of all, panel, am I right this is your current breakdown of the unit 2 costs?

MR. REINER:  Yes, that is correct.

MR. DEROSE:  And I appreciate this was filed before there were updates.  So, for instance, the contingency shows 694, and I believe it's now 677.

MR. REINER:  Yes.  Let me go back.  I believe this is the release quality estimate breakdown.  There was a unit 2 execution estimate breakdown provided as well, and that is the most current.

MR. DEROSE:  Okay.  For today's purpose, I think we can use this one, and if you feel the other is more appropriate, we can turn to it.  But I don't think we'll have to.

First of all, in terms of this chart, am I right that, if we take the scenario that unit 2 proceeds perfectly on time and perfectly on estimate right down to the cent, that, in 2020, if you were to reproduce this chart for the Board, there would be either no contingency line or zero contingency and that -- we'll say 694, since that is on the chart now -- that 694 would be allocated to the various lines above it?  Simple approach?

MR. REINER:  Yes.

MR. DEROSE:  And if that were to occur -- again, if the Board gives you the approvals that you're asking for and approves the entire 4.8, if that were to occur, while you may provide that chart as some form of reporting, there would be no Board review of the line-by-line costs that occurred at that time?

MR. LYASH:  Yes.  Our fundamental position is that the $4.8 billion estimate is reasonable when resting on the basis that we've established and that, if we deliver the project for that price on that schedule, that withstanding indications of fraud or misinformation or a number of other things, that the Board would accept that as prudently incurred cost.

MR. DEROSE:  Again, just to make sure, not that the Board would in the future accept it as prudently.  What you're asking is that they accept it right now as prudently incurred; correct?

MR. LYASH:  No.  And I think this is an issue we took offline yesterday in response to some of Mr. Poch's questions.  All we're asking is the Board conclude, since this is forward looking, that the $4.8 billion and what it rests on is reasonable and that that would be used as the standard or the measurement in determining prudence.

MR. DEROSE:  So, for instance, five years from now, if you came in at 4.8, would the Board, from your perspective, be entitled to look at that 4.8 and say, "It should have cost you 4.6," if you get the approves you're asking for in this case?

MR. LYASH:  Hopefully, it won't be five years from now.  It will be first quarter of 2020.

MR. DEROSE:  Okay.

MR. LYASH:  So I'm not sure I understand your question, but I think we believe what we've done in terms of building a detailed cost, a detailed schedule, a detailed risk register, and the foundation we put this on demonstrates that the company has taken every reasonable action to deliver the project for 4.8, and that if we deliver it at 4.8, that should be a primary measure of prudence.

If you get below that in a project of this nature and start parsing, because we've acknowledged that risks don't materialize in small pieces; they materialize in large pieces, and one project here if the risks materialize may be higher than the number that's on the sheet.  Another project may be lower than the number that's on the sheet.  And these offset, and we manage it under the 4.8.

Conceivably, you could continue to raise that bar until you lowered this test to the task level, but the farther down you go, the more you're moving toward perfection as a standard.

And so just -- I say this just illustratively.  So what we're suggesting is the ten years' worth of planning and the substantial amount of evidence we've given form a basis to conclude that $4.8 billion and our processes are reasonable and that, if we implement them as we've planned and achieve that result, that that would be a substantial measure against which to judge prudence.

MR. DEROSE:  And I don't disagree with anything you've said other than the fact I'm just trying to understand the timing of the board's approval.  And you're asking for the approval of 4.8 billion from this Panel in this case, and my question is:  In the first quarter of 2020, or when you bring your next application, the first moment after it goes into service, will the next Energy Board Panel also have to make a decision on that 4.8, or will that decision have come and gone, and this Panel has made it, and it is not available for scrutiny anymore?

MR. LYASH:  I think you're asking a legal question that perhaps I'm not the best person to answer.

MR. DEROSE:  I'm actually happy to have Mr. Keizer answer.  Well, I didn't think that this would be a tough question.  I actually thought the answer would be, yes, this Panel is going to make the decision on 4.8, and no other Panel can look at that 4.8.

MR. KEIZER:  Well, our position is that that -- you know, if it's added to rate base and brought into service at 4.8 and forms part of rate base, when we return, you know, our rate base is restated to reflect former test year rate base at the time we return to reflect, you know, on our forward test year rate base at the time we return for whatever -- let's say it's another five years.  I don't know.  Then it would -- the rate base would include the 4.8 billion as approved by this Panel, and if there is some different number, 4.6 or 4 whatever, it's a CRVA issue.  That's effectively our position.

MR. DEROSE:  Okay.  Thank you.

And if it is 4.6, I believe you said yesterday that the board would not have a review of that 200 million, but it would be through the CRV returned to ratepayers?

MR. KEIZER:  Well, ultimately the board -- I don't want to give evidence here, but our understanding is that, with respect to any disposition of a deferral or variance account, the board ultimately reviews the entry in the account and makes the decision as to how that amount gets disposed of and whether the appropriate amount is reflected in the account.

MR. DEROSE:  Okay.  Well, let me turn to the situation where the CRVA -- where more -- a greater amount than the 694 million contingency is incurred, and so, hypothetically, instead of it being 694, you actually spend 894, so that the result is that the CRV has an additional $200 million that you would be looking to collect.

MR. LYASH:  So I assume in that example -- let me focus on the total instead of just the contingency, because there may be flows in and out.  So you're asking if the project is delivered but delivered for more than $4.8 billion.

MR. DEROSE:  Let's say five for the hypothetical.

MR. LYASH:  Say five.

MR. DEROSE:  Just so that we walk through, and the Board -- again, I want to understand what a future Panel would be looking at.  So you --

MR. LYASH:  Then I would expect that to show up in the CVRA (sic), and I would expect the OEB to question whether that additional $200 million was prudently incurred and examine that, and in doing so, they may have to work up from a base, but I would expect that they would look at that $200 million and determine whether it was prudent or not.

MR. DEROSE:  Okay.  And, again, if we look at the chart, I'm picturing that, if the number at the bottom, instead of it saying 4.799 billion, said 5 billion, and we would have all the numbers above -- let's assume retube was the only number that changed -- and it went -- or, actually, let's take two numbers -- that retube was the 1.8 billion plus 694 million, and the turbine generator had another 200 million added to it.  How would the board determine which of the -- what construction element is above the 4.8 or below the 4.8, or what's the driver of the increase?

MR. KEIZER:  I think that's only fair, though, I mean, to be able to evaluate that at the time that the consideration is brought before the board, and the board would then, through its own discretion, decide how to inquire into the 200, if it's the $200 million overage, as to the nature of it, where it came about, why it came about, and what effects or measures were the implication of that.  I mean, I don't know how helpful it can be today to pick a line number and say, "Well, this one goes up, and that one goes up.  What would the board do?"  I think he can only look at the facts at the time when the application is made, and, you know, obviously through that process, it would be evaluated and considered.  So I don't think it's a fair question to pick a line and say, "What would happen if this is the case?"

MR. DEROSE:  I guess what I'm trying to understand is that there is a contingency built in that the board would be approving now, and if you approve it, you would be approving an amount of money that you do not know what it will be spent on.  And if the CRV captures money in addition to that, my question right now is:  How do you, as the board, post facto determine what is the contingency that you've approved and what is the -- what's driving the additional amount?  I mean, it's --

MR. KEIZER:  Well, but I think, as Mr. Lyash just said, that it's beyond just looking at the contingency, because there may be circumstances where no contingency was used and certain projects are below an amount of money.  So I don't know if we're only talking about the evaluation of any contingency at the time that the $200 million theoretical overage actually occurred, and that's where I don't think you can tie -- I raise the fairness of the question as to the overage to the contingency itself.  It's in respect of the total project cost, of which contingency is a part of it, only because certain risks have materialized, and so you understand what risks have or haven't materialized and how they were mitigated.  I don't know if you can really evaluate it in this proceeding.  It's really the proceeding to come.

MR. LYASH:  Yes.  And I would add that let's remember that you're not making that future assessment from a blank sheet of paper.  It's precisely why we have developed a unit 2 execution estimate.  It is a very detailed baseline budget and schedule, and the $694 million contingency has a very granular basis to it.  And so that gives you a clear picture of how we intend to execute the project that allows you then to -- I can't predict how it will be evaluated, but it gives you a basis upon which to evaluate the actual performance when the project is concluded and assess what cost drivers were relevant to any amount of money over the $4.8 billion.

So while it's not entirely precise, because it can't be predicting the future, in our views, it gives a good solid basis for the OEB to start from in reviewing those expenditures.

MR. DEROSE:  Okay.

MS. LONG:  Sorry, Mr. DeRose, can I take you back to your question?  I'm just not clear.  When you talk about the next time the OEB will see OPG, are you talking about the next fees case --

MR. DEROSE:  Well --

MS. LONG:  -- are you talking about the midterm review, or --

MR. DEROSE:  -- I was actually just about to ask on both the midterm review and the --

MS. LONG:  Okay.

MR. DEROSE:  -- rates case, so you've --

MS. LONG:  Okay.  I just wasn't clear, so --

MR. DEROSE:  Yeah.

MS. LONG:  -- perhaps you can ask your question.

MR. DEROSE:  I'll actually -- and let me ask one question between, and then I'll get right to that.

Now, when you mentioned granularity, are you able or  -- not are you able, but have you actually taken the 694 and broken it down or assigned it to the granular level of each of these line items?  So, for instance, could you tell us how much of the 694 has been allocated to contract management or engineering or to planning and controls?

MR. REINER:  Yes.  There is an allocation of that contingency across the projects.  There is also an allocation, as we talked earlier, and panel 1B will get into more detail on this.  There is some that's held at general contingency that goes across all projects.  But there is a breakdown of that contingency.

MR. DEROSE:  And is it possible -- and I'll ask this in advance of 1B, I guess.  But what would be very helpful for us is if this chart could be reproduced with one additional column that shows the allocated contingency for each of the line items, if it has been allocated to those line items?

MR. KEIZER:  I think there was a chart or table this morning we looked at, which had project level contingency and program level contingency.

MR. DEROSE:  It did have it at the project level.  My question is:  Do you have it at the level we're looking at in this chart?  If you don't, that's fine.  But if you do, we would like to be able to say, for instance, retube feeder replacement, 1.8 billion.  There would be a column that says contingency -- I'm throwing out numbers -- 100 million, turbine generator, et cetera.

If you don't have it at that level, that's fine.  But if you do, it would be helpful to have it in a single place, in a single chart, where the Board can see what the costs are and the attributed contingency.

MS. LONG:  Mr. DeRose, you're talking about the first five lines that you would like the contingency value?

MR. DEROSE:  If contingency has been allocated to the other subtotal functions or the bundles -- I don't think it has, but if it has, we would like to just see --

MS. LONG:  Do you know, Mr. Reiner, is there a contingency for work control, as an example?

MR. KEIZER:  Sorry, I don't want -- but maybe this is helpful.  Staff is showing me Exhibit D2, tab 2, schedule 7, page 8, a breakdown of contingency amounts.

Page 8 of 10 is now on the screen, Mr. Reiner.

MR. DEROSE:  Thank you very much.  I apologize; I had missed that.

MR. KEIZER:  Is that --

MS. LONG:  I think that meets your purposes.

MR. DEROSE:  That's exactly what I needed.  Thank you very much.

If we can go back to chart 4, please.  Now, I would like to talk about a scenario that again -- and I appreciate that you would not like this to happen, but if the Board were to approve in this case only the 4.1, the subtotal before contingency, to go into rate base at this time, am I right that any money that would be spent between now and 2020 that would normally be part of the contingency would automatically flow into the CRV?

MR. LYASH:  You're proposing a construct that's not the one we submitted, so I'm no the sure how that would work.  I would say that if you -- if you took contingency out of the project, fundamentally you're under funding the project.

MR. DEROSE:  Let me rephrase.  The Board is free to approve into rate base whatever amount they want.  First of all, we can agree on that?

MR. LYASH:  Yes.

MR. DEROSE:  And whatever amount the Board approves to go into rate base in this hearing does not prevent you from spending more money than that on the project.  Can we agree on that?

MR. LYASH:  Correct.

MR. DEROSE:  And any money that you spend in excess of what the Board approves, I understand, will be put in the CRV?

MR. LYASH:  That's the way I understand it, yes.

MR. DEROSE:  What I'm suggesting to you is that, if the Board -- if this Panel were to approve 4.1 billion instead of 4.8 billion to go into rate base, so they simply do not approve the contingency, am I correct, at the midterm review, when you clear the CRV, any incremental funds would be cleared at that time?

MR. KEIZER:  I think the treatment of the midterm review in the CRVA is probably better for panel 2, which is midterm review, as to what's expected and what would happen at that point.

MR. DEROSE:  Okay.  And whether it happens at the midterm review or not, I take it you would agree with me -- actually that's fine.   I'll just leave it there.

MS. LONG:  I thought I heard this morning, Mr. Keizer, that the CRVA would be handled at the midterm review.  Are you saying that's an issue better dealt with by another panel, and it can be flushed out then?

MR. KEIZER:  Just to clarify, my understanding is the CRVA consideration at the midterm review is in respect of 2018 balances, but any monies associated with this project wouldn't -- although registered in the CRVA, the project wouldn't be in-service by the time of the midterm review, so wouldn't be eligible for consideration in any event in respect of unit 2 DRP.

MR. DEROSE:  I can ask to panel 1B when the CRV would happen for this project.

MS. LONG:  Okay.

MR. DEROSE:  Those are all my questions.  I'll move to panel 1B afterwards.

MS. LONG:  Thank you, Mr. DeRose.  I think we will take our lunch break now for an hour and be back.  And it will be you, Mr. Janigan, that will be up?

MR. JANIGAN:  That's correct, Madam Chair.

### --- Luncheon recess taken at 12:49 p.m.

### --- On resuming at 1:58 p.m.

MS. LONG:  Mr. Janigan, I see a compendium in front of me here.

MR. JANIGAN:  Yes, it is, Madam Chair.

MS. LONG:  Is that K1.5?

MR. RICHLER:  It's K2.1.

MS. LONG:  Oh, 2 -- okay.  Sorry.

Exhibit No. K2.1:  VECC compendium

MS. LONG:  Are you ready?

# Cross-Examination by Mr. Janigan:

MR. JANIGAN:  I am.  Thank you, Madam Chair.

Good afternoon, panel.  My name is Michael Janigan with the Vulnerable Energy Consumers Coalition, and I believe you have a copy of my compendium.  I would like to start, actually, at the tail end of that, principally because you dealt with a lot of the oversight matters that I was going to deal with later, and I have just a few clean-up questions on that.

I wonder if you can turn up page 63 of my compendium.  And it deals with the internal audit group and the refurbishment construction review board.  And I was wondering:  Does one inform the other, or are they entirely separate in terms of their functions?

MR. LYASH:  They are entirely separate in terms of their functions.  The internal audit organization is a classic standards-based audit organization, compliance and performance, and it reports to our senior vice-president and chief financial officer.  And it reports directly out to the audit committee of the board.

The Refurbishment Construction Review Board is a set of industry experts that we retained on a periodic basis to evaluate performance and report out to Mr. Reiner and myself.  They also report their results out directly to the Darlington Refurbishment Committee, although I must say that each of those organizations has access to the others' products.

MR. JANIGAN:  Okay.  So the internal audit group's information might inform that committee?

MR. LYASH:  Correct.

MR. JANIGAN:  Okay.  On page 64, it deals with the Darlington Refurbishment Committee, and as you've indicated, the Ontario Government or Ontario -- Infrastructure Ontario has a member of that committee, a non-voting member, as I understand.

MR. LYASH:  That's correct.

MR. JANIGAN:  Now, did I read somewhere that the Infrastructure Ontario member is actually a consultant that has been appointed by Infrastructure Ontario and is paid by OPG?

MR. LYASH:  Yes.  The Minister of Energy selected Infrastructure Ontario to be their independent adviser, and, as I understand it, Infrastructure Ontario recognized that they needed a breadth of experience that they didn't possess internally, so they went out for a contract, and they independently decided who to hire, and that's the individual.  The budget for that, we don't set, but OPG is responsible for funding it.

MR. JANIGAN:  Okay.  And that individual is not connected with any of the contracting parties of OPG?

MR. LYASH:  No, they are not.

MR. JANIGAN:  Okay.  In the same area, just before that, on pages 55 and 56, I was wondering how the change management process works in with things like the Darlington Refurbishment Committee, or is this operating on a much lower level?

MR. REINER:  The change management process operates at a much lower level than the Darlington Refurbishment Committee.  It's a day-to-day process that tracks all changes.  It has a review board associated with it.  So based on the magnitude of the change, the change review board will get called in to assess and review and approve, and then it could make its way, depending on the nature of the change and the size of the change, it does -- all of this does roll up in terms of tracking performance for the project.  And if there is a material change that requires an approval authority in accordance with our OPG authority register, it could make its way up right up to the Darlington Refurbishment Committee.

MR. LYASH:  So just to add, there is a division of responsibilities and delegation limits of authority and a process lying overtop of this working change management process that would drive escalation of issues at certain -- certain types of issues or levels of materiality up through the DRC and the board of directors.

MR. JANIGAN:  Was the D20 heavy water project that -- change that took place, was that part of this process?

MR. REINER:  You'd have to tell me which particular -- so the recent change to remove it from this proceeding?

MR. JANIGAN:  That's correct.  Was that part of the change management process, or did it take place in another process altogether?

MR. REINER:  That change did not go through this -- the diagram that you have here.  That decision to remove it from this rate application did not go through this process.  However, the analysis that we are going through to assess schedule and cost for that project, that does follow this kind of a change control process.

MR. JANIGAN:  Is this a process that is frequently resorted to, or is it something unusual?

MR. REINER:  It is part of our project controls.  It's a day-to-day process.  It's a mechanism that allows us to clearly document and identify anything that creates a deviation or a variance on schedule or on budget.

MR. JANIGAN:  Okay.  I would like to go back to the front of my compendium now, and the first thing that I wanted to look at is a conversation you had yesterday with Mr. Buonaguro and, in particular, on pages 2 and 3 of that compendium.

And Mr. Buonaguro was discussing with you matters associated with the prudence of your capital estimates and whether or not overexpenditures might be imprudent and matters such as that, and he is quoting from the transcript from the Technical Conference of Mr. Rose.  And at the bottom of page 2 he indicates -- he reads from that transcript:

"Now, this answer talks about the program or project level.  That begs for me the question:  Is there some other level that is missing from the answer?  If there is some other level that was considered, whether it would be program costs that OPG would have anticipated as a risk that may be manifest, are you going to have to absorb rather than collect through the CRVA?"

And, in this case, Mr. Rose, who, I believe, was on panel 2, answered, and he said:

"No, I can't think of anything.  So we manage refurbishment as a program."

And goes on further down the page:

"The correlation to projects in excess of 12.8 billion, that's our internal motivation to be able to deliver the four units at 12.8 billion."

And further down the page he indicates, quoting from the Technical Conference again, then I said:

"Then, in fact, your answer here is that you can't conceive of a world where it wasn't prudent?"

And on the following page Mr. Rose indicates:

"That's correct."

It would appear, at least from Mr. Rose's standpoint, that, given the degree of planning and planned execution, that even though you may be expending monies that exceeded your estimates, that nothing that you did or expended would be imprudent.  Is that the sense you got from this exchange?

MR. LYASH:  No, it wasn't.

MR. JANIGAN:  Okay.  And certainly you come in with the -- at the bottom of page 4:

"Certainly, there's certainly risk associated with the project, and the risks may or may not have materialized, so OPG's obligation is to prudently -- reasonably and prudently manage this.

So the fact that the project, if there is a series of events that cause the project to run over, wouldn't necessarily mean OPG is imprudent.  So, in effect, what you've indicated is that, I believe, if there is an overexpenditure and the money is in the CRVA, there would be a prudence review of whether or not there is an overexpenditure, and that would determine whether or not OPG could collect on that amount.

MR. LYASH:  Yes, I agree.  And if I may, as I look at Mr. Rose's exchange -- and I wasn't there for this exchange, but as I read it over, Mr. Rose is projecting risk prospectively and identifying in the risk register risks that we can conceive may occur and that we then would have to manage.  And you wouldn't put a risk in the risk register of imprudence, right, that I would mismanage and, therefore, put it in the register, because then I'm pricing imprudence into the contingency.

I think what he was referring to is I can't imagine an imprudence-related risk that I would put in my risk register as a prospective matter.  But I think I agree with, if I heard you correctly, your characterization that, if the project costs us more than $4.8 billion and that is landed in the CRVA, then I would expect the OEB would closely evaluate that to determine whether imprudence was a factor in that cost overrun.  And it may or may not be imprudent, depending on the facts.

MR. JANIGAN:  Let's take this scenario where there is a cost overrun.  If I take you to page 38 of my compendium, which is the report from Concentric, it has in numeral III the standard of review about halfway down the page.

Specifically, Concentric defined the prudent standard as:

"Examining the range of actions a reasonable manager would take given the facts or circumstances that were known or knowable at the time of the decision or action.  The decision rejects the use of hindsight as a basis for determining the prudence of a decision or action."

Would you agree with me that is the standard that the Board would apply in looking it at whether or not the overexpenditure was prudent or not prudent?

MR. LYASH:  I'm sorry.  I had trouble getting to the spot.

MR. JANIGAN:  That's okay.

MR. KEIZER:  Isn't that a legal question, Madam Chair, and one of argument as to whether that does or does not apply?

MR. JANIGAN:  No.  I would ask if he agrees with that in terms of what the standard was that OPG would meet.

MR. KEIZER:  Again, I say -- he can give you what the position of the company is, how they intend to seek it and what the application says.  But whether that is the definition in law as put forward by Concentric, making reference to various cases and case law, I think is a point of argument.

MR. JANIGAN:  Let me rephrase the question.  Do you agree that OPG has acted as a reasonable manager in putting forward this application and has taken into consideration the facts and circumstances that were known or knowable at the time of putting forward this application?

MR. LYASH:  To the best of my knowledge, yes.

MR. JANIGAN:  Okay.  If I can turn you to page 7 of my compendium, you've outlined some of the steps that you've taken to try to be a reasonable manager, I would assume.  And that includes, down at the bottom of the page, that you've also engaged independent experts to review and verify key aspects of the program, and you list all of the independent expert reviews that were provided in support of the evidence.

Would you agree that that was in pursuit of your responsibilities as a reasonable manager?

MR. LYASH:  Yes.

MR. JANIGAN:  Okay.  And I want to look at what each of these reports included.  First of all, the KPMG report on pages 11 and 12 and on page 10 of my compendium notes that:

"KPMG was engaged by Ontario Power Generation to provide an independent review of the risk management and contingency development process for the released quality estimate for the Darlington Nuclear Refurbishment Program, DNRP."

On the following page, page 11, it indicates at the top that:

"Overall, OPG's governance, methodology, and approach aligns with AECC guidelines and industry practice in terms of identifying and classifying risk and utilizing an integrated Monte Carlo-based risk analysis."

Do you see that?

MR. LYASH:  I see it.

MR. JANIGAN:  And on the following page, at the top of the page:

"It is KPMG's view the risk register implementation by OPG in the RMO tool is of quality and integrity.  It is also in alignment with industry guidelines and best practices.  The RMO risk register adequately encompasses the risks identified by project managers and the broader OPG team through ongoing risk workshops and team meetings conducted by the OPG DNRP team."

So, effectively, this methodology was given some sort of seal of approval by KPMG.  Do you agree with me?

MR. REINER:  Yes.

MR. JANIGAN:  Moving ahead, on page 17:

"KPMG also was engaged by OPG to provide an independent review of their governance and process to develop a reasonable risk quality estimate."

And on page 17, midway down the page, it says that:

"OPG has demonstrated knowledge of the AACE guidelines and generally interpreted and correctly applied them to the DNRP program, and we also note that aspects of OPG's estimating governance and processes for the DNRP are strong."

In a number of areas that they list, and also gives, on the next page, that:

"In fact, there are no critical gaps in the A category."

Agree with that?

MR. REINER:  Yes.

MR. JANIGAN:  That's another way in which your  process or approach has been deemed reasonable by an outside expert; correct?

MR. LYASH:  Yes.

MR. JANIGAN:  Okay.  I'm not buttressing your evidence here.  I'm going to get to a point eventually.

On page 21, this is a report from Modus Burns McDonnell, and they were looking at -- they assessed at the top of the page the DR team's process for developing the release quality estimate which OPG and the DR team have been developing since 2009.  And on page 27, it's noted that:

"While risk management contingency development have many subjective aspects, the DR process has been relatively well constructed and executed.  It is perhaps in the upper percentile of comparable project practices."

Once again, a clean bill of health from this company?  Would you agree with that?

MR. REINER:  Yes.

MR. JANIGAN:  Further in that same report:

"In summary, Modus found that OPG has substantially conformed to the governance it put in place for RQE and the guidance from AACE International on which governance was based."

Going ahead, we have an expert panel review, and the expert panel review dealt with matters associated with the RFR project and indicates on page 32:

"One of the definitions of phase deliverables of the joint venture is an AACE Class 2 estimate to perform the execution phase of the RFR project.  As OPG prepares to accept, this estimate from the JV as part of the determination of the execution phase target price that ultimately the release quality estimate for the Darlington refurbishment projects due diligence requires an independent review of the Class 2 estimate."

And, on the next page, on page 33, that notwithstanding some of the things that they noted might be -- could be addressed, nevertheless the panel was able to conclude that the risk management processes, taken in context of all of the risk, recognizes that all the risk-related information provided is sufficiently mature to support the Class 2 estimate.

So your Class 2 estimate was also reviewed by independent sources and found to be sound; correct?

MR. REINER:  Yes.

MR. JANIGAN:  All right.  Now, on page 38 of the Concentric report, I earlier referred to notes that:

"As discussed below, Concentric has concluded that, based on the Ontario Power Generation's activities regard to amending and finalizing the retube and feeder replacement contracts since our last report, the terms of the retube and feeder replacement contract, including the target price and the allocation of risk, are both reasonable to meet the regulatory standard of prudence as we've defined the concept in the September 2013 report and repeat herein for convenience."

And that is that section that I read to you earlier.

So, once again, your activities in relation to amending and finalizing the retube and feeder replacement contract were also found to be sound; correct?

MR. REINER:  Yes.

MR. JANIGAN:  And, on page 45, the report -- the testimony of Dr. Galloway looks at the Darlington refurbishment program and finds on the top of page 45 that:

"OPG is using a strong matrix organization comprised of full-time project managers with considerable authority and full-time functional support stuff, and the content and scope of OPG's program and project management plans is consistent with industry best practices and other megaprojects and megaprograms that we've reviewed."

And finds that they have the most qualified individuals, efficient oversight in place, and the program management organizational staff decisions are reasonable in accordance with good utility practice.  Do you see that?

MR. REINER:  Yes.

MR. JANIGAN:  So it would appear that, at least in terms of your planning and the reports that you've obtained, that you've acted as a reasonable manager in attempting to bring forward this application?

MR. REINER:  Yes.

MR. JANIGAN:  Can you tell me, in the event that you have an overexpenditure of your estimate, what information would be brought before the Board that would suggest that whatever you've done in accordance with your planning, and application would be imprudent?

We have seven reports here that set out that you have followed the appropriate procedures of a manager, and what happens if there is an overexpenditure based on what you have planned and what you have approved?  What chance would you think that the Board would find your actions imprudent and associated with an overexpenditure?

MR. LYASH:  That's a very difficult hypothetical question to ask.  In the event that there was an overage on the project, whatever amount, we think we've taken all the reasonable actions that management can to establish the 4.8 and to be prepared to execute on it.  But we still must execute the project.

And, as we said, these are complicated projects.  There will be discovery.  There will be unexpected conditions occur.  There may be performance issues that arise with one or more contractors.  And it's the company's obligation to take those eventualities and manage them prudently and to defend that prudence if we run over the $4.8 billion estimate.

So, if we're over that estimate, I would expect, to the extent that that delta exists, that the OEB would want to examine that for prudence and that the burden to prove we were prudent would be on the company.

MR. JANIGAN:  That could well be the case, but won't you be pointing to all of these reports and processes that you have instituted to show prudence in the execution of your application?

MR. LYASH:  As we should, because they form a basis for reasonableness and prudence.  Now, our performance in consistently executing in concert with these is another matter.

MR. JANIGAN:  Okay.  Now, let's wind it back a little bit.  All of these reports and all of the planning and extensive planning that you've done has been part of a very detailed planning process that's all been paid for by ratepayers.  Wouldn't you agree?

MR. LYASH:  Well, the asset is not in-service, so I'm not sure of your question, but...

MR. JANIGAN:  Well, if this goes forward --

MR. LYASH:  As we sit here today, we've invested $2.8 billion in planning, preparation, and definition, and what we're proposing is to bring the portion associated with unit 2 into service in 2020.

MR. JANIGAN:  Given the fact that ratepayers have paid for all this, isn't there some expectation that they should be given a little more assurance about whether or not cost overruns are going to be mitigated in the event they occur?

MR. LYASH:  I'm not -- first of all, as I said, the asset is not in-service.  We're proposing to bring it into service.  So, to this point, the ratepayer hasn't shouldered these costs, but if our proposal is approved, they will at a date in the future.

MR. JANIGAN:  Understood.

MR. LYASH:  With your regard to assurance, I'm not sure what assurance you have in mind other than the thousands of pages of testimony we've put here, the reporting we've committed to the OEB, the layered oversight process we put in place, running from the project level through executive management, the board of directors, and through the shareholders' independent adviser.  And my sense is those provide a robust set of assurances that the project will be managed prudently to deliver the results and that, if we manage the project imprudently, then the OEB will be in a position to disallow that.

MR. JANIGAN:  Well, given what you have spent in terms of the planning process and given the fact that you've set up things like your contracting process to ensure that there are appropriate off-ramps and appropriate target pricing, given that you've built in contingencies, why shouldn't you have to bear at least some of the consequences if you are -- or, for example, some of the benefits if you exceed the budget or come in below budget?

MR. LYASH:  I think the shareholder does bear the consequences if we don't manage the project prudently.  That's the role of the OEB.  And there is the basic regulatory compact and the process we have before us that defines that.

MR. JANIGAN:  But you are the one that is executing this project.  You are the ones that have set up and done the planning associated with this.  And couldn't you stand behind this project and say, "Look it, this is the amount that we're going to meet.  If we don't meet it, we will take some of the consequences, but if we come under we should have the benefits too"?  What's wrong with that?

MR. LYASH:  That's not the process as it exists today.

MR. JANIGAN:  I know that's not the process, and you've indicated that the reason that that process has not been resorted to is that you believe that cost does not necessarily -- attention to cost does not necessarily reflect attention to performance, if I can paraphrase your answer.

MR. LYASH:  I did provide an answer of that nature, yes.

MR. JANIGAN:  And the reason that you say that is that you feel that, in the event that you were motivated by financial incentives, you think the performance of OPG would suffer?

MR. LYASH:  I did not make that leap in my answer.  Our determination would not be to allow it to suffer, not to allow it to suffer.  My point was that putting a -- putting a capital incentive on a project whose value is delivered over 30 years and that value is so dependent on the safety, the reliability, and the cost-effectiveness of the unit post-refurbishment would not be an incentive that would necessarily be in the customer's long-term best interests.

MR. JANIGAN:  Well, I think I'm going to try to square those two aspects of your answer.  First, you said that performance of OPG would not be affected by financial incentive, and I think what you've told us before this is that it's a destiny project, that you have an obligation -- as an Ontario business corporation, you have an obligation to the taxpayers of Ontario also personally invested in it.  None of that performance would suffer.  Do you agree?

MR. LYASH:  I'm sorry.  What I'm saying is we have plenty of incentives to deliver the project on or ahead of schedule, on or ahead of budget, and I think I've outlined those several times.

What I was referring to -- and, again, if you had a specific incentive in mind or disincentive, perhaps I could answer the question better.

MR. JANIGAN:  Effectively, the kind of incentive that's associated with meeting a budget, that, in fact, if you come under the budget that you've set, that you get some financial benefits from it, and if you exceed that budget, that you have to absorb at least some of those costs.

MR. LYASH:  If we come under the budget, then we will have delivered the project under budget.  It will reduce risk of the additional Darlington refurbs and provide us an opportunity to earn income on those assets, and it will serve to help expand our ability to make other capital investments.  And so we do benefit from that.

If we come in over the budget, and that is examined by the OEB and deemed to be imprudent and disallowed, then that disallowance comes directly off a net income and return on equity, and that is a penalty for that performance.

MR. JANIGAN:  But I would suggest the possibility of a disallowance, given the symmetries of information that exist between OPG and other stakeholder interests are so substantial that the likelihood of a prudence review resulting in some kind of penalty to OPG is pretty slim.

MR. LYASH:  I don't agree.

MR. JANIGAN:  You've gone over with my friends the previous experience of other megaprojects.  Given that experience, don't you think the ratepayers might require additional assurance of your ability to meet the estimated budget?

MR. LYASH:  We've tried to provide that assurance in the testimony that's on the docket, and in the way we have constructed the costs, the schedule, the risks and the contingency.  I'm not sure what additional assurance you're referring to.

MR. JANIGAN:  You've indicated, notwithstanding how prudent you've been in terms of planning this project, there is the possibility that the execution might go awry.

MR. LYASH:  I think, in a project of this nature, not all will go perfectly.  That is the only thing with a certainty of 100 percent.  The challenge for OPG will be to identify those issues early, characterize them completely, and take every reasonable and prudent action to mitigate them.

MR. JANIGAN:  What would be your response if the Board elected to put in the kind of financial incentive associated with meeting the budget you put forward in this application?

MR. LYASH:  The OEB has broad discretion.  They're our regulator, and we would certainly respond constructively, as constructively as we could to that.

MR. JANIGAN:  To circle back to your previous answer, this may induce greater attention to cost possibly.  Would that attention negate from OPG's performance?

MR. LYASH:  Again, it's a hypothetical question.  I don't think such an incentive would have an effect to drive OPG in some way to delivering the project at a lower cost.  That's already our objective.  We would have to guard against that introducing inappropriate behaviours or objectives into the project.

MR. JANIGAN:  Finally, I wonder if you could turn to page 49 of my compendium.  This is something that came up from a footnote in Dr. Galloway's report and was followed up by AMPCO, and it involves a memorandum of understanding between Bruce Power and Ontario Power Generation Inc. and issued under the authority of both yourself and Mr. Hawthorne of Bruce Power.  What's been the fallout of this?

MR. LYASH:  I'm sorry.  Your question is?

MR. JANIGAN:  What has been done in relation to the memorandum of understanding since the understanding was entered into?

MR. LYASH:  This formed the opening of what has become a rather extensive collaboration program.  I could spend some time detailing it.  I'll try to summarize it for you.  We have established teams in each organization who work on an ongoing basis on a set of collaboration opportunities, opportunities that can either shorten schedule, reduce cost, improve safety, reduce radiation exposure, or eliminate risk.  Those teams talk on an ongoing basis and work towards those ends.

There is also an executive steering team that is chaired by myself and Duncan Hawthorne's replacement, Dr. Renchek.  We review status every two weeks in a telephone call.  We meet quarterly to look at results over the last quarter and projected activities we want to complete in the next quarter, and that has produced a range of activities.

Mr. Reiner may want to add some other examples, but one I would give you is, as an example, we have seconded some experience -- some Bruce Power individuals with experience with their prior refurbishment directly into the OPG refurbishment team so they can bring that experience with them and so they can take experience from our project and return that firsthand to Bruce for their execution.

MR. JANIGAN:  I note on page 52, there is an annual summary report that's been prepared.  Has one been prepared?

MR. LYASH:  Yes.  It was issued and it's publicly available.  I can't recall the date; it's maybe 60 days ago.

MR. JANIGAN:  When you say "publicly available," is it on your website or something like that?

MR. LYASH:  I'm sure it is.  We can get you a reference to where that is.

MR. JANIGAN:  Okay.  Thanks very much.

Finally, just a question I forgot to ask initially:  The annual status reports, the annual status public reports and your report to the OEB, is that one and the same?

MR. LYASH:  Which?

MR. JANIGAN:  If you go to the oversight section, there's a mention that you're going to be preparing annual reports – sorry, just before the oversight section.  And on the bottom of the page 61:

"OPG plans to issue annual status reports to the public for the duration of the program through its website.  This reporting will include a range of measures."

Et cetera, et cetera.

Is that the same -- that public reporting, is that the same as your report to the OEB?

MR. LYASH:  The one referred to here in the table at the top of page 62, that particular reference is to the OEB report.

MR. JANIGAN:  Okay.  But is that also the report to the public, or is that different?

MR. LYASH:  We have established a practice of quarterly summary reports to the public posted on our website.  Perhaps that's what you're referring to.

MR. JANIGAN:  Okay.

MR. LYASH:  We do a monthly update, and then we do a quarterly more extensive report on the website.

MR. JANIGAN:  This is an annual report that's referred to here.

MR. LYASH:  This is the OEB report.

MR. JANIGAN:  And that's going to be available to the public as well?

MR. LYASH:  Correct.

MR. JANIGAN:  Okay.

MR. LYASH:  I should say, let me say -- I'm assuming submitting it through the OEB process makes it a public report.  Perhaps my language is a little loose there.

MR. JANIGAN:  Would the OEB release it, or would you release it?

MS. LONG:  I'm assuming it's going to be filed publicly.  Is that what you're contemplating?  And, therefore, it would be public filed on the record?

MR. JANIGAN:  Okay.  Thank you very much, panel, for your patience.  Those are all my questions.

MS. LONG:  Thank you, Mr. Janigan.

Mr. Tolmie?

MR. TOLMIE:  Is it working?

MS. LONG:  I can hear you, yes.

# Cross-Examination By Mr. Tolmie:

MR. TOLMIE:   Thank you.  You're both engineers by background, I think, so you can put on your engineering hats for what I'm going to talk about.  Maybe they should be hard hats, though.

What I want to talk about is energy storage, which is the field I work in.  I work in the field of R&D for energy storage in Sustainability Journal, and OPG presently uses energy storage on a very large scale.  People don't talk about it very much, but you have nuclear power sources that are providing power at a costed output.  You have this band that's fluctuating over a tremendously wide range, and the thing that matches those two is, in fact, the storage of the ponding of the hydro facilities.

You also have some generation involved, because there's peak generators run by natural gas, but a very large part of it is, in fact, a storage issue, and I think storage should be considered one of the risk factors in doing the engineering for this type of system, that if you're using storage appropriately, you can, in fact, reduce the costs of this kind of system very substantially, by billions of dollars, in fact.

Now, you've already gone through a definition phase for the NDRP project, and that phase is based on the 2013 long-term energy plan plus various regulations and directives that have flowed out of that plan.  The planning is subject, though, to off-ramp decisions that may be made to government approvals on the various components of the system, to potential changes in the LETP itself that are currently underway, and intervening events have been happening that are changing government policy in quite fundamental ways.  So we need to go back to basics to see if there is a possibility that energy storage could, in fact, help at this stage in the game to make the systems work better or cheaper or more reliably, and the basic number that we're dealing with in all energy systems is how many megawatt hours of electrical energy you're using per year.

In Ontario, that amounts to about 150 terawatt hours, 150.4, to be exact, for last year, and if you go back for about a decade, it was approximately the same, a little higher some years, lower other years, and the projections from the IESO are that it will either remain constant by one scenario or may increase quite substantially by some other scenarios.  It might increase by 50 percent up to the year 2035.  But, basically, we know we have to deal with that kind of output from the power system.

Are those numbers sort of reasonable to you?  I don't want to go off on a tangent here.  If the source of power, whatever it is -- we need 150 terawatt hours per year.  If you have a supply source of load following -- ACR 1000, for example, was supposed to have been load-following a reactor -- a load-following system can handle the demand changes as they occur, so a load-following system only needs 17,000 megawatts of power, capacity.  That's 150,000 -- 150 terawatt hours divided by the one year's worth of hours.  There is no need to generate more power than that if your system is load following.

MS. LONG:  Mr. Tolmie, I don't mean to interject here, but are you going to frame these questions --

MR. TOLMIE:  Yes, sorry.

MS. LONG:  -- in the context of Darlington?   Because --

MR. TOLMIE:  I go on for --

MS. LONG:  -- this is the Darlington --

MR. TOLMIE:  -- prologue the whole thing, and that leads to questions.  Is that okay?

MS. LONG:  Okay.  Well, can you get to the questions quickly?  I'm trying to follow your line of thought.  Is this with respect to off-ramps that you're discussing energy storage?  You need to bring this within the context of what this panel can talk about, which is an overview generally of the DRP project.  I know you have questions for many of the other panels, but this panel specifically is talking about overview of Darlington, so you can frame your questions in that context --

MR. TOLMIE:  That's what I'm trying to do --

MS. LONG:  -- it would be helpful --

MR. TOLMIE:  -- but unfortunately the question requires that I explain what the rationale for the question is before I pose the question itself.

MS. LONG:  Okay.  Well, I hope you get to the question soon.

MR. TOLMIE:  Okay.  I won't be very long.  I'll be well within the --

MS. LONG:  Okay.

MR. TOLMIE:  -- 20-minute time scale, so I'm not going to keep you too long.  And if there's any questions that you have, by all means, bring them up.

There is no need to generate more than 17,200 megawatt hours and -- megawatts, I should say, and it's possible that we might not need to produce even that amount.

I mentioned that we are going through periods of change in energy supply.  One of those changes is going to be the adoption of procedures that adapt to the Paris Climate Change, very tough thing to meet.  And that is going to mean that we have to look at all of the energy sources or none -- they all have to be looked at, at the same time.  If you're going to reduce the consumption of -- reduce the production of greenhouse gases, then you have to think about all the greenhouse gases that are being produced by heating your homes, and when you heat your home, one of the options is use energy storage.  You can store summer heat, heat the home with that.

One of the options, one of the opportunities that's available, is that you can use that process to also store electricity.  You're, in effect, using the electricity to  -- the technical word is to increase the exergy of the stored energy, so you're actually storing both heat and electricity concurrently, and that is what we're driving at.

Have you considered the potential of using that type of storage to reduce the overall load to the order of 11,000 megawatts of power, which implies that we wouldn't need to use natural gas to heat our homes or natural gas to provide peak power for generation or nuclear power to some extent?

MR. LYASH:  So, Mr. Tolmie, as you know, you and I have had long discussions about exergy, so I understand the technology, basically, and I and OPG are supporters of storage as a part of the system mix here that you mentioned.  We just refurbished the Sir Adam Beck pump hydro storage facility.  It's the largest storage facility in Canada.

So, in concept, I think, in the long-term, the development application of storage is important.  Whether that technology is exergy or others, I think, remains to be seen, and using storage can enhance the effectiveness of the rest of the generation fleet we have around climate change objectives, et cetera.

To the extent it's relevant to Darlington, you know, the IESO has thought about whether, in the future resource mix, Darlington plays a vital long-term role, and OPG has looked at that very carefully in making decisions about whether to proceed with the Darlington refurbishment, and our judgment -- and I think it's backed by the IESO -- is that, in any of those future scenarios, the Darlington units will be very valuable low-carbon resources paired with storage or otherwise.

MR. TOLMIE:  Can you give me an estimate of how much storage already exists in the system?

MR. LYASH:  I didn't come prepared to cover this material today, so I'm not in a position to do that for you right now.

MR. TOLMIE:  Okay.  Well, I'll throw out a number just so people have a concept for what we're talking about.  There's about 8,000 megawatts of capacity in the hydro ponding system plus pump storage, which is not widely used in Ontario.  Can you compare pump storage here vis-à-vis pump storage in other countries like China, for example?

MS. LONG:  Mr. Tolmie, this does not relate to Darlington.

MR. TOLMIE:  Yes, it does.

MS. LONG:  Pump storage?

MR. TOLMIE:  Yeah.  In order to make the Darlington --

MS. LONG:  In other countries?  In other countries?

MR. TOLMIE:  -- to make the nuclear system pump --

MS. LONG:  I don't think so.  So --

MR. TOLMIE:  Sorry.

MS. LONG:  You have to let me speak, and then you --

MR. TOLMIE:  Sorry, I'm sorry.

MS. LONG:  -- can speak.

What we're interested in, this Panel is hearing the evidence of these two witnesses.

MR. TOLMIE:  Yes.

MS. LONG:  So we can't accept anything that you are saying as evidence.  You're not giving evidence here.  You are asking questions, so you need to set the context and ask these two witnesses the questions, because we can only rely on the evidence that these two witnesses give us.  So I'm asking you to direct your questions to them squarely on the issue of Darlington.

MR. TOLMIE:  That's exactly what I'm trying to do.

MS. LONG:  I'll ask you to rephrase your question so that you do that, please.

MR. TOLMIE:  The objective of the Darlington project is to meet Ontario's requirement for power; right?

MR. LYASH:  Yes.

MR. TOLMIE:  And there's a confusion over whether power should be expressed in megawatts or megawatt hours or terawatt hours.  If you set megawatts as your objective, then the ISO says we need 36,000 of them.  If you set terawatt hours, we only need 11,000.  Do you agree?

MR. LYASH:  I agree that the concept of capacity megawatts and energy megawatt hours are two different concepts and have to be treated differently in planning a system.

MR. TOLMIE:  Which one do you use, though?

MR. LYASH:  You must use both.

MR. TOLMIE:  Do you need to know the power demand if, in fact, you're drawing your power from the storage system?

MR. LYASH:  Yes.  Because you're designing and operating a system that includes a wide range of generating resources, storage resources, transmission, distribution, loads with different real and reactive power profiles, voltage and frequency requirements.

So I don't disagree that you need to understand and utilize storage, but you asked me whether you could pick megawatts or megawatt hours, and I said you need to consider both.

MR. TOLMIE:  I can't disagree with you.  There are elements of power factor and that kind of thing involved. But from a straight physics point of view, I think I would question the need for paying too much attention to power capacity, because the real issue is energy capacity.  However, we're not here to debate.  We are here to consider the dollar value.

So the plan is to complete four Darlington reactors that will cost $12.8 billion.  Could we possibly do that cheaper if, in fact, we pay close attention to storage as the means of matching supply and demand?

MR. LYASH:  I think that was a question that was evaluated by the IESO and the Province in making a decision to proceed with the Darlington refurbishment.  But under any scenario, the Darlington refurbishment was a critical element of that solution.

MR. TOLMIE:  Has the OPG itself carried out any cost benefit analysis of the potential of using storage explicitly?

MR. LYASH:  We operate storage, and we operate in the market, so in a real sense, we evaluate alternative technologies on an ongoing basis.

MR. TOLMIE:  And you feel that the options that you have presented are absolutely the best to minimize the customer price, to quote you from yesterday, or to meet your fiduciary obligations?

MR. LYASH:  There's certainly a range of options and system planning.  The government considered them in LTEP.  The ISO considers them in their deliberations, and OPG considers them in evaluating what solutions we think are best and we want to advocate.  And all that was considered in reaching the decision to undertake the refurbishment at Darlington.

MR. TOLMIE:  When were those decisions arrived at?

MR. LYASH:  If you look at the Darlington timeline, certainly there was there was a feasibility study embarked on in 2009, a definition phase in 2010, a number of checkpoints all the way along the line up to and including board of directors and Cabinet approval at the point we put the RQE forward.  So it's he been ongoing decision-making process as we moved through the project beginning ten years ago.

MR. TOLMIE:  At what date did the Paris agreement on climate change come into effect?

MR. LYASH:  I don't have that reference available here.

MR. TOLMIE:  Would you agree it's quite recent, like November of last year?

MR. LYASH:  Yes.

MR. TOLMIE:  So since the decision was made, there has been a fundamental change in the direction of government planning on energy?

MR. LYASH:  The Government of Canada has certainly focused on carbon and put out materials on 2050 goals and action plans, and to the extent I reviewed them -- and I don't claim to have reviewed them in detail -- they all show an ongoing and growing element of the mix as nuclear for almost every scenario.

MR. TOLMIE:  Would you agree there is a potential for very large changes in how the system works?  I referred previously to the potential to store heat for thermal applications and, as a free consequence, you get a large amount of electricity storage via the exergy storage process.  So, in effect, you getter terawatt hours of energy coming free out of the system once you have adopted the concept of using storage for thermal applications.

I'm trying to help you.  There is --

MR. LYASH:  I have no way of predicting that.  I know what the system planning outputs are.  I understand what OPG and the Province's positions have been.  OPG is an advocate of technology and supportive of storage, but I have no way of validating the conclusion that it will be plentiful and free as a result at this point.  I hope it is, but I can't say that's the case as I sit here.

MR. TOLMIE:  Can anyone say what the case will be?  We presently don't have the new LDPE; presumably that will come later this year.  We do not have the federal plan for energy; presumably that will come soon.  We don't yet have a provincial plan for energy.  So it's perfectly correct to say that there are no plans in place, but there are potentially opportunities in place.

My question is:  Are you examining those opportunities as assiduously as you can?

MR. KEIZER:  Madam Chair, as you know, the Regulation 5305 prescribes that the need for the project has been determined by the government and determined by way of regulation.  So I'm not sure we need to go into what the various scenarios could be in the future or other issues, given that we're here today to consider the Darlington refurbishment project as it is and as it's planned and as it is intended to go forward in satisfaction of that need.

MR. TOLMIE:  Is it your position, then, that it doesn't matter that it might cost $12.8 billion more than we really need to spend?

MR. LYASH:  I wouldn't characterize that as my position.  But what I would say is that the Darlington units which provide a low-cost source of power, zero greenhouse gas emissions, or near zero, and 20 percent of the province's energy have a lifetime, and we are facing the end of that lifetime.  And based on that, and ten years' worth of efforts examined by the IESO, examined by the Province, decisions have been made that at least one of the central elements of the Province's energy plan going forward is to refurbish Darlington.  We face that decision now.  We can't wait ten years to see whether something else materializes, because if we do that, then the decision is not to refurbish Darlington and to retire it.  That wasn't the decision that was taken after all that analysis.

So, in my view, the review was done; the decision was made that, regardless of what other technology or scenario might develop in the future, the correct course of action in this time is to refurbish the Darlington refurbishment, and that's the path that we are on and what we're here to talk about today.

MR. TOLMIE:  Do you recognize that there are potential drawbacks to building the Darlington reactor from the point of view of achieving the greenhouse gas objectives?  For example, if you're going to use a constant energy source like a nuclear facility, you've got to cope with the load variations, and there's only a limited capacity in our hydro facilities, so the balance is made up by generation with gas-fired generators, and there's a potential to get rid of those gas-fired generators if you employ storage appropriately.  And you appear to be saying we're stuck with that.  We're going to have to continue using the gas-fired generators, because we need them for coping with the nuclear mismatch against the power demand.

MS. LONG:  Mr. Tolmie, do you have some final questions for this panel, because you have reached your 20-minute time period, and while I know engineers love to talk about these different concepts, it's really nothing that we can consider?  As Mr. Keizer has stated, the need for Darlington is established in the regulation, and what we're here to do is discuss payment amounts.

So I'm going to give you one final question for Mr. Lyash and for Mr. Reiner, but then we need to move on.

MR. TOLMIE:  My final question is:  May I have the opportunity to present a report to show that we could, in fact, save billions, many billions of dollars, if we make better use of storage?

MS. LONG:  Are you thinking that you're going to put it in front of these witnesses and have them comment on it?

MR. TOLMIE:  No.  I'm just, well, suggesting it as a report that would go to the Board for their consideration in coming to a conclusion on this issue.

MS. LONG:  Well, that's not before us, certainly not before us in this Panel.  We are discussing an overview of the Darlington project.

MR. TOLMIE:  I'm trying to do that too.

MS. LONG:  Well, I know you are.  But I don't see how the report would assist us in what we need to determine here, so my answer is no.

MR. TOLMIE:  Okay.  Fine.  Thank you.

MS. LONG:  Thank you.

Mr. Elson?

MR. RICHLER:  Pardon me, Madam Chair, if I might just add one thing.  I note that Mr. Tolmie circulated a hard copy of a two-page document.  I'm not sure if he wishes to add that document to the record, but if that is his intention and if the Panel wishes to admit it, we should probably give it an exhibit number.

MS. LONG:  I haven't seen it.  Do I have it?

Mr. Keizer, do you have an objection for this going on the record?

MR. KEIZER:  I don't have an objection.  I don't particularly know its use.  It's not something that's been put to our witnesses, so otherwise it would just be sitting on the record.  And I'm assuming that -- so my view is it does say at the top "Compendium for February/March Hearing," so I'm assuming, if Mr. Tolmie is going to use it for a subsequent panel, that he would bring it forward at that time and have it marked then.  Otherwise it wasn't put to the witnesses or --

MS. LONG:  Are you planning, Mr. Tolmie, to put this before other witness panels?

MR. TOLMIE:  No, I wasn't.

MS. LONG:  So what is the purpose of this?  You didn't put it to these witnesses, so --

MR. TOLMIE:  It was intended to provide a means for anyone interested to track back on what I had said.

MR. KEIZER:  Well, I think we have a transcript with respect to that, so -- which is -- you know, everybody has a record of, so, in my view, I mean, we don't need to mark it as an exhibit.

MR. TOLMIE:  Okay with me.

MR. KEIZER:  We have the transcript of Mr. Tolmie's examination.

MS. LONG:  Thank you.

Thank you, Mr. Richler.

Mr. Elson, do you have a compendium, do you?

MR. ELSON:  I do, yes.  Thank you, Madam Chair.

MS. LONG:  You're going to put it to these witnesses?

MR. ELSON:  I am, yes.

MS. LONG:  Okay.  Let's mark that, please.

MR. RICHLER:  So this one will be K2.2.

Exhibit No. K2.2:  Environment Defence compendium

MS. LONG:  Can you give us a time estimate, Mr. Elson?

MR. ELSON:  I should be below my estimate, max 20 minutes --

MS. LONG:  Okay.  And Mr. --

MR. ELSON:  -- probably even 15.

MS. LONG:  Mr. DeRose, do I understand that you plan on going in camera this afternoon?

MR. DEROSE:  Yes, that's correct.

MS. LONG:  Okay.  Then, I think the way we're going to structure the rest of the afternoon is I would like to have Mr. Elson ask his questions.  The Panel would like to ask our questions.  Then, Mr. Keizer, if you have any redirect, you can deal with that, and then I think we'll take the break so we can go in camera for the next panel.

# Cross-Examination by Mr. Elson:

MR. ELSON:  Thank you, Madam Chair.

Thank you, panel.  My name is Kent Elson.  I represent Environmental Defence.  And I have just a small number of questions, and I would like to start with some questions about reporting on the DRP.

And if the compendium could be turned up on the screen, and if we could turn to page 1 of the compendium.  And where this is all going is we're looking for an additional figure to be reported along with your quarterly reporting, and I'm going to take you through some references before getting to the specific metric that we are looking for, so bear with me for a moment.

Page 1 here of the compendium is ED interrogatory number 6, and you'll see here that we asked for the forecast of the cumulative capital expenditures for unit 2.  Do you see that there?

MR. REINER:  Yes.

MR. ELSON:  And turning over the page to page 2, this is JT1.17, and by way of undertaking, we asked that the full response be provided, breaking out by quarters for 2019 and 2020 as well, so this is the complete data here in JT1.17.  Do you see that there?

MR. REINER:  Yes, I see that.

MR. ELSON:  So if we turn to page 4, this is a Technical Conference transcript, and, on page 5, which is page 97 of the transcript, I had asked if the numbers that would be reported on a quarterly basis would be comparable with the cumulative capital expenditure figures that we received in IR 6.  Do you see that there?

MR. REINER:  Yes.

MR. ELSON:  And I'm turning over one page -- sorry for the long preamble -- page 6.  It said that they will not be comparable because there's some differences.  And so all of this is the lead-up for a very simple question, which is whether OPG is willing to report on the unit 2 actual cumulative total capital costs versus the forecast cumulative total capital costs as set out in JT1.17C, including a breakout of the contingency amounts.

MR. LYASH:  So how often -- can you clarify?  How often are you looking for this reporting and for what purpose?

MR. ELSON:  Because they're quarterly figures, the reporting would be quarterly.

MR. KEIZER:  Can I just understand Mr. Elson's question?  Are you asking that the numbers that are forecast in JT1.17 be frozen in time and that that be the comparison from this day forward?  Is that kind of what you're contemplating?

MR. ELSON:  I struggle with the terminology "frozen in time."  What we're seeking is reporting of the actual costs versus the forecast as of today, actual versus forecast.

MR. LYASH:  So before I go directly to this, one of -- some of the metrics that we had included in the OEB report that we proposed were cost performance index and schedule performance index.  And I just would -- for the sake of understanding what your objective is, I want to contrast those to these cash flows.

These cash flows exist at a point in time and are based on a schedule and a cash flow.  As we talked about many times, it's a dynamic set of activities, and so, as an example, in defuelling, schedule pull forward, cash expenditures pull forward with the execution of that schedule.

So the cash expenditures for the quarter go up, but, in fact, you're gaining schedule provided you're accomplishing – you're earning value for the cash you spent.  Likewise, there may be cases where resequencing occurs and expenditures move out.  And looking at cash flow may show an underrun against the cash flow.  That isn't necessarily a project underrun, because the work hasn't been executed, so the cash associated with it hasn't exited.

So our reporting approach here, which focuses on earned value and on -- through the MD&A on total expenditures life to date and whether there is any material change in the forecast give you, I think, a good picture of the status of the project.

My concern is that picking a point in time and a set of cash flows could, without all the in-depth project knowledge underneath that, could be, in fact, just plain misleading.

MR. ELSON:  Mr. Lyash, you actually hit on the precise issue which is why we're looking for this, which is a number where the baseline isn't changing.  The challenge with the CPI and SPI, the cost variance and the schedule variance, is that it's a single number, and under that single number, there is large amount of calculations, including a baseline which sometimes changes.  So that is the purpose for seeking something very simple, which is your quarterly capital expenditures, forecast versus actual, on a quarterly basis.

MR. LYASH:  And I think that is likely not to give you what you're looking for is my point.  And I think panel 1B can go into this in detail, but CPI and SPI are measured against a budget and a schedule that doesn't have a lot of fluidity to it.  It's measured against a firm baseline and change control against that.

So there may be some other way to get to what you're looking for.  I'm not optimistic that cash flow is going to give that to you.  And perhaps -- and we can discuss it more, but perhaps Mr. Rose and panel 1B may be a place to explore that.

MR. ELSON:  Let me ask you this question:  My understanding is that, when certain changes are made to the project, such as changing directions to contractors, you change the baseline for the CPI.

MR. REINER:  No.  The baselines do not change.  In project control's space -- and as Mr. Lyash said, we can get into this in more detail in 1B.  In project control's space, we maintain a baseline budget and baseline schedule that always links back to the approvals that were provided.  So it links back to the funds released by the Board in 2016 as part of the U2 execution estimate and links back to the execution schedule that we've presented in evidence.  That baseline is locked in.  And so, when we do a program level report of cost and schedule performance, it is always relative to that baseline.

Now, recognizing that -- and we spoke about a change control mechanism,  The change control mechanism is in place because it recognizes that, as you execute the project, things are not going to unfold exactly as planned.  And there needs to be an ability to understand what has changed and then measure performance against those changes.

So, for example, if something were behind schedule on a project, we would expect to see a recovery plan.  That recovery plan would then essentially provide another basis to track performance against.  The way we do this is through control budgets.  But they're always linked to the baseline budget and baseline schedule and in our program.  Reporting, it always rolls up to that baseline.

If you're looking at cash flows alone, I think the shortcoming there, which is why in our proposal we talked about cost performance and schedule performance, cost performance and schedule performance give you an indicator of how you're doing relative to the work that you planned to execute.  It tells you whether you're adhering to your schedule, whether you're ahead of your schedule or behind your schedule.  It also tells you, in terms of the costs you're expending, how that is doing relative to what you budgeted.  Are you spending more?  Are you spending less?

If you looked at just cash flows, you would actually not get the visibility into the performance that you need to get on a project like this.

MR. ELSON:  Could you turn to page 8, just further to your comment about the baseline not changing, paragraph 2, page 8 of Exhibit 2.2, which is our compendium.

The second paragraph says:

"If we are making a strategic change where we are directing the vendor to take on a new component or we are moving them on a schedule and it's an agreed-to change, in certain cases we would adjust the baseline for which we are measuring CPI."

MR. REINER:  I think this is -- and, again, we will have Mr. Rose on panel 1B and come back at this.  But this is specifically in reference to a project bundle, and that would be done through that control budget that I talked about.  We do establish control budgets, and those control budgets move up and down based on what the change review board has authorized and approved.  And then performance gets measured at the bundle level relative to this control budget.  But the ultimate base line that we put forth in evidence, which is unit 2 execution estimate and the execution schedule, that is the baseline that we will always continue to measure our performance against.

MR. ELSON:  I'm not suggesting that you're changing the 4.8, but it appears the baseline on which CPI is measured might change between the work bundles.

MR. REINER:  On a bundle level, it will always be reflective of the control budgets, but that gets rolled up into the program level where the reference is the common baseline that we put forward.

MR. ELSON:  And you're not providing reporting of the CPI on the work package level; correct?

MR. REINER:  We did not propose to provide it on the work package level; that we would do it at the rolled up program level.

The success of the project is really measured not just by the success of one bundle.  The entire program needs to execute to completion within the parameters that we've identified in order to be successful.  We certainly do, in the project management that we've implemented internally, we look at this in granular level of detail, because we're interested in ensuring everything moves along in concert to get to that complete outcome.

MR. ELSON:  I won't, I guess, continue to engage in a debate about why Environmental Defence wants to look under the hood of the CPI or the cost variance, and so I'll move on.  But before I do that, I would like to get a clear answer.  I think I know what the answer is, but is OPG willing to report on the unit 2 actual cumulative total costs versus the forecast cumulative total capital cost as set out in JT 1.17 C, including a breakout of contingency amounts, including -- because intervenors such as ourselves would like such a thing and would find it helpful?

MR. LYASH:  No, we're not prepared to commit to that at this time.

MR. ELSON:  I'll leave that for now and move on to another area.  Just a quick confirmation:  OPG has agreed to report the CPI cost variance, SPI, and schedule variance on a quarterly basis.  Fair?

MR. LYASH:  Just to be clear, we've laid out an annual report to the OEB that on cost includes CPI, life to date, forecast to complete, estimated completion, and a similar suite of metrics around the schedule.  And we've committed to provide that reporting to the OEB on an annual basis.  Of course, if the Panel deems that more often is necessary, that's certainly the OEB's prerogative to ask us to do that.

Separately from that -- that's for the purposes of the OEB's role.  Separately from that, we will be reporting information in our management disclosure and analysis around costs, schedule, performance, and any material development.

We've also committed to provide quarterly public reports, which we will make available on our website, and those will focus around safety, quality, cost, and schedule, including how we are doing on a broad sense on CPI, on SPI, and then we've committed to provide a monthly update on our website around that information as well.

That's designed more for public awareness and understanding, distinctly different from the kind of materials we would provide to the OEB to help it discharge its responsibility.

MR. ELSON:  I had asked this question to Mr. Reiner, and you provided an undertaking, and in the answer to Undertaking JT1.18, my understanding is that OPG had committed to quarterly reporting of the CPI, SPI, cost variance, and schedule variance.  That's in the materials at page 10.

It seems clear to me, and I just wanted confirmation on the record in this hearing that that's what OPG is agreeing to do.

MR. REINER:  So what I -- I believe at the Technical Conference what we had committed to, we had discussed the semi-annual public reporting, again, distinctly different from what we proposed for the Ontario Energy Board.  We talked about public reports that we previously, up to this point in time, have issued on a semi-annual basis, the most recent of which is posted on our website, and it's the August report.

We had committed to providing that on a quarterly basis.  That does -- that provides indicators.  It does not provide precise numbers.  The indicators tend to be qualitative in nature.  I mean, you can -- I can't recall if that was actually submitted in evidence, that --

MR. KEIZER:  It was part of SEC's compendium, or provided to us, I think, excerpts from OPG's website.

MR. REINER:  So it is that August report that's posted on our website, so that report looks at safety, quality, schedule, cost, and provides an indication in terms of status on a bar that ranges from red to green, obviously red being bad, green being good, and shows you where we are on an overall level.  It then also breaks that down into project bundles, giving more of a qualitative indicator, and we have committed to providing that report on a quarterly basis.

MR. ELSON:  Well, I'm very glad I asked that question.

Could you look up on the screen, JT1.18, and, at line 5, you'll see a description of the undertaking, which is to provide the OPG position on monthly and quarterly reporting of those figures, those figures being the SPI, CPI, cost and schedule variance.  And then at the second paragraph, it says:

"OPG has considered the request and will issue public reporting on the status of the DRP and specifically on unit 2 safety, quality, cost performance, and schedule performance on a quarterly basis."

But this answer is actually saying no.  You're saying, "No.  We're not agreeing to publish the SPI and CPI on a quarterly basis"?  Looks like yes to me, but if your answer is no, that's important for me to know.

MR. REINER:  That says:

"Cost performance and schedule performance and safety and quality."

And if you look at that semi-annual report, it does provide an indication of cost and schedule performance.  It does not provide a CPI, which is a specific metric, or an SPI, which is a specific metric, and I believe this response also doesn't reference SPI or CPI as a specific metric.  It talks about cost performance and schedule performance.

MR. ELSON:  So, just to clarify, in response to Environmental Defence's request for quarterly reporting of the CPI, SPI, cost variance, and schedule variance, OPG is saying, "No, we do not agree to that"?

MR. REINER:  Well, we would ask you to look at the August report, which is the one that we have proposed to provide quarterly, and see if that suffices, if that meets your request.

MR. ELSON:  It doesn't.  What we're looking for is the CPI, SPI, cost variance, and schedule variance, which are the specific figures.

MR. REINER:  We had not -- I mean, we had not contemplated doing that on a quarterly basis.  Our proposal still remains as submitted in evidence that we would provide that on an annual basis.  As Mr. Lyash said, you know, the Board can choose to do something different in this regard, but our proposal remains with what we have submitted.

MR. ELSON:  So the answer is to our request no, and I'm asking because I'll have to take up time in submissions to request that the Board address this as part of their order, and I want to be clear that OPG is saying that, no, it does not agree to do this.

MR. REINER:  That's correct.  At this stage, we're not agreeing to provide that level of granularity on a quarterly basis.

MR. ELSON:  Can you confirm that the SPI and the CPI are calculated internally on a monthly basis?

MR. REINER:  They are.  SPI and CPI are calculated internally on a monthly basis, yes.

MR. ELSON:  So you'll have the figures, but you don't want to release them?

MR. REINER:  The question of what is useful to the public for public reporting versus what gets used internally for managing a project -- I mean, SPI and CPI indicators are critical metrics for project managers to see so that they can take appropriate action in managing the project.  That's why they exist on an internal basis.  They are a project management tool.

The question on what the public extracts from that and what sorts of conclusions it draws is a separate question.  We do not see that as being a useful metric to provide on a more granular basis than what we've committed to.

MR. ELSON:  What's the difference between cost performance and the cost performance index?

MR. REINER:  So cost performance here, in the way we've identified it, is it's more of a qualitative measure, how are we doing overall on budget with the program.  A cost performance index is a fairly precise mathematical calculation, and there is a prescribed formula for deriving that, and we can get into details on panel 1B on how that's established and how it's calculated.

MR. LYASH:  There may be additions that we might be willing to make to the quarterly report if they're really valuable to the public and can be understood.  Many of these metrics, SPI and CPIs, these are metrics created for us to manage the project, not the best communication tools for the broad public.  They're also useful to the OEB because of the depth of understanding of the Staff and the Panel that can be developed.

I just give you an example.  A high-level SPI might, without any underlying knowledge from a project management point of view, might indicate that the project is well on track, but if the critical path is behind schedule, the end date may be in jeopardy.

Likewise, the SPI might show a value less than one, but until you drill down and understand precisely what it's telling you, you may not realize that it is being driven by non-critical path activities that are behind schedule where a recovery plan exists to return it to one at a future point in time.

So what we try -- what we're attempting to do with the public reporting is be transparent and inform the public of the status of the project, but do it in a way that the public can understand.

MR. ELSON:  Mr. Reiner, is the difference between the schedule performance, as referred to in JT1.17, and the schedule performance index the same as the difference between cost performance and cost performance index, in that cost performance and schedule performance are qualitative, and schedule performance index is a specific quantitative measure with calculations behind it?

MR. REINER:  Yes, the same holds true for that.  It is not -- so, in this August report, the indicator there is not the precise mathematical calculation, because it takes into consideration if there is a variance from plan in something like a cost performance index what has been done to address that and what do we foresee the outcome of that being.

So it looks at more than just the precise mathematical calculation.  So, yes, the same holds true for the scheduled performance and the cost performance.

MR. ELSON:  Thank you.

A few more questions on a different topic, and I apologize, Madam Chair.  I'm going beyond my re-estimated time.  I've had some unexpected answers, specifically about the decision to proceed with unit 3 and potential off ramps.

I understand that OPG would be seeking approval to proceed with unit 3 from its own board of directors roughly three to six months before starting with that unit?

MR. LYASH:  Nominally, that's accurate, yes.

MR. ELSON:  But you haven't put forward -- OPG hasn't put forward a process or timeline to seek approval from the government before proceeding with Unit 3; right?

MR. LYASH:  The government's expectation, I think that's for the government to set.  But my understanding is that we would, in the same time frame, at that three- to six-month period, we would proceed to our board to gain approval to proceed, and that would be precedent to going to the Province and requesting confirmation from the Province that they have no issue with proceeding.

MR. ELSON:  First, you'd go to the Board roughly three to six months before, and, after that, you'll seek approval from the Province?

MR. LYASH:  That's the process we used for unit 2, and I would expect to follow the same process for the subsequent units.

MR. ELSON:  But Energy Board approval is not required before proceeding with unit 3, because that would be the next test period for the next application; right?

MR. LYASH:  Correct.

MR. ELSON:  And you're seeking approval in this case for rates up to December 31, 2021?

MR. LYASH:  Yes.

MR. ELSON:  And the plan is to start the unit 3 refurbishment roughly in February 2020?

MR. LYASH:  Correct.

MR. ELSON:  If it's ahead of schedule for unit 2, you might start early, or if it's behind schedule, you might start a bit later?

MR. LYASH:  Correct.

MR. ELSON:  So in your next payment amount application, you'll be roughly two years into the unit 3 refurbishment?

MR. LYASH:  Depending on when unit 2 concludes and unit 3 begins.

MR. ELSON:  But it's roughly about two years in.  Is OPG willing to commit to seek energy approval for the budget for unit 3 before proceeding with unit 3, in the event that unit 2 is going over budget?

MR. KEIZER:  Madam Chair, I don't know what this has to do with the application that's currently before you.  My friend's questions all relate to unit 3, which is not something for consideration nor part of the application.  This application relates only to unit 2.

MS. LONG:  Mr. Elson?

MR. ELSON:  It relates to off-ramps in the event that there is a situation of there being -- unit 2 being over budget and whether, as part of that process, there will be any Board involvement or OPG would agree to Board involvement to look at those costs.

I also think it's relevant that unit 3 costs, by virtue of this application, will be largely spent before the next application, and that might be something that the Board is interested to hear something about.

MS. LONG:  Do you think this is the right panel to answer that question?

MR. ELSON:  It seemed to be to be a high-level question relating to off-ramps and relating to the position of a company on whether it will be coming to the Board to confirm that it's on the right track in the event it's off the rails with unit 2 before it proceeds with Unit 3.

MS. LONG:  I can understand why you might want to ask Mr. Lyash this question from a general oversight viewpoint, but I'm wondering if the whole regulatory panel dealing with applications and considerations is perhaps the better panel.  I know Mr. Keizer may say he objects to the question even at that point, but I'm not sure that this is the right panel to be talking about those issues.

MR. ELSON:  Perhaps --

MS. LONG:  Maybe conceptually you can ask the question.  But with respect to next fees case applications, I'm not sure that this is the right panel for it.

MR. ELSON:  I don't have a technical question about the regulatory framework.  I think everyone is in agreement and understands that, in this proceeding, there is not being sought approval for unit 3 costs; that won't happen until the next proceeding.  My question is whether OPG would be willing to come back to the Board, if unit 2 is off the rails, before proceeding with unit 3 to see if the Board has something to say about how it does unit 3 or how it will approve costs for unit 3, seeing as unit 2 is off the rails.

Perhaps it could be --

MS. LONG:  So you're saying off the rails, though. Is  that off-ramp exercised?  Is that over budget by X?  I don't know how they can answer that question.

MR. ELSON:  The question is just over budget, so beyond the P90.  And if this panel wants to take away, think about it, and provide an undertaking, that may be the best way.  But these are the high-level witnesses, and I think they'd be the best place to answer that question as to whether --

MR. KEIZER:  My view, Madam Chair, is that it's a hypothetical question for which I think today the OPG can't necessarily give an answer to.  It's been clear on the record OPG has said in the event there is some kind of an off-ramp, there is an entire process that gets affected through the Province, through itself, and ultimately what would be the next stages with respect to that, and that is only going to play out relative to the circumstances that arise at that time.

And with respect to a degree of cost changes or implications and how it could affect unit 3 or not, there could be a myriad of issues that could require OPG to take certain actions which I think are predicted today, nor can you state, based on that potentiality, which hasn't really been accessed or evaluated in evidence here as to what OPG would or wouldn't do.  Notwithstanding that, it is something that's outside the test period with respect to any kind of rate impact for rate consumers, and certainly OPG bears the risk of cost until such time as there is otherwise a determination.

I just don't see how it's relevant to unit 2 or the request that's currently before the Board.

MR. ELSON:  I don't have anything to add in terms of the relevance.  I think it's relevant both to the off-ramps, and I also think that this Board will want to know about the regulatory process for multi-billions of dollars that will be spent in the test period.  It's not coming in- service, but it's going to happen, and we're not going to be able to turn back the clock on that.

MS. LONG:  I have both your positions, and I'm not going to order them to answer it.  And I think to the extent the panel has any questions, we will ask them of another panel.

MR. ELSON:  Thank you.  I will just ask one more question for confirmation, which is that unit 3 costs, if incurred, will be either recovered through rates or the responsibility of the shareholder, which is the taxpayers.  Is that fair to say?

MR. LYASH:  Yes.

MR. ELSON:  Thank you.  I have no further questions.

MS. LONG:  Thank you, Mr. Elson.

I have changed my mind, and we are going to take a break now for 15 minutes.  We will come back.  The Panel will ask our questions.  Mr. Keizer, if you have any redirect, you can do it then.  And then we'll take a five-minute break to switch out the panel.  Thank you.

### --- Recess taken at 3:37 p.m.

### --- On resuming at 3:55 p.m.

MS. LONG:  Panel, the Panel has some questions, and we're going to start with Member Fry.

# Questions by the Board:

MS. FRY:  Good afternoon, gentlemen.  Can you hear me okay?

MR. LYASH:  Yes.

MR. REINER:  Yes.

MS. FRY:  All right.  Okay.  So I want to ask a few questions to get a better feel for how your management oversight processes are working.  You have, obviously, a number of different processes, and I just want to get a bit of a better feel for how they work on the ground.

So starting with you, Mr. Lyash, so obviously you have, obviously, overall responsibility for oversight of the project, and you have a management team to assist you, but I'm just wondering, in terms of all these oversight mechanisms, which are the ones that you would generally get involved in personally.

MR. LYASH:  Yes.  So if I kind of start at the highest level and work my way down, of course, the shareholder has some oversight, and we meet with the shareholder monthly, discuss the progress of the project, and answer questions for the shareholder.

Their representative, Milt Kaplan, who sits on the DRC on their behalf, spends time not only with the DRC but over the course of the -- between DRC meetings and looking independently at issues, and I interface with him when he has questions and answers as well to make sure he is getting full access.

If I roll to the board, of course, I'm at each DRC meeting, on-site, off-site, and of the full board meeting, as -- serving as both an executive and as a director of the company in that regard.

If I move down a step now from the board into the executive team's oversight, I have a role in oversight, so I -- and to discharge that, I've set up the RCRB, which we've talked about.  I talk to them when they're on-site.  I attend their debriefings.  It's not uncommon for me to discuss particular issues with them between reviews, because they're reviewing materials when they're not on-site, and so I have direct contact with the RCRB.

I also have very direct contact with the Nuclear Safety Review Board, which is similar to the RCRB, but their focus rather than just on unit 2 is on to what extent is the unit 2 evolution affecting the operating units and nuclear safety.  And I deal with them similar to the RCRB.

Internal audit.  Internal audit lays out an audit plan.  I have an opportunity to comment on that audit plan.  If I think there are particular areas that should be on the audit plan with respect to refurb to be probed, I have the opportunity to provide that input, and I'm debriefed on each of the internal audit results on refurbishment, and I would typically review the corrective action plans with Mr. Reiner to close any gaps identified by the audit.

MS. FRY:  Okay.  I was going to ask you about those, because I do remember reading several internal audit reports with a number of recommendations, so you personally follow up on those?

MR. LYASH:  Yes, I do.

MS. FRY:  Okay.

MR. LYASH:  I do.  And I follow up on those personally as part of my management responsibility, and then I'm engaged in discussion with the audit and risk committee of the board, to whom audit has a direct line of reporting.

Okay?  Moving down into engagement, on a day-to-day basis, I chair a quarterly senior leadership team review of the project, at which time Mr. Reiner and his team go through the last quarter's worth of performance, the next quarter's worth of plan, and we go over any gaps in that.  That's on a quarterly basis.

I also attend the quarterly meetings that we hold with each of the major contractors, where I sit with their CEOs and their leadership team and our project leadership team and review their execution of their scope of work and where their issues are, if they have recovery plans in place, how they're proceeding on the plans, so another level of direct contact with the CEOs of the major contracting firms.

There are also a series of -- when we go to Mr. Reiner -- that his management system implements, whether they are individual project reviews, weekly or monthly schedule reviews, cost performance reviews, quality or safety reviews, and I attend a sample of those, and my purpose for attending those is to judge whether the process is working effectively:  Is this the right standard?  Are they asking the right questions?  Do I see the right level of follow-up?  So, to do that, I generally spend about one day a week on-site at Darlington exercising that sort of oversight activity.

MS. FRY:  Thank you.  That's helpful.

Mr. Reiner, from your perspective.

MR. REINER:  Yes.  And I'll just add to Mr. Lyash, so Mr. Lyash and I are in regular contact, so --

MS. FRY:  I'm sure you are.

MR. REINER:  -- we talk probably on a daily basis, and we also have a weekly executive leadership team meeting where, at that meeting, the entire executive leadership team reports out on the significant issues or strategic issues for the team, so that's another area where I have an opportunity to report on status, some particular issue if there's a concern, if we're seeing something in terms of either a contractor's performance or safety performance or something of that nature.

If you go down into the project level, so I have a set of direct reports that are per the organization chart that we've shown.  I have a direct reports meeting.  That tends to deal with the more strategic issues that cut across all of the project work.  And then we also have in place essentially a standing calendar, and it's important on a project to have that so everybody knows what gets reviewed on what day, and it's the same each week.

There are meetings with contractors specifically on their projects.  There are roll-up meetings at project bundle level that include contractor and OPG performance rolled up at the bundle level.  There are project status meetings where weekly we go through the performance metrics, any issues.

We run a risk oversight committee, and that risk oversight committee does a forward look on what's ahead of us in terms of significant risks, given where we're at in execution, and have we got mitigation plans in place.  And that's a formal process and a subset of that risk oversight committee.  If there is a significant item that we identify, then we will get into our calendars a specific discussion around how that issue gets dealt with.

In regards to some of the oversight agencies, the Minister's oversight adviser has free and unfettered access to the site, so he will attend meetings and can attend any meetings that he chooses, also has access to information, so there is a physical presence on-site.

Same goes for, obviously, the Refurbishment Construction Review Board.  They are on-site physically looking at work being executed in the field, looking at metrics packages, and just sort of aligning what the reporting is telling us with what they're seeing in performance and in general sort of behaviours.

I also have in my organization a separate project assurance group, and that project assurance group is really that first level of defence where we look at our -- is the execution of the work being done in accordance with the processes and systems that we have put in place, and it's important to have some separation between an execution organization and that kind of assurance group.

So we take a look and see are the contracts being executed in accordance to what the provisions tell us.  Are any contractual events logged and properly dispositioned?  So all of that is run through a separate assurance group.

And as part of the project controls function, which is also separate, there are a variety of regular reports, and they range from updates that are done each shift that we work to each day to weekly to monthly.  So it's a very granular set of updates that work sort of up the organization.

MS. FRY:  Thank you.  Those are my questions.

MS. LONG:  I just want to go back to a discussion that you had with Mr. Mondrow today where you stated that the P90 factor was based on the four units.  But I guess that leaves me with the unit 2 that we're being asked to consider, and I understand the contingency being about 40 percent of what you've budgeted.

But does that have a P factor as well?  It's not a P90 factor.  That's for the four units.  But where does that leave us for unit 2 which we're considering?

MR. LYASH:  Perhaps Mr. Reiner can amplify this.  In establishing the contingency and the risk metrics for the project, you really need to consider the nature of the project.  For that reason, because this is a program spanning four units, the units overlap; at least three of the units overlap.  Unit 2 contains common systems and work that affects all four units.

The way that the contingency was established, the risk assessment and contingency when we talk about P90 level and all this Monte Carlo, that was done for the program, for the whole four units.

MS. LONG:  Understood.  Is it fair, Mr. Lyash, to say you can break it up per unit?

MR. LYASH:  We didn't do that.  We did not do that --

MS. LONG:  Okay.

MR. LYASH:  -- because of the interrelationships, but what we did then was take a look at the four-unit contingency and look at the scopes that were being executed on each of the units which are slightly different and allocate the contingency among the four.  We also looked at unit 2 and allocated additional contingency to it because it is the first time through.

So the first execution, no matter how well we've planned, will identify issues that will need to be dealt with, with respect to contingency cost and schedule contingency.  But my expectation, then, would be we take that emergent issue and mitigate it for the subsequent three units, and by doing that, we need a lower level of contingency as you work through the project.

That allocation among the units wasn't driven by unit-specific Monte Carlo analysis.  It took the programmatic analysis and then applied our knowledge of scope and first-of-a-kind factor in weighting how much contingency we would need on unit 2.

MR. REINER:  And I think that's exactly right.  In the simplest way, you could have just divided by four.  So rather than dividing by four, it is these kinds of adjustments where we look at -- there are some scope differences, and they've been factored into the allocation of contingency and the fact that unit 2 is the first unit through and, therefore, would carry a higher level of risk associated with our ability to mitigate issues as they arise, we put a heavier weighting on the allocation of contingency on the first unit.

But the second unit has a new element of scope that we spoke of earlier related to the turbine generator, that all the experience and industry suggests that return-to-service time can be significantly extended as a result of bringing that system online.  We factored that into the second unit, so it carries heavier weighting and contingency, and then you see sort of a following in the allocation.

MS. LONG:  Thank you.

Mr. Janigan took you through a number of expert -- well, reports that you filed to demonstrate reasonableness, and those reports deal with governance.  They deal with methodology.  They deal with process.  But is there anywhere in the evidence where you filed a report or commentary on any independent assessment of the actual costs of this project, be it the 12.8 or the 4.8 billion?  Is there anybody who took a sober second thought at that and said, "Yes, 4.8 is reasonable; 12.8 is reasonable"?  Not how you did it, not the methodology, not the risks that you identified, but the actual numbers?

MR. REINER:  What we did not embark on in this -- if you look at just the time it took to plan this project, to get from when we -- from the start of definition phase, so January 2010 to being ready to begin execution on the first unit, the complexity and effort associated with building up the estimates, we deemed it virtually impossible for an independent body to derive an estimate completely separate.

So the approach we took -- now, in the previous hearing, I believe we may have filed a report that specifically looked at scope of the turbine generator project.  That's a fairly standard type of an overhaul that we're doing, and we did get a technical agency to just have a look at the scope associated with the work that we're executing in line with what others do in that.  And we got a technical report on that which informed our estimate.

But the process we took internally to ensure we have the right checks and balances in place, estimating was done by people independent from projects, for example.  We brought in expertise to help us with estimating that have the ability to look at a scope of work and quantify an estimate.  And because of the complexity, it took us over a year to get the Class 2 estimate compiled for just the RFR project, and the effort that went into the option we took is bring in experts to have a look at the approach we took, the method we used, do some sampling to see if that methodology was followed.  Would it result in a reasonable outcome in terms of the project estimate?  That's what we opted to do.

We just did not see it feasible to have somebody completely independent come back to us with an estimate for executing the refurbishment and then trying to do a side-by-side comparison.

MR. LYASH:  The other body of information that the team used to help make sure the estimate is reasonable -- there's a lot of history.  So, in other words, if you begin to parse this into its pieces, there are activities that are going to be executed in the station in refurb that have been executed before.  So there are historical actuals on how long it takes to rebuild a valve, how long it takes to open a turbine generator.  So in building up the estimate, the estimators relied on also looking at actual durations historically at the station or in industry and making sure their estimate was reasonable.

If you look at the RFR, the heart of that is the removal of the feeders, the pressure tubes, the Calandria tubes, and their reinstallation.  And in building the full-scale mock-up and testing and proving out the tools, that helps form the basis for what are the productivity numbers we can reasonably expect out of that tooling and that environment.

So you start with an estimate, but then rationalize it to what you have seen on the mock-up with the individuals running the processes and the tools to benchmark the productivity that's applied to that very large job.

MS. LONG:  Thank you.  My final question is one of the things that you talked about.  I think, Mr. Lyash, you talked about, in us setting the revenue requirement, we would implicitly be agreeing with the reasonableness of the contracts that you have in place.  I just want to clarify that you're taking that position with respect to what we are being asked to consider in this time period.  So, for unit 2, because, as I understand it in my read of the contracts, you have the ability to terminate the contracts if, let's say, lessons learned tell you that you should be doing something else via contracting.  I just want to be sure that you're not taking the position that by us implicitly agreeing, if we do, that the contract is reasonable for what you should be doing with unit 2, that we would be binding a future panel by saying we thought the contracting strategy for all units was reasonable.

I just want to make sure we're clear on that.  What we're being asked is for this five years for this unit 2. That's what you're deeming we should be looking at with respect to reasonableness.

MR. LYASH:  Yes, I agree.  I didn't mean to imply that you were endorsing a contracting strategy, nor that you were endorsing our plan for future units.  What we're putting before you now is unit 2 and $4.8 billion, and the process we've taken to establish that as the set of objectives.  Nothing more.

MS. LONG:  Thank you.  Those are the Panel's questions.  Mr. Lyash, thank you very much for your evidence.

MR. KEIZER:  Just for the record, we have no redirect.

MS. LONG:  No redirect.  Mr. Reiner, you'll be on the next panel, so I won't thank you now.  Shall we --

MR. DEROSE:  Madam Chair, I do realize and I appreciate that Board Staff has tried to accommodate me today.  I'm more than happy to go today, if your timing still works.  But I just want to throw it out there that if -- I don't want to put the Panel out just to try and fit me in today.  I can have one of my colleagues here on Thursday to ask my questions, or I can go right now.  I just -- I'm in your hands.

MS. LONG:  I appreciate that.  How long do you think your direct is going to be, Mr. Keizer?

MR. KEIZER:  I would think it's probably no more than five minutes.

MS. LONG:  I mean, I think, given that, you know, you're here and we would like you to continue, we'll go ahead.

MR. DEROSE:  It will be in camera.  I believe --

MS. LONG:  Yeah.

MR. DEROSE:  -- Board staff has told you that, so --

MS. LONG:  Yes, they have.

So, Mr. Keizer, if you can get your next panel up.

MR. KEIZER:  I would ask Mr. Gary Rose and Mr. Leo Saagi come forward to be affirmed.

Madam Chair, the two new members have joined the panel, and just by way of introduction before they are affirmed, closest to me is Mr. Leo Saagi.  Next to him is Mr. Reiner, obviously, who has been affirmed and is continuing to testify, and next to Mr. Reiner is Mr. Gary Rose.  If they could be affirmed.

MS. LONG:  Thank you.

# ONTARIO POWER GENERATION - PANEL 1B

Mr. L. Saagi,

Mr. G. Rose, Affirmed;

Mr. D. Reiner; Previously Affirmed.

# Examination-in-Chief by Mr. Keizer:

MR. KEIZER:  Starting first with you, Mr. Rose, you are vice-president, planning and project controls, nuclear projects?

MR. ROSE:  That's correct.

MR. KEIZER:  You've held various positions at Ontario Power Generation and, prior to that, Ontario Hydro?

MR. ROSE:  That is correct.

MR. KEIZER:  And could you very briefly describe your role in the Darlington refurbishment program?

MR. ROSE:  Certainly.  I've been involved in Darlington refurbishment program since 2008.  I was involved in the original development of the feasibility business case and the planning that has happened through the definition phase and ultimately the release quality estimate.

Specifically, my role is project planning and project controls, so I ultimately own the procedures for cost management, scheduling, risk management, issues management, et cetera.  I land and manage the preparation of the release quality estimate on behalf of the team, and I was the leader.  It involved many hundreds of people in it over the years, but that is my responsibility.

MR. KEIZER:  And, Mr. Saagi, you are director, controllership, nuclear projects.  Is that correct?

MR. SAAGI:  That's correct.

MR. KEIZER:  And over your career, you've held various positions at both Ontario Power Generation and, prior to that, Ontario Hydro?

MR. SAAGI:  Correct.

MR. KEIZER:  And could you briefly describe your role in the Darlington refurbishment program?

MR. SAAGI:  Okay.  I've been with the project since the end of 2009.  I'm currently the director of controllership for nuclear projects.  I oversee a team, a dedicated controllership team, for the Darlington nuclear refurbishment project where we help facilitate and maintain the general ledger of the project and ensuring there's financial controls in place as well as overall framework of financial controls.

MR. KEIZER:  Thank you.

And, Mr. Rose, do you adopt the evidence that has been assigned to panel 1B as detailed in Exhibit A1, tab 9, schedule 1, which is the exhibit establishing the panel responsibility that OPG has filed in this proceeding?

MR. ROSE:  Yes, I do.

MR. KEIZER:  And you, Mr. Saagi, do you adopt the evidence that's been assigned to panel 1B as detailed in Exhibit A1, tab 9, Schedule 1, which is the exhibit that has been filed with panel responsibilities by OPG in this proceeding?

MR. SAAGI:  Yes, I do.

MR. KEIZER:  And I just have one other question in direct, Madam Chair, and that relates to something that arose in discussions with panel 1A, and it relates particularly to, if I can have it brought up on the screen, Exhibit L6.6, SEC 003, attachment 4, and it's before you now, and I believe this is probably a question for you, Mr. Reiner.

And so, during the hearing related to the examination of panel 1A, we heard various questions and answers about executive compensation incentives relative to the Darlington refurbishment program, and it's my understanding that information relating to that is found within this exhibit that's on the screen here.

And could I ask you, given the current scheduling, just to very briefly highlight some of the elements within the schedule to show the nature of the incentives and how they relate to the Darlington refurbishment program?

MR. REINER:  Yes.  So this is the OPG 2016 corporate scorecard and weighs directly into incentive compensation.  And there are -- there are four measures in total, but I'll start with three specific measures that touch on refurbishment.  And they show up right underneath the green line that has the 40 percent in it on the left-hand side.

So the first is refurbishment project cost, and what that looks at is the budget that has been established for the project.  In 2016, we were operating under a budget that was not yet for execution of unit 2.  That was what we called the mobilization phase and was an annual budget that was released by our board.

So to achieve threshold, that 100 percent aligns with what we've called a 90 percent confidence budget, so that budget had some contingency associated with it.  So we have to at least achieve at least P90.  If we are outside of P90, there would be a zero for this particular measure.  And then it looks at -- it's then a graded approach.  If we can execute the work at a 5 percent cost reduction relative to what was budgeted, we would achieve the maximum on this.  Where we landed in 2016 was at around target for this particular measure.

The second measure on here relates to defuelling of the reactors.  Towards the end of 2016, we were already in the defuelling phase.  And the metrics that you see on here for threshold -- so this takes a look at, on December 31st, where is the project on critical path.  Defuelling was the critical-path activity, and to achieve threshold in accordance with the P90 schedule, we would have achieved 212 fuel channels defuelled in accordance with the working schedule.  That doesn't have any of the contingency allocated to it.  We would have achieved 311 channels defuelled.  In this particular case, we did actually achieve the stretch target because we were running well ahead on defuelled.  Defuelled performance was quite good.

The third measure relates to the safety improvement projects and the D20 storage project, and what is in there are milestone dates, again, that were selected in accordance with the in-service dates that were in place for those projects.  For this particular measure, all three of the projects needed to meet their in-service dates in order for this to be recognized.  We did not -- we achieved a zero on this.  We did not achieve the in-service targets, and that was primarily related to two of the projects, EPG3 and containment filter venting, going beyond their in-service date.

There is also an element of refurbishment in the very first measure on safety performance, so that is a corporate safety indicator.  And the refurbishment performance gets rolled up into that corporate safety indicator.

MR. KEIZER:  Thank you, Mr. Reiner.

Madam Chair, those are the questions I have in direct, so the panel is available for cross-examination.

MS. LONG:  Thank you.

MR. KEIZER:  If I may, just before we go to CME, just, at the end of the proceeding, if I have a moment just to deal with one preliminary matter, just to advise you on an undertaking, just...

MS. LONG:  Okay.  We are going to go in camera now, so if you have not signed the declaration and undertaking and if you are not an employee of OPG and if you are not Board Staff and you are not the panel, then you need to leave the room.  And we are going to go off air.

### --- On commencing in camera at 4:27 p.m.

[Page 182, line 20 to page 202, line 16

have been redacted]

[Page 182, line 20 to page 202, line 16

have been redacted]

### --- On resuming public session at 4:59 p.m.

# Procedural Matters:

MS. LONG:  Mr. Keizer, you had an issue you wanted to deal with?

MR. KEIZER:  It's actually not really an issue.  It's more of an update on one of the undertakings --

MS. LONG:  Okay.

MR. KEIZER:  -- and maybe it's so people are preparing tomorrow.

With respect to the undertaking that was given on J2.3, I believe, today, which is the undertaking, what is the revenue-requirement impact, based on Unit 2, of moving from P90 to P50 confidence level?  First part of the undertaking.  Second question is:  Does the 40 percent allocation of contingency to Unit 2 still hold?

I can report that the answer to that undertaking is actually set out in an interrogatory response, which is Exhibit L 4.3-5 CCC 18.

MS. LONG:  Okay.  Thank you for that update.

Are there any other issues that we need to deal with before the end of the day?  No?  Then we're adjourned, and we will see everyone Thursday at 9:30.  Thank you.

### --- Whereupon the hearing adjourned at 5:00 p.m.