ONTARIO ENERGY BOARD

| FILE NO.: | EB-2016-0152 | Ontario Power Generation Inc. |
| --- | --- | --- |
| VOLUME: DATE: BEFORE: | 6 March 7, 2017 Christine Long Ellen Fry Cathy Spoel | Presiding Member and Vice Chair Member Member |

EB-2016-0152

THE ONTARIO ENERGY BOARD

Ontario Power Generation Inc.

Application for payment amounts for the period from

January 1, 2017 to December 31, 2021

Hearing held at 2300 Yonge Street,

25th Floor, Toronto, Ontario,

on Tuesday, March 7, 2017,

commencing at 9:32 a.m.

----------------------------------------

VOLUME 6

----------------------------------------

BEFORE:

CHRISTINE LONG			Presiding Member and Vice Chair

ELLEN FRY				Member

CATHY SPOEL			Member

MICHAEL MILLAR	Board Counsel

IAN RICHLER

VIOLET BINETTE	Board Staff

LAWRIE GLUCK

JANE SCOTT

RUDRA MUKHERJI

CHARLES KEIZER	Ontario Power Generation Inc.

CRAWFORD SMITH	(OPG)

BARBARA REUBER

JOHN BEAUCHAMP

CHRIS FRALICK

IAN MONDROW	Association of Major Power

SHELLY GRICE 	Consumers of Ontario (AMPCO)

MICHAEL BUONAGURO	Consumers Council of Canada (CCC)

JULIE GIRVAN

BRADY YAUCH	Energy Probe Research Foundation

LARRY SCHWARTZ

KENT ELSON	Environmental Defence (ED)

DAVID POCH	Green Energy Coalition (GEC)

SCOTT WALKER	Ontario Association of Physical Plant Administrators (OAPPA)

RICHARD STEPHENSON	Power Workers' Union (PWU)

MIKE McLEOD	Quinte Manufacturers' Association

MARK RUBENSTEIN	School Energy Coalition (SEC)

JAY SHEPHERD

BOHDAN DUMKA	Society of Energy Professionals (SEP)

MICHAEL JANIGAN	Vulnerable Energy Consumers

MARK GARNER	Coalition

--- On commencing at 9:32 a.m.	1

Appearances	2

ONTARIO POWER GENERATION - PANEL 1C	2

P. Galloway, Previously Affirmed

Cross-Examination by Mr. Rubenstein	22

--- Recess taken at 10:48 a.m.	45

--- On resuming at 11:06 a.m.	45

Cross-Examination by Mr. Buonaguro	45

Cross-Examination by Mr. Poch	62

Cross-Examination by Mr. Yauch	70

--- Luncheon recess taken at 11:59 p.m.	77

--- On resuming at 1:11 p.m.	77

Preliminary Matters	78

Cross-Examination by Mr. Yauch	78

Cross-Examination by Mr. Tolmie	82

Cross-Examination by Mr. Richler	88

Questions by the Board	95

Re-Examination by Mr. Keizer	101

--- Recess taken at 1:54 p.m.	103

--- On resuming at 2:00 p.m.	103

ONTARIO POWER GENERATION - PANEL 2A(I)	103

J. Mauti, C. Fralick, R. Puch, Affirmed

Examination-In-Chief by Mr. Smith	103

Cross-Examination by Mr. Stephenson	105

Cross-Examination by Mr. Millar	116

--- Recess taken at 3:02 p.m.	143

--- On resuming at 3:20 p.m.	143

Cross-Examination by Mr. Tolmie	165

Cross-Examination by Mr. Rubenstein	170

--- Whereupon the hearing adjourned at 4:33 p.m.	189

EXHIBIT NO. K6.1:  VECC COMPENDIUM.	3

EXHIBIT NO. K6.2:  Cross-Examination Compendium of Mr. Tolmie for OPG PANEL 1C.	82

EXHIBIT NO. K6.3:  Board Staff Cross-examination compendium for OPG Panel 2A(i)	116

EXHIBIT NO. K6.4:  CROSS-EXAMINATION COMPENDIUM OF SEC FOR OPG PANEL 2A(I)	170

UNDERTAKING NO. J6.1:  TO PROVIDE THE LOCATION IN THE EVIDENCE OF THE RISK REGISTER DR. GALLOWAY REVIEWED.	62

Tuesday, March 7, 2017

### --- On commencing at 9:32 a.m.

MS. LONG:  Please be seated.

Good morning, everyone.  Good morning, Dr. Galloway.  The panel continues to sit today in EB-2016-0152.

Mr. Keizer, are there any preliminary matters we need to deal with this morning?

Preliminary Matters:

MR. KEIZER:  Yes, there are two.  The first is a routine matter that we have filed Undertaking J2.8 and Undertaking J3.4.

The second matter relates -- and I've advised my friend from VECC with respect to this -- relates to some items that are in VECC's compendium, and this isn't really -- what I put my friend on notice is that after Dr. Galloway looked at the compendium she identified that there were pieces in the compendium that related to Kemper and she alerted me, the fact that she currently is involved in testimony and evidence with respect to the Kemper facility, I believe, as well Vogtle.  And so I've alerted my friend that there may be issues with respect to confidentiality that Dr. Galloway may encounter, and obviously this isn't intended to curtail my friend's cross, but we will obviously have to deal with it as the question arises.  And as I've said, I've alerted my friend to that fact.

MS. LONG:  Okay.  Ms. Khoo, what I intend to do, I mean, we'll let Ms. Khoo go ahead with her cross-examination.

MR. KEIZER:  Yes.

MS. LONG:  And if Dr. Galloway has an issue with the questions that are being asked we'll deal with them at that time, and I will ask Dr. Galloway put on the record why she's not able to answer the questions, and then, Mr. Keizer, you can raise any concerns that you have and we'll deal with each issue as it comes up in the cross.

MR. KEIZER:  No, that's fine.  That's as we would intend.

MS. LONG:  Okay.

MR. KEIZER:  Thank you very much.

MS. LONG:  Good.  Any other issues?

MR. RICHLER:  None from us, Madam Chair.

# Appearances:

MS. LONG:  Okay.  Then, Ms. Khoo, can you begin your cross-examination, please.

MS. KHOO:  Sure.  So first I wanted to apologize to the panel for not introducing myself yesterday.  This has been quite a sudden transition, and so I thank everyone in the room for bearing with me.

MS. LONG:  Oh, no problem.  I should have asked you.  I wasn't sure.  That's my fault.  So we have an appearance in for Ms. Khoo representing the Vulnerable Energy Coalition?

MS. KHOO:  Yes, that's right.

MS. LONG:  Thank you.

# ONTARIO POWER GENERATION - PANEL 1C

Patricia Galloway, Previously Affirmed.

Cross-Examination by Ms. Khoo:

MS. KHOO:  Good morning, Dr. Galloway.  And thank you for appearing today to answer our questions again.  As we established yesterday, I'm not going to challenge your qualifications, and there are just a few things I wanted to clarify.  I don't think, hopefully, it will be cross on what -- the confidential aspects of Kemper, but again, you can mention if that happens to be the case.

So first you testified yesterday, and in your report as well, that you found that OPG has reasonably and prudently prepared for its execution of DRP; is that correct?

DR. GALLOWAY:  That's correct.

MS. KHOO:  Okay.  And throughout your report --

MS. LONG:  Can I just stop you for one minute.  We're just checking that we have your compendium.

MS. KHOO:  Oh.

MS. LONG:  I do.  Do you have a copy?  We might just need some extra copies.  That's on our end here.  And Mr. Richler, if we can just mark it, please.

MR. RICHLER:  Yes, VECC's compendium will be K6.1.

EXHIBIT NO. K6.1:  VECC COMPENDIUM.

MS. LONG:  Okay.  Thank you.  Please continue.

MS. KHOO:  Thank you.  And throughout your report, Exhibit D2, tab 2, schedule 11, attachment 3 you frequently refer to industry standards and best practices.  Would it be correct to say that you rely on such standards and best practices as a basis for determining what is reasonable or prudent in managing projects?

DR. GALLOWAY:  It would be one of the bases, yes.

MS. KHOO:  Thank you.  Now, I would like to turn to the table you provided in response to Undertaking JT1.24.  This is on page 10 of the compendium.  This table provides a number of projects in response to the request to identify those within the last ten years of comparable scope to your work for OPG; is that correct?

DR. GALLOWAY:  I'm sorry, could you repeat the question, please?  I'm sorry.

MS. KHOO:  This table, it's a response to the request to identify the projects that you've worked on with work of comparable scope to your work for OPG?

DR. GALLOWAY:  Yes, it is a response to the last ten years that are comparable to scope.  That's correct, yes.

MS. KHOO:  Okay.  So I would like to go over some of these, and again, as mentioned, if they run into the limitations you have with respect to your other testimony you can just raise that at the time.

So on page 12 of the compendium -- this one is about Kemper County power plant -- you stated in the testimony that MPC's management decisions and actions as to the Kemper IGCC project fell within a zone of reasonableness and were prudent.

Was this assessment based on industry standards and best practices?

DR. GALLOWAY:  It was based on a number of things.  It was based on industry best practices.  It was based on utility practice.  It was based on what was known and reasonably known by Mississippi Power Company as of March 31st, 2013, and it was also based on what was provided to the commission in its CPCN and based on what the level of effort at the time the utility undertook based on the progress of Kemper up to its CPCN.  Those were all the things that were based on that conclusion.

MS. KHOO:  And these are all typical factors that go into drawing a conclusion like that on these sorts of projects?

DR. GALLOWAY:  Yes.

MS. KHOO:  Okay.  Thank you.  On page 17 of the compendium, a New York Times article from July 2016 stated that the Kemper County plant at that time was over two years behind schedule, over 4 billion dollars above budget, and still not operational.  On page 32 of the compendium an article from Mississippi Today states that as of October 2016 the plant cost over double the original estimate and was still not operational.

In light of that, do you stand by your original assessment that management decisions for Kemper County were within a zone of reasonableness and were prudent?

DR. GALLOWAY:  I would like to qualify the response.  As I'd indicated, the first response was the conclusions were effective as of March 31st, 2013.  The matters that are in the two articles put forth are beyond March 31st, 2013 and are part of an ongoing review and will be part of a prudence hearing that will be held later this year, and therefore my analysis and conclusions relative to the aspects so stated in these two articles is still under review, and therefore I do not believe that I can comment.

MS. KHOO:  That's fair.  Thank you for that.

I will now turn to page 36 of the compendium, which references your work for Duke Energy on the Edwardsport plant.  In the third paragraph from the bottom the article states that your firm concluded that Duke acted prudently in managing the project, and this assessment was based on the similar factors to those that you mentioned above with respect to Kemper?

DR. GALLOWAY:  Yes, but again I think that the conclusions must be put into perspective.  The conclusions for Duke Energy on reasonableness and prudence was on various aspects.  It wasn't on the entire project or the entire amount.  Qualifying that, we did find some imprudence and disallowance on one aspect of Duke Energy's management itself.  We also found disallowance relative to Duke Energy's EPC contractor.  Those amounts, while we found that Duke Energy was reasonable and prudent in its management of the EPC contractor, we found that the EPC contractor had taken actions that were deemed by us to be unreasonable and imprudent to the tune of a range, I believe it was 500 to 800 million dollars.

We -- under testimony I so indicated to the commission at that time.  It would be obviously up to the commission as how to handle that under the statute, and there was also allegations, I believe, that so cited in your compendium of fraud concealment and gross mismanagement.

So the commission found that there was no fraud concealment or gross mismanagement and, relative to the other matters, there was a settlement between the commission and Duke, and relative to the 500 to 800 million dollars the commission deemed that that was not a responsibility of the ratepayers but that Duke could go ahead and attempt to recover those in a separate action against the EPC contractors.

So that is the basis of the reasonableness and prudency.  It was within those bounds.

MS. KHOO:  Thank you.  So to clarify, reasonableness and prudency was found on Duke's part, and then it was because of the contractor that the project ended up going the way it did in terms of the adverse consequences?

MS. GALLOWAY:  Except for I indicated there was one other aspect.  I can't remember exactly the dollars.  It was in the millions relative to a specific area on how they handled grey water, and that particular aspect was deemed by us to be imprudent on the actions of Duke Energy.

MS. KHOO:  Thank you.

MS. LONG:  Dr. Galloway, can you clarify for me the distinction you're drawing between what your mandate was on the Duke Energy project and Kemper project?  Are you saying they were different scopes of work, one was more defined than the other?

MS. GALLOWAY:  No.  So Kemper and Duke were both full prudence audits for the entire aspect of the plant.  Duke Energy was ahead of Kemper in its building.  Kemper is going through its final start-up and commissioning.  Duke Energy's Edwardsport IGCC's plant was in its start-up and commissioning aspects when the prudence hearing was held.

And so the review for both plants was looking at the decision to build, the preplanning and execution, the entire execution of the project, and also that involved the actions of the EPC contractor as well.

The Kemper project was somewhat different, not in our scope, but somewhat different in the fact that they did not have an EPC contractor.  They had multi-prime contracting and they themselves took on the role of EPC contractor through their parent company.

They are one of the few utilities that actually have their own construction management arm, and so they did their own EPC contracting.  But yes, we would have looked at their role in that EPC contracting management.

So their roles were very similar.  It's just that the Duke proceeding is over and was finished, and the Kemper proceeding is not over and has not yet had a prudence hearing.  The testimony that I have filed in Kemper has been prefiled testimony.  The prudence hearing has actually not been held yet at all, and that is going to be done later this year.

MS. LONG:  Thank you.

MS. FRY:  Just to be clear, for both of those projects, the construction was essentially finished at the point at which you did your prudence review, is that correct?

MS. GALLOWAY:  Correct.  The Kemper project was due to the mandate from the commission is that when they pre-approved the estimate, Mississippi Power Company had to make annual filings of prudence.  So that is why there was an interim filing of testimony from everyone relative to prudence.  Up to the point of March 31, 2013, the project was still ongoing because it was annual prudence reviews.

Before the hearings was held on that, the commission changed its decision and made the decision, revised its order that they would not hear prudence on an annual basis, that they would wait until the completion of the project to hold one hearing instead of annual hearings.  And that's why no further testimony has been filed, an while the prudence evaluation we are doing is still underway.

MS. LONG:  Continue, Ms. Khoo.

MS. KHOO:  Thank you.  I realize it's getting repetitive, so this is the last one on the table.

On page 44 of the compendium, you testified before the Florida Public Service Commission that the company behind Levy County Nuclear Power Plant reasonably and prudently implemented its management decisions.

On the page before that, similarly you testified that PF's management decision was reasonable and prudent based on information known, and that reasonably should have been known by management at the time the decision was made.

Was that finding that PF's management decisions were reasonable and prudent also in accordance with industry standards, best practices, and the standard factors that you mentioned earlier in making this sort of assessment?

MS. GALLOWAY:  As I think I testified yesterday, Levy was very, very different in the mandate from that of Kemper and Duke.  It was an evaluation of only one decision, and that was the decision to continue with the Levy project on a limited basis, with work only proceeding for its combined operating license and the amendments to the contract that were made in light of that decision.

So the prudence review was only for that decision to continue, defer work, and whether the amendments within the contract were reasonable and prudent.  And as I indicated yesterday, that was the testimony that all of the parties had stipulated to and agreed to, and the commission adopted.  It was -- it wasn't a review of policies and procedures and processes and the things you compare against best practices.  It was the decision-making process on what was known or reasonably should have been known at the time that the utility made its decision to undertake that, which was more in light of the Nuclear Regulatory Commission and what the Nuclear Regulatory Commission was doing relative to review of the combined operating licenses in the United States, the timing of those combined operating licences, and other factors such as the demand for power, the need for power, why Levy was still a good option based on the economic circumstances at the time, and those would have been the factors surrounding that particular decision.

MS. KHOO:  Thank you.  However, after that, so on page 45 of the compendium, the Tampa Bay Times from August 2013 reported that Levy was shut down, and customers were on the hook for $1.5 billion.

In light of that, I suppose, would you stand by your original decision because it was limited in the scope as you described?

MS. GALLOWAY:  Yes.  Plus it was, as I indicated, based on the circumstances known at the time to the utility.  Circumstances changed in many ways from the nuclear industry all the way through economic conditions and the price of fuel, with natural gas prices especially plummeting, and all of those things resulted in different circumstances that resulted in this decision that Duke Energy made at that time.

MS. KHOO:  In relation to that project, is it true that Jeffrey Lyash was the CEO of Progress Energy or Duke at that time?

MS. GALLOWAY:  That's correct.

MS. KHOO:  This is the same Jeffrey Lyash who is the current CEO of OPG?

MS. GALLOWAY:  That is correct.

MS. KHOO:  To confirm, of the projects we just discussed, which seem to involve significant cost overruns and were considerably delayed or shut down, in all those cases at the time of the assessment, the assessment was their management was reasonable and prudent?

MS. GALLOWAY:  No.  I think I've testified on Duke that there was a significant disallowance that we found, one on both the utility and one on the EPC contractor of the utility to -- I think our total disallowance was in the range of 500 to 900 million dollars.

On Kemper, the testimony, yes, is still true up through March 31st of 2013.  The conditions or any actions taken by Mississippi Power after that time are still under review, and no testimony has yet been filed.

And relative to the Levy project, again that was just a contract basic decision that was accepted by all parties to be reasonable and prudent.

MS. KHOO:  Thank you.  So the Duke finding was after the fact of the actual project?

MS. GALLOWAY:  The project was still in start-up and commissioning at the time of the prudence hearing.

MS. KHOO:  And the Kemper County assessment is still under review?

MS. GALLOWAY:  That is correct.

MS. KHOO:  So would you agree that based on these projects, that there seems to be a certain disparity between the initial assessment at the time of reasonableness and prudence and how these projects actually turned out in practice?

MS. GALLOWAY:  No, I do not.

MS. KHOO:  Would you like to elaborate?

MS. GALLOWAY:  Well, prudence is -- in the U.S. jurisdictional aspect is based on what was known, or reasonably should have been known at the time a decision is made.  That is how the commissions view all of the decisions.

The Mississippi commission has not obviously met or heard any of the evidence yet.  It will be up to the Mississippi commission as to whether they deem the costs reasonable and prudent.

There is a distinction on the Kemper plant, of course.  The Kemper plant, which was a first of a kind in every single aspect, the technology had never been built anywhere before.  The plant had never been built anywhere before, and there had never been a plant that agreed to do 65 percent carbon capture.  So the cost that are being evaluated currently are against a lot of those knowns that were known to everybody at the time the commission approved the CPCN.

Also, there is a cap on the Kemper plant that both parties agreed to because of the fact that the plant had never actually been built before, so the ratepayers, the customers, are protected.  Southern Company has assumed the costs of those costs over that, and the ratepayers that -- the proceeding that is about ready to go forward will be on the exclusions, because there are exclusions to that cap for which the utility and the commission have agreed will be reviewed for prudence.  So that is a difference on Kemper.

On Duke there were provisions in the CPCN again, new technology that had never been used, first-of-a-kind elements of which both the commission and the utility recognized.  There were some -- there were cost estimates that came in based on that that both parties knew would probably occur due to those first-of-a-kind risks.  Those costs were approved by the commission.

And so the prudence element that was being reviewed was the cost over the second approved cost estimate, not the first approved cost estimate, and it's those costs that there was the issue of the EPC contractor's costs.

So those were two very distinct differences, and again, on Levy everyone agreed that the first decision was a reasonable and prudent decision at the time it was made.

MS. KHOO:  The fact of the matter is, however, that even if the outcomes had valid reasons or valid change of circumstances, even if a decision seems prudent and reasonable before implementation, that won't necessarily stop the project itself from running over budget and over schedule in its actual implementation?

DR. GALLOWAY:  It all depends on the circumstances and what was known or reasonably should have been known and what was known at the parties at the time that a plant is being built.  And as I had indicated yesterday, a very huge difference between both Kemper and Darlington and Duke and Darlington is that in the Darlington refurbishment program that there was an extensive pre-planning period and that the design was complete, that they were able to have lessons learned.  They were actually able to take lessons learned from other refurbishment projects and nuclear projects and other megaprograms.

The difference in the jurisdictional aspect in the United States, as I was explaining yesterday, is that when a utility applies for its certificate of public necessity and need, the CPCN, it does not have the same luxury of going through that.  For instance, on Kemper less than 10 percent design had actually been completed at the time.  They did not have fully established organizations.  They did not run any type of probabilistic modelling.  They did not have their organizational structure in place, and there was no lessons learned to be gained because the Kemper project had never been built before and the technology had never been used before, so there was no way to gain any prior knowledge.  And so that was the basis upon which that original estimate was made.

The same is true for Duke Energy.  There also was no probabilistic modelling done.  There was no extensive pre-planning done.  There was not the opportunity to again take lessons learned because again even though a different gasification technology, the technology had only been done on a very small scale, and not an expanded scale, and so those were very different factors than what Darlington has upon which that original estimate was made.

And everyone was quite aware at the time that this was put up for the CPCN that you also had economic conditions.  The Department of Energy was encouraging utilities to take advantage of the abundance of coal, which was a natural resource in the United States.  There was a push for clean energy, which was deemed to be viable with IGCC -- sorry, integrated gasification combined cycle.  There was also investment tax credits that were being offered by the government, and there was at that time, if everyone remembers, natural gas prices were not low.  They were extremely high, and there was a desire for fuel diversity.

All of the parties, including the customers, the intervenors, and the utilities all at the time of the CPCNs recognized that those types of risks were quite heavy, could not be modelled, because there was no way to model those risks because there was no subject-matter experts out there that would be able to identify the types of risks that might arise, and therefore everyone recognized that there would be cost increases that potentially would occur that could not be incorporated into that original cost estimate.

So I think it's very important to judge what was known and the pre-planning execution at the time of those two plants to put in context what the final cost is today.

MS. KHOO:  Thank you.  I'm just going to see if my colleague Mr. Garner has anything to add.

I believe that's everything for VECC.  Thank you very much.

DR. GALLOWAY:  Thank you.

MS. LONG:  Thank you.  Can I just ask a question, a follow-on to that.  You've talked about the limitations, I guess, on Kemper, for example, that there is not the same pre-planning as has gone on for the DRP and other things that were not done, and yet your opinion was that at the time when your review -- it was reasonable.

Are you saying that it was reasonable based on -- that it's situational based on what the current standard is that such pre-planning -- there were no lessons to be learned, that's just typical common practice that they wouldn't have designed?  Is that the context in which you came to your opinion?  I'm just trying to understand that.

DR. GALLOWAY:  Yes, the U.S. is much different in its regulatory regime of what a utility does and does not do before it makes its application to actually build a project.  And the regulatory regime in the United States is that utilities do not take under a lot of what I would call planning per se before they apply for their CPCN, because of the -- all the costs are at risk.

And so they do sufficient planning in order to come up with a reasonable estimate with what I would call qualifiers on -- based on the circumstances and what was known at the time.

So when the commissions review those applications for CPCN they also review those qualifications of what is known at the time.  And so it's those qualifications that also go through what I would call the reasonable and prudence review.  Each of those qualifiers is actually discussed in the commission hearing, the prudence hearing, and they talk about whether that's a reasonable assumption or not a reasonable assumption.

Just as an example on the Kemper project itself, because it had never been done before, ever, one of the issues that was raised in the CPCN hearing on Kemper was, was, for instance, the decision to go with the Department of Energy's desire to put into place IGCC a good thing for Mississippi and the state of Mississippi.

Part of what went into that look of whether that was a reasonable assumption underlying the need to go forward with the project included that Mississippi, for instance, has a huge amount of coal.  It is a very poor state, and it was looking relative to the number of jobs that the project would create.

And so there were economic -- there were other factors that the commission considered in that decision that did not actually go to cost that the commission in its order -- and if you read the order you will see this -- that those opportunities for the state of Mississippi and the fact that the utility would pay -- be making big tax payments, all of those were considered to be reasons that the project should go forward.

And then there was also a recognition that, being a complete first of a kind, that there may be increases that would come forward and that, you know, there was a discussion and actually an agreement between the commission and a settlement and the utility of how those first-of-a-kind types of risks would be handled.

And so the commission in the States for each of these jurisdictions on a CPCN looks at -- they recognize that the extent of pre-planning is not there.  They recognize that those estimates will probably come back for a cost increase, and if they do, it is those new conditions and circumstances that then will be reviewed, and whether the utility took actions that were reasonable and prudent based on the new circumstances that go beyond the original cost estimate.

MS. FRY:  Let me turn it around a bit.  Obviously, every project is individual, and you look at each project at the particular stage when you are asked to come in and opine.

So let me turn it around.  Of the projects that you're referring to that you've dealt with in the past, which is the one you would say is most similar to Darlington, in terms of the circumstances of the project and the point at which you were brought in?

MS. GALLOWAY:  As I indicated, most of the projects in the States do not have this extensive preplanning.  In fact, none of them have the extensive replanning and in fact, probabilistic modelling comes in typically after the project has been approved, when they go forth to look at their cost estimate when they refine that cost estimate and at that time, they will decide whether or not they need to come forth to the commission for any types of increase.

But I will say that the Vogtle project probably has some similarities in the fact that because the nuclear regulatory commission in the United States was reviewing these new designs that were going to be standardized designs that presumably would make the cost of nuclear more efficient and effective going forward instead of being one-off designs, which is what was going on in the '70s and '80s.  Each nuclear power plant was built completely different.  And so the NRC was looking at these licenses for these different types of reactor designs.

So the AP 1000, for instance, is a particular design that had to have NRC approval first before they could actually build that.  The EPC contractor -- and in the Vogtle case, everything depended on the EPC contractor in that case because, it's the EPC contractor that brings forth that AP 1000 design, it is going to be managing it, it has to come up with the policies and procedures, and so the risk profiling and the risk review was somewhat different than here, but similar in some respects.

So the risks were modeled within the contract, because the contractor held everything that was going to be done versus the utility putting in the policies and procedures and looking at the -- and having done the design first and having the contractor basically come in and execute that work.

In Vogtle, the EPC contractor was doing everything.  So the risk review looked at the risks within the contract, and the contractor was responsible for looking at how those risks were going to be modeled, or how the risk would be assumed by them versus the utility.  So the prudence review went through the actual risk profiling that was done on the contract and that is -- for instance, in our scope of work, we looked at the risk on how the risk was modeled and how it was included within the EPC contract, and that is what the commission actually took on was they have their own -- it's called an independent monitor, but they had their staff -- their consultant review the risks that were incorporated within the contract.

We reviewed the risk as they were incorporated within the contract.  And then the -- what the order came out to indicate is that the contract was reasonable and prudent, and that the risks within that contract were understood by both parties including risks that might arise that would result in a change order.

What the commission had to approve and did was that should the risks that were unknown but covered within the contractual provisions of the contract arise, then if those conditions did arise, those conditions would come back to the commission for review for those change order amounts.  And if they fell within the approved commission agreement for those risks, those costs  would be deemed reasonable and prudent.

So that is what has happened, is certain risks arose under that contract.  They were provided for in the contract.  The contractor and the utility came into a settlement.  That settlement was put forth to the commission.  They held a hearing on that, and the commission so determined in its order that those costs were part of the costs that would be applicable under the contract in the change order provision, and approved those cost increases.

MS. FRY:  Okay.  So if you were to summarize the key similarities between the Vogtle project and how you came in, the point you came in, and the Darlington project, can you just sort of name the key similarities you would see?

MS. GALLOWAY:  The risk review, but being different in the way I just described it.  The planning organization relative to the structure and the organizational structure that was going to be set up on both sides to execute the program.  The policies and procedures that were in place to manage the project, including the various metrics and the reporting.  The project control tools and who would be responsible for undertaking those project control tools, but whether the project control tools met best practices and would allow for a successful execution of the Vogtle project.

So I believe that even though the CPCN was limited and they didn't do as extensive a planning here, the same elements that we reviewed here we, reviewed there for that for their CPCN filing.  So they would be very, very similar in that respect.

MS. FRY:  Thank you very much.

MS. LONG:  Mr. Rubenstein, are you next?

# Cross-Examination by Mr. Rubenstein:

MR. RUBENSTEIN:  Yes, I am, thank you very much.  I would like to follow-up on your discussion at the end about the Vogtle.

Just to clarify, if I'm looking at JT 1.24 -- and this is page 10 of the VECC compendium -- it says that you participated in the engagement, but did not file testimony.

What exactly was your role?  Who were you representing and what was the engagement that you had?

MS. GALLOWAY:  So Pegasus Global did file testimony.  The late Dr. Kris Nielsen actually filed the testimony in the CPCN hearing that was the risk evaluation of the contract, the history of the nuclear industry -- because I think as I mentioned yesterday, Vogtle was the first nuclear plant in twenty years to be built in the United States, and served as the AP 1000 reference plant -- and also to opine on the organization structure, the policies and procedures, and project controls that were set in place.

So Dr. Nielsen filed that testimony and testified in front of the PUC hearing, and then the CPCN order was developed.  I was part of the team, the Pegasus team that did that evaluation.  There was a team of about five of us that reviewed all of those aspects.  It's just that I personally did not file and give testimony.  That was done by Dr. Nielsen of the Pegasus Global Group.

MR. RUBENSTEIN:  What year would that have been?

MS. GALLOWAY:  Two thousand and -- I want to say 2008, I believe.

MR. RUBENSTEIN:  My understanding, from documents and testimony we've heard about Vogtle in this proceeding, is that the project has gone significantly behind schedule.  I believe OPG, in one of their documents, has stated it's at least 39 months behind schedule.  Is that your understanding?

MS. GALLOWAY:  Well, I believe again it goes to the points that I was just raising with the Board.  Within the contract that was approved at the CPCN, it was recognized that there may be certain risks that would arise that would result in change orders.  Those risks did arise, were part of the contract.

Those change orders included both the time extension and the costs under the clauses.  That went through a hearing last year and those additional costs, through the settlement and additional extensions to the plant, were deemed reasonable and prudent and approved by the commission.

And relative to the cost, I think it's important to understand from a transparency standpoint -- and I believe that this information is very public; it's probably on the Georgia Power website.  Not for sure, but they're pretty transparent in what they show.  At the time of the CPCN there was an anticipation that there would be at the completion of this -- they do have CWIP, as we talked about yesterday, but there would be an anticipation that there would be about a 12 percent increase in rates for the Vogtle project.  That now has been re-evaluated through a number of -- from financing costs to looking at fuel prices that that is now looked at to be -- going to be much lower impact to the ratepayers, and so actually, even though the costs are higher, the actual costs that will be borne by the ratepayers will be much less than anticipated at the CPCN.

MR. RUBENSTEIN:  So as I understand what you're saying is there was an expectation that there were going to be scope changes in that project and Vogtle -- the sponsor of Vogtle would have to return to the commission.  That was -- there was an expectation from the beginning.

DR. GALLOWAY:  Yes, because at the time of the CPCN in 2008 they didn't even have a combined operating licence approved by the NRC yet, which everyone was fully aware of, and no one can anticipate what the NRC may or may not do.  It's a completely unknown risk in the United States, and I don't believe the combined operating licence was actually given to Vogtle until 2012, so some four years later.

So those are the types of things that were built into the contract and some of the risks that might arise.

MR. RUBENSTEIN:  When you say NRC you mean the Nuclear Regulatory Commission?

DR. GALLOWAY:  Yes, I'm sorry.

MR. RUBENSTEIN:  So from your discussion with Vogtle and the comments you were making with respect to the comparisons that VECC took you to, am I to -- I want to understand this.  I recognize in the U.S. different legislative systems in each of the -- in the States, and they each have their own unique circumstances.

Have you then ever done an engagement that is very similar to this that is a -- you're asked to provide on a forecast basis, essentially, that the budgeting, the management control, the contingencies are all reasonable, with the expectation that there will be no change orders, that they shouldn't be -- the utility shouldn't come back to the regulator?  Have you ever done anything like that specifically?

DR. GALLOWAY:  I'm a little bit confused by your question.  Can you just give a little bit more clarification of exactly what you're asking me whether I've done or not done?

MR. RUBENSTEIN:  Sure.  I'll try to, at least.  I want to understand if you've done something that is, at least in my view, a little bit more precisely exactly what you're asked to do in this proceeding.  As I understand your mandate in this proceeding is you're being asked for this project to comment on the reasonableness of the process to develop the budget, the schedule, the contingency, the program controls.

Have you ever done that for a project that has not gone in -- is not planned to go in-service for a number of years and there is an expectation from, I would believe, the utility itself that it should not need to go back to the commission, that there will -- it should not need to make scope changes or material scope changes?

DR. GALLOWAY:  Well, yes.  I mean, again, there are instances that are, I will say non-nuclear, because there are not a lot of nuclear examples, okay?  I mean, Vogtle is the -- and so Bellefonte was a different situation.  It's a government-run utility, and so it goes through completely different proceedings.

We did look at that decision-making, whether or not they had the pre-planning and the policies and procedures set up to make that decision to go with 1 and 2 versus 3 and 4 at the time.

If I go to non-nuclear, though, there are several examples.  For instance, we did a prudence evaluation on a transmission and distribution project for ATC company, looking at the same thing of whether their initial policies and procedures and government -- I mean, their structure and governance was all according to plan.  That project was executed and came in, I think, pretty much on time and on budget.

The Energy Strong program that we are an independent monitor on, which is public-service gas and electric in New Jersey, again, we were brought in at the very beginning of the project, a joint mandate by both the commission and the utility and rate council.  It's a three-party group.  Our mandate was to precisely look at the structure, the policies, the -- it's a megaprogram, by the way, as well.  It's about 1.2, 1.3 billion dollars, and it's made up of four major different projects underneath.  We were asked to look at the management structure, we were asked to look at the organization, the qualifications of the personnel, the planning, the schedule, the cost estimate, look at the project control systems, the reporting.  Everything that we're being asked to look at here, we were asked, and we were asked to report out on that, and we do report out on that to both the commission and the utility and rate council on a quarterly basis with an annual report as well.  And in fact, the next annual report review is tomorrow for last year's review.

And to date, we have been monitoring that project for three years now.  The project is going to -- it's forecasted to come in ahead of schedule by as much as maybe even a year, and it is forecasted to come in under budget.

And so we were asked to do the exact same thing that we were asked to do here, except we were retained by all three parties, and we are reporting out on that continuously over the time.

And there will be a prudence hearing that will be done at the conclusion of the project, which presumably we will also be asked to testify.

So that was -- it's very similar to here, it's just not a nuclear program.  It's a -- it's -- Energy Strong is a hardening of the system in order to protect it against hurricanes and floods and those types of events that have caused major outages in the state of New Jersey, because of the types of storms that they have had over the years.

The other example, of course, would be Crossrail that I talked about yesterday, where Her Majesty's Treasury asked us to come in and do a complete review of the risks, and again the structure, the policies and procedures, the project controls, and the whole setup for the Crossrail system that was then prepared in a report that was given to the treasury and then submitted to parliament.

MR. RUBENSTEIN:  But none for nuclear.

DR. GALLOWAY:  Excuse me?

MR. RUBENSTEIN:  But none for nuclear.

DR. GALLOWAY:  Well, as I've indicated, the only nuclear project in 20 years is the Vogtle nuclear project, other than -- we're not working on SCANA, so I can't comment on SCANA.

MR. RUBENSTEIN:  I want to ask you about -- if we can turn to your report.  And I'm looking at page 13, and when I use page numbers I'm using the page numbers in the top right-hand corner.  I just want to understand what you were asked to do, just to clarify what you were asked to do and what you did not -- you were asked not to do and you have not opined on.

And as I read the purpose of your testimony, and as I read it, it says you were asked to provide an assessment, an independent and objective assessment:

"...of the degree to which Ontario Power Generation's plan and approach to execution of the DRP, including the processes in place for management of cost, schedule, program controls, and the application of any contingency are consistent with other ways megaprojects and megaprograms of similar magnitude and scale, complexity, have been carried out."

Am I reading that correctly?

DR. GALLOWAY:  That's correct.

MR. RUBENSTEIN:  And if we take that to sort of a higher level, really, as I read your report, what you opined on in your understanding, you looked at the processes to develop the cost, the schedule, the program controls, the contingency, and you found them reasonable.

DR. GALLOWAY:  And also looked at the organization and the structure as well.

MR. RUBENSTEIN:  And you found that they were reasonable.

DR. GALLOWAY:  Yes, in light of all of the things that I indicated yesterday.

MR. RUBENSTEIN:  So just to be clear what you weren't asked to do and which you have not opined on, you have -- while you have determined that the processes and plans are reasonable, the numbers that underlie them, have you -- you have not determined that they're prudent.  Am I correct?

DR. GALLOWAY:  I'm a little bit --

MR. RUBENSTEIN:  So I'll give you an example.  So you talk about in your report that the process to determine the cost estimate is reasonable.  You have not determined that the $12.8 billion is specifically a reasonable number or the cost items that underlie the budget -- you haven't done a line-by-line to review to make sure they're correct.  Am I correct?

DR. GALLOWAY:  Well, there is not a line-by-line review done.  What we did review within the estimate is we looked at the basis of estimate that was prepared by OPG that is quite a detailed document that discusses how the actual costs were developed, the source documents for those costs, the actual estimates for the cost.  We did do reviews of samples of some of those source documents to ensure that the dollars that are composed of some of those elements follow through that cast basis of estimate, and then would translate into the model for the P90 confidence level.

We did look at the risk registers, for instance, which have input into how the total cost is developed, relative to whether or not the types of risks that were being looked at were reasonable types of risks to be modeled and incorporated within that.

Then we also looked at other independent reports that were done based on the estimate and the risk, to look at other subject matter experts that have done a much more in depth review of those.  And that's the whole process.

So the process is what we did look at, but that process does incorporate the review of actual samples of how they went about the process to get those numbers and to get the risks that go into the $12.8 billion.

So with that sampling and the way it's modeled, it should be a reasonable number based on the reasonable process, and the fact that it followed industry practices and it followed all of the lessons learned and the development of the actual cost estimates itself.

So based on those reviews, the inputs, and the independent reviews of those inputs on those specific dollar items, then the 12.8 was derived based on a reasonable and prudent process.

MR. RUBENSTEIN:  Let me ask you about -- you talked about you reviewed the risk register.  In doing so, as I understood it, you opined that the process to determine how to -- which risks to include and how to value those risks you think are reasonable.

Am I reading that correctly, that when you talk about your review of the risk register, that's what you've done?

MS. GALLOWAY:  Well, we went through the risk register.  Part of the reason we had reviews and interviews with individuals as well to understand how those risks were derived, how they were vetted, how they ensured all the risks were captured.

I don't remember, sitting here today, exactly which risks we probably talked about specifically from those risk registers.  But did look at specific risks to inquire as a sampling, you know, how did you get that risk, how was that looked at, how was it then incorporated.  So it wasn't merely going through the exercise.  It was the exercise of doing the risk register proper, but getting down a little bit more into the granulation how specific risks were identified, how they were vetted, how they were then incorporated into the risk register, and then how they were modeled in the probabilistic risk model itself.

MR. RUBENSTEIN:  So did you verify -- as I understand it, there are a thousand-plus risks in the risk register.  Did you look at each individual risk and determine that the risk has been described appropriately, the probability is being determined appropriately, the financial value or the cost if it materializes has been appropriately determined and is appropriate, and the scheduling cost -- essentially the delay it may cause, the impact is correct.

You didn't do that for each individual item?

MS. GALLOWAY:  As I indicated, we took a sampling.  We did not look at each individual item.  We looked at individual samples from the risk register, and then probed those specific items to determine whether or not they did in fact follow through the process of what we would expect a reasonable and prudent individual and organization, whether it be utility or another owner, or even a contractor, what would be expected of how they would look at those risks, cost those risks, and put those risks into the ultimate model.

MR. RUBENSTEIN:  Am I correct that you -- I don't think you were asked to, and I don't think you did.  You were not asked to opine on the reasonableness of certain cost overruns with respect to safety and improvement projects, and facilities and infrastructure projects, any prerequisite projects?

MS. GALLOWAY:  Not the actual cost itself, but how those cost impacts were being used relative to lessons learned, and how the lessons learned from those were being incorporated into the DRP estimate, and also the policies, procedures and management and how the DRP would be executed going forward to minimize against the type of cost increases that happened on the F&IP and SIO projects.

MR. RUBENSTEIN:  Thank you.  If we can turn to page 25, I'm reading from line 5, and you say:

"By utilizing the higher confidence number, e.g. P90,the owner and stakeholders reduce a significant amount of risk due to cost overrun."

Do you see that?

MS. GALLOWAY:  Yes, I do.

MR. RUBENSTEIN:  You'd agree with me that by utilizing a higher confidence level, the owner and stakeholders increase the likelihood that the project will come in under budget?

MS. GALLOWAY:  Yes.

MR. RUBENSTEIN:  And you say, and this is on line 19:

"Selection of a confidence level primarily is reflective of the risk appetite of the owner."

Do you see that?

MS. GALLOWAY:  Yes.

MR. RUBENSTEIN:  Can you explain to me what you mean by that?

MS. GALLOWAY:  So if you go back up to line 5 and 6, it's specifically -- and this is what I was referring to yesterday in my testimony -- by utilizing higher confidence number, e.g. P90, the owner and stakeholder reduces a significant amount of risk due to cost overruns.

The owner, and this is what we looked at here, has to look at what the confidence level must be from both a regulator and themselves, and whether or not those costs that are going to be put forth are going to be reliable so that the utility has some confidence that it will be able to manage the project and the program here within that envelope of risk to a certain degree of certainty that it can meet its budget.  And at the same time, the regulator has confidence that the program will also be able to be completed within a certain cost regime, because regulators have to look into the future as to, over a compendium of time, of where costs might be at some point in the future.

So it's important, from our review, that we look at both stakeholder expectations and we look at the circumstances of the risk, the complexities, the magnitude and that we build in some of those risks within a confidence level that allows management to manage a program potentially at a lower confidence level, but having an envelope to ensure the number that it's putting forth for approval at a point of time which is years earlier than completion, there is a much higher reliability in a.k.a. confidence that the program will not go beyond that cost or schedule, similar to what I was talking about with, for instance, Crossrail yesterday.

MR. RUBENSTEIN:  I understand why OPG would want to limit its risk.  That makes sense to me as the owner.  They ultimately have to pay for the cost overrun themselves.  They may be able to get approval and pass it on to ratepayers, but they have to pay for it.

I don't understand why ratepayers should have to pay to deal with OPG's risk appetite.  Can you help me understand that?

MS. GALLOWAY:  Again, when I indicated the -- the risk appetite is looking at what both stakeholders are going to have to put forward as a reasonable and reliable cost, ultimate cost of a program.

If you look at past megaprograms -- and this is what I was alluding to yesterday -- in which other megaprogram experts out there today have also now opined upon, is that the cost estimates were too low and they were not reliable because they did not adequately consider the types of risks that is could arise that one cannot see today.  And therefore, the probabilistic risk modelling is important and the confidence level, depending on the magnitude, the size, and the complexity of the project is important.  And what is being found today relative to megaprograms is that the stakeholders that are recognizing that, especially, I will say, public stakeholders that do have to report out to a customer, a ratepayer, the public at large, taxpayers, whatever the megaprogram is going to be, that you want to be able to have some assurance that when you tell your customer, your taxpayer, the public of what something is going to cost, there is now an expectation, and to prepare for that expectation, and to be able then to manage so you would come in at or even below that cost or schedule.  So at the end of the day all stakeholders' expectations have been met.

On lower confidence levels, it's, for instance, a P50 level, the AKA of that is there's a 50 percent chance it's going to come in on time and on budget, but there is a 50 percent chance it's not.  And that 50 percent is a huge risk if it's going to go over budget and over schedule and a cost that neither the governments want to try to reconcile of why that happened or even the utility or the owner building a project to say it's not a number that we're comfortable because of the risks that we do not know today that could happen.  That's why you do a probabilistic risk modelling with all the risks that potentially could occur and why you choose a higher confidence level on a program of this size and magnitude and complexity.

MR. RUBENSTEIN:  So I understand from what you're saying then that there is some benefit to coming in under budget, right?  OPG doesn't need to explain to other entities why it came in over budget.  There is just an inherent benefit for large projects to come in under budget.  Did I -- am I understanding that correctly?

DR. GALLOWAY:  I think when you plan a project of any sort the goal from all stakeholders is to come in within budget and within schedule.  If you can exceed that budget or schedule that's all a bigger benefit.  But the goal is to make sure that you meet the schedule and budget so set at the beginning.  That's an expectation on any project and should be an expectation on any project.

MR. RUBENSTEIN:  Well, I would have thought the goal here is to determine the right budget and the right schedule, it's not about setting expectations, necessarily.

DR. GALLOWAY:  Well, the expectations goes to how you've planned the project.  This program was planned on a P90 confidence level, meaning when they model the risks and come out and look at those risks, they are looking at the combination of all risks over four units that can accrue and possibly arise over the entire tenure of the planning for this program.

That P90 confidence level means that if a good portion of those risks arise, and they could, no one knows whether they will or will not arise sitting at this point today, then there is confidence that it is a reliable and a good budget based on that risk modelling.  That is what the P90 is showing.

So there becomes an expectation that you will meet whatever estimate that arise from that P90 modelling.  So that's the expectation.  If it's 12.8, the expectation is it's going to come in at 12.8.  And if it comes in below that, that will be a benefit to everyone.

MR. RUBENSTEIN:  As I understood from your examination-in-chief, you went back into your files and you looked and you said, well, what other projects that I've been involved in have a P90, and you were able to find two.  Did I understand that?  There's the Crossrail project, and I believe the other one was the Bellefonte project?

DR. GALLOWAY:  Yes, I think I indicated yesterday I did not remember -- first of all, we don't keep our records based on what confidence levels or where things modelled or don't model.  I even talked about today that there was no risk modelling at the time of the CPCN on either the Kemper or the Duke project.  It just wasn't done.  Back in the '70s and '80s risk probabilistic modelling did not even exist, and so obviously those projects would have never had one, because the modelling, the software, just wasn't in place to do that.

When I have obviously been reading the testimony every day, when I saw questions on the P90 I tried to think whether or not there potentially was recent projects where I did see that and records that I have, you know, available to me.  I remember something on Crossrail, because I knew it went through a very detailed risk modelling exercise.  I do know that it had a confidence level.  I could not remember the confidence level of the Crossrail project, so I did check that.  Similarly, I remembered there was risk modelling done for Bellefonte, and so I went back to determine whether or not that also had a P90 modelling, which I found that it did.

MR. RUBENSTEIN:  Do I take it -- you may not know this, but do I take it that those were the only two that you were able to remember or look up, that the majority of projects don't use a P90?

DR. GALLOWAY:  I would agree that there are not very many projects that use a P90.  It depends on the complexity and the magnitude.  The two that I mentioned I knew were of the same complexity and magnitude because one was a nuclear project and the one was an 18 billion dollar project.  That is part of the reason I went back to those files, because I thought they were of the same magnitude and complexity.

I don't know whether some of the others did or did not, because I didn't consider other projects to be of the same size and complexity, so I did not go back to the files to check.

MR. RUBENSTEIN:  And I am correct that your opinion as you've talked about earlier with respect to the DRP is that, you know, this project has done more work leading up to execution phase really than most projects?

DR. GALLOWAY:  Yes.

MR. RUBENSTEIN:  I want to ask you about -- briefly about megaprojects and nuclear megaprojects.  As we've heard from a number of OPG witnesses and from the documentary evidence, and I think you've commented on it indirectly, they have a habit of going over budget and over schedule, or beyond schedule, correct?

DR. GALLOWAY:  I believe you have to look at the circumstances at the time.  I do believe that, yes, the -- from the original cost estimate to where they are now, the ones in the '70s and '80s obviously were under different circumstances.  There is only three today that are out -- being actively built in the United States anyway to do comparisons on.  And I think I've already testified as to what those original estimates were and what the conditions and qualifications were.

MR. RUBENSTEIN:  I'm not saying that the reasons for the over budget or why they went behind schedule were imprudent, but just generally megaprojects, and made a career helping utilities work towards solving this problem, I think, you know, that they've gone over budget and they've gone over schedule, they have a chequered past in that regard, at a high level.

DR. GALLOWAY:  But I don't think it's fair, because there is not a fair comparison of how the original estimates were developed.  The original estimates were not developed on P90 modelling.  They weren't developed on the same pre-execution planning.

Had they done the same type of pre-execution planning and they done risk probabilistic modelling, the initial estimate would have been much higher, and if the initial estimate had been much higher their results may be much different than they are.

So I don't think it's a fair-to-fair comparison to look at what the initial estimate was and where they've ended up, because they're not apples-to-apples as to how the original estimate was initially developed.

MR. RUBENSTEIN:  So let me go back to page 13 of your report, where you were asked what your -- essentially your task was.  And you were to make an assessment of the processes in place for cost, schedule, program controls, and the application of the contingency to ensure that they are consistent with the way other megaprojects and megaprograms of similar magnitude, scale, and complexity have been carried out.

So would I be -- so do I understand what you're essentially doing is you're -- you looked at what OPG did and you compared it against, well, what is everybody else doing, and that's how you come to the assessment that OPG is doing a much better job than most other projects.

DR. GALLOWAY:  Yes, I mean, it was -- we looked at the industry standards.  We looked at other megaprograms, ones that are underway, ones that have been completed in the past, and we looked at utility industry best practice.  Those are the three items that we used to valuate the reasonableness and prudence of what's going on in the Darlington refurbishment program.

MR. RUBENSTEIN:  So if other utilities and other projects and other megaprojects, as you were saying, maybe didn't have the best comparison, they didn't do as much budgeting, and so they end up going -- at least maybe on an apples to oranges comparison -- over budget.

Is it maybe true that the way those megaprojects and megaprograms in the past are actually not the best way to compare.  We shouldn't look at these projects; there should be a better way to do it?

MS. GALLOWAY:  I think that as I so indicated yesterday, that's one of the areas where Mr. Roberts and I agree that each megaprogram -- there are so many different variables that go on between projects that make them unique, that it's not possible do an apples to apples comparison between a megaproject and a megaprogram.

However, as I also indicated yesterday and again this morning, is that what the global construction industry as a whole and both governments and owners and financers are learning is that there's a lot of elements of why megaprojects have gone over their initial schedule and budget, that we as an industry are learning from.

For instance, doing a probabilistic modelling, going to P90 confidence level for these very large projects is something that we are learning, when you do megaprojects, that you should do more of.  More pre-execution planning would assist greatly in having the megaprograms be successful, from both a cost and a schedule perspective.

This is something that Mr. Flyvbjerg, for instance, has come out I think even last year in an article that he prepared, that we are learning from megaprograms and how they were executed, and the very things I just talked about are things that different entities are now using, and that there is going to be a higher probability of success for these megaprograms as they apply these types of lessons learned from megaprojects in the past.

MR. RUBENSTEIN:  If we turn to page 22, here you're discussing -- this is with respect to is the setting up your discussion of cost management, and you were asked about the industry standards you use.  And as I see, you talk about the government accountability office, at GAO, you talk about the AACE basis.

Am I correct that those are the industry standards that you are looking at?

MS. GALLOWAY:  We looked at Project Management Institute, we looked at AACEI, we looked at the U.S. government accounting, and then with the experience that I have in the utility industry, obviously utility industry best practices as well.

MR. RUBENSTEIN:  When we turn to page 30 where you're talking about schedule management, again you're looking at the Project Management Institute, you're talking about the AACE, and you're talking about the government accountability office.

Those are the industry standards you're making the comparison to?

MS. GALLOWAY:  And utility best practices.

MR. RUBENSTEIN:  Are there industry standards for schedule development applicable to megaprojects?  "Yes, PMI and AACE, along with other entities such as GAO."

That's what I am reading of what you've --

MS. GALLOWAY:  Right, and at the very beginning of what you've read me on the initial pages comparing to other megaprograms and megaprojects, it goes into the utility best practice of other megaprograms and megaprojects of  what the utility industry has done in its planning.  That's one of the aspects that's also within this.

That's not, quote, a written standard, which is why it's not included in this answer.  But it's part of the evaluation process as outlined earlier in what we were comparing to.

MR. RUBENSTEIN:  Then if I go to page 34, where you are talking about reporting -- sorry, you're talking about reporting management.  Here you're utilizing the Project Management Institute best practices.  I see a reference to that.

MS. GALLOWAY:  It would be one of the references.  But again, it would be the same industry standards from Project Management Institute, what is also from AACEI utility best practices, those would be all the same standards we would be evaluating against.

MR. RUBENSTEIN:  When I go to page 25 and you talk about the contingency, am I correct -- is there an industry best standard of the confidence level you should choose, or is that strictly your industry experience that you're drawing your views from?

MS. GALLOWAY:  I think I include in my testimony that there is not an industry standard relative to the choosing of a confidence level, that it is unique to each project and it depends on its magnitude, complexity, size, and the risk that it's looking at.

I think I've made that statement in my testimony that there is not, quote, a standard for choosing a confidence level.

MR. RUBENSTEIN:  Thanks very much.  Those are my questions.

MS. LONG:  Thank you, Mr. Rubenstein.  I think we'll take our morning break for fifteen minutes, and then, Mr. Buonaguro, you can proceed.

### --- Recess taken at 10:48 a.m.

### --- On resuming at 11:06 a.m.

MS. LONG:  Mr. Buonaguro.

# Cross-Examination by Mr. Buonaguro:

MR. BUONAGURO:  Thank you.  Good morning.  Good morning, Dr. Galloway.  My name is Michael Buonaguro.  I'm counsel for Consumers Council of Canada, and I have some questions for you.

First I would like to follow up on some of the information you gave about the Kemper project.  That's what I'm going to call it, the Kemper project.  You had mentioned that March 31st, 2013 was the last time you were directly involved in reviewing that project pending the new review of the project, the new prudence review, I think you referred to.

DR. GALLOWAY:  No, I am currently still reviewing.  It's just the pre-filed testimony that was filed was only as of March 31st, 2013.

MR. BUONAGURO:  Right.  So your -- when you were referred to your opinion on the Kemper project it was the point-in-time opinion of March 31st, 2013?

DR. GALLOWAY:  Yes.

MR. BUONAGURO:  And so just for comparison purposes, your point-in-time review of the DRP, I think you've mentioned yesterday, I think it was to Mr. Stephenson, would be July 31st, 2016?

DR. GALLOWAY:  Correct.

MR. BUONAGURO:  Right.  So it's the same sort of thing, things that happened after that date you obviously haven't reviewed, so for example, whatever OPG has done since July 31st of 2016 you don't have an opinion on.

DR. GALLOWAY:  Correct.

MR. BUONAGURO:  Okay.  And you said something interesting about Kemper.  And you said, I think the last -- that March 31st, 2013 date related to an annual review of the Kemper project that you used to do?

DR. GALLOWAY:  So in the CPCN order on Kemper the commission had indicated that it was going to set up an annual prudence review to review matters annually and make a determination on prudence annually.  The pre-filings went in, and then the commission changed its decision, came out with a new order, and indicated that it was not going to review prudence on an annual basis and it would wait until the project was completed to hear prudence.

MR. BUONAGURO:  Okay.  So maybe I can follow up.  How many years of annual review actually happened, or are you telling me none happened?

DR. GALLOWAY:  None happened.  There have been zero prudence hearings on Kemper to date.

MR. BUONAGURO:  Okay.  That explains a lot then, because the way it came up earlier it sounded like it had been going on and it stopped, but you're saying it actually never really got started.

DR. GALLOWAY:  The prudence review, that's correct --

MR. BUONAGURO:  On an annual --

DR. GALLOWAY:  -- never been a hearing to date

since --

MR. BUONAGURO:  Okay.

DR. GALLOWAY:  -- the CPCN hearing.

MR. BUONAGURO:  Thank you.  And I want to lead into my questions in general with something I heard yesterday if I could.  This is from the transcript, page 154 -- or 153 to 154, from -- I don't know what volume number it is, sorry

-- volume 5.  It's going to come up on the screen.  Starting at line 26 of page 153.

So I pick up part of your answer there, and you say:

"And that is why the megaprograms that are taking what I would call a more realistic view of having as much information as they reasonably can based on what is known at the time and modelling that from a probabilistic standpoint that the financer of the megaprogram, whether that's a private entity, an investment bank, an owner, a commission, gives them a higher confidence of what they know and ultimate cost may be, and they can then make better informed decisions knowing what that ultimate cost may be."

So I took that to mean in the context of this case -- and we're talking about the OPG's use of a P90 for the DRP -- and I'm going to talk in terms of Unit 2 cost, as opposed to the entire program costs if I may.  So when we're talking about the DRP Unit 2 costs projected of 4.8 billion dollars to go into service in 2022 -- sorry, 2020, I believe, the P90 basically tells everybody, don't be surprised if it comes into 4.8 billion, because there's a lot of things that are going to happen between now and then that we've modelled using the Monte Carlo simulation, so on and so forth, but hopefully it will come in under, and if it goes over there's going to have to be pretty good reasons for it.  That's sort of how I took what's going on here; is that fair?

DR. GALLOWAY:  Well, the P90 confidence modelling was done on four units, not on just one unit.  And so all of the units, of course, with how they are interconnected and the risks are all modelled on a four-unit basis.  And so it would be difficult for me to opine specifically on, quote, how those risks may be separated out, because I don't think you can easily separate out the models since it was on four units.

MR. BUONAGURO:  Okay.  So thank you for that.

I had understood, and perhaps I misunderstood, that you had said something about what you were asked to do, and you talked about allocation, and I had assumed that that meant the allocation of the contingency.

Are you telling me that you don't have an opinion about how OPG has allocated the contingency amount of $1.7 billion between the units?

DR. GALLOWAY:  We looked at it from an entire program.  So the contingency as it applied in the P90 model for the entire program, and not specific to, quote, Unit 2.

MR. BUONAGURO:  Okay.  Fair enough.  You're aware, though, that they've allocated for the purposes of rate-setting 700 million or so of contingency to Unit 2?

DR. GALLOWAY:  Yes.

MR. BUONAGURO:  And again, I've rounded it up.  It's changed slightly, but -- thank you.

And I think, though, from what you're saying and what I had understood about contingency in the first instance, when the company comes with a completed Unit 2, hopefully, in 2020, if the total amount for Unit 2 isn't 4.8, it could be more than 4.8, because more than the allocated, quote unquote, amount of contingency occurred as Unit 2 is being built, but it also could be less, because less of the allocated contingency could have occurred in relation to Unit 2.  Those are both reasonable scenarios?

DR. GALLOWAY:  Yes, projects could come in before and under.

MR. BUONAGURO:  Yeah.  And then if we talk more holistically on the 12.8 billion and the $1.7 billion of contingency for the entire project, contingency may not come to fruition in that amount.  It might come in lower.  And hopefully it comes in lower, right?

DR. GALLOWAY:  Yes.

MR. BUONAGURO:  Okay.  Now, I want to talk briefly about imprudence, because a lot of your evidence that -- or, sorry, I should say a lot of the examples of evidence that you've given in the past related to what I would call ex post facto prudence reviews; is that correct?

DR. GALLOWAY:  Yes.

MR. BUONAGURO:  Where you've looked at how a company has managed a project to completion and then asked for approval of costs, and part of the review of those costs is to see if any of the costs incurred were actually imprudently incurred?

DR. GALLOWAY:  Yes, but with the caveat of it's not -- in hindsight it's not an after-the-fact review per se, because under the prudence statute in the U.S., the jurisdictions, is that every decision that is made has to be looked at and evaluated and it has to be looked at in the time that it was made based on what it was -- what was known or what reason it should have been known at the time.

So it's not like you have the ability on five years to say, well, that decision, actually, after five years doesn't look like it was a good decision.  It has to be put in the context of when the decision was made and what was known.

MR. BUONAGURO:  Fair enough.  The difference being, though, that because you're not able to sit with the company and watch them make decisions in real-time, you have do it after the fact, but I understand what you're saying.  The measure of whether they're being reasonable or not is in the context of the time they're making the decision and what they had available to them at the time of the decision.

DR. GALLOWAY:  Yes, but just to correct one -- I think your prior question was, our prudence reviews are always de facto after the fact.  I want to -- as I talked about with Vogtle this morning, those reviews was on the CPCN, so that was in the exact scenario as here, as I relayed to the Board.

So the project had not gone forth to an execution yet at all.  It was seeking approval to go forward, and so that prudence review was done on the pre-execution planning for Vogtle.

MR. BUONAGURO:  Thank you.  But I'm assuming that any -- whenever you do that type of review, you're always limited at the point in time, right?  As we talked about, you haven't -- and not presuming to evaluate all the decisions that OPG makes from July 31st forward and bless them as prudent in advance.  You're saying that as of July 31st, 2016, based on what they're planning to do, it looks good, it looks prudent.

DR. GALLOWAY:  And how they are planning to actually implement and go forward with the execution.  So it's not just the establishment of what they have in place, but actually their plans for execution and their understanding of those plans on how they will implement the policies, procedures, and processes.  That was true in Vogtle, and it is true here.

So you're looking at, and I think I so opined, that based on that approach, based on the interviews with the project personnel who will be responsible for executing the program, that plan would favourably position OPG for a successful execution.

MR. BUONAGURO:  That's assuming that they execute in accordance with their plans.

DR. GALLOWAY:  Yes.

MR. BUONAGURO:  I think that's what Schiff Hardin's evidence raises the issue of, which is that planning is great, and I think they generally agree that the planning is done well, but it's the actual execution of those plans over the next four years which may or may not result in imprudent costs, right?

DR. GALLOWAY:  True.  But I think Mr. Roberts and I both agree that the process and the tools that are in place are reasonable and prudent, and if executed in accordance, should allow for a successful execution of the DRP.

MR. BUONAGURO:  If we come to 2020 and the project comes into service, and the dollar value for the DRP is as budgeted, the $4.8 billion, are you saying that we know for sure that that does not include any interim costs?

DR. GALLOWAY:  I don't think I can answer that sitting here today.  Those are actions in the future for which no one has the ability to evaluate.

MR. BUONAGURO:  I fully expected that to be your answer; I'm just making sure.

Now, in order to determine whether or not there's imprudent costs built into that final cost, I assume this Board, if it were so inclined, would have to look at the evolution of the project and decision-making and essentially do a prudence review of the project to distinguish between costs that are what I might call true contingency costs -- i.e., costs that were identified and responded to and mitigated, but still incurred -- versus costs that resulted as a result of imprudent decision-making or execution by OPG.

That sort of analysis would have to be done in order to separate out prudent costs versus imprudent costs, right?

DR. GALLOWAY:  Again, in the pre-approval of a cost estimate -- I mean, no one goes into pre-planning assuming that you're going to be imprudent.  But barring things of fraud or issues of concealment, both items of which even the commissions and jurisdictions in the United States would say if those happened, then those particular costs would not be allowed even if they were under a particular cost.

But the pre-approval of the cost estimate is deemed to be reasonable and prudent and encompasses a contingency to cover risks that could happen, and if a utility comes in at that cost, those costs would go into rate base as pre-approved but for actions of fraud or concealment.

MR. BUONAGURO:  I see.  So if this Board approves $4.8 billion for Unit 2 and the project comes in at $4.8 billion or less, you're suggesting that the only disallowance of any of that amount would have to relate to -- I think you said fraud or concealment?

DR. GALLOWAY:  That would be up to the Board on  however they decide to look at those costs.  That wouldn't be for me to tell the Board what to do.

MR. BUONAGURO:  I'm following up on what you said.  You said pre-approval of a cost usually means that when they come in for -- when the final costs are incurred and the costs are at or below budget, then it's fraud or concealment?

DR. GALLOWAY:  That's the way the jurisdictions in the States handle it, yes.

MR. BUONAGURO:  If that were the way it worked here and the Board remained concerned it wants to distinguish between what I call contingency amounts -- so contingency amounts meaning amounts that don't necessarily relate specifically to a contract, but relate to the risks they identified and came to fruition and caused that -- some part of that 700 million budgeted amount versus costs that actually were imprudently incurred, in terms of failing to identify risks that they should have identified, or not reacting appropriately to a risk, the solution would be to lower the amount that's pre-approved?

DR. GALLOWAY:  I think you would have to look at the circumstances.  I think based on the premise you put forward is not enough facts to ascertain.  There's considered in prudence a zone of reasonableness.  There is not necessarily a -- there is not an optimal response.  There is not a preferred response.

There are different responses that management can take depending on the circumstances at the time, which is why you have to look at the circumstances at the time.  So even the examples that you gave, if they -- what would appear to be an inappropriate use to a risk would have to look at all the facts at the time on the circumstances of why that may appear to be an inappropriate risk, but based on other factors, would still fall within a zone of reasonableness which would have been covered within that contingency aspect for the estimate.

MR. BUONAGURO:  Fair enough.  But my point is that that examination would take place after the fact.  There's a difference between what you told me, I think, about the impact of a pre-approval of a budget versus part of a budget that isn't pre-approved.

Maybe I can attack it this way.  If the pre-approved budget is 4.8 billion and the costs come in at 5.5 billion, presumably there's going to be -- we know there's going to be a request from OPG to recover the impact of that additional .6 billion dollars in spending, and the examination by the Board is going to have to look at whether or not that extra cost was prudently incurred, correct?

DR. GALLOWAY:  I assume.  I'm not sure how this Board works in this jurisdiction, but I would presume so.

MR. BUONAGURO:  Right.  And in that instance, would the same limitations on the prudence review be in place that you were talking about?  It would only be if they were fraudulent or concealment?

DR. GALLOWAY:  I don't know.  I'm not familiar with what this Board -- one, what OPG will ask, what this Board will opine upon, and how that relates to the overall 12.8-billion-dollar estimate.

As I indicated, the risks and the costs are all done on a probabilistic modelling of all four units, and so a cost overrun on Unit 2 may potentially, based on the lessons learned from Unit 2 that resulted in those cost overruns, may be applied to the later units that potentially costs could be reduced in later units, so within the overall contingency of the $12.8 billion, the entire program still comes in on budget.

So it is with those considerations that would need to be looked at relative to any overage on Unit 2, because it can't be looked at in isolation on the total cost of the program because that -- the way the cost overruns and under-runs are modeled are on the four unit process, not an individual unit basis.

MR. BUONAGURO:  Thank you.  My point being, though, that the exercise would have to be done.  You would have to look at what actually happened in order to make the determination of whether or not there was imprudence, or whether it was simply an appropriate contingency event or contingency cost?

DR. GALLOWAY:  There's a lot of factors.  I'm not sure I can totally answer your question, because I don't know the facts and the circumstances that may arise 4 to 5 years from now.

MR. BUONAGURO:  Thank you.  I want to take you to page 34 of your evidence briefly, Exhibit D2, tab 2, schedule 11, attachment 3, page 34.

I am looking at the bullet points under what types of information is typically provided -- I guess that should have been what types of information are typically provided in performance or progress reporting.

I'm looking at the bullet points and most of them, I think I can fit under reporting that OPG is proposing to do on an annual basis with respect to the DRP.  But the one that sticks out to me is the current status or risks and issues.  Did you review -- I think you said you reviewed the reporting proposal by OPG with respect to the DRP, did you?

DR. GALLOWAY:  Yes.

MR. BUONAGURO:  And did you see them proposing to report on current status or risks in issues?

DR. GALLOWAY:  I believe that I saw a dashboard type of proposal where you have -- and it's very commonly used nowadays on megaprograms, where you have, like, colours, you have green, yellow, red, red being risks that are critical risks that could impact cost or schedule, yellow that means they might, and green meaning they probably don't have any impact.

I believe I saw some type of dashboard reporting that would on a macro level present overviews on risks and risks that were occurring to the project.

MR. BUONAGURO:  You note in the evidence in the preface to the bullet points, you say:

"PMI notes that more elaborate reports may include..."

Bullet, bullet:

"...current status or risks and issues."

Can you give an example of where that's occurred in another context?

DR. GALLOWAY:  It's occurring on Vogtle.  It's occurring on Kemper.  It's occurring on the Energy Strong program that we're doing the independent monitoring on.

MR. BUONAGURO:  And what's the depth of detail in those reports on the current status of risks and issues?  Is it --

DR. GALLOWAY:  It's the dashboard that I talked about.

MR. BUONAGURO:  That's it?

DR. GALLOWAY:  Yes.  There's not more detail that is provided in those particular annual reports.  I mean, us as the independent monitor, of course, look at more detail that the utility is actually using to look at those risks by looking at the risk registers and whether or not they are actually determining whether risks are retired or whether new risks have arisen and how they've been looked at and how they've been viewed, and then ensuring that that information rolls up to that dashboard type of a review, which is what we consider appropriate for a senior management and Board review of how the project stands currently to risks and issues.

MR. BUONAGURO:  So if the Board were interested in an annual report versus -- of that level of detail, that's the sort of reporting that would have to be done to the Board, the OEB, as opposed to the -- I can't remember what you called it -- the dashboard amount, which is what is given to the public?

DR. GALLOWAY:  No, no, no, no, no.  What I meant by the dashboard, that is the level of reporting that is given both to senior management of a utility, given to its Board, and given to the commission.  That is the level that is typically provided, is that dashboard overview.

MR. BUONAGURO:  So who is the target audience for what you just described to me in terms of the level of detail?

DR. GALLOWAY:  The risk -- which level of detail are you talking about, the dashboard or the risk registers --

MR. BUONAGURO:  The more detailed one.

DR. GALLOWAY:  That's the project management level, so these are the people that are actually in this instance managing the bundles, the project bundles.  They would be looking at the detail of the risks, and they would be the ones looking at whether risks have retired, risks have arisen, they would be working with the risk management organization that has been established for the DRP.  They would be doing that detail-level process and they would be handling that detail level and then rolling up the level as it goes higher up through the organization.

MR. BUONAGURO:  My understanding then from what you just said, that's the level of detail that you require in order to ensure that the company is managing the risks appropriately?

DR. GALLOWAY:  Which level?  Again, can you just be a little bit more --

MR. BUONAGURO:  The more detailed level, before --

DR. GALLOWAY:  The more --

MR. BUONAGURO:  -- it gets transformed into a dashboard.

DR. GALLOWAY:  So the more detailed level, the risk register and the risk monitoring is laid out quite in some detail in OPG's policies and procedures, along with the different levels within the organization that will be doing different tasks along that line.  So the risk register in this case for the program is quite detailed and has the mechanism of retiring risks and putting new risks on and evaluating the cost and schedule impacts of those risks through its risk assessment.

And that is what was in place when I -- we did our review and was being implemented when we did our review, and I would assume would continue to be implemented and in use as it was at the time of our review.

MR. BUONAGURO:  Thank you.  One last question, and I'm only asking it because there was some cross on this in panel 1B.

In terms of the risk register, is the risk register that you actually identified as part of your analysis on the record already?  I ask that because I understand there are risk registers on the record, but as we understood it through the cross-examination, they are a point-in-time document; i.e., if you print it today versus you print it four months ago, they will look very different.  So I'm wondering if the one that you reviewed is actually on the record.

DR. GALLOWAY:  I have no idea.

MR. BUONAGURO:  Okay.  So the one undertaking I would ask is that the risk register that you actually reviewed would be added to the record.

MR. KEIZER:  I believe it already is on the record.

MR. BUONAGURO:  Thought it might be.

MR. KEIZER:  I don't know the exact exhibit number --

MR. BUONAGURO:  If it's not -- if it's not --

MS. LONG:  You'll direct to us that?

MR. KEIZER:  Yes.

MR. BUONAGURO:  Perfect.

MS. LONG:  All right.  Can we just mark that just so I don't lose track, please.

MR. RICHLER:  That will be Undertaking J6.1.

UNDERTAKING NO. J6.1:  TO PROVIDE THE LOCATION IN THE EVIDENCE OF THE RISK REGISTER DR. GALLOWAY REVIEWEd.

MR. BUONAGURO:  Thank you, those are my questions.

MS. LONG:  Thank you, Mr. Buonaguro.

Mr. Poch, we have a hard stop today at noon.

MR. POCH:  That should be fine, Madam Chair.  If I don't notice the clock, please interrupt me.

MS. LONG:  I will do that, thank you.

# Cross-Examination by Mr. Poch:

MR. POCH:  First of all, just a few questions that have arisen from your discussion so far.  You've mentioned AP1000 a few times.  I take it that's the Westinghouse design?

DR. GALLOWAY:  Yes.

MR. POCH:  And Westinghouse was -- that part of Westinghouse was bought by Toshiba a number of years ago; is that correct?

DR. GALLOWAY:  That is correct.

MR. POCH:  And I read recently that -- correct me if I'm wrong -- that Toshiba has decided to get out of the nuclear business.

DR. GALLOWAY:  I've read the same thing.

MR. POCH:  Right.  Secondly, just in terms of your discussion with Mr. Buonaguro a few minutes ago, I just want to make sure I understand -- make sure we're on the same page.  If this Board were to agree that 4.8 is reasonable at this time, it's going to go into rate base in 2020, and that only any variance from that will be examined, would you agree that one possibility is OPG could proceed, come in at 4.8, but have imprudently allowed, say, 300 million dollars' worth of costs, yet that was fortuitously offset by 300 million dollars' worth of contingency at the P90 level that didn't materialize and we would never know that?  That's a risk with that approach.  Would you agree?

DR. GALLOWAY:  I don't know the circumstances upon which the Board has laid out its review, and further, again, I think as I was given the answer to the example earlier on when something was deemed -- appeared imprudent, that that actually would have to be looked at at the circumstances at the time.

MR. POCH:  Of course we can -- I understand your point.  I'm just saying your client in this case, OPG, has proposed the mechanism I've just described to you that it's 4.8 absent, you know, fraud or, you know, extreme situations like where there's an allegation of fraud, for example.  That's the end of it.  The Board won't subsequently get to evaluate prudence of the 4.8.

Would you agree that if that scenario was adopted by this Board -- and I agree with you we don't know what the Board will decide -- but if it were to be the approach, that there is this risk?

DR. GALLOWAY:  You know, that is why the -- in the U.S. the jurisdictions have taken the cost of pre-approval of an estimate absent fraud and concealment, and, yes, if a utility comes in within that estimate, that is the pre-approved cost, and that is what the commission will allow.

I don't know what this Board will allow, but that is the practice in the United States.

MR. POCH:  So in the States a Board in that situation where they've pre-approved something years before, as long as it meets that price they're not going to -- they don't ask whether the eventual sum was a product of imprudence being offset by good fortune or not?  They're just, they're content to let it lie; is that --

DR. GALLOWAY:  I think they look at it from the contingency level and building in that things may happen that cannot be predicted at the time of the pre-approval, and as long as again the project comes in within the pre-approval it has been accepted.  It is the costs that go over -- provided there is not a program where it has to be looked at the overall cost of the program, then those overages are what is being looked at.

I think, for instance, on Vogtle, if you were to look at the commission's order, that's exactly what the commission order said in Vogtle, that if the cost of the unit came in -- 3 and 4 within the initial certified cost, that any costs up to that would be approved and anything over that would have to come back, which is the exact mechanism they went through when it was increased, and that hearing has just finished a few months ago.

MR. POCH:  Right.  So that -- I think we're in agreement that that's what goes on, and that one of the -- the price we pay for that approach possibly is that there could be imprudence which never sees the light of day, because it's offset by contingencies not materializing.  It's entirely possible?

DR. GALLOWAY:  With the caveat of that's the cost and the risks that were looked at, that were built into the price and but for fraud and concealment, there is a built in risk for that entire cost that's pre-approved.

MR. POCH:  I understand what you're saying.  But I'm concerned about the contingency -- something that wasn't built into the price, that wasn't built into the contingency allowance, wasn't identified as a risk, and was imprudently incurred.

DR. GALLOWAY:  I don't know if I can actually answer the question, because the risk mechanism that is looked at covers everything up to a point cost which is asked for the pre-approval.  And again, within the exceptions as I've indicated, the fraud and concealment, that total cost would be approved.

MR. POCH:  Okay.  I think I can leave it there.  I think the situation is clear.

If you turn up L 4.3, schedule GC 5, we asked you about the history of your involvement in nuclear projects, and your corporation involvement is referred to there.  And I take there has been some -- I think you refer to some 55 nuclear projects that Pegasus-Global has been in some fashion involved in.

DR. GALLOWAY:  Yes.

MR. POCH:  If we turn to 4.3, schedule 15, SEC 40, there's a chart attached as attachment 1, and I think you referred to this earlier.

There's 29 projects there where you personally have testified or issued a report.

DR. GALLOWAY:  Or been participatory in the analysis.

MR. POCH:  Right, that involved nuclear.  Of all these projects you're aware of, and the ones you're aware of but weren't personally involved in or corporately involved in, including the ones in Canada, if we were to look at the cost and schedule estimates that is were provided 5 years in advance of the expected in-service date, would you agree that virtually in the nuclear world, the vast majority end up coming in either above cost, delayed in schedule, or both?

DR. GALLOWAY:  They have, based on what I had indicated previously, that they did not have the benefit of doing the P90 confidence level and the type of pre-execution planning.  Had they been done on a P90 cost estimating basis, there is a high likelihood that several of these would have come in within the budget and schedule.

MR. POCH:  But in fact, there haven't been any nuclear projects done in the way you just described?  This is the brave new world where you're trying to learn from other activity, other areas of activity that probabilistic estimation is helpful, for example?

DR. GALLOWAY:  Right.  As I had mentioned -- well, Bellafonte is different; it's on here.  Bellafonte was done on a P90 basis.  Other circumstances relative -- economics on TBA relative to the decision not to proceed.

But most of these, except for Vogtle 3 and 4 and Levy and of course Darlington, all the other were done before probabilistic modelling was even in effect.  So there was no opportunity to do such probabilistic modelling.

So you're only looking at the Levy unit, which we've already talked about and was decided to not to go forward. Bellafonte in the same situation, and Vogtle 3 and 4 is the only other one on this chart, and I believe we've discussed that in the contract risk reviews.  And currently, the units are tracking under the current re-approved estimate.

MR. POCH:  But not near the original estimate when the project was first approved to go ahead by the regulators?

DR. GALLOWAY:  Again, that was under the understanding by both the commission, the intervenors, and the utility that there would be costs and risks that would arise that, if they did, would go into a re-approved certified estimate.  And that's what occurred, and was what has been approved.

MR. POCH:  Now, in terms of your review of OPG's project, we've heard there's thousands of items in the risk registry, for example.

I take it -- am I correct in my understanding that it wasn't part of your mandate to go and look at the zirconium tube replacement and decide if they caught all the possible technical risks?  Your mandate was to say you've done an exercise, you've done your best to identify those risks, you're tracking them, you dealt with them in the contracts, and so on.  Is that fair?

DR. GALLOWAY:  No, I think I indicated before we did some sampling of the risks in the risk register, to follow back the roots of those risks, how they were identified, how they were vetted, how they were put in, how the costs in the schedule risks were determined and how they fit into the model.

And then we reviewed detailed other reports by subject matter experts that did do the in-depth deep dive review to see what they reviewed and how they made their findings and opinions, based on the deeper dives of those other risks.

MR. POCH:  I understand you've looked at the risks that have been identified, and seen they've been tracked through and included either in the base forecast or contingency, what have you.  I guess I'm talking about risks that weren't identified.

You didn't attempt to, did you, look and see if there were risks that simply weren't identified at the outset?

DR. GALLOWAY:  That was part of the interviews of the process of how they went about identifying the risks, how many groups or sessions, risk sessions, risk workshops which are typically the way you look at risks.

You have different workshops with subject matter experts that identify risks.  You then have vetting of those risks by other subject matter experts, which was performed here.

So we looked at the process of the risks and how they were identified, and by whom, and by how many types of individual groups.  And through that process of the various different levels of input in the multitude of subject matter experts, and internally and externally, we thought they had captured reasonably all of the input of all possible risks that could be reasonably identified.

MR. POCH:  What is your understanding of OPG's mandate from the government with respect to this project?

DR. GALLOWAY:  What do you mean by their mandate?

MR. POCH:  What's their marching orders, as you understand it?

DR. GALLOWAY:  To refurbish the Darlington four units so they have another 30 to 35 years of life extension.

MR. POCH:  And OPG has gone about this with the contracts and the allocation of work in-house versus contractors and so on, and you've looked at all that.

I can inform you one of the -- part of the mandate was to minimize commercial risk.  Did you go back and look to see if they got other bids with other contractual arrangements where they outsourced more of the risk?

DR. GALLOWAY:  We looked at the contracting methodology.  But as I indicated, we were not asked to look at the terms and conditions of how those contracts were actually selected and negotiated.  That was done by another company, I believe.

MR. POCH:  So the government wanted -- gave OPG some instruction in terms of how it wanted to see risk and cost traded off.  You're not opining on the manner in which OPG responded to that?

DR. GALLOWAY:  That would be embedded in the terms and conditions of the contracts, and we did not evaluate that.

MR. POCH:  Thank you.  Those are all my questions.  Thank you, Madam Chair.

MS. LONG:  Thank you, Mr. Poch.

Mr. Yauch, do you want to get started?

# Cross-Examination by Mr. Yauch:

MR. YAUCH:  Sure.  Good afternoon.

DR. GALLOWAY:  Good afternoon.  It's not afternoon yet.

MR. YAUCH:  It feels like it.

[Laughter]

Start on page 2 of your report.  So I'm going to take you through a couple documents and then I'll ask you a question.

DR. GALLOWAY:  Page 2, meaning page 2 of the filed testimony or --

MR. YAUCH:  Yes, of your testimony.

DR. GALLOWAY:  Or page 2 of my report?

MR. YAUCH:  Of your testimony.  I gave the --

DR. GALLOWAY:  But is it the page number or the exhibit number?

MR. YAUCH:  Page 7 of 122 or page 2 of --

DR. GALLOWAY:  Thank you.  Thank you.  I just want to make sure I'm on the right page.

MR. YAUCH:  Okay.  That's fine.  So in it, I'm line 12, and you go through this in other parts of your documents, you say OPG was active in issue resolution.  So I take that in your review of the company you found that OPG found -- encountered problems when it was doing work and took all the necessary steps to solve those problems.  Is that a correct way to characterize what you found?

DR. GALLOWAY:  I'm sorry, what --

MR. YAUCH:  On line 12.

DR. GALLOWAY:  -- I'm trying to look on page -- on line 12, and I don't see that statement.

MR. YAUCH:  "And active in issue resolution."  Am I not seeing it?

DR. GALLOWAY:  Oh, I see.  "And active and issue resolution"?

MR. YAUCH:  Yeah.  And you expand on it later in page 52, but essentially I'm going to characterize what you said.  You found that OPG did a good job at solving problems as it encountered them when it came to Darlington work?

DR. GALLOWAY:  I think I've talked in the context of the lessons learned that they took from the refurbishment projects and the other nuclear projects and the other megaprograms and they reasonably applied those lessons learned into the execution -- pre-execution planning for the Darlington program.

MR. YAUCH:  Okay.  So if you can go to page 39 of my compendium for 1A.  So this was an audit report.  If you scroll down a little bit, it's highlighted.  And the auditor -- this report was done at the same time you did your report, and it said there was a cultural tolerance for acceptance of work --

MS. SPOEL:  Exhibit number of that 1A compendium?

MR. YAUCH:  I forget the exhibit number.

MS. SPOEL:  Oh.  Oh, I have it.  It's 1.4 -- K1.4.

MR. YAUCH:  Thank you.  So this auditor at the same time found that there was a cultural tolerance for acceptance of work delays, and it said:

"This tolerance for work delays is being enabled by a leadership team."

So I was curious what they found compared to what you found, and if you can comment on why you didn't see these sorts of issues that this other auditor found?

DR. GALLOWAY:  Well, first, the Refurbishment Construction Review Board and I have been active in review boards as well.  The mandate for those review boards is to be critical, to try to find ways that you can catch potential issues early so that they don't manifest themselves into cost and schedule impacts.  And so I take this report in that context, having been in their shoes similarly for other programs.

And when they're talking about work delays from the enabled leadership team, I mean, that's a finding that they have at the time.  I don't think that's the same -- in the same context or response to what we were previously talking about in the incorporation of lessons learned from the other programs that were incorporated into the pre-execution planning here.  This is a point in time that they're looking at and their schedule adherence.

At this point in time in July the schedule was -- the final schedule was still under development.  At the time of our review the final integrated schedule was planned to be complete in August and September, and so I believe that they were probably trying to assist them, and from what I can just gather from looking at their report very briefly as to looking at ways as they're doing that work planning to ensure that again the processes and the procedures that they have in place will be emphasized and persons trained on those and that these types of reflections will be picked up before that schedule completion is finished.

MR. YAUCH:  So you said that the construction review board was a bit more critical than what you were tasked to do.  So you weren't tasked to critically look at the leadership team of OPG to see if they were able to meet the deadlines that they were tasked to meet.  Is that the difference between the two audit reports?

DR. GALLOWAY:  Well, again, I'll try to be a little bit more clear.  A construction review board on any program is tasked to come in at a point in time and to look at items at points in time that may be occurring to pick similarly as we are doing as the independent monitor on the Energy Strong program for PSE&G to find, even if they're isolated incidences, to find things that they want to bring to the senior leadership and the program management's attention so that the types of things that they are potentially seeing at a point in time can be either corrected or whether the policies and procedures need to be revised so that there is better clarity with who will be following those to minimize these point-in-time observations.

The part that -- the analysis and the scope that we were undertaking was that we were looking at the policies and the procedures and the processes and the organization and the structure to ensure that those met industry best practices and were put in such a way that if implemented would allow for successful execution of the program.

So there are differences in what the construction review board is being asked to do versus what we on the reasonableness and prudence of the actions taken by OPG.  There's different mandates between both of these exercises.

MR. YAUCH:  Okay.  Thank you.  If you can go to page 41 of that compendium.  Just to follow up on this, just go down, that bullet point under point 3, it says:

"Management behaviour when schedule expectations are missed is weak."

So as a follow-up of what you said earlier, your group just looked at whether OPG had the process in place and the construction review board looked at whether they were able to meet those processes, correct?  That's the difference between the two?

DR. GALLOWAY:  No, we went beyond just whether they're in place.  As I indicated, we then took on interviews of project personnel as to their understanding of what those policies and procedures and processes were, their understanding of how they were to be implemented, their current implementation of those policies and procedures, and the reasonableness of their understanding and their implementation of those.

These are point-in-time observations of -- which is typical of, again, a construction review board.  To identify I would have to, for instance, look at the specifics that they are talking about.  I mean, their reports would be very similar to our independent monitoring reports, that it doesn't dive down into the detail in the report, but in their discussions with management, they may be talking about a few activities, they may be talking about a particular area, and you would have to look at the specifics behind this bullet to see whether or not that's a programmatic concern or whether it is a particular specific area concern with particular people on particular activities.  Without that knowledge it would be difficult for me to ascertain what this bullet is referring to.

MR. YAUCH:  No, but in your report you actually never questioned management's behaviour to meet schedules.  You didn't find that as a problem.

DR. GALLOWAY:  No, I believe that we did, especially in respect to the pre-execution projects that were trending over schedule and over budget.  We specifically went into the reviews with OPG personnel to understand why, to understand why those potentially had different processes for which they were being managed, the lessons learned from those and how they were being incorporated into the new policies and procedures.

So yes, we were looking at where things stood against certain schedules for different projects that were underway, and how OPG was reacting to those particular delays, to some of those pre-execution projects.

MR. YAUCH:  In regards those pre-execution projects, in your evidence -- and OPG has sort of maintained this point as well -- that those weren't done how refurbishment is going to be done, so we shouldn't compare the two.  At the same time, the way in which we did the refurbishment planning was with this statistical model, the Monte Carlo model.

But in your evidence, you also say that those early projects were essentially guinea pigs for what comes Next, that a lot of groups do these early projects to see how things go.

But from the Board's point of view, we can't actually look at whether those are going to be any indication of how the rest are going to go, because they were done differently.  So in a way, they weren't really guinea pigs; they're just a different project, correct?

DR. GALLOWAY:  There's a lot of presumptions in your question.  But let me try to break that down a little bit.

It is correct that those early projects were not done to the same policies and procedures that were developed for the Darlington refurbishment program.  They were done to the projects and modifications, policies, and procedures that had been existing at the time.

The same was true for some of the contracting practices.  Those projects -- decisions were made to execute those to have them completed, but there was also lessons learned from that.  For instance, what was not working in the policies and procedures that needed to be incorporated in the policies and procedures for Darlington to minimize, to be able to ascertain what potential delays might be earlier to minimize against this, to look at the lessons learned from the contracting strategies to be able to incorporate that into different contracting strategies for Darlington.

So yes, while they were done under different policies and procedures and contracts, how those panned out were lessons that were in fact incorporated in the policies, procedures and contracting models on the Darlington refurbishment program in order to minimize and/or eliminate the issues that arose on the pre-execution projects.

MR. YAUCH:  Do you want me to keep on going, or take a break now?

MS. LONG:  Is this a convenient time?

MR. YAUCH:  Yes, I can stop now.

MS. LONG:  Thank you very much.  We are going to break and be back at 1:05, please.

### --- Luncheon recess taken at 11:59 p.m.

### --- On resuming at 1:11 p.m.

MS. LONG:  Mr. Keizer.

# Preliminary Matters:

MR. KEIZER:  Madam Chair, just one preliminary matter, and that is related to the undertaking given this morning, 6.1, and the location of the risk register that was reviewed by Pegasus is at issue 4.3, Staff 73, attachment 7, pages 21 to 235.

MS. LONG:  Thank you very much for that.

MR. KEIZER:  Thank you.

MS. LONG:  Mr. Yauch, are you ready to proceed?

# Cross-Examination by Mr. Yauch:

MR. YAUCH:  Good afternoon.  I think it's afternoon --

MS. LONG:  Good afternoon.

MR. YAUCH:  -- now.  I just have two areas left to explore.  So the first one is the -- it's the idea of the Monte Carlo model.  And I know a lot of people have talked to you about this, and it's been the centre of a lot of discussion.

As far as I can tell, this is the only nuclear project that's ever been built that has used this type of model to estimate the cost and the contingency involved with it, correct?

DR. GALLOWAY:  To my knowledge that would be correct.  I haven't analyzed the nuclear plants in Europe to know whether or not that is the case.

MR. YAUCH:  So during this application, these five years, Unit 2 will be completed, so at the end of this, this will be the first time, or maybe midway through, that this Board and the public in Ontario and the public worldwide will see whether a Monte Carlo model can actually tackle the nuclear industry and control costs, whereas in the past we weren't able to control the costs in the industry, correct?  This is our first live look at how this will actually play out when it comes to a nuclear project.

DR. GALLOWAY:  Relative, if you want to take nuclear, correct, but there are other megaprograms with the same magnitude and complexity that are underway under this probabilistic model.

MR. YAUCH:  So you don't think the nuclear industry is a statistical outlier when it comes to infrastructure projects and it falls in the complexity of other groups.

DR. GALLOWAY:  I think the Crossrails project is even more complex than the Darlington refurbishment program.

MR. YAUCH:  Okay.  So I just have one last area.  If you can go to page 5 of your testimony, or page 10 of 122, depending on how you see it.  So at the top you talk about metrics, and from what I gather you looked at all the metrics that OPG had laid out in this application and you said, yes, these meet industry standard?

DR. GALLOWAY:  Yes.

MR. YAUCH:  And OPG didn't go above and beyond, or is it -- it just stayed within line of what you'd expect for the number of metrics on a project of this complexity?

DR. GALLOWAY:  I think that I've laid out how they will be addressing those metrics is certainly commendable and in some aspects was maybe more than you would expect to see.  I think given the complexity of the program that was appropriate.  But the metrics that they have in place do conform with what is identified in the industry best practices and they are following along the lines of industry best practices.

MR. YAUCH:  Okay.  So if you can go to Energy Probe compendium 1A and page 38.  This is again from the construction review board.  I'll wait for them to bring it up.

And right under recommendation number 3 they say:

"While the project ask have a large number of metrics, they do not consistently provide an accurate, integrated picture of project health."

So the review board seemed to find, yeah, the metrics were there, but OPG didn't actually -- the metrics weren't providing OPG or the public at this point an accurate picture of what was actually happening.  Did you find that as well?

DR. GALLOWAY:  Again, being a point in time that this was taken, I believe, for instance, when I talked about schedule, that the schedule, which is a metric, the schedule was underway, being completed, and the integrated schedule was not planned to be done until August or September, so relative to those scheduled metrics they would not be the integrated picture in July of 2016, which is something that they were working on.

So whether or not the construction review board saw that at the point in time and made a recommendation, I again don't know the underlying reason of this, but we did find that the schedule, by not being yet complete, but being completed, you wouldn't have the ability to do an integrated view of July of 2016 on those metrics because the integrated schedule had not yet fully been completed and was planned to be so in August and September.

MR. YAUCH:  Now, did your group take a metric -- a sample of metrics and then dive deep in them and see if the actual health or schedule or cost of the project actually aligned with the metric?  Did you take a deep look at each one and see if what they were telling the company was actually true?

DR. GALLOWAY:  Yes, as I had indicated, we did some sampling, and so relative to, for instance, you know, progress, we would ask to see how they were measuring that at the time that they were reporting in light of the schedules at the time.  The same for cost.  We wanted to see the process and the numbers and how they were producing those metrics to understand that that was not only following the processes in the procedures, but that actually it was reflecting a metric that was reflective of the information that it had at the time.

MR. YAUCH:  Did you find overall the metrics were correct, that what they were saying was actually happening, or unlike the review board, which found that wasn't actually happening?

DR. GALLOWAY:  Well, again, the review board is a point in time, and when it says "integrated", as I indicated, since the schedule was not yet complete, you wouldn't have an integrated picture of those metrics.

So without knowing what they were particularly talking about, I would not be able to comment whether our findings are different or they are of the same finding.

MR. YAUCH:  Those are my questions.  Thank you.  Thank you very much.

MS. LONG:  Thank you.  Mr. Tolmie.

# Cross-Examination by Mr. Tolmie:

MR. TOLMIE:  Thank you, Madam Chair.  My name is Ron Tolmie, Sustainability Journal.  And I have -- this is a very brief point that I would like to make.

MS. LONG:  Mr. Tolmie, just before you proceed, I have a compendium here, 1C.  Is this something that --

MR. TOLMIE:  That's correct.

MS. LONG:  -- are you planning to file that?

MR. TOLMIE:  Yes.

MS. LONG:  Yes?  Okay.  Can we mark that, please?

MR. RICHLER:  Madam Chair, that will be Exhibit K6.2.

EXHIBIT NO. K6.2:  Cross-Examination Compendium of Mr. Tolmie for OPG PANEL 1C.

MS. LONG:  And Dr. Galloway, do you have a copy of that?

DR. GALLOWAY:  You know, I thought I did, and for some reason it must be the only piece of paper I did not bring with me, and I do apologize.

MS. LONG:  All right.  Let's just make sure --

DR. GALLOWAY:  Thank you.

MS. LONG:  -- everyone has a copy.

MR. TOLMIE:  This morning in your testimony you made the comment that more planning can give rise to better outcomes in megaprojects.  Is that more or less what you said?

DR. GALLOWAY:  Well, more planning does give more reliable results, yes.

MR. TOLMIE:  Okay.  So do you think that adequate planning has been applied in this particular case to anticipate the results?

DR. GALLOWAY:  We have certainly opined that the approaches and the extensiveness of the pre-execution planning positions OPG favourable for a successful execution of the program.

MR. TOLMIE:  Okay.  I don't know if you noticed, but in Ontario the base load generation capacity actually exceeds the average consumption of electricity.  Are you aware of that, or can you provide any...

DR. GALLOWAY:  Not within my scope, sir, so I wouldn't know the answer to that.

MR. TOLMIE:  Okay.  The numbers are not hard to find.  You can look at the daily reports from IESO or many other reports and they will show you the base load generation capacity, which is the nuclear capacity plus hydro, basically, and they show that our demand is in fact quite stable year after year.  If you divide the total annual demand in terawatt-hours by the number of hours, you'll come up with an average value for the power demand, and the generation capacity actually exceeds the power demand.

Does that imply that we could relieve all or some of the problems by simply adding storage -- electricity storage to the system?

DR. GALLOWAY:  Since it wasn't in my scope of review I don't think that it would be appropriate for me to comment, because I haven't reviewed any of the facts surrounding that.

MR. TOLMIE:  Why was this an issue that wasn't covered in the application itself, do you think?

DR. GALLOWAY:  I don't know.  I wouldn't be able to comment on that.

MR. TOLMIE:  The -- if there's storage available in Canada if one intended to apply storage as a means of matching supply and demand.

DR. GALLOWAY:  Again, it wasn't in my scope, so I would be unable to comment.

MR. TOLMIE:  So it's a planning problem that wasn't included in OPG's application itself.  That is an issue that is potentially significant that was not mentioned in the application, is that correct?

MR. KEIZER:  Madam Chair, the witness is here to respond to her report, the Pegasus report which relates to the policies, procedures, and risk aspects and other things related to the Darlington refurbishment plan.

She has not been here to tender a report related to storage, or to what is or is not in the application that OPG has filed.

MS. LONG:  That's true, Mr. Tolmie.  Do you have any questions of Dr. Galloway with respect to the report that she filed?

MR. TOLMIE:  My question is about the report.  It should cover all the issues that are significant.  Her report should cover whatever OPG is doing, and OPG should report all the major --

MS. LONG:  If you have an issue with what OPG -- the scope that OPG gave to Dr. Galloway, that's an issue for OPG.  That's not an issue for Dr. Galloway.

She can only speak to the scope of work that she was asked to complete, and her report that she's filed in evidence.  So you need to ask her questions, if you choose to do so, about the report she filed.

I see some in your compendium that look like they're related to the report, and those questions you can ask Dr. Galloway.  But beyond that, she can't speak to things outside of what she was asked to opine on.

MR. TOLMIE:  She was asked, in my view, to provide comments on the plan.  And the plan should cover --

MS. LONG:  She was asked to give her opinion on the plan that was provided to her, not to coach OPG on what should be in the plan, or opine on what should be in the plan.  Her scope of work is clearly outlined in the beginning of her evidence.

So if you have an issue of OPG's scoping of her work, that's something you can deal with with OPG through argument, not through Dr. Galloway.

MR. TOLMIE:  We're dealing with a missing element, whether it's missing in the OPG plan or in Dr. Galloway's review of that plan, I guess, is something that can be debated.

But it's a major missing element.

MS. LONG:  What she's here to give expert evidence to this panel on is what she was asked to review.  That's what this panel can benefit from hearing from her on.  You need to rephrase your questions.

MR. TOLMIE:  The objective of the Board hearing is to determine if the rates are appropriate; is that correct?

MS. LONG:  I'm very clear on what our objective is, so you don't need to coach me on that, Mr. Tolmie.

MR. TOLMIE:  Is it in fact a Board concern that one should look at things that relate directly to rates?

MS. LONG:  Mr. Tolmie, I'm not going to engage in this argument.  We've talked about your views on storage, and there are panels you can ask these questions of.  But Dr. Galloway is here to strictly speak to her report.

So if you don't have questions about her report, we're going to move to another intervenor that does.

MR. TOLMIE:  I'll ask this one straightforward question then.  Do you know who wrote the report?

DR. GALLOWAY:  My report?

MR. TOLMIE:  No, the OPG report that you were considering.

DR. GALLOWAY:  I'm not for sure I understand the question of the report that you're referring to.

MR. TOLMIE:  The application.

DR. GALLOWAY:  Well --

MR. KEIZER:  The application is actually thousands of pages of documents, covering a wide variety of panels and issues.  So there would be any number -- it's an OPG application from any number of contributors from OPG, of which some of those and most of those are probably witnesses in this proceeding.

MR. TOLMIE:  Just to explain why I'm asking, there are several different agencies involved in Canada in making decisions and plans and acting those programs, and it's not clear to us as to who is pulling the strings.  You know, does the IESO, or OPG, or the Minister of Energy make these plans.

So it would be extremely useful to know how the plan itself is generated -- not in a negative sense.  I just so want to know, so that we can contribute appropriately.

MS. LONG:  Do you mean the application that OPG has filed?

MR. TOLMIE:  Yes.

MR. KEIZER:  The application extends beyond the Darlington refurbishment program, which is what the past few days have been about, and that Dr. Galloway is here to address.  So I think if you have questions about the application, it's probably better placed with panel 2, which deals with the regulatory constructs of the application, not Dr. Galloway.

MR. TOLMIE:  I'll go on to panel 2 then.  Thank you.

MS. LONG:  Thank you, Mr. Tolmie.

MR. KEIZER:  Sorry, Madam Chair.  Can I note something?  We marked as an exhibit Mr. Tolmie's compendium, Exhibit 6.2.  And on his exhibit, he has a series of questions and answers and also cites where -- and I want to be clear that although we've marked it as an exhibit, that those questions and those answers may or may not be, depending upon where he has taken the information from, that they are not OPG's questions and answers.

MS. LONG:  That is well understood.  Thank you.  Thank you for clarifying that.  Mr. Richler?

# Cross-Examination by Mr. Richler:

MR. RICHLER:  Thank you, Madam Chair.

Good afternoon, Dr. Galloway.  My name is Ian Richler and I'm with OEB Staff.  Some of the questions I had have already been asked and answered, so I will be brief.

Yesterday, you provided a helpful summary of the similarities and differences between your report and the report prepared by Staff's expert, Ken Roberts of Schiff Hardin.

Just to clarify, would you agree with Schiff Hardin's central thesis that good planning does not ensure similar execution?

DR. GALLOWAY:  You certainly have to implement and execute according to the plans, so it may or may not, depending on how that is executed.

MR. RICHLER:  Have you seen megaprojects that were exemplary in the project definition phase, but faltered in the execution phase?

DR. GALLOWAY:  I think generally, again in the reviews that we have done, we may have found elements within the execution plan that were not executed.  These would be the areas, for instance, that I was talking about on Duke of areas of disallowance.

But I think as a general statement, it would be unfair to make that general statement.  I think that there potentially may be areas that would have to be looked at under the circumstances and at the time.

MR. RICHLER:  How about the Kemper and Vogtle projects you discussed this morning?  Did they have world class planning?

DR. GALLOWAY:  The Vogtle project, yes, the same types of findings for their CPCN filing was very similar to the findings here.  And the program, as I also indicated, as of just a few months ago the commission's order found the program is continuing to execute reasonably and prudently according to those plans.  And so, that one is following along based on those exemplary pre-execution planning and policies and procedures.

The Kemper, up until the period March 31st, 2013, yes, based on the conditions and the extent of the knowledge at the time of the CPCN, which was much less than even that of Vogtle, significantly less.  Those, in the preliminary findings, are deemed reasonable and prudent.  But as I think I testified earlier, that prudence review is still ongoing and the testimony will be filed later this year, and the hearing will be later this year.

MR. RICHLER:  I understood you to say yesterday that sometimes you are engaged to assist with project audits.  When you were assessing a project that has experienced problems -- in other words, when you are doing what Mr. Buonaguro characterized this morning as an ex post facto prudence review -- what role if any does the risk register play in your assessment?

DR. GALLOWAY:  So if you are looking at the project after it has been completed, then you would be looking at how management reviewed the risks and how they dealt with risks.  For instance, you would look at, similarly here, you would look at the risk register, how the risks were identified, how they were put on the risk register, and how they were modelled from cost and time, and you would look at that process and determine whether it was reasonable.

As the project moved forward, as it is often common, there will be risks that were not identified originally that may arise, and now you're looking at, you know, when they get on to the risk register, because that's the way risks happen, and that's why you have risk register.  Sometimes risks go off when they retire and you have new risks that come on that weren't identified in the beginning, and so you then look at how long the process of looking at management at the time, how they dealt with the new risks that came on, how did it model out, as far as cost and time impact, was it a risk -- I think I gave them those green, yellow, and red indicators of the type of impact that's done on a probabilistic basis based on consequence and probability of happening.  The ones that turn red are the ones that you would then develop a mitigation plan for, and then you would determine whether or not if that risk then occurred on the project then whether they executed according to that mitigation plan.

So that is the way the risk management process works, and that's what, if you looked at the end of the project, you would take every point in time where the risks were reviewed and how they were retired or how new risks when they came on came on, and then how they were modelled, reviewed, and whether plans were necessary to be prepared, and whether or not if the risk manifested itself whether they executed according to those mitigation plans.

MR. RICHLER:  Thank you, that's helpful.

Could you perhaps give us one example of a review where -- a risk -- looking backwards that a risk register helped you in your assessment of a project that had experienced difficulties?

DR. GALLOWAY:  Yes, I think Duke is a good example, because Duke had some first-of-a-kind risks relative to its technology.  And obviously, since the technology that was in place for that particular IGCC plant, while it had been on a pilot basis, they knew some of the risks, but of course when you scale it up to a larger scale you may not know all of the risks.

And so in our review we found a technology risk that had not been identified earlier that arose during the detailed design that was underway at the project.  We looked at how it was then added to the risk register when it was identified, because that was important for us to determine when a risk arises how does it quickly get looked at as far as its potential consequence.

So in the design the risk was identified.  Then the risk during the process actually did not manifest to the extent they thought it would, but because there was a high consequence a mitigation plan was written for that particular technical risk.

So during the beginning of startup -- and remember that I think I mentioned the prudence review was happening during the startup and testing phase -- the risk was not as consequential as it had been modelled for, but because they did have the mitigation plan, startup was able to look at that technical risk and execute according to the mitigation plan so outlined and mitigated the impact that it was deemed to potentially have.  The mitigation allowed that impact to be less than it was modelled out to be.

MR. RICHLER:  Could you turn to page 76 of 122 of your report, please.  Again, for the record, this is Exhibit D2-2-11, attachment 3.  At the top of page 76 you address the question:

"In your opinion, does the fact that the facilities and infrastructure projects and safety improvement opportunities were not executed per the cost and schedule plan foreshadow similar issues in the execution of the DRP?"

And your answer is no.

Following up on the discussion you had with Mr. Yauch just before lunch, I'm wondering, when you were conducting your review and interviewing OPG folks, did you look into what went wrong with those pre-execution projects?

DR. GALLOWAY:  We explored the reasons why schedule and/or costs were over on the projects, and that is what I believe I was explaining earlier relative to some of the contractual issues at the time, that maybe the risk allocation was not as robust as it could have been, and the strategies, and they took those lessons learned to apply them to the contracts in the DRP project.

Relative to schedule I think I had mentioned that the policies and procedures and processes and project control tools that were in place in the projects and modifications group from which these projects were executed may not have allowed earlier detection of some of the issues that arose, and so corrections and revisions were made in the policies and procedures and processes for the Darlington refurbishment program that would allow earlier detection of issues and more intense monitoring from the OPG staff to minimize and/or eliminate some of those issues that happened in the pre-execution projects.

So those are the types of reviews that we did on those overruns on cost and schedule.

MR. RICHLER:  So I just want to make sure I understand.  What in your view was the root cause of the problems that materialized on those pre-execution projects?

DR. GALLOWAY:  I think it's what I've just indicated, is that the policies, procedures, and project control tools may not have been as robust as they are now to have early detection to be able to mitigate and/or recover the schedule delays and/or to mitigate issues with cost to allow the correction to minimize those costs or find opportunities for those risks on cost to be shared differently than they were on these early projects.

MR. RICHLER:  Was it a problem of planning or execution or both?

DR. GALLOWAY:  Well, if your policies and procedures and processes are not robust enough to pick up some things, if you execute according to those, you may not pick up on the early detection.  I think that was the lessons learned, is to ensure that the policies and procedures and processes and project controls would be robust enough for early detection and allowing for mitigation and correction.  I mean, that was the lesson learned.

MR. RICHLER:  And I think you just mentioned that you considered OPG's contracting approach in respect of these pre-execution projects.  Did you have any concerns specifically with OPG's decision to undertake those pre-execution projects under its existing extended services master service agreements, as opposed to developing a tailor-made contract for those projects?  In other words, in your view, was it reasonable to rely on those standard pre-existing contracts or, in light of the magnitude of some of those projects, would it have made more sense to develop tailor-made contracts?

DR. GALLOWAY:  Well, our scope did not cover the contracts that were developed for those early execution projects.  Rather, our scope was, what lessons were learned from the issues that occurred relative to cost and schedule, and how those were mitigated with the processes, the policies, procedures, and the contracting methodology for DRP.

MR. RICHLER:  So just to be clear, you have no opinion on the way the contracts for those pre-execution projects were structured?

DR. GALLOWAY:  That was not within our scope.

MR. RICHLER:  All right.  Thank you.  Those are all my questions.

MS. LONG:  Thank you, Mr. Richler.  The Panel has some questions for you.

# Questions by the Board:

MS. FRY:  I have just a couple of questions to follow-up on your earlier testimony.

So at one point you were discussing the Darlington project metrics, and you said in that some aspects, the metrics were more than you would expect to see.

Can you explain which metrics you were talking about that exceeded expectations?

DR. GALLOWAY:  I think in, for instance, the way that they're looking at earned value, they're more granular than I have seen other utilities look at relative to the detail of the level of progress, the level of the actual budgets and costs that they are looking at in capturing.

Some utilities roll those numbers up and do it at a more macro level.  Darlington seems to be doing it at a much more lower level within the system and the program of those metrics which, in our view allows for earlier detection of issues that go to cost and schedule.

MS. FRY:  Was that the main example, or were there other metrics that exceeded expectations?

DR. GALLOWAY:  That was one example I remember.  The others pretty much follow the industry best practices in standards.  Without going back to my specific review, I can't tell you if some of the others were exemplary above what I would expect.  But the earned value clearly, I think, is much more granular and robust here than I have seen on other programs.

MS. FRY:  Okay.  You've said a few types that you've noted that lessons learned were incorporated into the Darlington planning, and one example you just gave was early detection.  Are there other specific examples of what the lesson learned was, and how it was incorporated into the Darlington planning?

DR. GALLOWAY:  I think the entire depth of, for instance, design completion.  I think that was a big lessons learned from megaprograms in general that you typically, whether it's the ability of having the luxury or just the decision not to go that far, that you seldom see completion of design to what we have at Darlington, what we saw.  So that was a huge lessons learned.

I think there were some lessons learned from some of the refurbishment projects.  I don't have the detail off of my head, but we went through the various tables of lessons learned that they captured from the prior refurbishment projects and went through them specifically with them at the time to see how they incorporated those specifics, whether they were technical lessons learned, or whether they were contractual, or later we looked through that to see how they then incorporated that either into their probabilistic modelling, their risk reviews to give it a higher or lower list -- I mean a higher or lower probability of that risk manifesting and its calculation.

I think we, also in those lessons learned, did look at what they were learning on the other nuclear projects, for instance Vogtle, SCANA, Bellafonte; Watts Bar is also mentioned relative to lessons learned on both allocation of risk -- I think I mentioned before the contract and how much risk you actually turn over to your EPC contractor versus the decision to take some of those risks and manage them yourself because you think you're in a better position to do that.

I think again the pre-execution planning for the other nuclear plants was much less than here, and I think that was a lessons learned that they took.

So there was, I think, numerous examples of those risks, and what we did is we wanted to go through each of those lessons learn and see how they applied it.  And it went into various categories; it wasn't just a cost.  Those lessons learned went into how they looked at those risks, how they might change the project control tools to have earlier detections, as I just indicated, relative to the earned value system.

They may have looked at how they want to handle some of those technical issues so they wouldn't have the same problem in Darlington they may have had in other refurbishment projects.

So that's the level we went through on those lessons learned.

MS. FRY:  Thank you.

MS. LONG:  Dr. Galloway, I just have two questions for you.  If you can turn to page 52 of your report, around line 16, your answer here:

"Based on my review and the interviews conducted, it is my understanding that OPG benchmarked against the available cost data from other refurbishment projects at Point Lepreau, Pickering, and Bruce units 1 and 2, incorporating lessons learned from these projects into the DRP estimate."

And then you go on to say because it was the first of a kind nature of the program that you understand that much of the benchmarking was based on their own operating experience.

And I guess I wasn't clear on the first part of your answer where you say "based on my review".  What is it exactly that you reviewed with respect to benchmarking?

DR. GALLOWAY:  Again, how it's mostly in the lessons learned that I just discussed.

MS. LONG:  So you didn't actually look at any benchmarking cost data from any of these other projects?

DR. GALLOWAY:  No.

MS. LONG:  Thank you.  My final question: you spoke a bit this morning -- I was very interested when you spoke about the energy strong program, and how your role is basically as an independent monitor.

DR. GALLOWAY:  Yes.

MS. LONG:  I wonder if you can expand upon how it is you came to be in that role.  Was that something that the commission asked you to take on, or was that something that the utility proposed, that you become involved?  How was it that you became involved in that mandate?

DR. GALLOWAY:  So the original energy strong program that was proposed by the utility was probably 2 to 3 types the size that it is now.  The commission expressed concern at the time of trying to do too much at once, and so the commission, through a settlement of what actually the scope of work that would be for the energy strong program, the commission determined that it wanted an independent monitor that the utility would pay for, of course, hopefully potentially recovering that through its rates at some point in the future.

But the commission is the one that determined that they wanted the independent monitor, and that independent monitor would report to both the commission rate counsel and also to the utility.

MS. LONG:  Okay.  And then as I understand it, you do quarterly reports and an annual report.  And I guess to the extent that you've noticed anything in those reports that needs improvement, how is it that -- well, I guess those reports are made public.  And is it up to the utility then to make the corrections based on what your recommendations are, and has that been the common practice that those things have been undertaken?

DR. GALLOWAY:  Yes.  The procedure that was established, the protocol that was established is that we will -- it's continuous monitoring.  So for instance, we're attending the weekly meetings, we are reviewing all reports.

Any decision that is going to be made by the utility is discussed with the monitor before the decision is finally implemented.  This is something that -- a request of the commission in order to allow the utility to look at its options and potentially make different tweaks of that method at the decision, you might say, or the outcome.

We have found that the utility has been very cooperative.  The utility has not taken all of the Recommendations, but where the recommendations have not been taken, the utility provides its response to the commission on why it has not taken that recommendation.  The utility, on the other hand, has taken a lot of the recommendations.

And as I believe I stated either today or yesterday -- I can't remember now which one -- I think that all the parties believe that the process has been beneficial in that the program, which is probably about 80 percent done at this time, is tracking below budget and under schedule.  So everyone seems to be very pleased with the process.

MS. LONG:  Thank you.  Mr. Keizer, any redirect?

MR. KEIZER:  If I can just have one moment?

MS. LONG:  Sure.

# Re-Examination by Mr. Keizer:

MR. KEIZER:  I have a couple questions in redirect and one relates to, I believe, your discussion this morning with Mr. Poch where there were some discussions about unanticipated risk, and I guess it's a clarification with respect to it, is that if a risk occurs that -- on a project that's not anticipated, does that necessarily equate to imprudence?

DR. GALLOWAY:  No, that's exactly what I was referring to, I believe, under the other question, that all projects will have risks that get retired and will have risks that arise during a project, and that is just the way projects happen, so, no, there would be no indication of imprudence just because a risk arose.

MR. KEIZER:  The other question, actually, follow on from Madam Chair's questions, and that is, on the Energy Strong work that you do, the report that you prepare -- and I just wanted to clarify -- is that a public report or a private report?  Is it private as between the utility and the Board or is it something that's published and put on the website?

DR. GALLOWAY:  My understanding is that it is between the commission and the utility and rate council.  I do not believe that it is a document that is made public on the website of either of those -- any of those parties.

MR. KEIZER:  And would it eventually be used in a public endeavour, or not at all?

DR. GALLOWAY:  I believe the understanding is that if a prudence hearing is held at the end of the project that potentially the reports may be made available.  I don't think the commission and the rate council and the utility have come to an agreement on that yet.  And I don't mean there is a disagreement.  I just don't -- the three haven't decided as to -- yet as to how those reports potentially might be used at some point in the future.

MR. KEIZER:  If I can just have one moment.

Those are my questions, Madam Chair.

MS. LONG:  Thank you, Mr. Keizer.

Thank you very much for your testimony, Dr. Galloway.  You are excused.

DR. GALLOWAY:  Thank you.

MS. LONG:  Mr. Keizer, I understand your next panel is ready to go?

MR. KEIZER:  Yes, and I -- Mr. Smith, Crawford Smith, is going to take that panel through its paces.

MS. LONG:  Okay.  You'll be back on Thursday then?

MR. KEIZER:  I'll be back on Thursday.

MS. LONG:  I think we'll take five minutes here just to change the deck chairs and get the next panel up.

MR. KEIZER:  Thank you.

### --- Recess taken at 1:54 p.m.

### --- On resuming at 2:00 p.m.

MS. LONG:  Mr. Smith?

MR. SMITH:  Madam Chair, good afternoon.  We have OPG's panel 2A(i), which is the application overview, nuclear rate setting framework, and business planning panel.  I'll introduce them briefly.

We have Mr. John Mauti furthest from me, Mr. Chris Fralick, and Randy Pugh, and I'd ask they be affirmed.

# ONTARIO POWER GENERATION - PANEL 2A(I)

John Mauti,

Chris Fralick,

Randy Pugh, Affirmed

# Examination-In-Chief by Mr. Smith:

MR. SMITH:  Very briefly, members of the Board, let me start with you, Mr. Fralick.  I understand you are the vice-president of regulatory affairs of OPG.

MR. FRALICK:  I am.

MR. SMITH:  And that is a position you assumed early last year?

MR. FRALICK:  I did.

MR. SMITH:  And you have been with OPG in positions of increasing responsibility since approximately 2000?

MR. FRALICK:  That's correct.

MR. SMITH:  Including responsibility as regional plant manager for northwest operations?

MR. FRALICK:  Yes.

MR. SMITH:  I understand that you have an MBA in business from Wilfred Laurier University, and an engineering degree from the University of Waterloo.

MR. FRALICK:  Yes.

MR. SMITH:  Mr. Mauti, I understand you are the vice-president, chief controller, and accounting officer of OPG.

MR. MAUTI:  I am.

MR. SMITH:  In that position, you provide overall corporate controllership services.

MR. MAUTI:  Yes, I do.

MR. SMITH:  You have been with OPG or its predecessor since approximately 1991?

MR. MAUTI:  That's true.

MR. SMITH:  And you have had business planning or controllership responsibilities since roughly 2012?

MR. MAUTI:  That's true, yes.

MR. SMITH:  And you have a business degree from Wilfred Laurier university?

MR. MAUTI:  Yes.

MR. SMITH:  And you are a CPA?

MR. MAUTI:  Yes.

MR. SMITH:  Finally, Mr. Pugh.  I understand you're the Director of regulatory affairs, regulatory accounting and finance?

MR. PUGH:  I am.

MR. SMITH:  You have been with OPG since 2004?

MR. PUGH:  Correct.

MR. SMITH:  Prior to that, you were employed by this Board and before that, by Union Gas Limited?

MR. PUGH:  I was.

MR. SMITH:  I understand, sir, you are also a CPA.

MR. PUGH:  I am.

MR. SMITH:  Mr. Fralick, maybe I can turn to you.  On behalf of the panel, do you adopt the evidence assigned to panel 2A(i) as detailed in Exhibit A1, tab 9, schedule 1?

MR. FRALICK:  I do.

MR. SMITH:  Thank you.  I have no further examination-in-chief, and tender them for cross-examination.

MS. LONG:  Mr. Stephenson, are you ready to commence your cross-examination?

# Cross-Examination by Mr. Stephenson:

MR. STEPHENSON:  I am.  Good afternoon, panel, and good afternoon, witnesses.   I think I've met all of you in the past.  My name is Richard Stephenson, and I am counsel for the Power Workers' Union.  Good afternoon.

I want to talk about the nuclear stretch factor.  As I understand it, the purpose of this mechanism is to attempt to improve OPG's performance relative to one of its key performance metrics, which is the total cost per megawatt-hour metric.  Am I right about that?

MR. FRALICK:  Yes.

MR. STEPHENSON:  And OPG is increasingly looking for that metric as being an important performance indicator, I gather, and it's embedded in fact in your business plan, correct?

MR. FRALICK:  It is, yes.

MR. STEPHENSON:  I think this is self-evident, but you'll agree with me that obviously that metric turns on two numbers.  On the one hand, it's your costs, and on the other hand, it is your actual output, your production, correct?

MR. FRALICK:  It is, yes.

MR. STEPHENSON:  Can I just ask you if the object of the exercise is to improve your performance relative to that metric, why do you have a proposal that deals with only one of the two elements of that metric?

Your proposal deals entirely with costs, correct, and not about production?

MR. FRALICK:  The stretch factor is applied to 75 percent of the total OM&A cost in our proposal.  The production is based on our forecast, the way we've done it as per our historical methodology.

As you're aware our rate, is 100 percent variable so we are incented to increase our output as much as possible.

MR. STEPHENSON:  Sure.  But this is a cost-cutting metric, correct?  Sorry, your stretch factor is all about cost-cutting; that is you've got to find savings on your costs, correct?  That's the way it works?

MR. FRALICK:  It's an efficiency measure as we understand it, so it is applied to the cost.  However, one way in which to make up for that stretch factor would be to increase our production relative to plan.

MR. STEPHENSON:  That would be true, but it's certainly not going to be measured by your stretch factor, it's not going to be captured in that mechanism, correct?

MR. FRALICK:  Correct.

MR. STEPHENSON:  I mean, aren't I right that one of the ways that you can improve your performance against the total cost per megawatt hour metric is by increasing your costs by increasing your costs in a cost effective manner such that you're increasing your production that such an revenue -- the incremental revenues exceed the incremental costs?

MR. FRALICK:  Yes, we do have a category of projects in fact that we would pursue on the basis of value enhancing, and we do those types of analyses and pursue projects that fall into that category.

MR. STEPHENSON:  That's true not only in terms of capital projects, but also -- I mean, outage management has been an ongoing priority for the company, correct?

MR. FRALICK:  Yes.

MR. STEPHENSON:  And the simple reality is the best way for the company to increase production is to manage your outages efficiently, make them as short as possible, correct?

MR. FRALICK:  Well, that would certainly be one predominant way, but also managing our reliability so we minimize forced loss rate would also achieve the same.

MR. STEPHENSON:  Sure, I got it.  But just in terms of minimizing your outage length, one of the ways of doing that is by deploying more resources during the outage. You're actually putting incremental costs in, correct?

MR. FRALICK:  Yes.  In terms of making decisions about the length of an outage or how to manage and resource an outage, the duration and the impact on our revenues associated with the cost and what we expect to be able to get as a result of that investment, is always part of the decision-making.

So on a real-time basis, if we think that we can return a unit quicker and the incremental revenue that would result is more than the cost that we would incur to achieve, then we would pursue that.

MR. STEPHENSON:  And that would be a means whereby you are in fact increasing your costs, but doing better on the metric, right?

MR. FRALICK:  That's right.

MR. STEPHENSON:  But your stretch factor just doesn't deal with that the all, right?

MR. FRALICK:  That's right.

MR. STEPHENSON:  Let me just talk now about your challenge in in fact taking costs out of the company during the rate period.

Your evidence indicates that you are constrained in a variety of ways, in terms of your ability to take costs out and that's in part why you're only applying it to a portion of your costs, correct?

MR. FRALICK:  Yes.

MR. STEPHENSON:  And you've excluded certain areas that have to do with safety, as I understand it, so that you've got -- it's 75 percent of your OM&A is the basket that you're capturing in this for the stretch factor purposes, correct?

MR. FRALICK:  Yeah, our stretch factor in our proposal applies to our base OM&A plus the corporate allocations.  Now, within base OM&A there are certain cost drivers where we do not expect to be able to achieve efficiencies, so as you alluded to, safety, regulatory requirements, things that are very prescriptive in nature that you won't be able to improve from an efficiency perspective.  So that necessarily drives us to look at our total cost bucket in order to come up with the cost savings that we will need to identify in order to offset that stretch factor.

MR. STEPHENSON:  So you've got a savings number for your stretch factor, but as I understand it, I mean, have you got a calculation anywhere in your evidence where you can have attempted to isolate as a practical matter the amount of cost from which you are able to make some savings, you know, you say even within this there's, you know, safety issues that we can't meaningfully extract any costs anyway.

So once you extract the things that you don't have a meaningful ability to extract costs, what's left?  What is the -- what's the bucket from which you're taking costs out of?

MR. FRALICK:  I don't have that number off the top of my head.  It would be something less than the 75 percent of our OM&A that we have applied it to.  We treat that as a bit of a proxy for where we think we can obtain efficiencies, but we know that it's not -- I do not have that figure directly.

MR. STEPHENSON:  So if we think about it, that it's not 75 percent, it's a number lower than 75 percent, then the actual amount in practical terms of your stretch factor is a number higher than the notional stretch factor that you've got -- or, sorry, the nominal stretch factor that you have got in your application, correct?

MR. FRALICK:  Yes, if I'm following you, then the -- if the 75 percent includes things that we will not be able to achieve efficiencies upon, then the degree to which that amount decreases, then what's left of a fixed amount of stretch factor that we have calculated now divided by a smaller number becomes a bigger percentage, yes.

MR. STEPHENSON:  We just don't know exactly what that number is?

MR. FRALICK:  No.

MR. STEPHENSON:  Okay.  Another way of thinking about constraints on your ability to take costs out is -- are the legal and committed limitations that you've got on at least certain buckets of your costs, and one of those limitations is with respect to your compensation envelope, correct?  There are some constraints on your ability to extract costs out of that envelope, correct?

MR. FRALICK:  Yes, the compensation costs are -- they're the outcome of collective agreement negotiating process, to a large extent.  We do have some control of measures by way of overtime and things like that, but as I'm sure panel 4 will go into much greater detail, once that collective agreement is negotiated and set, then the rates for that term of the collective agreement are indeed set, and therefore our ability to extract labour costs from -- certainly on a rate basis are -- we don't have that as a lever.

MR. STEPHENSON:  Okay.  Can I just get you to turn up -- it's Exhibit A1, tab 3, schedule 2.  It's the evidence for this part.  And in particular page 38.  I just want to correct one thing.

In the middle of the page there is a reference to the PWU collective agreement.  Line 17:

"These agreements run from April 1, 2015 to March 31, 2017."

Do you see that?

MR. FRALICK:  On line 17?

MR. STEPHENSON:  Yes.

MR. FRALICK:  Yes.

MR. STEPHENSON:  That's wrong, right?  It's actually 2018?  That's just a typo?

MR. FRALICK:  That's correct.

MR. STEPHENSON:  Okay.  And I think this is true for both of your labour agreements, at least the two big ones with the Society and the PWU, and I may have to deal with this with another panel, but let's see how far I can get with you.

Both of those agreements prohibit the company from doing any involuntary layoffs or terminations during their period, correct?

MR. FRALICK:  As I understand it, yes.

MR. STEPHENSON:  So as I understand it, in terms of the company's ability to decrease the costs associated with those collective agreements, it's really limited to three things.  Item number 1 is attrition, correct?

MR. FRALICK:  That would be a means.

MR. STEPHENSON:  People leave the company, you have some ability to not replace them, correct?

MR. FRALICK:  Yes.

MR. STEPHENSON:  But however, if we look in your material -- and I can check this with somebody else if you don't know it -- you're not actually forecasting decrease in complement until after 2020.  Not in any material way.

MR. FRALICK:  I have to turn up the evidence, but I believe it's relatively flat through most of the five-year term, yes.

MR. STEPHENSON:  The second way that you can take costs out is by controlling the amount of overtime, and you've indicated that, correct?

MR. FRALICK:  Yes.

MR. STEPHENSON:  But this dovetails back to the issue of outage management to a large degree, doesn't it?  That's where the lion's share of your overtime in fact is dedicated, correct?

MR. FRALICK:  We incur a lot of overtime, particularly in the maintenance ranks, during outages, yes.

MR. STEPHENSON:  And from the company's perspective, you actually in a -- colloquially, you make money on that overtime.  If you can deploy those additional resources even at higher rates, if you can shorten that outage duration, you're back online and making revenue?

MR. FRALICK:  Yeah, I guess if you're saying that it would be a myopic view to look strictly at overtime, say, and minimize that at all costs, to use the phrase, would be a narrow way to look at how to run the business.  You would not do that.

MR. STEPHENSON:  Right.  I mean, you may save a dollar, but it may cost you a dollar and a half, right?

MR. FRALICK:  Yes.

MR. STEPHENSON:  Okay.  And the third way you can take some costs out of these collective agreements is that you have got some temporary employees governed by these collective agreements and you can, you know, increase or decrease the number of those, correct?

MR. FRALICK:  Well, linked to your first metric, being attrition, as people leave, particularly in light of what we were looking at at Pickering and end of commercial operations in the next decade, we have got the term employee provision now, so we would look to shift more employees to that from a full regular FTE, yes.

MR. STEPHENSON:  Right.  But that's more of a theoretical than a real issue in terms of your ability to say, because you're not actually forecasting any material change in complement, right?

MR. FRALICK:  Correct.

MR. STEPHENSON:  And that's governed by your perceived need, right, that you would take -- you would be -- if you could get more complement down you would, but you perceive you need these bodies to do your operations, right?

MR. FRALICK:  We have a challenging mandate to meet at our stations over the next decade, and we have a work program that has to be executed to ensure that we maintain the reliability and execute the tough mandate that we have, and that's the complement that -- and the full plan that we require in order to be successful in that endeavour, yes.

MR. STEPHENSON:  So -- and obviously on management comp you have less legal constraints around your ability to reduce that, but again, as I understand your staffing plan from elsewhere in your materials, you're more or less looking at a fairly flat complement in that area as well, at least until 2020, again because you perceive that that's what you need to run the operation.

MR. FRALICK:  That's right.

MR. STEPHENSON:  So if you -- if you're -- and the compensation bucket is a very substantial proportion of your OM&A spend, correct?

MR. FRALICK:  Yes, it's -- I'd be guessing, but somewhere two-thirds or more.

MR. STEPHENSON:  And if that bucket is -- you'd agree with me it's pretty highly constrained in terms of your ability to extract dollars, fair?

MR. FRALICK:  Yes.

MR. STEPHENSON:  And bearing in mind those constraints, if we're looking only at the remaining aspect of your OM&A budget, again if you're going to extract all the vast majority of the savings for your stretch factor out of that remaining portion, again the actual amount of the stretch is that much bigger, correct?

MR. FRALICK:  To achieve the stretch factor that we've proposed will be a challenge.  It totals, on the nuclear side some $50 million cumulative over the full five years, and that's not going to be easy for us to find.

MR. STEPHENSON:  I didn't see in the evidence actually any plan, proposal, any identification actually where the money is coming from.  Is there something I missed?

MR. FRALICK:  No, you didn't miss it.  The stretch factor by design is an up-front give that is incremental to our challenging business plans.  Our business plan includes a number of initiatives that we will need to execute in order to achieve, and the stretch factor is above and beyond that, and we have not identified what those initiatives will be in detail at this point in time.  We need to do that.

MR. STEPHENSON:  The number that you've indicated is this .3 percent, which is essentially compounded, as I understand it, over the term.

MR. FRALICK:  Yes.

MR. STEPHENSON:  But just as we've gone through and talked about the constraints on areas where you can't meaningfully get money out -- I mean, if we talked about the stretch factor as a practical matter in terms of controllable costs being at, say, one percent or higher, does that sound like a reasonable number?

MR. FRALICK:  I'd be guessing, but certainly it's greater than .3.

MR. STEPHENSON:  Those are my questions.  Thank you very much.

MS. LONG:  Thank you, Mr. Stephenson.  Mr. Millar?

MR. MILLAR:  Good afternoon, Panel.  When would you be looking at taking an afternoon break?

MS. LONG:  Around 3 o'clock.

MR. MILLAR:  Thank you.

# Cross-Examination by Mr. Millar:

Good afternoon, panel.  My name is Michael Millar; I am counsel for Board Staff.  I believe we've all had the pleasure of meeting before.

First, I have some questions about your custom incentive regulation proposal for your nuclear operations, and -–

MR. SMITH:  Sorry, Mr. Millar.  You provided a compendium; was it your intention to mark that?

MR. MILLAR:  Yes, why don't we do that?  That will be K6.3, Staff compendium.  Panel, you have copies of this?

MR. FRALICK:  Yes.

EXHIBIT NO. K6.3:  Board Staff Cross-examination compendium for OPG Panel 2A(i)

MR. MILLAR:  You proposed a five-year custom incentive for your nuclear facilities?

MR. FRALICK:  Yes, we have.

MR. MILLAR:  And one of the features is the stretch factor which you were just discussing with Mr. Stephenson, and I'm going to start with a few questions about that.

Maybe we could begin by turning to page 2 of the compendium.  And this gets a little bit to with a Mr. Stephenson as talking about, but I thought I would take you to the Board's words on this.  It sort of describes what a stretch factor is.

If you look at the third full paragraph about the middle the page, it states:

"The stretch factor component of the X factor is intended to reflect the incremental productivity gains that firms are expected to achieve under incentive regulation, and is a common feature of IR plans.  These expected productivity gains can vary by company, and depend on the efficiency of a given company at the outset of the IR plan.  Stretch factors are generally lower for firms that are relatively more efficient."

Now first of all, it's talking about an X factor there.  So obviously, this is discussing IRM as opposed to custom IR.

But for our purposes here today, is that an accurate description of a stretch factor, from your perspective?  Is that what you were thinking when you proposed a stretch factor, that that's the purpose of a stretch factor?

MR. FRALICK:  Yes.  We essentially took the definition of the stretch factor to be akin to the one that we applied to our hydroelectric assets, which is more of a pure fourth generation IRM, and we treated it the exact same.  From a  construct perspective, a stretch factor is the same, yes.

MR. MILLAR:  This is not unique to OPG; it's a standard tool the Board has been using under incentive regulation for many years?

MR. FRALICK:  As I understand it, yes.

MR. MILLAR:  The document I took you to is for distributors, for example, and I know you modeled your plan on that.  But this is not new to OPG, is my point.

MR. FRALICK:  The use of a stretch factor is absolutely new for OPG.  We have not applied that in any previous proceeding.  This is the first time we have applied a stretch factor.

MR. MILLAR:  Certainly it's new to OPG, but the concept of a stretch factor has been around at the Board for a while under incentive regulation plans for distributors?

MR. FRALICK:  Understood, yes.

MR. MILLAR:  Just to take you to a couple things Mr. Stephenson mentioned, it's been used by distributors for many years.  LDCs have employees and they have collective agreements with those employees; is that fair?

MR. FRALICK:  I would assume so, yes.

MR. MILLAR:  You can take that subject to check, that Hydro One has collective agreements.

MR. FRALICK:  I know Hydro One does, yes.

MR. MILLAR:  And many, at least of the larger ones, would have collective agreements with their employees?

MR. FRALICK:  Yes.

MR. MILLAR:  And there are probably doubtless other areas.  They wouldn't be regulated by CNSC, but there would be areas where a distributor simply can't find efficiencies; is that probably true?

MR. FRALICK:  Probably true.  However, OPG is unique in the fact that we have a 100 percent variable rate design and no part of our costs are fixed, and that is a significant difference to other regulated entities.

MR. MILLAR:  But a stretch factor applies against the entire -- okay, I take your point.  Let's move on to savings that you might be able to find from your compensation costs.

There was a suggestion that you have very little wiggle room when it comes to making savings on compensation costs, although you did concede there are some things like over time, and I'd also suggest the number of FTEs that are outside the collective agreement that you do have some control over?

MR. FRALICK:  Yes, we have control over the numbers and overtime to a certain extent.  However, when you're running the operation, you're not strictly looking at how many people you have or how much your overtime is.  You're looking at are you able to get the work done within the overall envelope.

So you're switching in between your resource types and resource work execution methods, as appropriate in the given circumstance.

MR. MILLAR:  Mr. Fralick, you'd be familiar with OPG's business transformation initiative from several years ago.

MR. FRALICK:  I am, yes.

MR. MILLAR:  I am doing this from memory, but it ran something like from 2011 to 2015?  Does that sound right, in that range?   Mr. Mauti, you may know better?

MR. MAUTI:  Yes, it did.  That was the approximate range, yes.

MR. MILLAR:  And through that initiative, you were able to shed over 2000 positions, 2000 FTEs.  Is that correct?

MR. MAUTI:  I believe the number we quoted was 2700.

MR. MILLAR:  Okay, so closer to 3000.  And by doing that, you were able to realize significant OM&A savings?

MR. FRALICK:  Yes.

MR. MILLAR:  And you also realized significant efficiency through business transformation, is that fair?

MR. MAUTI:  Part of the approach for coming up with the centre led sort of structure was to try to gain those efficiencies, and operate the business as effectively as possible, yes.

MR. MILLAR:  And your collective agreements did not prevent you from realizing those savings, or realizing those efficiencies?

MR. MAUTI:  Not directly.  We were able to leverage the demographics of the company that would allow for those departures to happen, without there being a formal process to downsize in the company.

MR. MILLAR:  Can I ask you to turn to page 3 of the compendium, please?  As you discussed with Mr. Stephenson, you proposed a stretch factor of 0.3 percent, and this would apply to a portion of your OM&A expenses as we've already discussed.

You also mentioned that's approximately 75 percent of your total OM&A?

MR. FRALICK:  That's correct.

MR. MILLAR:  The savings that would result from your proposal over the five years of the custom IR term is $50 million; is that correct?

MR. FRALICK:  The cumulative total over the five years is 50 million, yes.

MR. MILLAR:  Let's start with the derivation of how you came up with the 0.3 percent.  Under the current framework for electricity distributors, there's five different buckets you can fall in, is that right?

MR. FRALICK:  Yes.

MR. MILLAR:  And you can see that in the footnote at the bottom of page 3 of the compendium.  There's zero percent, .15, .3, .45 and .6.  So those are the five buckets?

MR. FRALICK:  Yes.

MR. MILLAR:  And maybe we can turn to page 7 of the compendium.  Electricity distributors are slotted into one of these groups based on the relative efficiency of their operations, is that correct?

MR. FRALICK:  As we understand it, yes.

MR. MILLAR:  Okay.  And I guess the way they do that is a report is prepared, and this -- the most recent one is by Pacific Economics Group, and they do some research on their relative efficiency, and then all of the LDCs are slotted in one of those five buckets; is that right?  As you understand it?

MR. FRALICK:  As we understand it, yes.

MR. MILLAR:  Okay.  In fact, if you turn to page 7 of the compendium you can see the most recent stretch factor assignments for the LDCs.

MR. PUGH:  That's correct.

MR. MILLAR:  Now, OPG, of course, is not part of this, because you're not an LDC, and you weren't part of this study, but your proposal is to place yourself in the middle group, the 0.3 percent?

MR. FRALICK:  Yes, OPG utilized the existing ScottMadden methodology for benchmarking that's been in place for many years, and we assessed where we ranked on our TGC basis relative to, you know, the benchmark, and through our calculation determined that we would be at .3, yes.

MR. MILLAR:  Yes, in fact you'll see that if you turn to page 8 of the compendium.  I've taken an excerpt from your application.  And first, just to backtrack a little, the measure you used for efficiency was TGC, and I think Staff tends to agree with that measure, but maybe you could let us know why that is the measure you selected.

MR. FRALICK:  I think ultimately it is a fair reflection of OPG's cost performance.  It's one that's readily benchmarkable, and its denominator is megawatt hours, which is our product, and so we feel that that is appropriate for use in the determination of a stretch factor.

MR. MILLAR:  Okay.  And then if we look at chart 9, we see what you did.  You split Darlington and Pickering, and you assigned each of them their own value based on their relative efficiency, and for Darlington the TGC was top quartile, so you gave that a zero.  For Pickering it was bottom quartile.  You gave that .6.  You sort of ran that through the production forecast, weighed it, and you ended up at more or less 0.3.  That's how you arrived at 0.3?

MR. FRALICK:  Correct.  We production-weighted the individual stations' stretch factor determination based on their TGC performance.

MR. MILLAR:  And what you did was you chose to consider Pickering TGC and Darlington TGC separately, as opposed to considering an overall number for OPG.  If I can ask you to turn to page 9 of the compendium.  This is your business plan.  We can see here near the -- this is not the approach you take in the business plan.  If you look -- I think it's the second sentence overall:

"In 2016 OPG adopted TGC as an enterprise-wide measure of operational cost-effectiveness in addition to TGC metrics for each of the nuclear and hydro operations."

So why is it appropriate to use an all-in number for your business planning purposes but for setting a stretch factor you wanted to divide it between Pickering and Darlington?

MR. MAUTI:  In the business plan that you referenced on page 9 we summarized an enterprise and by technology level the two total generating cost measures.  They are further in the back of the business plan, and A221, attachment 1, page 30, provides the operational targets, including TGC at a Pickering and Darlington individual level.

So the way we described it in the front part of the business plan was just to get an overall flavour from a technology point of view.  So the front of the business plan package tends to have a consolidated kind of use of things.  We have a lot more detail in the back as well.

So they are calculated -- they're benchmarked at a station level.  We just reported them at the front part of this on the technology basis.

MR. MILLAR:  Okay.  The numbers that you used to set the 0.3 that we just looked at on page 8, I guess it was, those were based on the 2015 nuclear benchmarking report; is that correct?

MR. FRALICK:  That's correct.

MR. MILLAR:  And although it's called the 2015 benchmarking report it's actually for 2014 numbers; is that right?

MR. FRALICK:  That's correct.

MR. MILLAR:  And at the time you prepared the application that was the most recent data that you had?

MR. FRALICK:  That's correct.

MR. MILLAR:  And just to take a step back, this nuclear benchmarking report, I do have some benchmarking questions here.  Obviously it's panel 3 with which we'll be getting into more detail on benchmarking, but I think since it relates to stretch factor we will have to go over this just a little bit here.

What this benchmarking report does is it compares your performance against other North American nuclear operators?

MR. FRALICK:  It does.

MR. MILLAR:  And the comparators in this report and the entire methodology was established with the assistance of the consulting firm ScottMadden?

MR. FRALICK:  It was, yes.

MR. MILLAR:  And you've been reporting on this basis for quite a number of years now.

MR. FRALICK:  Yes, that's right.

MR. MILLAR:  Okay.  And back with the 2015 benchmarking report, as we've discussed, Darlington was top quartile and Pickering was bottom quartile.  However, since then we have the 2016 benchmarking report, and if I could ask you to flip all the way ahead to page 29 of the compendium.  We see the results of that here.

If you look under the "value for money" metric just over halfway down the page, you'll see the three-year total generating cost, and it's colour-coded, so if you loacross to Pickering we see red, which means fourth-quartile, which is where it was in the previous report, but Darlington now is second quartile; is that right?

MR. FRALICK:  That's right.  So this, as you'll see, is a rolling three-year average for the Darlington metrics.  So 2015 would have come in and 2012 would have dropped off.  And 2015 was a very unique year for Darlington, in that it executed a one-in-ten-year vacuum building outage, so you've taken the entire plant down, so the corresponding production is down considerably, the costs are up.  So that was a significant driver for the cost performance coming in for Darlington in 2015.

In addition to that you'll see further on down in this report on page 80 the capital performance and -- while still well within the first quartile, the capital program for Darlington has increased in recent time as it's gearing up for the Darlington refurbishment.

And the third contributing factor which again reinforced the need for refurbishment is, the FLR rate at Darlington has exceeded our target, and that has also contributed to the variance.

MR. MILLAR:  And those may all be the reasons for that, but you've dropped to second quartile under TCG.

MR. FRALICK:  Yes, the point being that the 2015 is not a representative year for those matters.

MR. MILLAR:  Okay.  But we don't -- when we look at these figures it's based against your comparators.  In any given year one of your comparators may have higher FLR than they anticipated or there may be a major project coming.

When we look at TGC the result is what the result is; is that fair?

MR. FRALICK:  Yes, but the entire benchmark doesn't take a VBO at the same time in the same year.

MR. MILLAR:  It doesn't, but other years you might have benefited when somebody else had an outage like that.  Is that possible?

MR. FRALICK:  Marginally.

MR. MILLAR:  Let's flip back to page 10 of the compendium.  This shows your most current results for OPG as a whole.  And am I right that of the 13 nuclear operators that are measured you are 12th out of 13th when it comes to TGC?  You're the second-worst?

MR. FRALICK:  That appears to be what this table says, yes.

MR. MILLAR:  And that's a drop-off of what you had when you originally filed.  You can see that -- if you flip ahead to page 12, this was the original pre-filed material.  You were a bit better than -- you were 10th out of 13th overall, but as I say, you're now 12th out of 13th.

MR. FRALICK:  Right.  And the reasons for that I outlined.

MR. MILLAR:  Okay.  And then indeed if we look at your business plan that's back on page 9, I note first on page 10 that your TGC for 2015 was $54.58.  For 2016, a year after, you'll see on page 9 of the compendium right at the top $63.20, so you're predicting a very significant increase from 2015 to 2016 as well; is that fair?

MR. FRALICK:  Yes, and while panel 3 can go into this in greater detail, certainly a significant driver would be the commencement of the Darlington refurbishment program, as well as other outage activities.

MR. MILLAR:  So is that a normal -- we'll get into normalized with panel 3, I think, but is that a normalized number, is that a non-normalized number?

MR. MAUTI:  As you see it on page 9, this would be a non-normalized number.  This is the raw number itself.

MR. MILLAR:  Okay.  That's the raw number.  Thank you.

For 2016, Darlington shut-off -- Unit 2 went out at the end of November?

MR. FRALICK:  No, it went out in the middle of October.

MR. MILLAR:  Middle of October, okay.  You'll see that over the test period, the costs are up in the 75 to -- 74 to 77 range.  Again, those are the raw numbers not normalized, so I take it the DRP is one causes of the high costs at that time.

MR. MAUTI:  Correct.  That's probably the most predominant by far.

MR. MILLAR:  Given the numbers up to 2015, if you wish to exclude 2016, is it still your view that this is mid range performance on TGC?

MR. FRALICK:  Well, we would look at the period before 2015, given the unique outage in 2015.  If you want to look at a period that's reflective of what OPG's underlying performance is, and in that period OPG was indeed top quartile for Darlington.  And Pickering has, as you've noted, has been unchanged.

MR. MILLAR:  But most recent actual data we have from 2015, at least on a company-wide basis, shows you as 12th out of 13th in TGC performance.  To some, that would suggest a stretch factor of 0.6.

Do you have anything to add to what you just said?

MR. FRALICK:  I wouldn't say that that is a direct conclusion.  I think if you run through the calculation methodology that we have utilized, that would not come out at 0.6.

MR. MILLAR:  You didn't rerun on the numbers, though, did you based on the most updated results -- or did you?

MR. PUGH:  We did do is we ran the results using these 2015 benchmark numbers that appear on page 29 of your compendium.  So it shows that Darlington is in fact right at the median at .3, and it shows Pickering is in the fourth quartile at .6.

And when we ran the numbers for those, we came up with .43.

MR. MILLAR:  Okay.  So that would be closer to .45 than .3, obviously.  And is OPG actually amending its application to reflect that, or are you still seeking 0.3?

MR. FRALICK:  We're seeking 0.3.

MR. MILLAR:  Let me move to my next area.

I have some questions about the memorandum of agreement, and I actually thought these would be questions for panel 3 because they're really about benchmarking.  But I saw on your consolidation sheet that they're questions for you.

So I'll try them with you.  But if there posed to panel 3, by all means punt me to them.   I don't want to lose my chance.  Are these questions for you, Mr. Fralick?

MR. FRALICK:  Likely John, Mr. Mauti.

MR. MILLAR:  Mr. Mauti, you're familiar with the memorandum of agreement that OPG has with its shareholder?

MR. MAUTI:  Yes, I am.

MR. MILLAR:  And there have been changes to that memorandum of agreement since last we enjoyed a discussion here in this room, since the last case?

MR. MAUTI:  Sorry, the memorandum of agreement changed in August 2015.

MR. MILLAR:  So after the last main OPG proceeding.   I'm sorry, I did see you at the technical conference, so I apologize for that.

One of the changes relates to benchmarking, and if you look at page 16 of the compendium, we have the old memorandum of agreement.  You'll see that in paragraph 3,  it discusses continuous improvements, and that you're to benchmark and target the top quartile against other North American operated utilities.

And if we look at the revised version of the memorandum of understanding, you'll see that on page 15 of the compendium -- I didn't reproduce the whole thing, but I think I have the replacements here -- that language no longer appears, is that fair?

MR. MAUTI:  The language on benchmarking has changed and it is now in a subsection 6.1.3.

MR. MILLAR:  That's right.  Should questions I have about this, are they for you now or should these be for panel 3, questions about your approach to benchmarking?

MR. MAUTI:  You can try the questions for me, depending on the technical --

MR. MILLAR:  I'll try them, and you can tell me if we've gone too far.

The MOA no longer specifies you should target top quartile in your benchmarking efforts.  First, do you know why that change was enacted?

MR. MAUTI:  I guess as part of updating the memorandum of agreement that had, I believe, been in existence in since 2005.

There were several changes and Board Staff IR number 1 described what those main changes were.  When it came to benchmarking, I believe it was a recognition it was a recognition to do appropriate benchmarking, as it should always be, you should try to find an appropriateness of how you're doing the benchmarking and what you were comparing to.

So I think in our case, recognizing that in 2015 our nuclear fleet was getting to a point where the plants were going through very different changes, whether that's refurbishment for a second life for Darlington or approaching commercial end of commercial operations or potential extension for Pickering, it was more appropriate to have a memorandum of agreement that required benchmarking that was appropriate for the operations as we have them at the time.

They have changed substantially since 2005, and I would assume that's what led to the change in the wording to make it an appropriate benchmark as opposed to something more specific.

MR. MILLAR:  And the new language, which we see at page 15, it doesn't say anything about targets at all; is that right?

MR. MAUTI:  No, it just says you should benchmark to what's appropriate.  And again, understanding the life cycle of that plant and how you're comparing what some of those factors would be, that you do benchmarking to be able to come up with actionable things you can take from that, not just necessarily to compare to what's at the top or the bottom of that comparator group.

MR. MILLAR:  It doesn't mention continuous improvement Either, at least not specifically; is that fair?

MR. MAUTI:  Perhaps not specifically within that, but in the expectations for operations in terms of improvement, I believe that language is in the MOA, just not specific to the benchmarking.

MR. MILLAR:  OPG still proposes to set targets for TGC and in fact, we see that in the application, right?

MR. MAUTI:  That is correct, yes.

MR. MILLAR:  And you are targeting -- it's not just an absolute number.  You have targets with respect to quartiles as well?

MR. MAUTI:  We try to understand obviously where we believe the industry is going from a quartile basis and set our targets, again in taking into account the evolution of the plant, and specifically with Darlington as it's going through refurbishment for the next decade, where you'll have one and sometimes two units out for refurbishment, that has a dramatic impact on the TGC value.  So we need to take that into account.

It would be inappropriate to suggest we are targeting top quartile to Darlington while it's going through that phase of refurbishment.

MR. MILLAR:  With respect to continuous improvement, I assume you'd agree with me that despite the fact that those words don't appear in the MOA anymore, OPG still does strive for continuous improvement?

MR. MAUTI:  Yes.  I believe you had a compendium excerpt from the previous hearing as well, and Ms. Swami also did reference the fact that we're always trying to improve and make changes to our operations targeting, whether it's a how we do our outages or the reliability of our plants, safety and what-not.

Those are things we continuously look at and continue to compare ourselves.

MR. MILLAR:  Let's turn to that.  That's page 20 of the compendium, I believe.  At the bottom of the page, this is a response from Ms. Swami to a question I asked.  She states:

"And would I like to see us move up the relative ranking?  Of course.  OPG is always interested in trying to make our performance better, and that's why we targeted improvement programs," et cetera.

I assume that still holds true today?

MR. MAUTI:  Yes, it does.

MR. MILLAR:  Thank you.  I have a couple of more questions about the stretch factor, but not about the number, the 0.3 or what have you, but the portions of your spend you propose to apply it to.

Could we turn to page 22 of the compendium?  We went over this a little bit already, but to refresh everybody's memory, you don't propose to apply the stretch factor to your entire O&M budget.  It will be applied to nuclear base O&M and allocated service O&M, is that right?

MR. FRALICK:  And allocated corporate support costs.

MR. MILLAR:  Sorry, yes, I misstated that yes.  When we turn to page 23, we see those numbers and without straining anyone's vision too much, you can see that project OM&A is line 2 and allocation of corporate cost is line 7, is that right?

MR. FRALICK:  Yes.

MR. MAUTI:  That's correct.

MR. MILLAR:  And 11 is the total OM&A.  So I just want to make sure I understand how you did the calculation.  You added lines 2 and -- I'm sorry, it's base OM&A.  I misspoke.

MR. FRALICK:  Yes.  It's base OM&A.

MR. MILLAR:  My mistake.  So line 1 and line 7, you added those together, and then you took that as a proportion of the total OM&A, which is line 11.  That's how you came up with the 75 percent?

MR. FRALICK:  Yes.

MR. MILLAR:  Okay.  When we did the calculations it actually -- it varied between 70 and 75 percent depending on the year.  Would you take that subject to check?

MR. FRALICK:  Subject to check.

MR. MILLAR:  Okay.  All right.  And you propose to exclude all other O&M from the application of the stretch factor because in -- I'm reading from page 24 here.  I don't know that you need to pull it up, but you state:

"OPG does not expect to find material efficiencies in the remaining 25 percent."

MR. FRALICK:  Yes, so the projects, for example, and outages, they are discrete activities, so they're not activities that we do on a repetitive basis.  Each one is a unique endeavour, and we develop a scope, and that is tailored to that specific need at that time.

So from the perspective of efficiency of getting better at doing the same thing, these cost categories do not lend themselves to that type of gains.

MR. MILLAR:  Well, let's look at that a little bit more carefully.  If we go back to page 23, which is up on the screen, first, the two largest things you look to exclude -- or two of the larger things that are excluded are project OM&A and outage OM&A, which you were just discussing?  That's lines 2 and 3?

MR. FRALICK:  Yes.

MR. MILLAR:  And together those are about 500 million dollars a year?  It varies a little bit?

MR. FRALICK:  Sure, yes.

MR. MILLAR:  Give or take?  In fact, the bulk of that is outage OM&A.  In 2017, for example, it's 394, and it's mostly around that range until you get to 2021, give or take 400 million?

MR. FRALICK:  Yes, between 394 and 415, yes.

MR. MILLAR:  That's right.  And the Darlington units are on a -- on outage cycle that's every three years?

MR. FRALICK:  That's right, yes.

MR. MILLAR:  And Pickering is faster than that.  It's two years.

MR. FRALICK:  Correct.

MR. MILLAR:  So these are -- the work may vary, but outages are not unique, are they?  They're things you do on a set schedule?

MR. FRALICK:  To a certain extent they are, but they're also -- the scope of any given outage is defined by the corrective backlog that you want to undertake at that point in time, so if something is broken, you need an outage to fix it.  That would inform the scope of your outage to a large extent, so while there would be some component inspection type work that would be common, there would certainly be a large portion that would be unique to a given outage.

The extent to which that breakdown is detailed, that would be a question best asked to panel 3, though.

MR. MILLAR:  Okay.  Understood.  And -- but it's your view no lessons learned on outage OM&A?  You don't get more efficient over time?

MR. FRALICK:  No, that's not my point at all.  My point is that each of these outages is unique endeavour, and we set a budget that is challenging to execute the scope of work that we need to for a given outage.  We would execute lessons learned on outages like we do on projects, and we continue -- we seek to improve our performance.  Indeed, outage performance is one of the initiatives listed in our business plan.

MR. MILLAR:  So I guess I'm not quite following why you don't think there are significant efficiencies to be found there when there could be under base OM&A.  But I assume you have an aggressive forecast for base OM&A as well, but you think a stretch factor is reasonable to apply there.  I guess I'm not quite seeing what the difference is.

MR. FRALICK:  Yeah, it's the repetition of the work.  It's the likeness of the work.  Within base OM&A there is much more work that is like for like, where you're repeating a similar task over and over again, where it would be more reasonable to seek efficiency gains.

In an outage it's not like that.  Each outage is constructed uniquely, given the circumstances and scope at that time.

MR. MILLAR:  In your review of the Board's -- the renewed regulatory framework and all its related documents, did you find any references there that suggested that a stretch factor would only apply to a portion of O&M?

MR. FRALICK:  No, we did not find a reference to that extent.  We did note that the note of steady state is something that is referenced in the RRFE, so when we looked at our cost categories we looked for costs that we would feel would be -- well, that are more objectively in a steady state, and that is base OM&A and the corporate support costs.

MR. MILLAR:  Your stretch factor also excludes your capital spend; is that right?

MR. FRALICK:  It does.

MR. MILLAR:  And the same question I just asked with respect to the RRFE or its related documents, did you find a source there that suggested that capital should be excluded from productivity measures such as a stretch factor?

MR. FRALICK:  We did not find such a reference.  However, similar to the project OM&A bucket the capital project bucket is similarly constructed of very discrete projects, so unlike distributors, where you would see a lot more repetition, each of this -- each project is unique, by and large.

OPG employs what we call a project portfolio -- portfolio management approach, sorry.  So we determine an annual budget for our capital program that is informed by benchmarks.  However, we are incented to execute our capital program as efficiently as possible in order to enable us to execute additional projects.

We always have more projects than we have budget.  So we are inherently incented to become as efficient as possible on capital in order to make more investment in the station which will improve reliability and performance, and given the fact that our rate design is 100 percent variable, we are always incented to try to maximize production.  So our incentive within the capital portfolio is that.

MR. MILLAR:  Now, you -- I know this isn't the hydro panel, but under hydroelectric you're doing IRM, which also has a stretch factor; is that right?

MR. FRALICK:  Yes, it does.

MR. MILLAR:  And that applies to everything.  Am I correct?  It applies to O&M and capital?

MR. FRALICK:  Yes, we -- as we'll talk to in panel 2A(i), we have endeavoured to mirror the hydro IRM structure as closely to the fourth-generation IRM construct as possible.

MR. MILLAR:  So why should the stretch factor apply to capital under IRM but not under custom IR?

MR. FRALICK:  Well, under IRM we understand it's an all-in.  And while everything I said about the capital program is also appropriate for hydroelectric, when it comes to custom incentive regulation, we looked at that from the perspective of, you know, what was in a steady state on the nuclear side of the house, and the capital program, as I said, is much more discrete, and we feel that it is -- an incentive on the capital program would not -- an efficiency -- stretch factor on the capital program would not result materially in a change in our behaviour towards how we executed that capital program.

MR. MILLAR:  Do I take that to mean that -- well, you're -- I think you're proposing there be less incentives for productivity under custom IR than under IRM, in that you're not applying the stretch factor to everything?  Would that be a fair way to characterize it?  And I have taken your answer as to why you think that's appropriate, but that's the ultimate outcome of your proposal; is that fair?

MR. FRALICK:  No, I think there are unique risk challenges on the nuclear side that are also relevant here compared to hydroelectric, so for example, where hydroelectric has variance accounts to address certain unknown risks, and rightfully so, nuclear, on the other hand, is strictly 100 percent variable.

So it's risk exposure, risk profile, is materially different than what it is on the hydroelectric side, notwithstanding the technology differences and the risk associated with nuclear risks as opposed to hydroelectric, and that's gone into in great detail in our Concentric cost-of-capital report, attachment 12C2  C1-1-1.

MR. MILLAR:  Okay.  But you're not without protection on the nuclear side.  You have many deferral accounts on the nuclear side.

MR. FRALICK:  We do, but none with regards to production.

MR. MILLAR:  Well, there is the midterm review, which we will discuss.  Your proposal --

MR. FRALICK:  There's none currently in effect.

MR. MILLAR:  Okay.

MR. FRALICK:  We are seeking that the midterm review, yes.

MR. MILLAR:  Madam Chair, I just have one or two quick more questions on this area and then it would be appropriate for a break if that's --

MS. LONG:  Yes.

MR. MILLAR:  Okay.  Are you familiar with the Toronto Hydro custom incentive regulation decision?

MR. FRALICK:  At a high level.

MR. MILLAR:  Okay.  I reproduced a page of it from -- page 25 of the compendium, and I don't have much of a question here other than to point out at least in that case the Board was resistant to the idea of excluding capital from the stretch factor in a custom IR.

You've already given many reasons why you think OPG shouldn't have a stretch factor applied to capital.  Is there anything you want add in light of the Toronto Hydro decision?  I just thought I'd put it to you, in fairness.

MR. FRALICK:  I think exploring the portfolio management approach, as I discussed with panel 3, would be helpful to further understand how that portfolio is managed to the view of stretch factor not being meaningful incentive, if it were to be applied on that.  I reiterate the point that distributors, their capital program is discretely different from nuclear.  The nuclear industry faces very significant safety and regulatory requirements,  training requirements that is are indeed incremental to what the distributors would face.

And thirdly, our rate design, again going back to the fact that it's a 100 percent variable rate design.  That is a distinct difference for OPG relative to the distributors.

MR. MILLAR:  Finally on this point, let's imagine the Board was inclined to consider a stretch factor on capital. Its a not always obvious how that would work.  I guess there's two ways that leap to mind for me.

One would be you could use the stretch as an offset to the revenue requirement impact of new capital spend over the test period.  Or alternatively, you could use it as a straight offset to the capex number itself.

Do you have any thought -- I know this isn't in your proposal, but if the Board wanted to go that way, do you have any thoughts on what the best way to implement that would be?

MR. FRALICK:  We have not turned our mind to that.

MR. MILLAR:  Madam Chair, would this be an appropriate time for a break?

MS. LONG:  It would be, yes.  We'll break for 15 minutes.

### --- Recess taken at 3:02 p.m.

### --- On resuming at 3:20 p.m.

MS. LONG:  Mr. Millar, are you ready to continue?

MR. MILLAR:  Yes, I am.  Thank you, Madam Chair.

I have some questions now about your proposed nuclear annual reporting.  And you will recall that the Board established a number of reports and measures that OPG would be required to file on an annual basis in the 2010-0008 proceeding?

MR. PUGH:  That's correct.

MR. MILLAR:  And essentially you propose to continue filing this material throughout the test period.

MR. FRALICK:  Yes.

MR. MILLAR:  Can I ask you to turn to page 27 of the compendium.  And I think you've listed here the things you propose to report on?

MR. FRALICK:  That's correct, yes.  That's out of A132, yes.

MR. MILLAR:  Yes, that's right.

Could I ask you to flip the page to page 28.  Is this the format you would be filing in, in other words, showing quartiles, or would it just be the raw numbers?

MR. FRALICK:  I'm not sure.

MR. MILLAR:  If I told you Staff's preference would be for quartiles would you have an opinion on that?

[Laughter]

MR. PUGH:  We would be happy to help.

MR. MILLAR:  Okay.  Thank you.  And in terms of -- we see here things are broken out by Pickering and Darlington.  Is it your proposal to continue reporting on that basis?

MR. FRALICK:  Yes.

MR. MILLAR:  Would you be willing to file -- we'll get into this in benchmarking, but the three key metrics are generally thought to be total generating cost, the WANO nuclear performance index, and the UCF, the unit capability factor.

Would you be willing to report those on a company-wide basis, an OPG-wide basis?

MR. FRALICK:  Well, on a company-wide basis -- you mean you're referring to nuclear only --

MR. MILLAR:  Yes --

MR. FRALICK:  -- I'm assuming.

MR. MILLAR:  That's right, nuclear.

MR. FRALICK:  I'm not sure how we break that down.  We would have to talk to panel 3 about the specifics of how they calculate their metrics.

MR. MILLAR:  Okay.  If that's practical is there an objection to filing that?

MR. FRALICK:  We don't -- if it's practical we don't have an objection.

MR. MILLAR:  Okay.  Thank you.  If we can turn to pages -- or page 31 of the compendium.  You'll see at the top of the page you propose to file what are called normalized numbers.  You calculate normalized and non-normalized, but I think for reporting purposes you propose to file normalized numbers, or do I have that right?  Maybe you haven't said how you plan to report?  I guess my question is, are you filing normalized or non-normalized for Darlington?

MR. FRALICK:  Yeah, just looking down at line 8 there.  We are proposing to compare Darlington's TGC on a normalized basis.

MR. MILLAR:  Okay.  And I apologize to the Board Panel.  We haven't gotten into exactly what normalized means, but just for the purposes of our discussion here today it's a mechanism you've developed to sort of correct for the fact that Darlington will be under refurbishment for essentially the entire test period, and you've adjusted the denominator to reflect that.

MR. FRALICK:  Yeah, that's right.  So the extent to which Unit 2 is out of service now, it would be contributing -- expected to contribute a certain amount of megawatt hours in a given year.  It's on refurbishment.  It's not, so we would add that back into the denominator.

Now, it's not a perfect correction to adjust on a benchmarking basis, but it's something that we're proposing that's easy to do.

MR. MILLAR:  Understood.  And we'll get into the details of that more with panel 3, I believe, but for reporting you propose to file normalized numbers?

MR. FRALICK:  Yes.

MR. MILLAR:  Do you have an objection to filing normalized and non-normalized?

MR. FRALICK:  No.

MR. MILLAR:  Okay.  Thank you.  If we look at page 33 of the compendium, you propose to file your targets for the coming year?  Do you see that at the very top?

MR. FRALICK:  Yes.

MR. MILLAR:  Is there any opposition to providing as well the variance between your last target and actuals?  In other words, in 2018 -- when 2019 comes you'll have actual figures for 2018, but you'll also have what your target had been for 2018.  I'm wondering if there is any opposition to filing the delta between what you predicted and what your actuals were?

MR. FRALICK:  I don't believe so.  Subject to any issues that panel 3 would have.  They have got the numbers.  But again, without any principal reason to object we wouldn't have one.

MR. MILLAR:  And is the reporting going to be done on a year-by-year or an annual basis or on a rolling average basis?

MR. FRALICK:  The reporting would be done on an annual basis.  However, the metrics, where indicated, would be based on rolling average data.  And that's how the benchmark works within the ScottMadden methodology.

MR. MILLAR:  With respect to the timing of this, maybe you can help me with this.  Let's look at the first year of the test period.  For 2017, when would you expect to file your 2017 numbers?  Your annual report for 2017?

MR. PUGH:  If the purpose is going to be to include benchmark quartile data, that may take some time.  We'll probably have the actuals early in the year.  But depending on the benchmark that's coming from ECG or from WANO, that might take several months into the next year to have that comparator.

MR. MILLAR:  Yeah, that's what I understood.  We get the raw data earlier than the quartile data?

MR. MAUTI:  That's definitely true.  And I'm not exactly sure when the WANO data for some of your operational measures would be available.

MR. MILLAR:  And I guess we'll see how this shakes out, but assuming that there is a significant delay between those two numbers being available, is there any opposition to filing the raw data first and then updating it with the quartiles when that comes in?

MR. MAUTI:  Again, principally, no, it's just, it's a matter of when those data points are available.

MR. FRALICK:  For example, we filed the 2016 ScottMadden benchmarking report as an attachment to an IR, so that was in the October time frame, so it's quite some time through the year before that ScottMadden methodology would be complete.

MR. MILLAR:  Yeah, that's why I was asking, because I understand the raw data is available much earlier than that, and I think Staff wants the quartiles, but we don't necessarily want to wait eight months or whatever the time period may be.  But I think we understand each other.  Thank you.

So I'll move on to my next area, which is the midterm review.  And in that light perhaps we could turn to page 36 of the compendium.  Yes, thank you.

And just to frame this issue to remind us what we're talking about, your proposal is that a review be conducted at the midterm of your test period, and the purpose of that review will be limited to updating your nuclear production forecast plus the clearance of your year-end 2018 balances for certain DVAs; is that right?

MR. FRALICK:  Yes, just to be clear, the midterm review in terms of updating the production forecast is separate and distinct from the clearance of the deferral and variance accounts.

MR. MILLAR:  Okay.

MR. FRALICK:  So in other words, if the midterm review is not ultimately accepted, we would still intend to file, to clear our deferral and variance accounts --

MR. MILLAR:  That's helpful.

MR. FRALICK:  -- at this time.

MR. MILLAR:  But if your proposal is accepted as filed, this would all be one proceeding?

MR. FRALICK:  Yes.

MR. MILLAR:  And the review would take place sometime in the first half of 2019?

MR. FRALICK:  That's what we're proposing, yes.

MR. MILLAR:  So it would apply to the first two-and-a-half years of the test period.

MR. FRALICK:  That's right, yes.

MR. MILLAR:  Okay.  So it's DVAs in the production forecast.  If we turn to page 40, it's fair to say that historically you've had some difficulty in meeting your production forecast?

MR. FRALICK:  As outlined in chart 2 and further explained below, yes, we have had challenges meeting our production targets.

MR. MILLAR:  And in fact since -- from 2008, 2015, I don't think you ever hit your -- first of all, neither the Board-approved production forecast or indeed your own applied-for production forecast, although it's been pretty close in some years.

MR. FRALICK:  That is correct.

MR. MILLAR:  And if we flip back to page 37 of the compendium, you list a number of factors here starting at the bottom of page 37, that make forecasting your production over a five-year term difficult; you present some challenges.

So I would like to go through those with you.  The first is the risk of public policy changes; do you see that?

MR. FRALICK:  I see that.

MR. MILLAR:  Is there anything new there?  I read through it.

MR. FRALICK:  No.  It's just inherent risk something in the realm of public policy could occur that we have not currently anticipated, and that would have an impact on production.

MR. MILLAR:  The reason you're seeking an ability to update the production forecast in this case -- not to put words in your mouth, but I assume the five years is the problem here.  If this was one or two year test period, that would be less of a risk?

MR. FRALICK:  Yes, thanks for that.  We have historically set our nuclear production forecast in rates on, at most, two-year basis and this would see us setting rates on 30 months at the outset, and then re-setting that again for the second 30 months.

So it would still be an extension of what we have historically set our production forecast on, but yes.

MR. MILLAR:  Okay.  Similarly, if we flip to page 38, items IV and V, regulatory requirements and approvals and ageing facilities, this is all steady state, right?  There is nothing particularly new in this application that we wouldn't have seen in previous applications.  Those risks have always been around?

MR. FRALICK:  We have faced regulatory uncertainty.  Given the state of Pickering's endeavours and Pickering standard operations, and then leading into Pickering end of commercial operations, we know there is a particular regulatory requirement that we're going to have to meet, so there could be some risks associated with that that we today don't foresee.

MR. MILLAR:  Sure.  But that would have been true of your last application as well.  I guess the chief difference here is the length of the forecast.

MR. FRALICK:  The length of the forecast, yes.

MR. PUGH:  And I think for the ageing facilities as you get closer to the end of your life.  When we had a consultation here with respect to incentive regulation, they talked about the ageing curve being an S-curve, and as you get towards the end of your life, you have a lot more variability in your production.

MR. MILLAR:  Sure, but you've identified different risk categories for both Pickering and Darlington, so I assume those would be captured under those headings.

MR. PUGH:  Certainly the ageing facilities would be more particular to Pickering, as it nears the end of its life.

MR. MILLAR:  Let's talk about Pickering.  You see that at the bottom of page 37 and the top of page 38, one of the risks you highlight is Pickering extended operations and you state -- this is again at the very bottom of page 37:

"Canadian Nuclear Safety Commission approval is still required and as discussed elsewhere in the application, OPG has not yet completed work necessary to confirm that the Pickering units would be fit to operate beyond 2020."

So that's a risk you identify with your production forecast?

MR. FRALICK:  It is, yes.

MR. MILLAR:  Let's flip to page 41 of the compendium.  This is a press release issued by OPG on January 11th of 2016.  And if you look down to the second last paragraph, it states a quote from Mr. Lyash:

"Our technical work shows that Pickering can be safely operated to 2024, and that doing so would save Ontario electricity customers up to 600 million dollars, avoid 8 million tons of greenhouse gas emissions, and protect 4500 jobs across Durham Region."

Mr. Lyash appears to be fairly confident here that the plant will operate 2024.  I'm wondering if you can compare and/or contrast that with what I've just read you about Pickering.

MR. FRALICK:  If you read the very last sentence at the bottom:

"Any plan to extend Pickering's life would require approval of the CNSC."

So that's the only thing we are referring to.

MR. MILLAR:  It was caveated in that press release as well.  That's fair enough.

If we go back to your list of risk factors, this time page 38 of the compendium, the last one is the execution of the Darlington refurbishment program.  And again you've highlighted risks around whatever delays there may be would have a significant impact on your production forecast.  Is that fair?

MR. FRALICK:  It could, yes.  It could go either way.

MR. MILLAR:  Right.  If we go to page 42 of the compendium, I don't know if this is the same press release, but it was issued the same day.  It's a press release from OPG, and in the very first paragraph:

"OPG is well positioned to deliver the DRP on time and on budget.  Darlington is one of the world's top performing nuclear stations.  We've put in years of detailed planning,  built a state of the art training facility, assembled an excellent team and partnered with top companies from across Ontario."

This press release -- I know it's a not regulatory document, but it doesn't highlight any -- you seem fairly confident here that everything is going to go well with the DRP.

MR. FRALICK:  We've just heard five and a half days of testimony with regard to the Darlington refurbishment program and the complexities associated with that, the risks associated with it the P90 considerations.

I won't rehash all of that, but there is a significant amount of risk associated with the execution of this project.  And to portray that this is a done deal would be nothing short of misleading.

MR. MILLAR:  Okay.  I agree with you; we've heard plenty about the risks of Darlington over the past couple of days, so I won't ask any more on that.

However, if there is a delay in restarting Unit 2, this would have a very significant impact on your production forecast in 2020 and 2021?

MR. FRALICK:  Potentially.  You'd have to run different scenarios because as Unit 2 delays, then the Unit 3 start would delay, and Unit 1 at the back end may push off into the next term.  And there's these warranty outages on Unit 2 that play into the mix here.

So the actual production impact varies and is very dependent upon just how much and what direction the DRP changes by.

MR. MILLAR:  That's a fair comment.  Certainly there are scenarios where it could have a very significant on your production forecast?

MR. FRALICK:  In either direction.

MR. MILLAR:  How would it work in the other direction that would increase production forecast?

MR. FRALICK:  If it was done early.

MR. MILLAR:  Wouldn't you be shutting down Unit 3 early?

MR. FRALICK:   You would, but then you'd be -- there would other outages that play into the mix.  As I said, I don't want to get into the scenarios here in a hypothetical, but we could look at a given scenario, and have looked at some of these where if it's early by this much or late by that much.

There's many moving parts is the bottom line.

MR. MILLAR:  That's fair enough.  The midterm review; you are proposing to -- outside of a DVA analysis, you're proposing to adjust your production forecast only, and you are not proposing to have any look at revenue requirement; is that right?

MR. FRALICK:  That is correct.  Yes.

MR. MILLAR:  And if I look at page 38 of the compendium, the page we were already on, do I understand if you look starting around line 23, that its a your view that -- well, I'll just read it:

"Subject to the OEB concluding that rates are no longer just and reasonable pursuant to the Act, the regulation does not entitle the OEB to revisit those approved revenue requirement amounts during the five years."

And then you go on to say there is no such limitation for production.

So do I understand you to be suggesting that the regulation prevents the Board from reviewing the revenue requirement after it's been set in this proceeding?

MR. FRALICK:  Yes, that's our interpretation of the regulation.  It requires that the Board establish revenue requirements for five years.

MR. MILLAR:  Now, in your adjustment of the production forecast, imagine we do as you've proposed.  As a midterm review, you adjust the production forecast.  You're also proposing to make consequential adjustments to your fuel costs?

MR. FRALICK:  We are indeed, and we're doing that fundamentally because the fuel is an absolutely direct marginal cost, and any fluctuation in production forecast would have a direct impact on fuel cost and, quite frankly, it would be wrong for us to not update for fuel cost.

MR. MILLAR:  I understand the rationale behind it.  But is fuel cost an O&M expense?

MR. FRALICK:  I believe that's where it's captured, yes.

MR. MILLAR:  It's part of revenue requirement?

MR. FRALICK:  It is part of revenue requirement, yes.

MR. MILLAR:  In your view, is there a carve-out in the reg that allows for adjustments to revenue requirement if they're related to fuel costs?

MR. FRALICK:  It was a principal position we've taken with regards to the fact that fuel is a direct marginal cost, and we felt it would be wrong for us to exclude that from an update on production.  It would be disingenuous.

MR. MILLAR:  Okay.  Let's imagine that there is some type of problem with Unit 2, it's delayed for some reason

-- and I take your point that that doesn't necessarily result in a lower production forecast.  But let's imagine a scenario where that does happen.

So you find two years in that your production forecast is too high.  So you come to the Board and you apply to have the production forecast lowered.  If that happened, obviously the ultimate impact of that would be to raise payment amounts, is that fair?

MR. PUGH:  The actual impact of that would be recorded in a variance account that we proposed -- I think you have it in the compendium.  But it would be recorded in the midterm review variance account.

MR. MILLAR:  That's right.  So it goes into a variance account, but ultimately that would serve to increase payment amounts.

MR. PUGH:  Once it's cleared.

MR. MILLAR:  Yeah.  You're right that it wouldn't happen at the review, but at some point that -- those monies would be recovered from ratepayers.

MR. PUGH:  If the Board approved a lower forecast to reflect that, then that would be the implication of it, yes.

MR. MILLAR:  Okay.  But in your view the Board is not able at the same time to update the revenue requirement to reflect the fact that Unit 2 is not in rate base, that there may be different O&M costs associated with that.  That would be outside of the scope of the review in OPG's proposal.

MR. PUGH:  That's correct.

MR. MILLAR:  Similarly, let's imagine a scenario where you don't get CNSC approval for Pickering beyond 2020.  You would -- in that scenario you would come in to seek to adjust your production forecast downwards?

MR. FRALICK:  I think in the event of something as dramatic as that to OPG's plans we would be coming into the Board in any event.

MR. MILLAR:  Is that because it would trigger the 300 basis points off-ramp, or is there some other reason you'd be --

MR. FRALICK:  Well, similar to what we've said in GEC, I think 464, whereas in the event that an off-ramp is triggered we would come back to the Board, that's not part of an application cycle or part of the midterm review proposal.

But that is -- it would be a very significant event that would fundamentally change the outlook on the company, and we would come back to the Board and seek direction in that event.

MR. MILLAR:  Okay.  I was going to save my off-ramp questions, but you've brought it up.  So I had understood you to say that the reg prevents the Board from adjusting revenue requirement, and I'm trying to square how that would mesh with the idea of off-ramp.  An off-ramp would require a review of the revenue requirement.

And I understood you to say the rate prevented that, so I just, I want to understand why it's okay if there is an off-ramp.

MR. FRALICK:  Are you referring -- like, in my previous description of off-ramp, it was as the -- in the context of DRP, in that language.  When you say off-ramp are you referring to off-ramps within the context of the RRFE?

MR. MILLAR:  Well, OPG's proposal in this case for nuclear is, there is an off-ramp if your earnings are plus or minus 300 basis points --

MR. FRALICK:  Okay.

MR. MILLAR:  -- off the forecast.  That's the off-ramp I'm talking about.  And I guess I wanted to see how this squared with your assertion that the regulation does not allow the Board to revisit the five years of revenue requirement once it has set that for this proceeding?

MR. FRALICK:  In terms of the applicability of the off-ramp, OPG is not seeking unique treatment with regards to how an off-ramp would work as a mechanism under any incentive regulation.

MR. MILLAR:  I understand that.  And if this is a matter for argument, that's fine.  But I understood OPG's position to be that you can't change revenue requirement after it's been set in this proceeding because of the regulation.  There is no similar regulation for anybody else.

So I just wanted to understand how there could be off-ramps if the regulation permitted adjustments to revenue requirement.

MR. SMITH:  I think this may be a matter of argument.  I mean, it will obviously depend on the overall caveat as to whether or not the Board determines under section 78.1 the resulting rates are just and reasonable, Mr. Millar.

MR. MILLAR:  Well, and that's what I expected the answer might be.  So I take it that it's OP -- it's not OPG's room (sic) that there is an absolute prohibition on any adjustments to revenue requirement after it sets rates through this proceeding.  Certainly I don't read the reg to actually say that.

But as you fairly pointed out in your application -- you do say subject to the OEB concluding that rates are no longer just and reasonable, so maybe we're talking ourselves into a circle here, but I don't read that to say that once the OEB sets just and reasonable revenue requirements for five years it is forbidden from ever looking at that again.  Does OPG agree with that?

MR. SMITH:  I think the fairest articulation of the position is the one that's at page 38 of your compendium, set out at line 23.

MR. MILLAR:  All right.  Well, we can leave the rest to argument.

All right.  Just let me get back to forecasting, your production forecast.  Could we go to page 39 of the compendium.  So at about line 9 you state:

"In general it is more difficult to forecast events further into the future.  This difficulty increases further when the subject matter of the forecast is inherently certain."

And I think that's what you were speaking to earlier, Mr. Fralick; is that right?

MR. FRALICK:  Yes.

MR. MILLAR:  So no doubt there are risks in predicting the production forecast out five years.  My question to you, though, is, you seem to be very comfortable in forecasting your revenue requirement out for five years.  Why is that easier to predict than your production forecast?

MR. FRALICK:  Not to be facetious, but I don't think we've said anywhere that we're comfortable with forecasting our revenue requirement out five years.  What we have done is put an application before the Board which is -- has endeavoured to match the Board's intentions and directions with regards to OPG's regulatory construct and framework for the next five years, so it's a custom incentive regulation for nuclear and an IRM for hydroelectric, and we've only sought to apply changes where it's appropriate, and in the case of the midterm review, that is a very significant area of risk for the business.  You've rightly highlighted on chart 2 and F -- E211 that it has been a historical challenge for us.  We are increasing our production forecast window from 24 to 30 months in this proposal.  We are accepting some risk.  Given the unparalleled state of the nuclear life cycle that we're in within OPG, both at Darlington and at Pickering, we feel that it's not an unreasonable request to come in and seek to update the nuclear production forecast, given the fact again that we have a 100 percent variable rate design.

MR. MILLAR:  And I apologize if I put words in your mouth.  I didn't mean to do that.  And I didn't mean to suggest that OPG had said it was easy to forecast revenue requirement out five years, but when we went through the list of risk factors that you'd identified for production forecast, the five factors, is it fair that those apply equally to the forecasting of revenue requirement?

MR. FRALICK:  Sorry, what page was that again?

MR. MILLAR:  That is on page 37 and 38 of the compendium.  I mean, generally speaking, it seems to me these would all apply to revenue requirement as well?

MR. FRALICK:  I mean, they would have different impacts, but I think they would all be considerations that would have to be taken into account in terms of the revenue-requirement impact.  They could.

MR. MILLAR:  You've proposed -- we discussed -- you're proposing a deferral account, the nuclear production variance account.  That's where these differences would be tracked, assuming the Board found there were any differences?

MR. PUGH:  Midterm account, yes.

MR. MILLAR:  Yes, sorry, the -- yeah, the midterm nuclear production -- I might have described it wrong, but it's going into a variance account?

MR. PUGH:  It is.

MR. MILLAR:  Does that variance account actually have to be made now -- there wouldn't be any entries until after the midterm review; is that fair?

MR. PUGH:  That's fair.

MR. MILLAR:  Okay.

MR. FRALICK:  That's correct, yes.

MR. MILLAR:  And finally, I don't know if you'll be able to answer this question or not, but I'll put it to you so I don't lose it.  There have been some updates to the regulation on rate smoothing, and it now appears to incorporate DVA balances and the Board's consideration of how to smooth.  Are you familiar with that?

MR. PUGH:  Yes.

MR. MILLAR:  And you'll be proposing, if your proposal is accepted, you'll be looking to clear DVA balances as part of the midterm review.  And I just want to know if you've given any thought to whether the regulation will impact that any way, would it include a proposal for smoothing of those amounts, or if the regulation -- if you've had any thought about that?

MR. FRALICK:  Yeah, in our interpretation of the regulation we understand that the consideration of deferral and variance accounts for hydroelectric and nuclear would be utilized in the determination of the smoothing of the nuclear payment amount in a major application, so -- and where we are now for the next five years.

When we come in the midterm to seek clearance of the deferral and variance accounts, as I understand the Board has mechanisms to consider with regards to the overall impact that any of those riders could have on customers, be that spreading the disposition over a longer period of time or whatnot.

So I don't believe that the regulation is at all in conflict with that.

MR. MILLAR:  And I wasn't suggesting it was in conflict.  I guess my question was more, will the new regulation result in changes in the way that you present the DVA balances for clearance, and if this is a better question for the rate smoothing panel, or if you don't know yet, that's fine.  I just wondered if you had given any thought to that.

MR. PUGH:  First of all, I do think it's a better question for the rate smoothing panel.

MR. MILLAR:  Okay.

MS. LONG:  Mr. Fralick, are you on the rate smoothing panel?

MR. FRALICK:  We all are.

MS. LONG:  With additions?

MR. FRALICK:  Yes, Lindsay Arsenault is also on that panel with us.

MR. SMITH:  There is an addition, yes.

MS. LONG:  And the mechanics of how this is all going to work are going to be --

MR. SMITH:  Filed tomorrow.

MS. LONG:  -- explained to us.  I'm waiting with bated breath.  But I understand it's going to be filed tomorrow, and you'll take us through this?  You understand we have a lot of questions about the actual mechanics of this are going to work in the context of what we've talking about now.

MR. SMITH:  I understand there will be many questions about this.

MR. FRALICK:  In an effort to be responsive in our impact statement, we have -- we will be including a number of interrogatories that we will be updating because a number of scenarios were requested.

So we hope that that will be illustrative of the impact of what the new rate smoothing proposal will do.

MR. SMITH:  To be clear on that, there were IRs asked on the last methodology.  We've updated all of those.  They are attachments -- they will be attachments to the evidence that's being filed tomorrow.

MS. LONG:  I don't want to derail Mr. Millar's cross-examination here, but have you, Mr. Smith, had any contact from any other intervenors who are looking to delve deeper into what's filed as of Wednesday?

I guess we can deal with it on Thursday, based on what's filed, whether or not you anticipate that there will be more interrogatories asked, or these updated interrogatories may be sufficient.

I guess we'll hear from people on Thursday or Friday, once they've had a chance to review the material.

MR. SMITH:  We have not had any contact, no.

MR. MILLAR:  Thank you, Madam Chair.  I'm actually finished with my cross-examination, so thank you very much, panel.

MS. LONG:  Mr. Tolmie?  Do you have some questions for this panel?

MR. TOLMIE:  I had submitted a compendium.  But in the interests of getting on with the job and shortening the time, I would like to simply respond to your invitation to bring up the storage issue for this particular panel, if that's okay.

MS. LONG:  You can pose a question.  I don't know what the question is, and I don't know if this is the proper panel to answer it.  But you can ask your question and we'll see what it is.

# Cross-Examination by Mr. Tolmie:

MR. TOLMIE:  What we discussed earlier today is the concept that the base load generation currently exceeds the actual demand for power on average in Ontario, and that's giving rise to problems right now.

If you look at the price record over the past several years, there have been many occasions in which the price has gone negative.  That indicates that the supply is exceeding the demand, right?

MR. FRALICK:  Yes.

MR. TOLMIE:  Okay.  But every day of the year for many years now, the night time price for electricity has gone to a very low value, typically close to zero, is that correct?

MR. FRALICK:  I wouldn't be able to speak with authority with regards to the trend in the HOEP.  I know that it varies quite a bit.  I know it's not a high number.  What it is on a given day, or its trend, I don't know if I could speak with any specificity.  I don't know if any OPG panel could.  That's an IESO type of an area that we are not experts in.

MR. TOLMIE:  You're aware, though, that it goes through a big trough every night?

MR. FRALICK:  Certainly.

MR. TOLMIE:  Okay.  And OPG gets paid per megawatt hour of energy actually delivered, is that correct?

MR. FRALICK:  That's correct.

MR. TOLMIE:  Okay.  Now, if you look at the numbers that come from IESO, the surplus generation over average  demand is something like 43 hundred megawatts.  That's quite a bit.

But if you look at what's happening with the policies in Ontario, they're trying to reduce the consumption of fossil fuels in particular, and those fossil fuels are being used to heat homes.  And part of the heat and cooling -- most of the cooling of that comes from the electricity.

So if the government and industry succeed in reducing the demand for electricity for heating purposes, the potential is to the order of 5700 megawatts, which brings up the possibility that you may be facing a deficit of demand over supply of around 10,000 megawatts in the not too distant future.  In other words, there would be no demand for a lot of the power that you're committing to produce; is that possible?

MR. FRALICK:  I don't know.

MR. TOLMIE:  Is it significant if it's possible?

MR. FRALICK:  Is it significant if it's possible?  10,000 megawatts is significant.

MR. TOLMIE:  Would that have an impact on your revenue then?

MR. FRALICK:  I don't know.

MR. TOLMIE:  Would it have an impact on the appropriate rate setting for this Board to determine?

MR. FRALICK:  That level of change in provincial demand has not been reflected in our application.

MR. SMITH:  Madam Chair, I simply ask for guidance.  I don't know what to do with Mr. Tolmie's question, other than these seem like broad system planning questions.  We don't have a witness panel to address them.  If there are

-- nor do I think, frankly, OPG is the right party to address them.

To the extent we want Mr. Tolmie to ask the questions, there is an IESO witness.  I don't want that person to be put on the spot.  But on the other hand, I don't know what we can say when we have certain evidence responsibilities that are outlined in the schedule that we talked about at the outset of this.

If Mr. Tolmie wants to ask any question about any of the evidence that OPG has prepared, we're certainly happy to take those questions.

MR. TOLMIE:  If it has an impact on the rate, should it not be something that would be considered by the Board?

MS. LONG:  Mr. Tolmie, I think to the extent you have a question about what this panel is giving evidence on, so if you related your question to production forecast, that is something they can ask answer a question on.

You can ask questions about what they considered in putting their application before the Board.  That is fair.

But to talk about system wide planning, that's not something that this panel is charged with answering questions on.

MR. TOLMIE:  The IESO person that's going to talk about the Pickering system, as I understand, which is really a different --

MS. LONG:   The IESO witness, we were very clear in our procedural order that they are going to speak to the analysis they've done, and I'm going to constrain parties to speak about -- to ask questions about what was filed and not have other scenarios that the witness is going to do system planning on the spot.  That is not the intention of the IESO witness being here.  He is going to speak to that report.

MR. TOLMIE:  That was my assumption, so it really doesn't provide an opportunity to raise an issue that I think is fundamental to setting the rate.

MS. LONG:  Well, this rate hearing may not be the forum for you to raise the issues you want to discuss.  I want to get back to this witness panel, and whether or not you have any questions to ask them of the evidence they've given and they're responsible for.

MR. TOLMIE:  Well, as you suggested, one of the questions is with regard to future projections for demand for your services.

MS. LONG:  So do you have a question related to that, a specific question that this panel can answer?

MR. TOLMIE:  Does the plan to reduce that demand, by eliminating the requirement for both fossil fuels and electricity for thermal applications, have an impact on your estimates?

MR. FRALICK:  Our application has not factored in any significant system demand reductions, or the impact thereof, in the next five years.

MR. TOLMIE:  That's what I was driving at, that the production may not be precise.

MS. LONG:  Thank you, Mr. Tolmie.  Mr. Rubenstein?

MR. RUBENSTEIN:  Thank you very much.  Panel, I have a compendium of documents, if we can mark that.  I don't know if the hearing panel has a copy.

MR. MILLAR:  K6.3.

EXHIBIT NO. K6.4:  CROSS-EXAMINATION COMPENDIUM OF SEC FOR OPG PANEL 2A(I)

MR. RUBENSTEIN:  Mr. Millar has asked a lot of my questions, so --

MR. SMITH:  Sorry, Mr. Rubenstein's compendium -- are we at 6.3 or 6.4?

MR. MILLAR:  My mistake.  6.4.

# Cross-Examination by Mr. Rubenstein:

MR. RUBENSTEIN:  Staff has asked a number of my questions, so I just have some odds and ends I would like to ask you about.  I just want to go back to the beginning here and how you set the structure of this application, specifically the structure of the nuclear side of the business and the payment amounts, and as I understand from the Board's direction you were required to set the hydroelectric assets on an IR framework and the OPG assets on a custom IR framework.  Is that your understanding as well?

MR. FRALICK:  I'm not sure, when you say OPG assets -- we were required to set --

MR. RUBENSTEIN:  Regulate --

MR. FRALICK:  -- hydroelectric assets on an IRM mechanism and the nuclear assets, as is stated in the February 17th, 2015 letter:

"A longer-term approach to payment amount setting for the nuclear assets that focuses on the parameters of -- for a multi-year cost-of-service application while incorporating elements of IR."

MR. RUBENSTEIN:  I'm on page 3.  I think I have this letter that we're talking about here.  We see this:

"The Board expects OPG to develop IR framework for its hydroelectric assets, any custom IR framework for its nuclear assets, based on the principles outlined in the RRFE."

MR. FRALICK:  I see that, yes.

MR. RUBENSTEIN:  All right.  So you're set -- and your proposal is for the nuclear assets to set them on a custom IR basis?

MR. FRALICK:  Yes.

MR. RUBENSTEIN:  All right.  And then I just want to understand what that means in your -- from your perspective.  And my understanding, your proposal to do so and how you've set them on a custom IR basis, is to set them on a five -- to determine your budget for the five years on a five-year cost-of-service basis, and then to put in place the stretch factor on 75 percent of your OM&A.  Am I correct?

MR. FRALICK:  As it pertains to strictly the cost items and the framework requirements of a custom IR, yes, the cost was on a five-year basis with a stretch factor that will apply to 75 percent of the OM&A.

MR. RUBENSTEIN:  And Mr. Millar talked to you about how you determine the stretch factor and why it's only applied to OM&A, and I just wanted to understand that a little bit better.

As I understand for the OM&A perspective you've determined that you should -- it's only appropriate to apply to, I believe it was base OM&A, and -- I forget the term you used.

MR. FRALICK:  Corporate support cost.

MR. RUBENSTEIN:  Corporate support cost, and not for project OM&A and outage OM&A, correct?

MR. FRALICK:  Correct.

MR. RUBENSTEIN:  And as I understood your discussion, it was because project and outage OM&A, there is no productivities, further productivities, to be had.

MR. FRALICK:  I wouldn't characterize it that way.  I would say that, while we strive to get better at projects and outages over time, because of the fact that they're discrete undertakings, we reflect the best estimate for the cost for that given scope of work within our business plan.

MR. RUBENSTEIN:  And so it's your expectation, though, you forecasted in amount, like, for 2017 and 2018 and 2010 and so on, so if we look at 2018, you're not going to be, from today until you start doing that work, find any more productivity.

MR. FRALICK:  Well, we will continue to look for areas to improve.  With regards to where we are going to be able to find incremental efficiency gains above and beyond what we've outlined in our business plan, we have not yet identified what those are going to be, but out of necessity, given the fact that the -- where we have applied the stretch factor we will have limitations with regards to identifying costs to that magnitude, we're going to have to look wherever we can in order to come up with the extra savings in order to account for the full quantum of that stretch factor.

MR. RUBENSTEIN:  But I just want to talk, because your proposal, as I understood it, is for project and outage OM&A as compared to other OM&A that is covered.  It's not appropriate, and I just want to focus on that.  And as I took it, as I understood it, it's because there is something inherently different with that type of work that you won't be able to find more efficiency benefits than may be embedded in that budget.  Is that correct?

MR. FRALICK:  I mean, without restating my testimony with Mr. Millar, yes, we look to apply the stretch factor to the areas of the nuclear cost that were in a steady state that would be subject to efficiency gains.

MR. RUBENSTEIN:  So when I look at the chart that Mr. Millar took you to on page 23 of his compendium, I see that for 2018, so this was the first year stretch factor is applied to any amount, if you take a look at the project and outage OM&A, I did about $503 million.  Do you see that?  Line 2 and 3?

MR. PUGH:  Yes.

MR. RUBENSTEIN:  And so if we applied a stretch factor of your proposed stretch factor of 0.3, I get about one-and-a-half million dollars.  Does that sound reasonable to you?

MR. FRALICK:  It's in the ballpark, yeah.

MR. RUBENSTEIN:  So your evidence -- and as I understand is for the $503 million that you plan to spend, you don't think you could find $1.5 million of savings?

MR. FRALICK:  What we're suggesting is for the reasons we outlined earlier with our -- some of the compensation restraints, regulatory and safety requirements, and other things that are inherent within the base OM&A where we are applying the stretch factor, we will necessarily be required to look elsewhere in order to come up with that savings.

So I'm not saying that we cannot find or won't be looking to get better within those cost categories, but as a category, they are much more discrete, and they do not lend themselves to efficiency gains the way the base OM&A cost category does.

MR. RUBENSTEIN:  Okay.  So I think I understand.  The rationale then is more, you don't even think you can get the 0.3 on everything else, the 75 percent?

MR. FRALICK:  Yes.

MR. RUBENSTEIN:  So then it would be unfair to add in this amount?  Is that my understanding?

MR. FRALICK:  The 0.3 stretch factor applied as we have accumulates over the five years and eventually totals $50 million will be a significant challenge for us, yes.	MR. RUBENSTEIN:  And as I understood the evidence, capital is also inappropriate to do the stretch factor, correct?

MR. FRALICK:  Yes, for the reasons that I outlined earlier with Mr. Millar.

MR. RUBENSTEIN:  And I want to understand, the way that you determined the stretch factor was using the total -- was the total generating cost per megawatt hour.  That's how you determined which cohort you would be in, to determine the 0.3?

MR. FRALICK:  Yes, so it's in A132, the methodology, but we took a look at Pickering and Darlington independently, look at their TGC rating, what stretch factor would you apply to Darlington based on its TGC performance, what stretch factor would you apply to Pickering based on its TGC performance, and then we production-weighted those two numbers to come up with an ultimate stretch factor that was reflective of all of nuclear, and in the case of our pre-filed that equals 0.3 percent.

MR. RUBENSTEIN:  And my understanding about the total generating cost per megawatt hour is that's an all-in.  That includes capital cost and OM&A cost, correct?

MR. FRALICK:  It is, yes.

MR. RUBENSTEIN:  So if we're only applying it to OM&A, why is it not more appropriate to use some form of OM&A costs per megawatt hour, an apples-to-apples comparison?

MR. PUGH:  I think it's because the metrics that we have that are benchmarked for the ScottMadden methodology provides a reasonable basis for comparison, and those are the numbers that are available, are the total generation costs, and because we felt that was a reasonable representation of the company, as we said earlier, that we've actually adopted as a metric for our company, we thought that was a reasonable basis for which to do a comparison.

MR. RUBENSTEIN:  Can I ask you to turn to page 21.  This is from the benchmarking report -- the updated benchmarking report, the 2016.  Sorry, 21 of the -- and my understanding is you do benchmark on non-fuel operating costs per megawatt hour.

Why isn't this the more appropriate benchmark to use?

MR. FRALICK:  Fundamentally it is not an appropriate metric to benchmark CANDU plants on, so the fundamental design benefit of CANDU is the fact that you can get away with using cheaper fuel.

So the cost trade-off for that is that you have some higher OM&A costs.  So the appropriate metric, as we have done and laid out over many years, is on a TGC basis.

MR. RUBENSTEIN:  Sorry, I don't understand.  My understanding is your fuel costs are not included in the -- while they're part of the revenue requirement and I guess in some sense they're OM&A costs, you don't -- in the categories in Mr. Millar's table on page 23 you -- it's sort of outside what you consider total OM&A, correct?

MR. FRALICK:  In the benchmarking, it is not included in the non-fuel operating cost category.

MR. RUBENSTEIN:  I still don't understand why, if we're now comparing your OM&A costs, why we shouldn't use the more appropriate me metric, which is non-fuel operating cost per megawatt hour.

MR. FRALICK:  I'll try to explain myself better.  The benchmarks that we compare ourselves to, which are at the front of this report, are many utilities from across North America, many of which -- most of which are not CANDU.

So one of the fundamental design differences of CANDU compared to a pressurized water reactor or boiling water reactor is that we can utilize unenriched uranium fuel.

The trade-off in the design is you have higher OM&A costs to enable that technology.  So you have a design trade-off that costs you more on the technology side, but gets you that benefit on the fuel side.

So to only extract the one piece of it and then compare is not an apples to apples comparison.  So that is why a TGC is an appropriate comparator for CANDU in amongst a peer group that includes others in addition to CANDU.

MR. RUBENSTEIN:  Can I ask you to turn to page 25?  You also have a metric fuel cost per megawatt hour.  So why don't we just add up, I would have thought based on your response, the non-fuel operating cost per megawatt hour and The fuel cost per megawatt hour.  And then you have the benefits you’re talking about, about the CANDU reactor and how it has cheaper fuel costs, and you have the issues you believe you have with using non-fuel operating costs, and have all-in OM&A cost per megawatt hour.

MR. MAUTI:  I guess one reason the company overall has adopted a total generating cost in terms of a comparator is within the nuclear industry, the total generating cost takes into account all basically cash expenditures that are required to operate the plant for any given year.

In previous proceedings, we looked at our capitalization policies and thresholds about what's considered capital versus O&M.  Total generating cost actually sees through all that and actually takes a look at the total cost to operate.  We believe it's the most appropriate way of an apples-to-apples comparative basis to look amongst all within the industry.

So I think for that reason that's why, in terms of standings us up against others, that's probably the most appropriate one too use.

MR. RUBENSTEIN:  But it includes capital cost which you are not then applying the stretch factor to.

MR. FRALICK:  Correct.  From a comparison perspective, the total cost metric is the most appropriate to benchmark.

MR. RUBENSTEIN:  My understanding of the Board's IRM framework and what your -- essentially your proposal with respect to the hydroelectricity is sort of an I minus X mechanism, correct?

MR. FRALICK:  Under hydroelectric, yes, we've applied an I minus X, yes.

MR. RUBENSTEIN:  And my understanding is the X mechanism that the Board uses and what you're forecast to use for hydroelectric is made up of two parts, a stretch factor as well as industry productivity factor, correct?

MR. FRALICK:  Correct.

MR. RUBENSTEIN:  So you were asked at Energy Probe 34 -- sorry Energy Probe 2, on page 34, about why you have not proposed a productivity factor for nuclear.  And as I read your response, essentially the high level -- there’s a lot of work being done on Pickering and Darlington, and thus the historical periods will not be reflective of the future.  Is that fair?

MR. FRALICK:  That's one of the reasons why.  I think the subject of a total factor productivity for nuclear has been one of significant discussion over the years, as OPG has evolved its regulatory framework.  So if you look back to the Board's EB 2012-0340 report, there is quite a bit of discussion in there about the suitability and applicability of the total productivity study for nuclear.  In fact, SEC submitted some comments with regards to that report that go to that extent.

So that report also itself, on page 7, I believe, outlines the fact that a total factor productivity is not appropriate for nuclear.

MR. RUBENSTEIN:  If I can ask you to turn to page 36?  I want to understand this question from a business planning perspective of how OPG plans its operations.

We asked you in SEC number 1 a number of questions, and we were asking you how -- in essence, about any forecast or estimates you've done with respect to a number of different things, but they include price levels when generating becomes unproductive, or your own price levels which potentially customers to exit the system.

And your response was essentially, well, we don't have any of those; we don't have any of those studies.  Is that a fair characterization?

MR. FRALICK:  I think OPG prides itself on being a low-cost electricity generator in Ontario.  And in fact, we strive to maintain that position through this application.

The smoothing mechanism that we will be discussing in panel 6 is another consideration that will be deployed to minimize the impact of OPG's rates.  We're going through a very challenging time, as you're well aware, with the Darlington refurbishment, so it is a fundamental tenet of OPG’s competitive advantage to retain its position as a low cost provider.

MR. RUBENSTEIN:  I understand.  I want to understand from a planning perspective, how do you implement that process where you want to be a low cost provider, you want to ensure you are competitive.

From a planning process, how do you go about making sure that occurs?  Can you just give me some insight?

MR. MAUTI:  In terms of the cost to operate the facilities we have and the applications we're putting forward to the Board to determine our price position, the IESO has information available and we have groups within Ontario Power Generation that to try to assess where that marketplace is going in comparison to that, and we sort of look at what our weighted average price of our generation is versus the price for other generators in the province.  And historically, we've been some 35 to 40 percent on average overall cheaper than all the other generation within the province.

We look at our forecast, and what's happening through our smoothing proposals and through our IRM proposals with hydroelectric, and we still believe that on a forecast basis, we will still continue to be significantly below, somewhere in the 30 to 40 percent, based on our forecast, below other generators.

So we do feel that we do have that price mitigation aspect of what we are doing, notwithstanding the fact we're trying to refurbish the nuclear station, which has its own specific pressures on prices as generation comes up and investments are made, and as Pickering approaches its end of life.

There are a lot of things obviously happening within the nuclear fleet in the next ten years, and we're trying to navigate through that while being cognizant what our position is in relation to our customers.

MR. RUBENSTEIN:  Is that an output of -- sort of the end of the line conclusion based on the planning, so essentially you've forecasted your rates and what you believe you need to operate the plants and so on, and then you've come to the determination that we're still lower than -- we're going to be okay because we're 30 percent lower than other sources, or whatever the number is?  Or is that something at the top end in the planning process, where you say we must ensure that we are competitive.  Which one is it?

MR. MAUTI:  Historically, you know where you are within -- it's easy to get the historical information now.  IESO publishes enough information and data for you to be able to, at least globally, look at that.  And going forward in terms of our path that we’re taking with our smoothing proposal and IRM, there’s more unknown trying to forecast into the future how the rest of the marketplace and the rest of the generation will play out in the province.

We feel comfortable -- not as much as when you are looking backwards historically, but we do feel, based on information available, at the end we would still have the competitive advantage position.

MR. RUBENSTEIN:  Let me ask you about the off ramp proposal.  My understanding is it's -- I don’t want to use the word standard, but it’s generally the usual 300 basis point.

MR. FRALICK:  We've not sought any deviation from the definition of an off ramp in the RRFE.

MR. RUBENSTEIN:  I want to understand what you mean by the -- what's going to happen when you tell the Board.  Is it your view that if you’re plus or minus 300 bases points at the end of the year, you will file something with the Board, or is it simply they will alert you if there is an issue based on your annual triple R filings, or whatever the equivalent is for OPG?

MR. PUGH:  We would file on June 30th, which was our filing requirements in 2010-008, we would file our regulatory ROE and the results would be there, and with that we would advise the Board whether we thought that this was because of a temporary activity, whether it was ongoing, so we would provide them some advice, and then the Board would determine whether they wanted to bring us in for an application, because the RRFE said they may have an application, and therefore we would provide them input in order to do that --

MR. RUBENSTEIN:  All right.

MR. PUGH:  -- beyond just the 300 basis point number.

MR. RUBENSTEIN:  Maybe this is for the smoothing panel, and I -- how is this going to work with the rates being smooth?  What are we comparing 300 basis points to?

MR. PUGH:  What are you comparing it to?

MR. RUBENSTEIN:  Well, you're deferring -- as the plan goes on you're smoothing, so you're not actually bringing in the revenue that you would need in that year, an amount goes into an account.  Just trying to understand how the -- if there's a -- maybe there is no interaction between the smoothing proposal and the 300 basis points.

MR. MAUTI:  In the calculation of the regulatory ROE it's based on our net income, and our net income is largely driven on revenue requirement.  The process of smoothing the amount through rates, think of more of a financing sort of aspect of it.  It doesn't specifically change the net income that would be sort of reporting in each individual year.

MR. PUGH:  That example is drawn out in your compendium at Board Staff 271.

MR. RUBENSTEIN:  Yeah, I was going to bring you to that, and this is on...

MR. PUGH:  The short is -- it's not -- the RSV has no --

MR. RUBENSTEIN:  Page --

MR. PUGH:  -- income impact.  It has a cash-flow impact.

MR. RUBENSTEIN:  So you will have a -- you will get -- the Board will approve a revenue requirement for a given year that you're seeking as approved -- say it's exactly as approved.  But the revenue that you will actually collect in that given year from the smooth payment amounts will differ.

MR. PUGH:  Correct.

MR. RUBENSTEIN:  And I'm just trying to understand if you can help us understand the -- how this -- the calculation.  I know -- and I didn't fully understand the

-- how this works with this interrogatory that you had provided.  So I was wondering if you can go through it now, or is it better for the smoothing panel, because this may all change.

MR. FRALICK:  Well, hopefully this will sum it up, and if not, Randy can fill in with the details, but if the entries that OPG makes into the rate smoothing deferral account affect our cash flow but they do not affect our net income, so the balances that get recorded into the RSDA are recognized as income in the year that they're recorded.

MR. RUBENSTEIN:  All right.  If I can ask you to turn to page 40.  You were asked essentially what the threshold would be.  And as I see for, say, 2020, it's about $221.7 million?  Am I -- that's my --

MR. PUGH:  You've got the right number.

MR. RUBENSTEIN:  So just based on sort of a simple calculation, if Darlington Unit 2 is delayed by a year for some -- and doesn't go in-service in 2020 as forecasted, aren't you going to be fully offside the 221.7 million?  It's my understanding it's coming in to sort -- $4.8 billion are coming -- forecasted and will be built into the revenue requirement to come in in February.

MR. PUGH:  Unless we had a very good hydro year, yes.

MR. RUBENSTEIN:  So my question is, will accounts that have some sort of variance account protection on it, such as the Darlington refurbishment, because of the nuclear capacity refurbishment variance account, in that case would you seek for the -- would you ask the Board to do anything if you're 300 basis points off?

MR. PUGH:  We didn't understand your question.  You'll have to try it again.

MR. RUBENSTEIN:  That's totally fine.  Considering that for an example like Darlington you can be significantly offside the 200 basis points but there is a variance account that captures the in-service timing difference, my understanding, that is the refurbishment -- nuclear refurbishment capacity variance account.  For other amounts where there is an in-place variance account treatment, is that an area where you would say to the Board, we don't think you need to -- we may be 300 basis points off, but you don't need to worry about it?

MR. FRALICK:  I think I'm trying to think how to answer this.  The -- where we have costs that are subject to a deferral and variance account, those are still recognized as revenue, so the extent to which something were to occur that caused the cost to, instead of being part of a revenue requirement, to flow into a deferral and variance account, that would not impact our ROE.  So it would only be costs that would not flow to a deferral and variance account that could potentially impact ROE to the point of triggering an off-ramp in this example.

MR. RUBENSTEIN:  I'll have to think about that, but I'll move on.

I just want to ask just about -- quickly about the midterm review.  Mr. Millar has discussed a number of aspects of that.  So as I understood originally as originally filed the production forecast for the second half there would be an update as well as the consequential fuel cost, correct?

MR. FRALICK:  Correct.

MR. RUBENSTEIN:  The deferral and variance accounts will also be updated?  I mean, there will be a clearance of the deferral and variance accounts?

MR. FRALICK:  Yes.

MR. RUBENSTEIN:  And as well, from the N2 update, we will be reviewing the D -- proposed to review the D2O project as well?

MR. FRALICK:  That's our proposal, yes.

MR. RUBENSTEIN:  And you went with Mr. Millar, and Mr. Millar took you through to a number of risks that you thought was specific to the nuclear production element, and I was wondering, had you considered how much -- what component of those risks could be dealt with through the Board's Z factor policy, which my understanding you still want to leave open in your proposal?  Custom IR proposal?

MR. FRALICK:  I don't believe we looked at it through that lens, but we have looked at the Z factor.  We understand that it -- we would be seeking it for -- within this application, and if we were to encounter an exogenous event that would be appropriately subject to a Z factor, then we would pursue recourse through that mechanism.

MR. RUBENSTEIN:  But my question was you -- Mr. Millar took you through to a number of risks that were -- for why you believe you needed to update the production forecast.  Do you recall that?

MR. FRALICK:  Yes.

MR. RUBENSTEIN:  My question to you is, did you consider how those risks may be alleviated by the ability to potentially come before the Board for a Z factor, meaning there would be no need for a midterm review for production?

MR. FRALICK:  We would assess any given event that were to materialize through that lens at that time.  So I wouldn't say that we went through and imagined any infinite number of possible scenarios, but, yes, we would view an event through the lens of a Z factor before seeking another treatment.

MR. PUGH:  I think, Mr. Rubenstein, one of the things we did consider, as Mr. Fralick has said, we started off with the RRFE, said, what can't we live with.  The production forecast was an element of that, and then what we said was, can we make it as close to custom IR as possible.

So by coming up with another forecast we're again subject to forecast risk for the other term, and we thought that was consistent with taking on the risk of RRFE and custom IR.

MR. RUBENSTEIN:  Can I get you to turn to page 6.  You're aware of the Board's handbook on utility rate applications?

MR. FRALICK:  Yes, it was issued during our interrogatory period last year.

MR. RUBENSTEIN:  I recognize that.  If I can ask you to turn to page 26.  Sorry, page 7.  26 of the handbook.  And under "updates" the Board is talking about custom IR, and the Board says:

“Updates:  After the rates are set as part of a custom IR application, the OEB expects that there be no further rate applications for annual updates within the five-year term unless there are exceptional circumstances, with the exception of the clearance of established deferral and variance accounts.  For example, the OEB does not expect -- address annual rate application for updates of cost of capital, working capital allowance, or sales volume.  In addition the establishment of new deferral and variance accounts should be minimized as part of the custom IR application."

Do you find that the need to adjust your sales volume, essentially your production forecast is an exceptional circumstance?

MR. PUGH:  I think in the circumstances which we're forecasting now, I think it's very different than anything we've been through, so yes.

MR. RUBENSTEIN:  Thanks very much.  Those are my questions.

MS. LONG:  Thank you, Mr. Rubenstein.  That concludes cross-examination for today.  We are back on Thursday with the panel 1D, Schiff Hardin.  And, Mr. Smith, I would ask that you have this panel ready, just in case we do have some time on Thursday.

MR. SMITH:  Yes, they are queued up to be available.

MS. LONG:  Good.  If there is nothing further, we are adjourned until 9:30 Thursday morning.

MR. SMITH:  Thank you.

### --- Whereupon the hearing adjourned at 4:33 p.m.