## Material Capital Projects
Undertaking JT2.19 referencing 2-AMPCO-13
Ref: Attachment #50 Page 265 Table 55
a) Please update table to include YTD and forecast for 2017
Business Unit | Description | 2017 | Actual YTD Oct | Actual YTD Sep | 2017 Q3 Forecast | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
C0531 - Roads | Other Non-Material Road Projects | 1446215 | 323480 | 284603 | 460577 | 323555 | 661243 | 327838 | 330622 | 351036 | 4509169
C0531 - Roads | Project - Creditview - Britannia To Argentia | 0 | 0 | 0 | 0 | 1294220.0085 | 0 | 0 | 0 | 0 | 1294220.0085
C0531 - Roads | Project - QEW - Various Bridge Rehabilitations | 0 | 0 | 0 | 0 | 970665.0064 | 0 | 0 | 0 | 0 | 970665.0064
C0531 - Roads | Project - QEW - Evans to Cawthra | 0 | 0 | 0 | 0 | 1617775.0106 | 0 | 0 | 0 | 0 | 1617775.0106
C0531 - Roads | Project - Mavis - Courtney Park to City Limits | 0 | 0 | 0 | 0 | 0 | 1322486.011 | 0 | 0 | 0 | 1322486.011
C0531 - Roads | Project - Drew - Dixie to Tomken | 0 | 0 | 0 | 0 | 0 | 661243.0055 | 0 | 0 | 0 | 661243.0055
C0531 - Roads | Project - Courtney Park - Kennedy to Tomken | 0 | 0 | 0 | 0 | 0 | 661243.0055 | 0 | 0 | 0 | 661243.0055
C0531 - Roads | Project - Creekbank - Matheson To Shawson | 0 | 0 | 0 | 0 | 0 | 0 | 1311350.9191 | 0 | 0 | 1311350.9191
C0531 - Roads | Project Hwy 401 - Credit River To Hwy10 | 0 | 0 | 0 | 0 | 0 | 0 | 1967026.3787 | 0 | 0 | 1967026.3787
C0531 - Roads | Project - Ninth Line -Eglinton to Britannia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1322486.011 | 0 | 1322486.011
C0531 - Roads | Project - Ninth Line - Britannia to Derry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1653107.5138 | 0 | 1653107.5138
C0531 - Roads | Project - Hwy 401 - WCB to Credit River | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1755179.1896 | 1755179.1896
C0531 - Roads |  | 1446215 | 323480 | 284603 | 460577 | 4206215.0254 | 3306215.022 | 3606215.2978 | 3306215.5248 | 2106215.1896 | 19045951.0596
C0532 - LRT | LRT - Underground | 200000 |  | 46000 | 200000 | 2200000 | 4600000 | 4525000 | 4300000 | 2700000 | 18771000
C0532 - LRT | LRT - Overhead | 200000 |  | 136620 | 200000 | 2200000 | 4200000 | 4025000 | 3500000 | 2500000 | 16961620
C0532 - LRT |  | 400000 | 182620 | 182620 | 400000 | 4400000 | 8800000 | 8550000 | 7800000 | 5200000 | 35732620
C0541 - New Subdivisions(OfferConnect) | New Subdivisions | 2171524 | 788448 | 650808.37 | 671524 | 2171524 | 2171524 | 2171524 | 2171524 | 2171524 | 15139924.37
C0541 - New Subdivisions(OfferConnect) |  | 2171524 | 788448 | 650808.37 | 671524 | 2171524 | 2171524 | 2171524 | 2171524 | 2171524 | 15139924.37
C0542 - Ind/Comm Services | Industrial/Commercial Services | 4345963 | 4325425.61 | 3995327.75 | 4345964 | 4345963 | 4345963 | 4345963 | 4345963 | 4345963 | 38742495.36
C0542 - Ind/Comm Services |  | 4345963 | 4325425.61 | 3995327.75 | 4345964 | 4345963 | 4345963 | 4345963 | 4345963 | 4345963 | 38742495.36
C0544 - Residential Service Upgrades | Residential Service Upgrades | 763068.8 | 478151.85 | 412275.37 | 763068.8 | 763068.8 | 763068.8 | 763068.8 | 763068.8 | 763068.8 | 6231908.82
C0544 - Residential Service Upgrades |  | 763068.8 | 478151.85 | 412275.37 | 763068.8 | 763068.8 | 763068.8 | 763068.8 | 763068.8 | 763068.8 | 6231908.82
C0568 - Major Spares - Meters |  | 0 | 29976.95 | 79976.95 | 309624 | 0 | 0 | 0 | 0 | 0 | 419577.9
C0568 - Major Spares - Meters |  | 0 | 29976.95 | 79976.95 | 309624 | 0 | 0 | 0 | 0 | 0 | 419577.9
C0594 - Smart Meters Large Users |  | 0 | 774522.29 | 649351.09 | 650000 | 0 | 0 | 0 | 0 | 0 | 2073873.38
C0594 - Smart Meters Large Users |  | 0 | 774522.29 | 649351.09 | 650000 | 0 | 0 | 0 | 0 | 0 | 2073873.38
C0597 - Grid Supply Point Metering | Program - TCP/IP GSP Conversion & Reseal | 35000 | 0 | 0 | 35000 | 45000 | 35000 | 65000 | 10000 | 280000 | 505000
C0597 - Grid Supply Point Metering | Tomken Upgrade | 1100000 | 332526.99 | 278831.99 | 550000 | 0 | 0 | 0 | 0 | 0 | 2261358.98
C0597 - Grid Supply Point Metering |  | 1135000 | 332526.99 | 278831.99 | 585000 | 45000 | 35000 | 65000 | 10000 | 280000 | 2766358.98
C0598 - Metering | Program - Metering Renewal | 806775 | 942405 | 726472 | 870245 | 764000 | 717200 | 717200 | 717200 | 817200 | 7078697
C0598 - Metering | Program - New Metering Installations | 620000 | 721112 | 698290 | 724733 | 620000 | 620000 | 620000 | 620000 | 620000 | 5864135
C0598 - Metering |  | 1426775 | 1663517 | 1424762 | 1594978 | 1384000 | 1337200 | 1337200 | 1337200 | 1437200 | 12942832
C0899 - Smart Meters - New Condos | Program - New IMS | 1038500 | 143600 | 478930.59 | 1038500 | 1054000 | 1069500 | 1069500 | 1069500 | 1069500 | 8031530.59
C0899 - Smart Meters - New Condos | Program - Retrofit IMS | 368000 | 0 | 0 | 368000 | 372000 | 376000 | 376000 | 376000 | 376000 | 2612000
C0899 - Smart Meters - New Condos |  | 1406500 | 143600 | 478930.59 | 1406500 | 1426000 | 1445500 | 1445500 | 1445500 | 1445500 | 10643530.59
C0900 - Green Energy - FIT/MicroFIT | FIT & MicroFIT Projects | 125000 | 204226 | 146782.6 | 150827 | 95000 | 70000 | 65000 | 50000 | 0 | 906835.6
C0900 - Green Energy - FIT/MicroFIT |  | 125000 | 204226 | 146782.6 | 150827 | 95000 | 70000 | 65000 | 50000 | 0 | 906835.6
SYSTEM ACCESS |  | 13220045.8 | 9246494.69 | 8584269.71 | 11338062.8 | 18836770.8254 | 22274470.822 | 22349471.0978 | 21229471.3248 | 17749470.9896 | 142572034.6796
C0505 - Subdivision Rebuild | Project - Burningoak Cres | 2490588 | 1896069.7 | 1740153.36 | 2490588 | 0 | 0 | 0 | 0 | 0 | 8617399.06
C0505 - Subdivision Rebuild | Project - Beechhollow Section 3 | 2490588 | 396436.09 | 391144.81 | 2490588 | 0 | 0 | 0 | 0 | 0 | 5768756.9
C0505 - Subdivision Rebuild | Project - Ellengale | 1556617 | 1298702.05 | 1298282.48 | 1556617 | 0 | 2059941 | 2055778 | 1541834 | 2055778 | 13423549.53
C0505 - Subdivision Rebuild | Project - Clarkson | 2334926 | 1915342.06 | 1758602 | 2334926 | 0 | 2059941 | 2312751 | 2055778 | 2312751 | 17085017.06
C0505 - Subdivision Rebuild | Project - Malton | 1556617 | 1474929.27 | 1463190.71 | 1556617 | 0 | 2317434 | 1541834 | 2055778 | 1798806 | 13765205.98
C0505 - Subdivision Rebuild | Project - Truscott Plaza Area | 1816053 | 644490.1 | 605940.49 | 1816053 | 0 | 0 | 0 | 0 | 0 | 4882536.59
C0505 - Subdivision Rebuild | Project - Maple Ridge | 1556617 | 1480437.82 | 1480437.82 | 1556617 | 0 | 0 | 0 | 0 | 0 | 6074109.64
C0505 - Subdivision Rebuild | Project - Gananoque - Section 1 | 0 | 0 | 0 | 0 | 1961142 | 0 | 0 | 0 | 0 | 1961142
C0505 - Subdivision Rebuild | Project - Boughbeeches - Section 1 | 0 | 0 | 0 | 0 | 1238616 | 0 | 0 | 0 | 0 | 1238616
C0505 - Subdivision Rebuild | Project - Copenhagen - Section 1 | 0 | 0 | 0 | 0 | 2374014 | 0 | 0 | 0 | 0 | 2374014
C0505 - Subdivision Rebuild | Project - Appledore - Section 1 | 0 | 0 | 0 | 0 | 1238615.5 | 0 | 0 | 0 | 0 | 1238615.5
C0505 - Subdivision Rebuild | Project - Credit Woodlands Crt/Wiltshire (design complete) | 0 | 0 | 0 | 0 | 1548270 | 0 | 0 | 0 | 0 | 1548270
C0505 - Subdivision Rebuild | Project - Glen Erin & Montevideo - Section 1 | 0 | 0 | 0 | 0 | 1961141.5 | 0 | 0 | 0 | 0 | 1961141.5
C0505 - Subdivision Rebuild | Project -Tenth Line Main Feeder | 0 | 0 | 0 | 0 | 1135397 | 0 | 0 | 0 | 0 | 1135397
C0505 - Subdivision Rebuild | Project - Folkway & Erin Mills Main Feeder - L6259 to L6263 | 0 | 0 | 0 | 0 | 1032180 | 0 | 0 | 0 | 0 | 1032180
C0505 - Subdivision Rebuild | Project - Glen Erin & Battleford | 0 | 0 | 0 | 0 | 2064360 | 0 | 2055778 | 1798806 | 1798806 | 7717750
C0505 - Subdivision Rebuild | Project - City Centre Drive Cable Renewal | 0 | 0 | 0 | 0 | 1548270 | 0 | 0 | 0 | 0 | 1548270
C0505 - Subdivision Rebuild | Project - Baldwin Rd/ ROW | 0 | 0 | 0 | 0 | 0 | 1544956 | 0 | 0 | 0 | 1544956
C0505 - Subdivision Rebuild | Project - Golden Orchard/ Grassfire | 0 | 0 | 0 | 0 | 0 | 1544956 | 0 | 0 | 0 | 1544956
C0505 - Subdivision Rebuild | Project - Cedarglen Gate - Section 1 | 0 | 0 | 0 | 0 | 0 | 2059940.5 | 2312751 | 2055778 | 2055778 | 8484247.5
C0505 - Subdivision Rebuild | Project - Main Feeder renewal at Folkway Dr. from L6177 to L6405 | 0 | 0 | 0 | 0 | 0 | 2059940.5 | 2312751 | 0 | 0 | 4372691.5
C0505 - Subdivision Rebuild | Project - Traders - Section 3 | 0 | 0 | 0 | 0 | 0 | 2059941 | 2312751 | 2312751 | 2055778.4 | 8741221.4
C0505 - Subdivision Rebuild | Project -Tamar & Copenhagen main feeder | 0 | 0 | 0 | 0 | 0 | 1544956 | 0 | 0 | 0 | 1544956
C0505 - Subdivision Rebuild | Project - Forestwood/Stainton | 0 | 0 | 0 | 0 | 0 | 0 | 2055778 | 2055778 | 2055778.4 | 6167334.4
C0505 - Subdivision Rebuild | Project - Tenth Line West main feeder | 0 | 0 | 0 | 0 | 0 | 0 | 1541834 | 0 | 0 | 1541834
C0505 - Subdivision Rebuild | Project - Paisley Blvd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2312751.4 | 2312751.4 | 4625502.8
C0505 - Subdivision Rebuild | Project - Other Immaterial | 0 | 444165 | 431659 | 47080 | 0 | 0 | 0 | 2312751.4 | 2055778.4 | 5291433.8
C0505 - Subdivision Rebuild |  | 13802006 | 9550572.09 | 9169410.67 | 13849086 | 16102006 | 17252006 | 18502006 | 18502005.8 | 18502005.6 | 135231104.16
C0561 - Overhead Rebuilds | Program - Equipment Replacement | 1556617 | 1142168 | 1108176 | 1318144 | 1545617.3 | 1542016 | 1542016 | 1542016 | 1540939 | 12837709.3
C0561 - Overhead Rebuilds | Program - Pole Installations | 1245294.2 | 2581917 | 2224883 | 2463287 | 1236494.4 | 1233613 | 1233613 | 1233613 | 1232750 | 14685464.6
C0561 - Overhead Rebuilds | Project - Etude/Justine | 1120764.4 | 914385.94 | 890919.79 | 900000 | 0 | 0 | 0 | 0 | 0 | 3826070.13
C0561 - Overhead Rebuilds | Project - Credit Woodlands | 635100 | 9702.1 | 25786 | 635100 | 0 | 2405545 | 0 | 0 | 0 | 3711233.1
C0561 - Overhead Rebuilds | Project - Capricorn/Michaud | 709817 | 483914.39 | 427305.37 | 512245 | 0 | 0 | 0 | 0 | 0 | 2133281.76
C0561 - Overhead Rebuilds | Project - Munden/Pear Tree | 0 | 0 | 0 | 0 | 741896.2 | 0 | 0 | 0 | 0 | 741896.2
C0561 - Overhead Rebuilds | Project - Holburne/Ogden | 0 | 0 | 0 | 0 | 1020107.4 | 0 | 0 | 0 | 0 | 1020107.4
C0561 - Overhead Rebuilds | Project - Lake/John | 0 | 0 | 0 | 0 | 927370 | 0 | 0 | 0 | 0 | 927370
C0561 - Overhead Rebuilds | Project - Church | 0 | 0 | 0 | 0 | 1020107.4 | 0 | 0 | 0 | 0 | 1020107.4
C0561 - Overhead Rebuilds | Project - Rometown | 0 | 0 | 0 | 0 | 0 | 1850419 | 1850419 | 0 | 0 | 3700838
C0561 - Overhead Rebuilds | Project - Northmount/Alexandra/Meredeth | 0 | 0 | 0 | 0 | 0 | 0 | 1665377 | 0 | 0 | 1665377
C0561 - Overhead Rebuilds | Project - Greaves/East/Westmount | 0 | 0 | 0 | 0 | 0 | 0 | 740168 | 0 | 0 | 740168
C0561 - Overhead Rebuilds | Project - Cliff/Burslem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832688.5 | 0 | 832688.5
C0561 - Overhead Rebuilds | Project - Redstone/Bonaventure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925210 | 0 | 925210
C0561 - Overhead Rebuilds | Project - Other Renewal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370083.5 | 1849126 | 2219209.5
C0561 - Overhead Rebuilds | Project - Donnelly/Glenburnie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555125.5 | 0 | 555125.5
C0561 - Overhead Rebuilds | Project - Dejong/Wareham/Turney | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925210 | 0 | 925210
C0561 - Overhead Rebuilds | Project - Alexandra/Halliday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647646.5 | 0 | 647646.5
C0561 - Overhead Rebuilds | Project - Blanefield | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647194 | 647194
C0561 - Overhead Rebuilds | Project - Truscott | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554738 | 554738
C0561 - Overhead Rebuilds | Project - Lornewood/Glenhill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 647194 | 647194
C0561 - Overhead Rebuilds | Project - Stavebank/Kenolie | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 739651 | 739651
C0561 - Overhead Rebuilds |  | 5267592.6 | 5132087.43 | 4677070.16 | 5828776 | 6491592.7 | 7031593 | 7031593 | 7031593 | 7211592 | 55703489.89
C0562 - Subtransmission Renewal | Project - North Sheridan Way | 933970 | 782044 | 731012 | 933970 | 0 | 0 | 0 | 0 | 0 | 3380996
C0562 - Subtransmission Renewal | Project - Park – Section 1 - Ann to Stavebank [Formerly: Park – Hurontario to Kane] | 996235.3 | 9564 | 0 | 596235 | 0 | 0 | 0 | 0 | 0 | 1602034.3
C0562 - Subtransmission Renewal | Project - Summerville MS - Feeder Egress & rebuild | 1400955 | 1077369 | 1047159.87 | 1300955 | 0 | 0 | 0 | 0 | 0 | 4826438.87
C0562 - Subtransmission Renewal | Other Non-Material Projects | 404720.4 | 182514 | 165498 | 386267 | 0 | 938823 | 0 | 0 | 463150 | 2540972.4
C0562 - Subtransmission Renewal | Project - Lakeshore to Cawthra | 0 | 525433.78 | 510431.38 | 600000 | 0 | 0 | 0 | 0 | 0 | 0
C0562 - Subtransmission Renewal | Project - Courtney Park - Dixie To Ordan | 0 | 0 | 0 | 0 | 778308.5 | 0 | 0 | 0 | 0 | 778308.5
C0562 - Subtransmission Renewal | Project - Stanfield - North Service to Queensway | 0 | 0 | 0 | 0 | 1245293.5 | 0 | 0 | 0 | 0 | 1245293.5
C0562 - Subtransmission Renewal | Project - Hydro One ROW - Fieldgate/Audubon | 0 | 0 | 0 | 0 | 541042 | 0 | 0 | 0 | 0 | 541042
C0562 - Subtransmission Renewal | Project - Southdown - ROW to Lakeshore | 0 | 0 | 0 | 0 | 1171237 | 0 | 0 | 0 | 0 | 1171237
C0562 - Subtransmission Renewal | Project - Dixie - Londonderry to CN Tracks | 0 | 0 | 0 | 0 | 0 | 1251764 | 0 | 0 | 0 | 1251764
C0562 - Subtransmission Renewal | Project - Shawson - Dixie to Luke | 0 | 0 | 0 | 0 | 0 | 1095294 | 0 | 0 | 0 | 1095294
C0562 - Subtransmission Renewal | Project - Dixie - Dundas to QEW | 0 | 0 | 0 | 0 | 0 | 0 | 1561764 | 0 | 0 | 1561764
C0562 - Subtransmission Renewal | Project - Stanfield - Queensway to Dundas - Section 2 | 0 | 0 | 0 | 0 | 0 | 0 | 780882 | 0 | 0 | 780882
C0562 - Subtransmission Renewal | Project - Hydro One ROW - Cawthra to Stanfield | 0 | 0 | 0 | 0 | 0 | 0 | 1093235 | 0 | 0 | 1093235
C0562 - Subtransmission Renewal | Project - Hydro One ROW - Southdown to Lorne Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085228.3 | 0 | 1085228.3
C0562 - Subtransmission Renewal | Project - Hydro One ROW - Lorne Park to QEW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085228.2 | 0 | 1085228.2
C0562 - Subtransmission Renewal | Project - Hydro One ROW - Hurontario to Cawthra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2015424 | 0 | 2015424
C0562 - Subtransmission Renewal | Project - Goreway - Derry to CP Rail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617532.5 | 617532.5
C0562 - Subtransmission Renewal | Project -Tomken - Britannia to Courtney Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1543832.6 | 1543832.6
C0562 - Subtransmission Renewal | Project - Hydro One ROW - Erindale TS to Mavis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2161366 | 2161366
C0562 - Subtransmission Renewal |  | 3735880.7 | 2576924.78 | 2454101.25 | 3817427 | 3735881 | 3285881 | 3435881 | 4185880.5 | 4785881.1 | 30377873.17
C0563 - U/G TX/Replace/Overhaul | Program - Underground Transformer and Equipment Renewal | 716044 | 688703 | 688579 | 1216044 | 716044 | 716044 | 716044 | 727407 | 890047.3 | 7074956.3
C0563 - U/G TX/Replace/Overhaul | PCB & Leaking Transformer Replacement Project - Underground | 4784003.5 | 4825510 | 4089924 | 6784004 | 4784003.5 | 4784003.5 | 4784003.5 | 3162640.3 | 0 | 37998092.3
C0563 - U/G TX/Replace/Overhaul |  | 5500047.5 | 5514213 | 4778503 | 8000048 | 5500047.5 | 5500047.5 | 5500047.5 | 3890047.3 | 890047.3 | 45073048.6
C0564 - O/H TX/Replace/Overhaul | Program - Overhead Transformer and Equipment Renewal | 415098 | 221354 | 185868 | 415098 | 415098 | 415098 | 431229 | 442382 | 548337 | 3489562
C0564 - O/H TX/Replace/Overhaul | PCB & Leaking Transformer Replacement Project - Overhead | 3663239 | 669950 | 650071 | 1663239 | 3663239 | 3663239 | 1617108 | 1105955 | 0 | 16696040
C0564 - O/H TX/Replace/Overhaul |  | 4078337 | 891304 | 835939 | 2078337 | 4078337 | 4078337 | 2048337 | 1548337 | 548337 | 20185602
C0565 - U/G Cable Replace | Program - Pad Mounted Switchgear Replacement | 1686335.4 |  | 1524076 | 1686335.4 | 1686335.4 | 1686335.4 | 1686335.4 | 1686335.4 | 1686335.4 | 13328423.8
C0565 - U/G Cable Replace | Program - Primary Distribution Equipment Replacement | 498117.5 |  | 335349 | 498117.5 | 498117.5 | 498117.5 | 498117.5 | 498117.5 | 498117.5 | 3822171.5
C0565 - U/G Cable Replace | Program - Underground Cable and Splice Replacement | 2485398.8 |  | 2430469 | 2485398.8 | 2485398.8 | 2485398.8 | 2485398.8 | 2485398.8 | 2485398.8 | 19828260.6
C0565 - U/G Cable Replace |  | 4669851.7 | 4525063.92 | 4289894.29 | 4669851.7 | 4669851.7 | 4669851.7 | 4669851.7 | 4669851.7 | 4669851.7 | 36978855.9
C0567 - Emergency Replacements | Program - Emergency Replacements | 332078.3 | 291885.91 | 199092.36 | 332079.3 | 332078.3 | 332078.3 | 332078.3 | 332078.3 | 332078.3 | 2815527.37
C0567 - Emergency Replacements |  | 332078.3 | 291885.91 | 199092.36 | 332079.3 | 332078.3 | 332078.3 | 332078.3 | 332078.3 | 332078.3 | 2815527.37
C0569 - Major Spares | Major Spares from Inventory | 0 | 349321 | 349321.38 | 0 | 0 | 0 | 0 | 0 | 0
C0569 - Major Spares |  | 0 | 349321 | 349321.38 | 0 | 0 | 0 | 0 | 0 | 0
SYSTEM RENEWAL |  | 37385793.8 | 28831372.13 | 26753332.11 | 38575605 | 40909794.2 | 42149794.5 | 41519794.5 | 40159793.6 | 36939793 | 326365501.09
C0504 - Substation Upgrade | Station Upgrades | 5109244 | 4609394 | 3905723.78 | 5862814 | 5176186.3 | 1965575 | 5324164 | 4031012.2 | 3459471.3 | 39443584.58
C0504 - Substation Upgrade | Webb MS | 0 | 0 | 0 | 0 | 0 | 2069026 | 2377782 | 0 | 0 | 4446808
C0504 - Substation Upgrade | York MS | 1042703 | 0 | 14800 | 186000 | 2225760.2 | 0 | 0 | 0 | 0 | 3469263.2
C0504 - Substation Upgrade | Rockwood MS | 0 | 0 | 0 | 0 | 0 | 3517345 | 0 | 0 | 0 | 3517345
C0504 - Substation Upgrade | Mini Britannia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2583982 | 2581695.2 | 5165677.2
C0504 - Substation Upgrade | Summerville MS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1136952 | 1920781 | 3057733
C0504 - Substation Upgrade |  | 6151947 | 4609394 | 3920523.78 | 6048814 | 7401946.5 | 7551946 | 7701946 | 7751946.2 | 7961947.5 | 59100410.98
C0507 - Subtransmission Expansion | Project Southdown – South of Royal Windsor | 1763198 | 495191.76 | 312786.21 | 1721455 | 0 | 0 | 0 | 0 | 0 | 4292630.97
C0507 - Subtransmission Expansion | Other Non-Material Projects | 985316 | 756420 | 644439 | 1048473 | 312112 | 0 | 0 | 0 | 0 | 3746760
C0507 - Subtransmission Expansion | Project - Churchill Meadows Feeder Egress - TS to Winston Churchill | 0 | 0 | 0 | 0 | 1040375 | 0 | 0 | 0 | 0 | 1040375
C0507 - Subtransmission Expansion | Project - Derry – WCB to Argentia | 0 | 0 | 0 | 0 | 1186027 | 0 | 0 | 0 | 0 | 1186027
C0507 - Subtransmission Expansion | Project - Centreview - Mavis to Duke | 0 | 0 | 0 | 0 | 0 | 1249257 | 0 | 0 | 0 | 1249257
C0507 - Subtransmission Expansion | Project - Webb MS - Feeder Egress | 0 | 0 | 0 | 0 | 0 | 1249257 | 1249257 | 0 | 0 | 2498514
C0507 - Subtransmission Expansion | Project - Derry - Airport to Goreway | 0 | 0 | 0 | 0 | 0 | 0 | 1249257 | 0 | 0 | 1249257
C0507 - Subtransmission Expansion | Project - Lakeshore - Clarkson to Bexhill | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249257 | 0 | 1249257
C0507 - Subtransmission Expansion | Project - Mini-Britannia TS Feeder Egress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249257 | 1249257 | 2498514
C0507 - Subtransmission Expansion | Project - Feeder Egress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249257 | 1249257
C0507 - Subtransmission Expansion |  | 2748514 | 1251611.76 | 957225.21 | 2769928 | 2538514 | 2498514 | 2498514 | 2498514 | 2498514 | 20259848.97
C0576 - Auto Switches/SCADA | Program - U/G installation of SCADA/Automation switches | 622647 |  | 1143000 | 1265877 | 716824 | 819962 | 921411 | 1025616.5 | 1125941.5 | 7641279
C0576 - Auto Switches/SCADA | Program - O/H installation of SCADA/Automation switches | 716044 |  | 96540 | 179786 | 808987 | 912207 | 1013552.2 | 1117922.4 | 1228300 | 6073338.6
C0576 - Auto Switches/SCADA | Program - RTU System Enhancements & Equipment Upgrades | 752365 |  | 1023460 | 1118493 | 1085477 | 753340 | 967481 | 882030 | 946815 | 7529461
C0576 - Auto Switches/SCADA | Program - SCADA Master Upgrade | 103774.2 |  | 62110 | 89931 | 102403 | 102495 | 102379 | 102562.2 | 102358.3 | 768012.7
C0576 - Auto Switches/SCADA | Project - WiMAX Wireless Network Project | 51887.3 |  | 89394 | 100000 | 768026 | 768714 | 511895 | 143586 | 143302.3 | 2576804.6
C0576 - Auto Switches/SCADA |  | 2246717.5 | 2471307 | 2414504.47 | 2754087 | 3481717 | 3356718 | 3516718.2 | 3271717.1 | 3546717.1 | 24588895.9
SYSTEM SERVICE |  | 11147178.5 | 8332312.76 | 7292253.46 | 11572829 | 13422177.5 | 13407178 | 13717178.2 | 13522177.3 | 14007178.6 | 103949155.85
C0581 - Engineering & Asset Systems | Program - Hardware/Software Renewal | 345000 | 201292 | 201091.66 | 345001 | 345000 | 315000 | 365000 | 315000 | 315000 | 2747384.66
C0581 - Engineering & Asset Systems |  | 345000 | 201292 | 201091.66 | 345001 | 345000 | 315000 | 365000 | 315000 | 315000 | 2747384.66
C0584 - Rolling Stock | Program - Cars/Light Trucks/Vans | 907000 | 0 | 0 | 280000 | 1290000 | 529000 | 571000 | 480000 | 952000 | 5009000
C0584 - Rolling Stock | Program - Heavy Trucks/RBDs/Buckets | 1350000 | 0 | 0 | 1000000 | 1180000 | 2040000 | 1180000 | 1560000 | 500000 | 8810000
C0584 - Rolling Stock | Program - Other/Trailers/Lifters | 170000 | 214153 | 214152.74 | 220000 | 50000 | 227000 | 1350000 | 387862 | 435000 | 3268167.74
C0584 - Rolling Stock |  | 2427000 | 214153 | 214152.74 | 1500000 | 2520000 | 2796000 | 3101000 | 2427862 | 1887000 | 17087167.74
C0585 - Computer Equip | Various Hardware Renewal/Upgrades | 341000 | -4836 | -4836 | 341000 | 572000 | 269000 | 580000 | 150000 | 607000 | 2850328
C0585 - Computer Equip |  | 341000 | -4836 | -4836 | 341000 | 572000 | 269000 | 580000 | 150000 | 607000 | 2850328
C0588 - ERP System | Program - Additional software licenses/Upgrades | 50000 | 0 | 0 | 50000 | 55000 | 55000 | 60000 | 60000 | 65000 | 395000
C0588 - ERP System |  | 50000 | 0 | 0 | 50000 | 55000 | 55000 | 60000 | 60000 | 65000 | 395000
C0589 - Meter to Cash | Other Non-Material Projects | 580000 | 110528 | 110528 | 580000 | 580000 | 620000 | 530000 | 550000 | 500000 | 4161056
C0589 - Meter to Cash |  | 580000 | 110528 | 110528 | 580000 | 580000 | 620000 | 530000 | 550000 | 500000 | 4161056
C0591 - Grounds & Building | Project - Mavis building envelope | 650000 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 1250000
C0591 - Grounds & Building | Project - Mavis Building Generator replacement | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 950000
C0591 - Grounds & Building | Program - Building Upgrades - Mavis | 760000 | 432851 | 429952 | 665000 | 0 | 1200000 | 250000 | 1200000 | 400000 | 5337803
C0591 - Grounds & Building | Program - Building Upgrades - Derry | 245000 | 119869 | 75550 | 500240 | 275000 | 600000 | 1050000 | 675000 | 700000 | 4240659
C0591 - Grounds & Building | Project - Derry HVAC Upgrades | 550000 | 526091 | 506090.59 | 550000 | 500000 | 0 | 0 | 0 | 0 | 2632181.59
C0591 - Grounds & Building | Project - Derry Windows | 0 | 0 | 0 | 0 | 0 | 725000 | 0 | 0 | 0 | 725000
C0591 - Grounds & Building | Project - Derry Renovations | 0 | 0 | 0 | 1364763 | 0 | 0 | 0 | 0 | 0
C0591 - Grounds & Building | Other Non-Material Projects | 650000 | 67595 | 66215 | 0 | 1025000 | 800000 | 1325000 | 1175000 | 1195000 | 6303810
C0591 - Grounds & Building |  | 2855000 | 1146406 | 1077807.59 | 3080003 | 2400000 | 3325000 | 3575000 | 3050000 | 2295000 | 21439453.59
C0595 - Major Tools Constr | Major Tools | 200000 | 89625 | 89006 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 1578631
C0595 - Major Tools Constr |  | 200000 | 89625 | 89006 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 1578631
GENERAL PLANT |  | 6798000 | 1757168 | 1687749.99 | 6096004 | 6672000 | 7580000 | 8411000 | 6752862 | 5869000 | 50259020.99
GROSS CAPITAL EXPENDITURES |  | 68551018.1 | 48167347.58 | 44317605.27 | 67582500.8 | 79840742.5254 | 85411443.322 | 85997443.7978 | 81664304.2248 | 74565442.5896 | 623145712.6096
C0531C - CIAC - Roads |  | -534215 | -100207 | -70207 | -72500 | -1086215 | -906215 | -966215 | -906215 | -666215 | -5308204
C0532C - CIAC - LRT |  | 0 | 0 | 0 | 0 | -1500000 | -3000000 | -3000000 | -3000000 | -1700000 | -12200000
C0541C - CIAC - New Subdivisions (OTC) |  | -1171524.2 | -495495 | -485206.58 | -500000 | -1171524.2 | -1171524.2 | -1171524.2 | -1171524.2 | -1171524.2 | -8509846.78
C0542C - CIAC Ind/Comm Services |  | -3045962.8 | -2884308 | -2545891.69 | -3045963 | -3045962.8 | -3045962.8 | -3045962.8 | -3045962.8 | -3045962.8 | -26751939.49
C0544C - CIAC Residential Service Upgrades |  | -354268.9 | -117702 | -291359.51 | -354269 | -354268.9 | -354268.9 | -354268.9 | -354268.9 | -354268.9 | -2888943.91
C0900C - CIAC -Green Energy-FIT/MicrFIT |  | 0 | -11000 | -11000 | 0 | 0 | 0 | 0 | 0 | 0 | -22000
CUSTOMER CONTRIBUTIONS |  | -5105970.9 | -3608712 | -3403664.78 | -3972732 | -7157970.9 | -8477970.9 | -8537970.9 | -8477970.9 | -6937970.9 | -55680934.18
NET CAPITAL EXPENDITURES FOR DSP (EXCLUDING ALLOCATED SYNERGIES) |  | 63445047.2 | 44558635.58 | 40913940.49 | 63609768.8 | 72682771.6254 | 76933472.422 | 77459472.8978 | 73186333.3248 | 67627471.6896 | 567464778.4296