## I-24-Staff-115-02
Project Name | Year Complete | Forecast Cost ($M) | Actual Cost ($M) | Variance ($M) | Variance Explanation | Variance %
Duart TS M6 Relocation Phase 2 of 2, Kent | 2015 | 2.3 | 3.5462 | 1.2462 | Estimate completed at time of filing were high-level in nature, without having completed engineering, design and customer engagement work | 54.18%
Otonabee TS 128M28 Relocation Phase 1 of 3, Peterborough | 2015 | 2 | 2.4892 | 0.48925 | Estimate completed at time of filing were high-level in nature, without having completed engineering, design and customer engagement work | 24.46%
Timmins Underground Vaults | 2015 | 5.2811 | 5.1167 | -0.1644 | N/A | -3.113%
Brockville 24M2 Phase 3 | 2015 | 2.8119 | 3.1604 | 0.34853 | N/A | 12.39%
Murillo DS F1 Relocation | 2015 | 1.494 | 2.2106 | 0.71654 | Estimate completed at time of filing were high-level in nature, without having completed engineering, design and customer engagement work | 47.96%
Manitouwadge TS 13M2 Rebuild-Phase 1 - Hornepayne to Mill | 2015 | 1.5574 | 2.0546 | 0.49726 | Estimate completed at time of filing were high-level in nature, without having completed engineering, design and customer engagement work | 31.93%
Meaford TS M1 Relocation | 2015 | 2.7564 | 2.0431 | -0.71333 | Estimate completed at time of filing were high-level in nature, without having completed engineering, design and customer engagement work | -25.88%
Minden TS 87M2 Feeder Relocation | 2016 | 6.1333 | 6.24 | 0.10665 | N/A | 1.739%
Manitouwadge TS 13M2 Rebuild - Phase 2 | 2016 | 4.2313 | 4.3261 | 0.094786 | N/A | 2.24%
Havelock TS 57M4 Relocation | 2016 | 3.0783 | 3.2038 | 0.12553 | N/A | 4.078%
Martindale TS 9M5 Relocation Phase 5 of 6, Sudbury | 2017 | 2.1 | 3.2468 | 1.1468 | Estimate completed at time of filing were high-level in nature, without having completed engineering, design and customer engagement work | 54.61%