## I-30-Staff-175-1
In Reference to Exhibit EB-2013-D2-2-3 Ref#D-02 |  |  | Current Project Status
Project Description | Year | Cost Estimate ($M) | Status | Cost ($M) | Cost Variance
Brown Hill TS New Feeder Development, Queensville, East Gwillimbury | 2015 | 3.5 | Completed 2017 | Note 1 | NA
Clark TS M2 Feeder Reinforcement, Ilderton | 2015 | 2.1 | Completed | 1.5263 | Scope was reduced based on more detailed engineering analysis.
Commerce Way TS M3 Feeder Reinforcement, Woodstock Surrounding Area | 2015 | 2.1 | Completed | 2.6393 | More detailed cost estimate was developed.
Courtice DS Upgrades, Courtice, Clarington Township | 2015 | 3 | Completed | 3.8 Note 2 | More detailed cost estimate was developed.
Courtice DS Voltage Conversion, Courtice, Clarington Township | 2015 | 1.8 | Completed
Nobleton DS Upgrade, Nobleton, King Township | 2015 | 3 | Completed 2017 | Note 1 | NA
Owen Sound TS M28 Feeder Reinforcement, Northern Bruce Pennisula | 2015 | 1 | Completed 2017 | Note 1 | NA
Allanburg TS M7 Feeder Reinforcement, Thorold | 2016 | 1 | Need met by another project | N/A | Need met through another project. Tie made to M6 to offload M7
Beckwith DS Upgrades, South of Carleton Place (Mississippi Mills) | 2016 | 2.2 | Complete | 2.7 | More detailed cost estimate was developed.
Brown Hill TS M4 Feeder Reinforcement, Georgina Township | 2016 | 1.9 | Completed 2017 | Note 1 | NA
Massey DS F3 Feeder Reinforcement, North Shore Algoma | 2016 | 1 | Completed | 1.5 | More detailed cost estimate was developed.
Note 1: 2017 actuals not available.
Note 2: Combined project cost for both Courtice DS Upgrades and Courtice DS Voltage Conversion.