## Sheet2
Past Filing (2015-2019) | [5 empty] | Current Project Identification Infromation
Exhibit | Project Description | Year (2013 filing) | Cost $M (2013 filing) | AR Project Description | AR# | Status | Cost ($M) | Cost Variance (short)
EB-2013-D2-2-3 Ref#D-05 | 44kV Extension to Coniston, Sudbury | 2015 | 2.8 | Extend 44 kV Supply to Coniston | 22855 | completed 2017 | 2.8
EB-2013-D2-2-3 Ref#D-05 | Belle River DS Voltage Conversion, Belle River | 2015 | 1.1 | Belle River DS Voltage Conversion | 22732 | completed 2017 | 2.1 | More detailed cost estimate was developed.
EB-2013-D2-2-3 Ref#D-05 | Mattawa Voltage Converson, Mattawa | 2015 | 1 | Mattawa Voltage Conversion | 22566 | completed 2017 | 3 | More detailed cost estimate was developed.
EB-2013-D2-2-3 Ref#D-06 | Allanburg TS M7 Feeder Upgrades, Thorold | 2015 | 1 | #N/A | #N/A | Need met through another project | NA | Need met through another project, M6 tie to offload some M7 load.
EB-2013-D2-2-3 Ref#D-06 | Brant TS M21 to Wolverton DS F1 Tie Line | 2019 | 1.2 | #N/A | #N/A | Need met through another project | NA | Met objective with more cost effective altenative with project cost under $1M.
Life Cycle Optimization not Identified in Plan | Bob-Lo DS Voltage Conversion | NA | NA | Bob-Lo DS Voltage Conversion | 22733 | completed 2017 | 2.4 | NA
Life Cycle Optimization not Identified in Plan | Edgeware TS M3 - Re-establishment | NA | NA | Edgeware TS M3 - Re-establishment | 22675 | completed 2017 | 2.1 | NA
Life Cycle Optimization not Identified in Plan | Port Arthur M6 Resupply of Port Arthur f2 | NA | NA | Bobcaygeon Area Study Implementation | 22304 | completed 2015 | 1.7266 | NA
Life Cycle Optimization not Identified in Plan | Bobcaygeon Area Study Implementation | NA | NA |  |  | completed 2016 | 1.43 | NA