## Appendix 2-AB_Capital Expend
[17 empty] | File Number: |  | 0
Exhibit:
Tab:
Schedule:
Page:
Date:
OEB Appendix 2-AB
Table 2 - Capital Expenditure Summary from Chapter 5 Consolidated Distribution System Plan Filing Requirements
First year of Forecast Period:
CATEGORY
| 2015 |  |  | 2016 |  |  | 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 | 2021 | 2022 | 2023 | 2024
| CIR Filing Plan | Actual | Var | CIR Filing Plan | Actual | Var | CIR Filing Plan | Actual | Var | CIR Filing Plan | Actual | Var | CIR Filing Plan | Bridge | Var | Forecast | Forecast | Forecast | Forecast | Forecast
| $ M |  |  | $ M |  |  | $ M |  |  | $ M |  |  | $ M |  |  | $ M | $ M | $ M | $ M | $ M
System Access | 86131706.7602 | 58347919.4375 | -32.26% | 95344705.7832 | 78961620.7941 | -17.18% | 104883670.31 | 65496506.413 | -37.55% | 95797930.5106 | 87994382.3841 | -8.146% | 92326016.9104 | 112128602.1622 | 21.45% | 91839851.1733 | 93296875.1985 | 93904018.2276 | 105984256.3474 | 116357770.7152
System Renewal | 251740122.6877 | 304125236.243 | 20.81% | 239640343.6343 | 266097407.2062 | 11.04% | 256244232.0962 | 250265299.2478 | -2.333% | 275907509.3209 | 245473627.6863 | -11.03% | 287274173.0464 | 244220307.7357 | -14.99% | 306565761.191 | 325696968.5182 | 323148393.0752 | 338954230.8342 | 325530649.1654
System Service | 76451078.3456 | 37918017.7495 | -50.4% | 70740174.6457 | 53302993.5396 | -24.65% | 65075074.1024 | 72434896.2791 | 11.31% | 52609367.6382 | 31035164.4296 | -41.01% | 80158251.3055 | 41545528.3413 | -48.17% | 34208033.7955 | 60090728.7388 | 71271494.4824 | 33586716.8262 | 38524677.4384
General Plant | 104626071.2352 | 79434269.35 | -24.08% | 101501568.6518 | 109543242.44 | 7.923% | 30304688.3242 | 98911028.76 | 226.4% | 34212203.09 | 58380356.19 | 70.64% | 30303328.1921 | 46425000 | 53.2% | 78831042.3889 | 93705904.0223 | 88968506.3514 | 77668265.3319 | 85221535.2478
Other | 12182594.3366 | 11594265.48 | -4.829% | 11561958.8618 | 3713718.9824 | -67.88% | 10849394.8767 | 10702693.5508 | -1.352% | 11520004.8375 | 12727486 | 10.48% | 12098164.7245 | -1340116.0368 | -111.1% | 6962887.6346 | 9037037.9117 | 9823794.8632 | 9526717.7063 | 8730933.3946
TOTAL EXPENDITURE | 531131573.3653 | 491419708.26 | -7.477% | 518788751.5767 | 511618982.9624 | -1.382% | 467357059.7095 | 497810424.2508 | 6.516% | 470047015.3971 | 435611016.69 | -7.326% | 502159934.1789 | 442979322.2024 | -11.79% | 518407576.1832 | 581827514.3895 | 587116206.9998 | 565720187.0462 | 574365565.9614
Capital Contributions Paid | -6600000 | -3958976.92 | -40.02% | -29128423.7171 | -16632849.13 | -42.9% | -48206857.4401 | -37360222.38 | -22.5% | -32050033.6852 | -12431310.63 | -61.21% | -30548190.7107 | -18500000 | -39.44% | -12840616.8 | -16128239.184 | -15236315.0841 | -16779820.047 | -14579956.9597
Net Capital Expenditures | 524531573.3653 | 487460731.34 | -7.067% | 489660327.8596 | 494986133.8324 | 1.088% | 419150202.2693 | 460450201.8708 | 9.853% | 437996981.712 | 423179706.06 | -3.383% | 471611743.4682 | 424479322.2024 | -9.994% | 505566959.3832 | 565699275.2056 | 571879891.9157 | 548940366.9991 | 559785609.0017
System O&M | 128800000 | 116100000 | -9.86% |  | 126500000 | -- |  | 126300000 | -- |  | 139600000 | -- |  | 131000000 | -- | 130400000
Note: Variances due to rounding may exist
Notes to the Table:
1. Historical “previous plan” data is not required unless a plan has previously been filed. However, use the last Board-approved, at least on a Total (Capital) Expenditure basis for the last cost of service rebasing year, and the applicant should include their planned budget in each subsequent historical year up to and including the Bridge Year.
2. Indicate the number of months of 'actual' data included in the last year of the Historical Period (normally a 'bridge' year): | [8 empty] | 12
Explanatory Notes on Variances (complete only if applicable)
Notes on shifts in forecast vs. historical budgets by category
Refer to respective category sections for discussion on historical vs forecast shifts: Section E5 for System Access, Section E6 for System Renewal, Section E7 for System Service and Section E8 for General Plant. For variance explanations as a result of updated financial information, refer to Exhibit U, Tab 2, Schedule 2.
Notes on year over year Plan vs. Actual variances for Total Expenditures
Refer to Section E4 on Variance analysis for between Plan vs Actuals. For variance explanations as a result of updated financial information, refer to Exhibit U, Tab 2, Schedule 2.
Notes on Plan vs. Actual variance trends for individual expenditure categories
Refer to Section E4 on Variance analysis for between Plan vs Actuals. For variance explanations as a result of updated financial information, refer to Exhibit U, Tab 2, Schedule 2.