## U-AMPCO-130 App A
U-AMPCO-130 Appendix A (Updated 2B-SEC-51) |  | LEGEND |  | EB-2014-0116 Application Numbers Verified
EB-2014-0116 Application Numbers Unverified & Corrected Accordingly within this IR Response
Data Populated
|  | Program/Assets | EB-2014-0116 Application |  |  |  |  | Actual/Forecast |  |  |  |  | EB-2018-0105 Proposal
|  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
E6.1 | Underground Circuit Renewal
|  | Underground Switches | 84 | 71 | 74 | 88 | 88 | 47 | 79 | 87 | 39 | 28 | 49 | 45 | 45 | 46 | 46
|  | Underground Transformer | 348 | 291 | 305 | 362 | 361 | 105 | 710 | 740 | 251 | 264 | 407 | 380 | 380 | 387 | 387
|  | Underground Cable (circuit km) | 150 | 126 | 132 | 156 | 156 | 105 | 442 | 173 | 156 | 131 | 103 | 96 | 96 | 98 | 98
E6.2 | Paper-Insulated Lead-Covered (PILC) Piece-outs and Leakers
|  | PILC Cable (km) | 5.39 | 3.66 | 2.59 | 2.66 | 0.7 | 1.8 | 2.3 | 2 | 0 | 0 | 2.9 | 5.1 | 5.3 | 7.1 | 7.1
E6.3 | Underground Legacy Infrastructure
|  | Sachsenwerk Switch and Fuse Units | 6 | 12 | 12 | 10 | 0 | 22 | 2 | 6 | 3 | 10 | Remaining locations to be addressed through Underground System Renewal
|  | Powerlite Switches | 0 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 1 | 3
|  | Single Phase Submersible Transformers | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 16
|  | Step Transformers | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | 1 | 3
|  | Transclosures | 6 | 9 | 9 | 9 | 9 | 0 | 9 | 6 | 1 | 20
|  | SF Switches | 2 | 1 | 2 | 1 | 0 | 2 | 0 | 1 | 0 | 2
|  | Cable Chamber Covers | 25 | 375 | 375 | 375 | 350 | 0 | 0 | 9 | 79 | 79 | 200 | 200 | 200 | 200 | 200
E6.4 | Overhead Circuit Renewal
|  | Poles | 3332 | 1735 | 1900 | 1934 | 2313 | 3656 | 2692 | 1513 | 1510 | 1330 | 2230 | 2230 | 2220 | 2400 | 2450
|  | Overhead Switches | 294 | 160 | 166 | 154 | 207 | 192 | 167 | 120 | 90 | 13 | 130 | 130 | 130 | 160 | 160
|  | Overhead Transformers | 972 | 511 | 478 | 598 | 673 | 940 | 769 | 441 | 412 | 310 | 1300 | 1300 | 1300 | 1400 | 1400
E6.5 | Overhead Infrastructure Relocation
|  | Poles |  | 32 |  | 27 | 8 | 81 | 0 | 7 | 11 | 8 | Remaining locations to be addressed through Overhead System Renewal
|  | OH Conductor (mts) |  | 5656 |  |  | 3400 | 12432 | 0 | 455 | 244 | 0
|  | OH Switches |  | 10 |  | 6 | 6 | 83 | 0 | 10 | 1 | 9
|  | OH Transformers |  | 22 |  | 1 |  | 43 | 0 | 3 | 1 | 4
|  | Underground Cable Chamber | 2 |  | 18 |  |  | 0 | 5 | 3 | 5 | 0
|  | Underground Duct (mts) | 110 |  | 3000 | 165 | 200 | 144 | 251 | 524 | 1541 | 0
E6.6 | Rear Lot Conversion
|  | Pole | 63 | 218 | 110 | 31 | 175 | See Notes for 2B-SEC-51. 2,090 customer conversions |  |  | 173 customer conversions | 84 customer conversions | See Notes for 2B-SEC-51. 2,350 customer conversions.
|  | Transformer | 33 | 62 | 48 | 30 | 40
|  | Manual Switch | 16 | 14 | 7 | 5 | 8
|  | Fuse | 13 | 15 | 16 | 20 | 19
|  | Riser | 13 | 5 | 6 | 5 | 22
|  | Conductor (m) | 1910 | 9314 | 4632 | 1796 | 7886
|  | Cable (m) | 4583 | 4305 | 5476 | 5598 | 1566
E6.7 | Box Construction Conversion
|  | OH Transformer | 201 | 381 | 86 | 175 | 77 | 2422 Poles |  |  | 586 poles | 1060 poles | 4,100 poles
|  | OH Switch | 162 | 301 | 70 | 176 | 85
|  | Poles | 407 | 780 | 277 | 255 | 117
|  | UG Switch | 0 | 0 | 0 | 6 | 0
|  | UG Transformer | 21 | 27 | 9 | 52 | 17
|  | OH Conductor (km) | 25.5 | 46.2 | 11.4 | 24.4 | 11.5
|  | UG Cable (km) | 6 | 10.4 | 1.5 | 5.8 | 1.4
E6.8 | SCADA-MATE R1 Replacement
|  | R1 Switch | 72 | 67 | 57 |  |  | 40 | 18 | 31 | 87 | 31 | 0 | 0 | 0 | 0 | 0
|  | RTU | 52 | 49 | 14 |  |  | 76 | 19 | 47 | 17 | 15 | 0 | 0 | 0 | 0 | 0
E6.9 | Network Vault Rebuild Program
|  | Vaults | 6 | 9 | 9 | 9 | 9 | 34 |  |  | 11 | 18 | 33
|  | Roofs | 4 | 2 | 2 | 3 | 4
|  | UG Network Units | 11 | 18 | 17 | 20 | 20 | See Network Unit (Transformer and Protector) |  |  |  |  | 0 | 0 | 0 | 0 | 0
E6.10 | Network Unit Renewal Program
|  | Network Unit (Transformer and Protector) | 40 | 50 | 50 | 50 | 50 | 17 | 25 | 21 | 11 | 18 | 40 | 40 | 40 | 40 | 40
E6.11 | Legacy Network Equipment Replacement (ATS & RPB)
|  | ATS | 3 | 2 | 3 | 2 | 3 | 3 | 3 | 9 | 18 | 7 | 5 | 5 | 3 | 0 | 0
|  | RPB | 0 | 2 | 2 | 2 | 2
E6.12 | Network Circuit Reconfiguration
|  | UG Transformers (600 V Network) |  | 8 |  |  |  | 0 | 0 | 2 | 1 | 2 | 5
E6.13 | Stations Switchgear Renewal
|  | TS Switchgear | 0 | 3 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 3 | 1
|  | MS Switchgear | 3 | 4 | 2 | 1 | 1 | 2 | 0 | 4 | 3 | 2 | 3 | 3 | 2 | 2 | 2
E6.14 | Stations Power Transformer Renewal
|  | Power Transformers | 5 | 19 |  |  |  | 2 | 0 | 6 | 3 | 5 | 2 | 2 | 2 | 2 | 2
E6.15 | Stations Circuit Breaker Renewal
|  | KSO Oil Circuit Breaker | 10 | 6 | 6 | 7 | 6 | 4 | 2 | 5 | 8 | 7 | 1 | 1 | 2 | 2 | 3
E6.16 | Stations Control & Monitoring
|  | Etobicoke RTU Replacement (MOSCAD) | 2 | 5 | 5 | 5 | 5 | 1 | 5 | 7 | 6 | 5 | 3 | 3 | 3 | 3 | 3
|  | Scarborough SCADA Installation | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2
|  | Downtown RTU Replacement (DACSCAN) | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 1 | 3 | 3 | 3 | 4
|  | Pilot-wire Relay Upgrade | 0 | 6 | 10 | 12 | 12 | 0 | 0 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 1
E6.17 | Stations Ancillary Systems
|  | Air Compressors | 4 |  |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | Station Service Power Supply |  | 1 |  |  |  | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2 | 2 | 2
|  | Fire Alarm System |  |  | 2 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 5
|  | Fire Barrier/Suppression System | 1 | 2 |  |  |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
E6.18 | Stations Buildings
E6.19 | Stations DC Battery Replacement
|  | Battery System 50 Ah | 2 | 8 | 5 | 6 | 5 | 3 | 9 | 13 | 13 | 10 | 11 | 13 | 13 | 15 | 15
|  | Battery System 80 Ah |  |  |  |  | 1
|  | Battery System 100 Ah | 3 | 8 | 7 | 5 | 7
|  | Battery System 200 Ah |  |  | 1
|  | Battery System 300 Ah |  | 1 | 2 | 2
|  | Battery System 400 Ah | 1 | 1 |  |  | 2
E6.20 | Reactive Capital
|  | Smart Meteres | 3930 | 3930 | 3930 | 3930 | 3930 | 3247 | 3004 | 4058 | 5350 | 3930 | 5585 | 5685 | 5785 | 5885 | 5985
|  | RIMS | 88 | 88 | 88 | 88 | 88 | 108 | 66 | 53 | 178 | 88
|  | Quadlogic | 1057 | 1157 | 1257 | 1357 | 1457 | 1004 | 2233 | 1117 | 1172 | 1457
|  | Primary Metering Units | 8 | 10 | 10 | 10 | 10 | 3 | 23 | 6 | 8 | 10
E6.21 | Worst Performing Feeder
E6.22 | Distribution System Communication Infrastructure
|  | IP Data Network Retro-fit (SONET Multiplexers to be augmented with CWDM Multiplexers) (Number of sites) | 34 | 11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 45
|  | IP Data Network Installation (Without SONET technology Present) (Number of sites) |  | 34 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Fiber-Optic Ring Fiber replacement in Toronto (km) | 72 |  |  |  |  | 0 | 21 | 50 | 8 | 0 | 2 | 2 | 2 | 2 | 2
|  | Fiber-Optic Ring Fiber replacement in Scarborough (km) | 45 |  |  |  |  | 54 | 31 | 0 | 10 | 0
|  | Fiber-Optic Ring Expansion in Toronto (km) |  | 54 | 48 |  |  | 0 | 0 | 0 | 18 | 0
|  | Fiber-Optic Ring Expansion in Scarborough (km) |  | 64 | 72 |  |  | 0 | 0 | 0 | 2 | 1
|  | New Wireless SCADA SD9 High-Site Deployment (# of Sites) | 3 | 1 |  |  |  | 0 | 0 | 0 | 0 | 6 | 12
|  | Wireless SCADA GE Transit to GE SD9 Endpoint Radio Equipment Migration (# of Radios) |  | 194 | 289 |  |  | 0 | 0 | 0 | 0 | 270 | 885
Please completed the shaded era
Note on B13: Author: Why did we group the 5 year figures? From Filing Why is there a decrease in 18/19 compared to forecast?