## Table 17
Table 17: Programs with Applicable Variance Explanations
[5 empty] | 2017 Capital Expenditures |  |  | 2017 In Service Capital Additions ($ Millions) |  |  | Units
($ Millions)
ISD |  |  |  | Description | Approved | Actuals | Variance | Approved | Actuals | Variance | Reportable Unit | Approved | Actuals | Variance | Variance Explanations
Sustaining Capital
Transmission Stations
Tx Transformers Demand and Spares
|  |  | Other | Tx Transformers Demand and Spares | 4.2 | 2.4 | -1.8 | 3.7 | 2.1 | -1.5 | NA | NA | NA | NA | Emergent Needs
|  |  | S52 | Minor Demand Capital | 4.6 | 5.7 | 1.1 | 4.7 | 5 | 0.3 | NA | NA | NA | NA | No material variance
|  |  | S53 | Spare Transformer Purchase | 10 | 6.5 | -3.6 | 11.2 | 7.9 | -3.3 | Number of Transformers | 5 | 2 | -60% | Emergent Needs
Site Facilities and Infrastructure
|  |  | S61 | Station Building Infrastructure | 12 | 10.8 | -1.2 | 11.2 | 9.4 | -1.8 | NA | NA | NA | NA | Preliminary Project Definition
Transmission Lines
Overhead Lines Refurbishment Projects, Component Replacement Programs and Secondary Land Use Projects
|  |  | S75 | Wood Pole Replacements | 38.8 | 41.2 | 2.4 | 49.4 | 53.5 | 4 | Number of Structures | 935 | 966 | 3% | Preliminary Project Definition
|  |  | S76 | Steel Structure Coating | 39 | 42.1 | 3.1 | 30.8 | 31.5 | 0.7 | Number of Structures | 1145 | 725 | -37% | Emergent Needs
|  |  | S77 | Steel Structure Foundation Refurbishments | 6.6 | 7.5 | 0.9 | 7.2 | 7.2 | 0 | Number of structures | 590 | 525 | -11% | Emergent Needs
|  |  | S78 | Shieldwire Replacements | 4.8 | 5.4 | 0.7 | 5.3 | 5.6 | 0.3 | Number of KM of shieldwire replaced | 105 | 105 | 0% | No material variance
|  |  | S79 | Critical Insulator Replacements | 55.1 | 49.8 | -5.3 | 49.4 | 46.6 | -2.8 | Number of Circuit Structures | 3190 | 3456 | 8% | Project Delivery Issues
|  |  | S80 | Transmission Lines Emergency Restoration | 7.6 | 8.3 | 0.7 | 8 | 8 | -0.1 | NA | NA | NA | NA | No material variance
Capital Common Corporate Costs and Othe
r Costs
Transport and Work & Service Equipment
|  |  | CC2 | Transport & Work Equipment | 14.5 | 13.9 | -0.6 | 14.3 | 13.9 | -0.4 | NA | NA | NA | NA | No material variance
|  |  | CC3 | Service Equipment | 3 | 2.9 | -0.1 | 3.3 | 2.9 | -0.4 | NA | NA | NA | NA | No material variance
Information Technology (including Cornerstone)
|  |  | IT1 | Hardware/Software Refresh and Maintenance | 6.7 | 6.2 | -0.5 | 4.5 | 4.5 | 0 | NA | NA | NA | NA | No material variance

## Table 18
Table 18: Projects with Applicable Variance Explanations
[5 empty] | 2017 Capital Expenditures |  |  | 2017 In Service Capital Additions 2017 ($ Millions) |  |  | Project Status
($ Millions)
ISD |  |  |  | Project Description | DRO Forecast | Actuals | Variance | DRO Forecast | Actuals | Variance | DRO Forecast In Service Date | DRO Forecast Status | Actual/ Bridge In Service Date | Status | Variance | Variance Explanations
(in Quarters)
Transmission Stations
Power Transformers
|  |  | Other | Power Transformer Replacements - Lakehead TS T7 & T8 | 1.1 | 1.3 | 0.2 | 9.7 | 9.9 | 0.2 | Q3 2017 | Execution | Q3 2017 | Execution | - | No material variance
|  |  | Other | Power Transformer Replacements - Dymond TS T3 & T4 | 2.8 | 2.4 | -0.4 | 3.3 | 2.6 | -0.6 | Q4 2017 | Execution | Q4 2017 | Execution | - | Project Delivery Issues
|  |  | Other | Power Transformer Replacements - Kirkland TS T12 & T13 | 4.6 | 2.9 | -1.7 | 8.9 | 7.1 | -1.8 | Q4 2017 | Execution | Q4 2017 | Execution | - | Project Delivery Issues
Integrated Station Investment
|  |  | Other | Hinchinbrooke SS BULK | 2.7 | 2.5 | -0.2 | 11.7 | 14.5 | 2.7 | Q4 2018 | Execution | Q4 2018 | Execution | - | Preliminary Project Definition
|  |  | Other | Stewartville TS – ISCR | 5.6 | 5.4 | -0.2 | 6.6 | 4 | -2.6 | Q3 2019 | Execution | Q3 2019 | Execution | - | Project Delivery Issues
|  |  | Other | Sidney TS – ISCR | 1.8 | 1.5 | -0.3 | 5.7 | 3.3 | -2.4 | Q4 2017 | Execution | Q2 2018 | Execution | 2 | Project Delivery Issues
|  |  | Other | Lauzon TS T5/T6; PCT & Component Replacement | 3 | 3.2 | 0.2 | 4.7 | 4.9 | 0.2 | Q4 2017 | Execution | Q2 2018 | Execution | 2 | Project Delivery Issues
|  |  | Other | OverBrook TS, EOL Transformer Asset Rep | 9.3 | 9.5 | 0.3 | 29 | 29.3 | 0.3 | Q4 2017 | Execution | Q4 2017 | Execution | - | No material variance
|  |  | Other | Scarboro TS ISCR | 5.6 | 4.1 | -1.4 | 15.1 | 13.6 | -1.4 | Q4 2017 | Execution | Q4 2017 | Execution | - | No material variance
|  |  | Other | Integrated DESN Replacement - Goderich TS | 2.1 | 2.3 | 0.2 | 13.6 | 13.8 | 0.2 | Q2 2017 | Execution | Q4 2017 | Execution | 2 | Project Delivery Issues
|  |  | Other | Nepean TS T3/T4 | 0.6 | 0.6 | 0 | 7.3 | 7.2 | -0.1 | Q1 2017 | Execution | Q1 2017 | Execution | - | N/A
|  |  | Other | CMS Station Service and Yard Supply Repl | 7.9 | 6.9 | -1 | 8.3 | 7.1 | -1.2 | Q4 2017 | Execution | Q4 2017 | Execution | - | Project Delivery Issues
|  |  | Other | Richview TS T5/T6; Component Replacement | 1.4 | 1.5 | 0.2 | 4 | 4.1 | 0.2 | Q4 2017 | Execution | Q4 2017 | Execution | - | No material variance
|  |  | S02 | Air Blast Circuit Breaker Replacement - Beck #2 TS | 20.9 | 22.7 | 1.8 | 18.9 | 17.8 | -1.1 | Q4 2021 | Execution | Q4 2022 | Execution | 4 | Project Delivery Issues
|  |  | S03 | Air Blast Circuit Breaker Replacement - Bruce A TS | 15.6 | 17.3 | 1.6 | 4.5 | 4.8 | 0.3 | Q4 2019 | Execution | Q4 2020 | Execution | 4 | Project Delivery Issues
|  |  | S07 | Air Blast Circuit Breaker Replacement - Richview TS | 11.7 | 14 | 2.3 | 26.7 | 26.5 | -0.2 | Q4 2019 | Execution | Q4 2019 | Execution | - | No material variance
|  |  | S08 | Integrated Station Component Replacements - Beach TS | 15.5 | 16.4 | 0.9 | 20.2 | 20.1 | -0.1 | Q4 2019 | Execution | Q4 2019 | Execution | - | No material variance
|  |  | S12 | Integrated DESN Replacement - Espanola TS | 3.1 | 3.3 | 0.3 | 3.5 | 3.8 | 0.3 | Q2 2017 | Execution | Q2 2017 | Execution | - | No material variance
|  |  | S19 | Integrated Station Component Replacements - Allanburg TS | 10.6 | 8.6 | -2 | 11.6 | 8.4 | -3.2 | Q4 2018 | Execution | Q4 2018 | Execution | - | Accelerated Investments
|  |  | S20 | Integrated DESN Investments - Aylmer TS | 2.3 | 2.3 | 0 | 22.3 | 22.4 | 0 | Q2 2017 | Complete | Q2 2017 | Complete | - | No material variance
|  |  | S21 | Station Re-Investment - Barrett Chute SS | 11.4 | 12.1 | 0.7 | 3.1 | 3.6 | 0.5 | Q4 2018 | Execution | Q4 2018 | Execution | - | Project Delivery Issues
|  |  | S22 | Station Re-Investment - Birch TS | 14 | 15.1 | 1.1 | 4.9 | 5.6 | 0.7 | Q3 2019 | Execution | Q3 2019 | Execution | - | Accelerated Investments
|  |  | S25 | Buchanan TS BULK | 6.4 | 5.5 | -0.9 | 12.8 | 11.5 | -1.3 | Q4 2017 | Execution | Q4 2017 | Execution | - | Preliminary Project Definition
|  |  | S28 | Station Re-Investment - Crawford TS | 5.7 | 5.2 | -0.6 | 10.1 | 9 | -1 | Q4 2017 | Execution | Q4 2017 | Execution | - | Project Delivery Issues
|  |  | S29 | Station Re-Investment - DeCew Falls SS | 3.7 | 3.7 | 0 | 13.8 | 13.8 | 0 | Q2 2017 | Execution | Q2 2017 | Execution | - | No material variance
|  |  | S32 | Station Re-Investment - Frontenac TS | 3.6 | 3.5 | -0.1 | 3.9 | 4 | 0.2 | Q2 2018 | Execution | Q2 2018 | Execution | - | No material variance
|  |  | S33 | Station Re-Investment - Hanmer TS | 17.7 | 19.5 | 1.8 | 29.4 | 30.2 | 0.8 | Q3 2019 | Execution | Q2 2020 | Execution | 3 | Preliminary Project Definition
|  |  | S34 | Integrated Station Component Replacements - Hawthorne TS | 7.3 | 7.9 | 0.6 | 4.8 | 5.9 | 1.1 | Q4 2019 | Execution | Q4 2019 | Execution | - | Project Delivery Issues
|  |  | S36 | Station Re-Investment - Leaside TS | 12.1 | 14.1 | 1.9 | 23.4 | 20.8 | -2.5 | Q4 2019 | Execution | Q4 2019 | Execution | - | Preliminary Project Definition
|  |  | S40 | Station Re-Investment - Martindale TS | 18.1 | 19.3 | 1.2 | 21.1 | 20.8 | -0.3 | Q4 2021 | Execution | Q4 2021 | Execution | - | No material variance
|  |  | S43 | Integrated DESN Replacement – National Research Council TS | 8.3 | 7.6 | -0.8 | 26.3 | 0 | -26.3 | Q2 2018 | Execution | Q2 2019 | Execution | 4 | Project Delivery Issues
|  |  | S45 | Richview TS | 6.3 | 7.3 | 1 | 14.9 | 20.2 | 5.3 | Q2 2018 | Execution | Q2 2018 | Execution | - | Accelerated Investments
|  |  | S47 | Station Re-Investment - St. Isidore TS | 9.5 | 8.9 | -0.7 | 27.8 | 0 | -27.8 | Q4 2017 | Execution | Q2 2018 | Execution | 2 | Project Delivery Issues
|  |  | S50 | Integrated DESN Investments - Strathroy TS | 5.9 | 6.1 | 0.2 | 10.4 | 18.1 | 7.7 | Q4 2017 | Execution | Q4 2017 | Execution | - | Emergent Needs
Transmission Lines
Overhead Lines Refurbishment Projects, Component Replacement Programs and Secondary Land Use Projects
|  |  | Other | H24C - Line Refurbishment | 4.2 | 3.9 | -0.2 | 9.3 | 9.1 | -0.2 | Q3 2017 | Execution | Q3 2017 | Execution | - | No material variance
|  |  | S62 | Line Refurbishment - C22J/C24Z/C21J/C23Z | 12.5 | 8.4 | -4.1 | 18.6 | 14.5 | -4.1 | Q4 2017 | Execution | Q4 2017 | Execution | - | Preliminary Project Definition
|  |  | S63 | Line Refurbishment - D2L - Dymond TS x Upper Notch Jct and Martin River Jct x Crystal Falls SS | 9.8 | 10.5 | 0.7 | 14.4 | 16.4 | 2 | Q4 2018 | Execution | Q4 2018 | Execution | - | Project Delivery Issues
Inter Area Network Transfer Capability
|  |  | D01 | Clarington TS: Build new 500/230kV Station | 29.9 | 29.7 | -0.1 | 0 | 15.2 | 15.2 | Q2 2018 | Execution | Q2 2018 | Execution | - | Accelerated Investments
Local Area Supply Adequacy
|  |  | D06 | M20/21D Install 230 kV In-Line Switches | 2.5 | 2.5 | 0.1 | 4.3 | 4.4 | 0.1 | Q4 2017 | Execution | Q4 2017 | Execution | - | No material variance
|  |  | D07 | York Region – Increase Transmission Capability for B82V/B83V Circuits | 19.2 | 19.5 | 0.4 | 34.2 | 34.5 | 0.3 | Q4 2017 | Execution | Q4 2017 | Execution | - | No material variance
|  |  | D08 | Hawthorne TS: Replace two existing Transformers | 10.5 | 10.7 | 0.2 | 7.5 | 7.5 | 0 | Q2 2020 | Execution | Q2 2021 | Execution | 4 | Project Delivery Issues
|  |  | Other | Toronto Area Station Upgrades for Short Circuit Capability: Manby TS Equipment Uprate | 0.8 | 0.7 | 0 | 5.4 | 5.4 | 0 | Q1 2017 | Execution | Q1 2017 | Execution | - | No material variance
Load Customer Connection
|  |  | D14 | Supply to Essex County Transmission Reinforcement | 31.9 | 38.3 | 6.5 | 0 | 43.7 | 43.7 | Q4 2018 | Execution | Q4 2018 | Execution | - | Accelerated Investments
Risk Mitigation
|  |  | D24 | Nanticoke TS New 600V Station Service S | 6.9 | 6.3 | -0.6 | 7.3 | 6.6 | -0.7 | Q4 2017 | Execution | Q3 2018 | Execution | 3 | Preliminary Project Definition
Information Technology (including Cornerstone)
|  | Information Technology (including Cornerstone) | IT3 | Work Management & Mobility | 4.5 | 4.2 | -0.3 | 19.5 | 19.4 | -0.1 | Q3 2017 | Complete | Q2 2017 | Complete | -1 | No material variance
Facilities & Real Estate
|  | Facilities & Real Estate | CC1 | Real Estate Field Facilities Capital | 7 | 5 | -2 | 3.3 | 4.6 | 1.3 | Q4 2020 | Planning | Q4 2020 | Execution | - | Project Delivery Issues

## Table 38
Table 38: Programs with Applicable Variance Explanations
[5 empty] | 2018 Capital Expenditures |  |  | 2018 Capital In Service Additions ($ Millions) |  |  | Units
ISD |  |  |  | Description | Approved | Actuals | Variance | Approved | Actuals | Variance | Reportable Unit | Approved | Actuals | Variance | Variance Explanations
Sustaining Capital
Transmission Stations
Circuit Breakers
|  |  | Other | Circuit Breakers | 3 | 0.1 | -2.9 | 5.2 | 0 | -5.2 | Number of Breakers | - | - | 0% | Project Delivery Issues
Tx Transformers Demand and Spares
|  |  | S51 | Demand Capital – Power Transformers | 8.2 | 2.8 | -5.3 | 10.7 | 0.9 | -9.8 | Number of Transformers | 4 | 0 | -100% | Preliminary Project Definition
|  |  | S52 | Minor Demand Capital | 4.1 | 9.6 | 5.5 | 4 | 7.3 | 3.3 | Number of Instrument Transformers | - | 18 | 100% | Emergent Needs
|  |  | S53 | Spare Transformer Purchase | 23.2 | 24.5 | 1.3 | 23 | 26.4 | 3.3 | Number of Transformers | 5 | 13 | 160% | Emergent Needs
|  |  | Other | Demand Capital - Equipment Failure | - | 11.3 | 11.3 | 0.2 | 9 | 8.8 | Number of Transformers | - | 4 | 100% | Emergent Needs
Protection and Automation
|  |  | S58 | PSIT Cyber Equipment EOL | 5.9 | 0.6 | -5.3 | 7.8 | - | -7.8 | N/A | - | - | 0% | Project Delivery Issues
Site Facilities and Infrastructure
|  |  | S61 | Station Building Infrastructure | 10 | 16.4 | 6.4 | 7.8 | 17.2 | 9.4 | N/A | - | - | 0% | Emergent Needs
Transmission Lines
Overhead Lines Refurbishment Projects, Component Replacement Programs and Secondary Land Use Projects
|  |  | S75 | Wood Pole Replacements | 33.9 | 35.3 | 1.3 | 33.3 | 33.2 | -0.1 | Number of Structures | 850 | 735 | -14% | No material variances
|  |  | S76 | Steel Structure Coating | 26.2 | 37.7 | 11.5 | 32.6 | 39.9 | 7.4 | Number of Structures | 1600 | 1050 | -34% | Project Delivery Issues
|  |  | S77 | Steel Structure Foundation Refurbishments | 8.3 | 5.8 | -2.4 | 7.1 | 5.5 | -1.6 | Number of Structures | 700 | 800 | 14% | Project Delivery Issues
|  |  | S78a23 | Shieldwire Replacements | 4.9 | 0.7 | -4.2 | 3 | 0 | -3 | Number of Kilometers | 110 | 209 | 90% | Project Delivery Issues
|  |  | S78b23 | Shieldwire Replacements | 4.9 | 8.6 | 3.6 | 7.5 | 11.3 | 3.9 | Number of Kilometers | 110 | - | -100% | Project Delivery Issues
|  |  | S79a23 | Critical Insulator Replacements | 31.6 | 29.7 | -1.8 | 35.5 | 27.5 | -8 | Number of Circuits | 1850 | 1998 | 8% | Project Delivery Issues
|  |  | S79b23 | Critical Insulator Replacements | - | 0.3 | 0.3 | - | 0.3 | 0.3 | Number of Circuits | - | - | 0% | No material variances
|  |  | S79c23 | Critical Insulator Replacements | 31.6 | 35.8 | 4.2 | 30.1 | 30.1 | 2.8 | Number of Circuits | 3700 | 3905 | 6% | No material variances
|  |  | S80 | Transmission Lines Emergency Restoration | 8.7 | 9.7 | 0.9 | 10.2 | 10.9 | 0.7 | Number of Work orders | - | - | 0% | No material variances
|  |  | Other | O/H Line Refurbishment and Component Replacement | 2 | 3.4 | 1.3 | 1.4 | 3.4 | 2 | Number of Bridges | 9 | 10 | 11% | Project Delivery Issues
|  |  | Other | Transmission Lines Re-Investment | 5 | 3.7 | -1.3 | 3.9 | 3.5 | -0.4 | N/A | - | - | 0% | No material variances
Capital Common Corporate Costs and Other Costs
Transport and Work & Service Equipment
|  |  | CC2 | Transport and Work Equipment | 14.1 | 7.2 | -7 | 14.3 | 7.2 | -7.2 | N/A | 677 | 503 | -26% | Preliminary Project Definition
Information Technology (including Cornerstone)
|  |  | IT1 | Hardware/Software Refresh and Maintenance | 7.3 | 4 | -3.2 | 10.2 | 5.1 | -5.1 | N/A | - | - | 0% | Preliminary Project Definition
|  |  | IT2 | MFA Servers and Storage | 1.8 | 3.6 | 1.8 | 1.8 | 3.6 | 1.8 | N/A | - | - | 0% | Emergent Needs
|  |  | Other | MFA Client Tech & Periph Refresh | 1 | 3.2 | 2.2 | 1 | 3.2 | 2.2 | N/A | - | - | 0% | Emergent Needs
Facilities & Real Estate
|  |  | CC1 | Real Estate Field Facilities Capital | 19.3 | 5.4 | -14 | 21.1 | 5.3 | -15.7 | N/A | - | - | 0% | Preliminary Project Definition
|  |  | Other | Station Civil Infrastructure | 2 | 1.6 | -0.4 | 3.7 | 0 | -3.7 | Number of Stations | - | - | 0% | Project Delivery Issues
23 Multiple line items for S78 and S79 as there are some material variances at program level