## I-12-AMPCO-38
ISD List of Material Capital Investments
(Net $ Millions)
Table 5 - System Access - Material Capital Investments Proposed
|  | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Forecast
ISD | Investment Name | 2015 | 2015 | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019
SA-01 | Connect New IAMGOLD Mine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0
SA-02 | Horner TS: Build a Second 230/27.6kV Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 2
SA-03 | Halton TS: Build a Second 230/27.6kV Station | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.4
SA-04 | Connect Metrolinx Traction Substations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4
SA-05 | Future Transmission Load Connection Plans | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
SA-06 | Protection and Control Modifications for Distributed Generation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SA-07 | Secondary Land Use Transmission Asset Modifications | 0.1 | 0.4 | 1.2 | 0.5 | -0.7 | -1 | 4.3 | 5 | 2.9
Table 6 - System Renewal - Material Capital Investments
|  | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Forecast
ISD | Investment Name | 2015 | 2015 | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019
SR-01 | Air Blast Circuit Breaker Replacement Projects | 66.8 | 61 | 89.2 | 58.9 | 88 | 79.6 | 79 | 61.6 | 88.5
SR-02 | Station Reinvestment Projects | 6.7 | 45.7 | 37.8 | 38.6 | 67.6 | 64.4 | 70 | 63.1 | 104.8
SR-03 | Bulk Station Transformer Replacement Projects | -0.2 | 0 | 0.2 | 0.2 | 1.2 | 1.3 | 0.9 | 7.8 | 9.9
SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | 0 | 0 | 0 | 0 | 0.5 | 0.2 | 1.8 | 3.3 | 2.4
SR-05 | Load Station Transformer Replacement Projects | 10.1 | 5 | 8.8 | 0.9 | 12.2 | 12 | 15 | 26.8 | 40.3
SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | 0.3 | 1.9 | 3.7 | 9.7 | 1.6 | 1.7 | 16 | 15.7 | 11.7
SR-07 | Protection and Automation Replacement Projects | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.4 | 2.5 | 1.9
SR-08 | John Transformer Station Reinvestment Project | 0.1 | 14 | 0 | 5.9 | 0 | 0.1 | 0 | 0 | 0.2
SR-09 | Transmission Station Demand and Spares and Targeted Assets | 27 | 11.1 | 24.2 | 16.4 | 18.5 | 23.6 | 49.6 | 37.1 | 49.7
SR-10 | Transformer Protection Replacement | 0.1 | 0 | 1.5 | 0 | 3.4 | 3.1 | 3.1 | 4.1 | 3
SR-11 | Legacy SONET System Replacement | 0 | 0 | 0 | 0 | 1.2 | 1.1 | 3.3 | 2.4 | 1.5
SR-12 | Telecom Performance Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR-13 | ADSS Fibre Optic Cable Replacements | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.4 | 0.5
SR-14 | Mobile Radio System Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6
SR-15 | Telecom Fibre IRU Agreement Renewals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR-16 | NERC CIP-014 Physical Security Implementation | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 17.9
SR-17 | NERC CIP Transient Cyber Asset Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
SR-18 | PSIT Cyber Equipment Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 5.4
SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | 0.2 | 0 | 2.1 | 0 | 8.1 | 7.8 | 42.7 | 47 | 104.6
SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | 0 | 0 | 0 | 0 | 0.4 | 0.4 | 0.3 | 3.6 | 12.8
SR-21 | Wood Pole Structure Replacements | 20.8 | 13.8 | 43.8 | 14.1 | 42.7 | 40.3 | 35.3 | 34.9 | 34.8
SR-22 | Steel Structure Coating Program | 5.1 | 8.8 | 2.3 | 10.3 | 42.1 | 39 | 37.7 | 27 | 9.3
SR-23 | Tower Foundation Assess/Clean/Coat Program | 1.4 | 4.2 | 1.6 | 4.3 | 7 | 5.9 | 4.7 | 7.7 | 13.1
SR-24 | Transmission Line Shieldwire Replacement | 4.8 | 4.3 | 1.4 | 4.4 | 5.4 | 4.8 | 9.3 | 10.2 | 9.9
SR-25 | Transmission Line Insulator Replacement | 2.9 | 3.6 | 29.5 | 3.7 | 48.9 | 53.1 | 65.5 | 64.8 | 66.2
SR-26 | Transmission Line Emergency Restoration | 8.7 | 10.9 | 13.8 | 11.1 | 8.3 | 7.6 | 9.7 | 9 | 9.4
SR-27 | C5E/C7E Underground Cable Replacement | 0 | 0 | 0 | 0 | 0.5 | 0.3 | 0.5 | 0.6 | 3.2
SR-28 | OPGW Infrastructure Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 1.2
SR-29 | Physical Security ISL Application Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 5 | 7.8
Table 7 - System Service - Material Capital Investments
|  | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Forecast
ISD | Investment Name | 2015 | 2015 | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019
SS-01 | Lennox TS: Install 500kV Shunt Reactors | 0 | 0 | 0 | 0 | 0.3 | 0.2 | 1.1 | 2 | 13.2
SS-02 | Wataynikaneyap Line to Pickle Lake Connection | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 3.2
SS-03 | Nanticoke TS: Connect HVDC Lake Erie Circuits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SS-04 | East-West Tie Connection | 0.1 | 0 | 1.7 | 0 | 4.4 | 4.3 | 8.6 | 10.8 | 31.5
SS-05 | St. Lawrence TS: Phase Shifter Upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
SS-06 | Merivale TS to Hawthorne TS: 230kV Conductor Upgrade | 0 | 0 | 0.1 | 0 | 0.1 | 0.1 | 0 | 0.3 | 0.5
SS-07 | Milton SS: Station Expansion and Connect 230kV Circuits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SS-08 | Northwest Bulk Transmission Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5
SS-09 | Barrie Area Transmission Upgrade | 0 | 0 | 0.4 | 0 | 1.8 | 2 | 1.8 | 6.5 | 2.6
SS-10 | Kapuskasing Area Transmission Reinforcement | 0 | 0 | 0.1 | 0 | 0.7 | 0.7 | 1.7 | 1.5 | 17.5
SS-11 | South Nepean Transmission Reinforcement | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.8 | 0
SS-12 | Alymer-Tillsonburg Area Transmission Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 1 | 1
SS-13 | Leamington Area Transmission Reinforcement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9
SS-14 | Southwest GTA Transmission Reinforcement | 0 | 0 | 0.2 | 0 | 0.1 | 0.1 | 0.3 | 1.2 | 1.9
SS-15 | Future Transmission Regional Plans | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
SS-16 | Customer Power Quality Program | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 3.3 | 3.3
Table 8 - General Plant - Material Capital Investments
|  | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Forecast
ISD | Investment Name | 2015 | 2015 | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019
GP-01 | Integrated System Operations Centre - New Facility Development | 0.2 | 0 | 4 | 0 | 0.8 | 1 | 0.6 | 23 | 28.8
GP-02 | Grid Control Network Sustainment | 0.5 | 2 | 3.4 | 3 | 2.9 | 2.4 | 3.6 | 6.4 | 7.2
GP-03 | Network Management System Capital Sustainment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GP-04 | Integrated Voice Communications and Telephony System Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GP-05 | Transmission Non-Operational Data Management System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GP-06 | Operating Common IT Infrastructure | 0 | 0 | 0 | 1.6 | 0 | 0.9 | 0 | 1 | 1.7
GP-07 | Hardware/Software Refresh and Maintenance | 5.7 | 4.7 | 8 | 4.4 | 6.2 | 6.5 | 4 | 7.3 | 3.7
GP-08 | Corporate Services Transformation - HR / Payroll | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 2 | 0.5
GP-09 | Corporate Services Transformation - Finance | 0 | 0 | 0 | 0 | 0.3 | 0.2 | 0 | 0.5 | 0.2
GP-10 | Facility Accommodation & Improvements Service Centres & Admin | 0.1 | 0.8 | 6.4 | 0.8 | 5.3 | 7.9 | 4.9 | 19.3 | 7.2
GP-11 | Transmission Facilities & Site Improvements | 0 | 0 | 6.2 | 0 | 10.6 | 12 | 16.4 | 10 | 12
GP-12 | Transport & Work Equipment | 16.7 | 14.9 | 20.4 | 17.1 | 13.7 | 14.5 | 7.2 | 14.1 | 13.3