## Appendix K Cost Estimate
2020/2021 Smart Grid Project
Project Costing w/ EPC & PUC Cost Estimate
Scope notes:
All 12.5kV Feeders to be part of VVM system
All 12.5kV Feeders in DA
Includes 34.5kV Transfer Trip
Sub 16 Rebuild in Separate project
Sub1 - all underground area so likely padmounted VReg equipment
Sub 1, 2, 10,11,12,13,15,18,19,20,21 to be evaluated for all options depending on site fit & $'s.
[K] / [C]
VVM (excludes AMI, SCADA, Comm, etc.) | Qty | Unit Costs | Total
DS with new LTC's (incremental) |  |  | 0
48 feeders (note Sub 16 LTC)
> Bus/Padmount /Feeder/ VReg's(per set of 3) | 44 | 120833.5909 | 5316678
> feeder balancing Vregs | 6 | 55487 | 332922
> feeder balancing Caps | 6 | 42633.6667 | 255802
5905402
Engineering (check sum) | 1 | 2362042.3226 | 2362042.3226 | ~PUC includes prelim Eng
Add'l Scope & Contingency | 1 | 462846 | 462846 | $125k x 5 &34.5TT not in EPC
8730290
Project Mgmt/ Ext'l Commissioning Review | 1 | 379800 | 379800
Contract/Regulatory/ Legal | 1 | 353703 | 353703
VVM |  |  | 9463794 | 28.67%
9463794
DA (excludes AMI, SCADA, Comm, etc.)
Reclosers | 40 | 99573.325 | 3982933
SW's(pole) | 40 | 93278.925 | 3731157
2 way padmount SW's | 12 | 62231.25 | 746775
4 way padmount SW's | 8 | 304824.625 | 2438597
OH FCI's | 40 | 1549.3 | 61972 | may require more units?
UG FCI's | 40 | 1930.5 | 77220 | may require more units?
Poles (added qty for adjacent lift/siting issues) | 120 | 11837.1333 | 1420456 | ~EPC 50/ PUC 70 @ 12000
12459110
Engineering (check sum) | 1 | 5205848.5715 | 5205848.5715 | ~PUC includes prelim Eng
Add'l Scope & Contingency | 1 | 844036 | 844036 | $125k x 5 &34.5TT not in EPC
18508995
Project Mgmt/ Ext'l Commissioning Review | 1 | 759600 | 759600
Contract/Regulatory/ Legal | 1 | 726371 | 726371
DA |  |  | 19994966 | 60.58%
19994966
AMI Integration, SCADA, OMS, CIS, Comm, etc.)
All IT H/W, S/W, SCADA, OMS, GIS, communication
type work combined in to central sub-project.
VVO/FLSIR/OMS/CIS/AMI | 1 | 2013446 | 2013446 | EPC/Survalent
0
2013446
Engineering (check sum) | 1 | 1284009.246 | 1284009.246 | Eng & IT (includes prelim Eng)
Add'l Scope & Contingency | 1 | - | -
3297455
Project Mgmt/ Ext'l Commissioning Review | 1 | 126600 | 126600
Contract/Regulatory/ Legal | 1 | 124223 | 124223
AMI |  |  | 3548278 | 10.75%
|  |  | 3548278 | 100%
Project Estimate Total System |  |  | 33007038
33007038