## Notes
PUC Distribution Inc.
Long Range Capital Planning
Revision Date: 2016-03-15
Notes
1) In the two attached spreadsheets, the estimated capital cost expenditures for Distribution Station and Transmission Station rebuilds is considered for two scenarios. The first scenario considers if we were to continue with our current long term plan. The second considers if we were to accelerate a number of DS rebuilds, those shaded in blue, all to occur in the next OEB rate cycle.
2) the budget numbers in the long range plan are preliminary and order of magnitude only, based on presently available information. These will be further refined in 2016 as part of the development of an Asset Management Plan (AMP) and Distribution System Plan (DSP) for the OEB.
3) The sequence of station rebuilt projects proposed in this plan may be changed somewhat due to the outcomes of the DSP. At present the sequencing is based primarily on simple age and condition based assessments and technical factors (e.g.: risk associate with loosing a station that has no backup or where no ability exists to transfer loads in a contingency). The DSP is will see these factors more systematically documented than current planning processes and may lead to a more optimal sequence. In all cases, one underlying goal has been to flatten expenditures as evenly as possible over time and that will continue to be the case with the implementation of the DSP.
4) The attached long range plan does not consider Customer Demand or Allocated Capital. Nor does it consider 'Overhead Distribution System' , 'Underground Distribution System', 'Distribution Transformers' or 'Voltage Conversion Program' which were identified in Exhibit 5-6, p 77 of the METSCO Asset Management Plan prepared in 2012 for the period 2013-2016. It is expected that in all the aforementioned areas, levels consistent with past practice will continue to be required to keep up asset sustainment and respond to customer demand.

## Long Range DS Plan - no UDM
CAPEX for Transformer Stations and Distribution Stations |  |  |  | NPV rate | 4%
Without UDM
Priority | Station | Age at Replacement | Comments | NPV 2016 | 2017-2021 | 2022-2026 | 2027-2031 | 2032-2036 | 2037-2041 | 2042-2046 | 2047-2051
1 | Sub 14 | p 54 years in 2015 | Completing voltage conversion will allow retirement of substation. Target 2017 with some 4kV load supplied via Sub 4 temporarily.
2 | Sub 16 | p 52 years in 2017 | UDM #1 rebuild - Health Index Score 50 in 2012 | 3.3654 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0
| TS1 | p 45 years in 2018 | Health Index Score 52 in 2012 | 22.8846 | 23.8 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 26.25 | 27.3 | 0 | 0 | 0 | 0 | 0 | 0
3 | Sub 19 LTC | p 45 years in 2018 | Health Index Score 54 in 2012 | 1.3868 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
| Sub 19 SwG | p 45 years in 2018 | Health Index Score 54 in 2012 | 1.3868 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
| Sub New |  | To replace Sub 4 & 5 at end of Voltage conversion | 3.2359 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0
| Sub 20 | p 45 years in 2018 | UDM #3 Rebuild - Health Index Score 56 in 2012 | 3.2359 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9.2456 | 0 | 10 | 0 | 0 | 0 | 0 | 0
4 | TS2 | p 51 years in 2028 | Health Index Score 66 in 2012 | 21.1581 | 0 | 0 | 23.8 | 0 | 0 | 0 | 0
| Sub 18 LTC | p 63 years in 2031 | Health Index Score 61 in 2012 | 1.3335 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
| Sub 18 | p 63 years in 2031 | Health Index Score 61 in 2012 | 1.3335 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
|  |  |  | 23.8251 | 0 | 0 | 26.8 | 0 | 0 | 0 | 0
5 | Sub 11 | p 57 years in 2033 | UDM #2 rebuild - Health Index Score 61 in 2012 | 2.9918 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0
| Sub 2 LTC | p 62 years in 2036 | (rebuilt) Health Index Score 71 in 2012 | 1.2822 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
| Sub 2 SwG | p 62 years in 2036 | Health Index Score 71 in 2012 | 1.7096 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  |  |  | 5.9836 | 0 | 0 | 0 | 7 | 0 | 0 | 0
6 | Sub 12 | p 62 years in 2038 | Health Index Score 61 in 2012 | 2.8767 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0
| Sub 1 | p 60 years in 2041 | UDM #4 Rebuild - Health Index Score 64 in 2012 | 2.8767 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0
|  |  |  | 5.7535 | 0 | 0 | 0 | 0 | 7 | 0 | 0
7 | Sub 21 | p 60 years in 2044 | Health Index Score 58 in 2012 | 2.7661 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0
| Sub 13 | p 54 years in 2046 | Health Index Score 76 in 2012 | 2.7661 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0
|  |  |  | 5.5322 | 0 | 0 | 0 | 0 | 0 | 7 | 0
8 | Sub 15 | p 54 years in 2048 | Health Index Score 62 in 2012 | 2.6597 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
|  |  |  | 2.6597 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
Totals |  |  |  | 79.2497 | 27.3 | 10 | 26.8 | 7 | 7 | 7 | 3.5
|  |  | PV of Average Annual CAPEX over next 35 years | NPV 2016: 2.2643
|  | Legend: | blue indicates CAPEX within UDM that is part of long term PUC Capital Plan | bar: NPV 2016 to 2017-2021
indicates required CAPEX not yet identified in OEB AMP of DSP | bar: NPV 2016 to 2017-2021

## Long Range DS Plan -with UDM
CAPEX for Transformer Stations and Distribution Stations |  |  |  | NPV rate | 4%
With UDM
Priority | Station | Age at Replacement | Comments | NPV 2016 | 2017-2021 | 2022-2026 | 2027-2031 | 2032-2036 | 2037-2041 | 2042-2046 | 2047-2051
1 | Sub 14 | p 54 years in 2015 | Completing voltage conversion will allow retirement of substation. Target 2017 with some 4kV load supplied via Sub 4 temporarily.
2 | Sub 16 | p 52 years in 2017 | UDM #1 rebuild - Health Index Score 50 in 2012 | 3.3654 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0
| TS1 | p 45 years in 2018 | Health Index Score 52 in 2012 | 22.8846 | 23.8 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 26.25 | 27.3 | 0 | 0 | 0 | 0 | 0 | 0
3 | Sub 19 LTC | p 45 years in 2018 | Health Index Score 54 in 2012 | 1.4423 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
| Sub 19 SwG | p 45 years in 2018 | Health Index Score 54 in 2012 | 1.3868 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
| Sub New |  | To replace Sub 4 & 5 at end of Voltage conversion | 3.2359 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0
| Sub 20 | p 45 years in 2018 | UDM #3 Rebuild - Health Index Score 56 in 2012 | 3.3654 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 9.4305 | 5 | 5 | 0 | 0 | 0 | 0 | 0
4 | TS2 | p 51 years in 2028 | Health Index Score 66 in 2012 | 21.1581 | 0 | 0 | 23.8 | 0 | 0 | 0 | 0
| Sub 18 LTC | p 63 years in 2031 | Health Index Score 61 in 2012 | 1.4423 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
| Sub 18 | p 63 years in 2031 | Health Index Score 61 in 2012 | 1.3335 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
|  |  |  | 23.9339 | 1.5 | 0 | 25.3 | 0 | 0 | 0 | 0
5 | Sub 11 | p 57 years in 2033 | UDM #2 rebuild - Health Index Score 61 in 2012 | 3.3654 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0
| Sub 2 LTC | p 62 years in 2036 | (rebuilt) Health Index Score 71 in 2012 | 1.4423 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
| Sub 2 SwG | p 62 years in 2036 | Health Index Score 71 in 2012 | 1.7096 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  |  |  | 6.5173 | 5 | 0 | 0 | 2 | 0 | 0 | 0
6 | Sub 12 | p 62 years in 2038 | Health Index Score 61 in 2012 | 2.8767 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0
| Sub 1 | p 60 years in 2041 | UDM #4 Rebuild - Health Index Score 64 in 2012 | 3.3654 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 6.2421 | 3.5 | 0 | 0 | 0 | 3.5 | 0 | 0
7 | Sub 21 | p 60 years in 2044 | Health Index Score 58 in 2012 | 2.7661 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0
| Sub 13 | p 54 years in 2046 | Health Index Score 76 in 2012 | 2.7661 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0
|  |  |  | 5.5322 | 0 | 0 | 0 | 0 | 0 | 7 | 0
8 | Sub 15 | p 54 years in 2048 | Health Index Score 62 in 2012 | 2.6597 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
|  |  |  | 2.6597 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5
Totals |  |  |  | 80.5657 | 42.3 | 5 | 25.3 | 2 | 3.5 | 7 | 3.5
|  |  | PV of Average Annual CAPEX over next 35 years | NPV 2016: 2.3019
|  | Legend: | blue indicates CAPEX within UDM that is part of long term PUC Capital Plan | bar: NPV 2016 to 2017-2021
indicates required CAPEX not yet identified in OEB AMP of DSP | bar: NPV 2016 to 2017-2021