## 2015
Projects | Ref # | 2015 Budget | 2015 Actual | Difference Actual vs Budget ($) | Difference Actual vs Budget (%)
System Access
Customer Driven System Reinforcements for New Commercial Service Connections | 1 | 1026947 | 849328.7012
Commercial Connection Projects Less Than Materiality | 2 |  | 835479.1022
King St. Bell Joint Use Pole Replacement | 3 |  | 241068.0834
Motor Vehicle Accidents | 9 |  | 80382.1712 | 979311.0579 | 95.36%
Metering | 10 | 336650 | 111449.9647 | -225200.0353 | -66.89%
Warren Woods Subdivision Phase 3 | 11 |  | 172666.7233
Oldfield Estates Subdivision Phase 1 | 11 |  | 160905.1287
New Subdivision Projects Below Materiality | 11 |  | 464908.0333
New Connections in Existing Subdivisions | 11 | 587004 | 395224.1393 | 606700.0246 | 103.4%
Transfer of Expansion Facilities from Customers | 11 |  | 3160319.09 | 3160319.09 | 100%
Road Relocation Projects | 12 | 500000 | 411611.782
RMN - Reg Rd #18-Mountain Relocation | 12 |  | 311300.1297
CNF Level St U/G Relocate | 12 |  | 230733.328 | 453645.2396 | 90.73%
Miscellaneous | 22 |  | 37540.12 | 37540.12 | 100%
Sub-Total |  | 2450601 | 7462916.4968 | 5012315.4968
System Renewal
Crawford St. Rebuild - Thorold Stone to Sheldon | 23 | 737691 | 463166.18 | -274524.82 | -37.21%
Willodel Rd. - Gonder to Koabel | 24 | 310710 | 313260.63 | 2550.63 | 0.8209%
Willoughby Dr. - Main to Cattell | 25 | 372191 | 12798.74 | -359392.26 | -96.56%
Willoughby Dr. - Cattell to Weinbrenner | 26 | 383293 |  | -383293 | -100%
Transformer Replacements - PCB > 50 ppm | 27 | 495104 | 235322.16 | -259781.84 | -52.47%
Station 22 Rebuild - Ph 1 Carryover / Phase 2 | 29 | 650863 | 682134.55 | 31271.55 | 4.805%
Beck Road Rebuild - Marshall to Schisler | 30 | 144237 | 170696.15 | 26459.15 | 18.34%
Frederica St Rebuild - Dorchester to Drummond | 31 | 220777 | 14695.58 | -206081.42 | -93.34%
Jordan Rd Rebuild Phase 2 - Honsberger from Jordan to Thirteenth | 33 | 449324 | 460242.45 | 10918.45 | 2.43%
Pole Replacements | 53 | 431729 | 546418.04 | 114689.04 | 26.57%
Kiosk Replacements | 54 | 647029 | 311260.3 | -335768.7 | -51.89%
Switchgear Replacements | 55 | 250002 | 201851.72 | -48150.28 | -19.26%
Rolling Acres OH to UG Conversion | 57 | 1061077 | 764210.63 | -296866.37 | -27.98%
NWTC Metering |  | 289605 |  | -289605 | -100%
Sub-Total |  | 6443632 | 4176057.13 | -2267574.87
System Service
King St. 27.6 kV Extension to Martin Rd | 60 | 217014 | 130845.14 | -86168.86 | -39.71%
Grid Modernization Program | 62 | 318000 | 143148.46 | -174851.54 | -54.98%
System Sustainment / Minor Betterments | 66 | 780000 | 1570561.58 | 790561.58 | 101.4%
Sub-Total |  | 1315014 | 1844555.18 | 529541.18
General Plant
Building |  | 86000 | 468659.65 | 382659.65 | 445%
Hardware |  | 240248 | 248788.8 | 8540.8 | 3.555%
Software |  | 368740 | 183006.46 | -185733.54 | -50.37%
Vehicles |  | 698877.94 | 490774.46 | -208103.48 | -29.78%
General Equipment |  | 95626.51 | 146974.06 | 51347.55 | 53.7%
Sub-Total |  | 1489492.45 | 1538203.43 | 48710.98
Total |  | 11698739.45 | 15021732.2368 | 3322992.7868

## 2016
Projects | Ref # | 2016 Budget | 2016 Actual | Difference Actual vs Budget ($) | Difference Actual vs Budget (%)
System Access
Customer Driven System Reinforcements for New Commercial Service Connections | 1 | 1007500 | 736317.3807
Commercial Connection Projects Less Than Materiality | 2 |  | 1243722.4651
NRWC Wind Farm Line Conflicts | 4 |  | 607960.8005
Enercon Wind Farm Line Conflicts | 4 |  | 430071.1934
Eptcon Stringing Conflicts | 4 |  | 279260.5359
FWRN LP Line Conflicts | 4 |  | 210544.8
Oldfield Rd 3-Ph Pole Line | 5 |  | 293937.2718
Motor Vehicle Accidents | 9 |  | 115957.6849 | 2910272.1322 | 288.9%
Metering | 10 | 480860 | 138788.7059 | -342071.2941 | -71.14%
Oldfield Estates Subdivision Phase 2 | 11 |  | 183380.7055
Warren Woods Subdivision Phase 4 | 11 |  | 171971.7468
New Subdivision Projects Below Materiality | 11 |  | 476662.984
New Connections in Existing Subdivisions | 11 | 737004 | 564008.3447 | 659019.781 | 89.42%
Transfer of Expansion Facilities from Customers | 11 | 1000000 | 688451.72 | -311548.28 | -31.15%
Road Relocation Projects | 12 | 500000 | 142942.12 | -357057.88 | -71.41%
Clifton Hill Primary Upgrade | 13 | 237796 | 309572.72 | 71776.72 | 30.18%
Miscellaneous | 22 |  | -103819.08 | -103819.08 | 100%
Sub-Total |  | 3963160 | 6489732.0991 | 2526572.0991
System Renewal
Willoughby Dr. - Main to Cattell | 25 | 369271 | 458728.92 | 89457.92 | 24.23%
Willoughby Dr. - Cattell to Weinbrenner | 26 | 380290 | 375385.21 | -4904.79 | -1.29%
Downtown core PILCDSTA Decomissioning | 28 | 795701 | 382898.77 | -412802.23 | -51.88%
Station 22 Rebuild - Ph 1 Carryover / Phase 2 | 29 |  | 202991.58 | 202991.58 | 100%
Frederica St Rebuild - Dorchester to Drummond | 31 | 671753 | 689883.55 | 18130.55 | 2.699%
NS&T ROW - Crossing the QEW | 32 | 272236 | 207136.19 | -65099.81 | -23.91%
Jordan Rd Rebuild Phase 3 | 33 | 335377 | 307408.16 | -27968.84 | -8.34%
Dorchester Road Rebuild - McLeod to Dunn | 35 | 531912 | 377754.73 | -154157.27 | -28.98%
Victoria Ave South of Fly Rd - Phase 1 | 42 | 298862 | 8935.93 | -289926.07 | -97.01%
Oakwood Drive - South of Smart Centre to QEW | 43 | 611940 |  | -611940 | -100%
Dorchester Road Rebuild - Mountain to Riall | 44 | 626867 | 1943.46 | -624923.54 | -99.69%
Pole Replacements | 53 | 535930 | 583550.09 | 47620.09 | 8.886%
Kiosk Replacements | 54 | 841137 | 1165578.74 | 324441.74 | 38.57%
Switchgear Replacements | 55 | 250002 | 222441.11 | -27560.89 | -11.02%
Rolling Acres OH to UG Conversion Phase 3 | 57 | 405867 | 640910.65 | 235043.65 | 57.91%
Sub-Total |  | 6927145 | 5625547.09 | -1301597.91
System Service
Grid Modernization Program | 62 | 253000 | 575199.52 | 322199.52 | 127.4%
Glenholme to Franklin Ave - 600 MCM UG Install | 63 | 133262 | 68206.58 | -65055.42 | -48.82%
System Sustainment / Minor Betterments | 66 | 780000 | 1089323.09 | 309323.09 | 39.66%
Sub-Total |  | 1166262 | 1732729.19 | 566467.19
General Plant
Building |  | 87000 | 52753.45 | -34246.55 | -39.36%
Hardware |  | 243100 | 241216.89 | -1883.11 | -0.7746%
Software |  | 356800 | 342477.02 | -14322.98 | -4.014%
Vehicles |  | 840000 | 792445.48 | -47554.52 | -5.661%
General Equipment |  | 89843 | 149530.53 | 59687.53 | 66.44%
Sub-Total |  | 1616743 | 1578423.37 | -38319.63
Total |  | 13673310 | 15426431.7491 | 1753121.7491

## 2017
Projects | Ref # | 2017 Budget | 2017 Actual | Difference Actual vs Budget ($) | Difference Actual vs Budget (%)
System Access
Customer Driven System Reinforcements for New Commercial Service Connections | 1 | 1124500 | 933982.6021
Commercial Connection Projects Less Than Materiality | 2 |  | 1019677.3161
Mcleod @ Montrose & Oakwood | 6 |  | 166309.716
Motor Vehicle Accidents | 9 |  | 258090.7422 | 1253560.3764 | 111.5%
Metering | 10 | 543500 | 601440.9795 | 57940.9795 | 10.66%
Warren Woods Subdivision Phase 4 Stage 2 | 11 |  | 184982.8919
New Subdivision Projects Below Materiality | 11 |  | 340921.3571
New Connections in Existing Subdivisions | 11 | 837004 | 577899.1242 | 266799.3732 | 31.88%
Transfer of Expansion Facilities from Customers | 11 | 1000000 | 901555.03 | -98444.97 | -9.844%
Road Relocation Projects | 12 | 500000 | 93776.61 | -406223.39 | -81.24%
Miscellaneous | 22 |  | 622402.69 | 622402.69 | 100%
Sub-Total |  | 4005004 | 5701039.059 | 1696035.059
System Renewal
Willoughby Dr. - Cattell to Weinbrenner | 26 |  | 317.5 | 317.5 | 100%
Downtown core PILCDSTA Decomissioning | 28 | 292171 | 469444.1 | 177273.1 | 60.67%
Frederica St Rebuild - Dorchester to Drummond | 31 |  | 26364.83 | 26364.83 | 100%
NS&T ROW - Crossing the QEW | 32 |  | 159228.88 | 159228.88 | 100%
Jordan Rd Rebuild Phase 4 | 33 | 561614 | 582371.2 | 20757.2 | 3.696%
Kalar TS Protection Equipment Refurbishment | 34 | 400000 | 56943.41 | -343056.59 | -85.76%
Dorchester Road Rebuild - McLeod to Dunn | 35 | 359131 | 232047.73 | -127083.27 | -35.39%
Campden DS Power Tx - Replace with Former Jordan DS Tx | 39 |  | 35884.07 | 35884.07 | 100%
Station St. DS - Power Transformer Replacement | 40 | 200000 | 179626.02 | -20373.98 | -10.19%
Station 14 Voltage Conversion - Phase 1 | 41 | 589623 | 399195.29 | -190427.71 | -32.3%
Victoria Ave South of Fly Rd - Phase 1 | 42 | 308719 | 137553.23 | -171165.77 | -55.44%
Oakwood Drive - South of Smart Centre to QEW | 43 | 600819 | 11807.92 | -589011.08 | -98.03%
Dorchester Road Rebuild - Mountain to Riall | 44 | 678670 | 510844.61 | -167825.39 | -24.73%
Chippawa Redundant Supply - Phase 1 | 45 | 343719 | 279777.13 | -63941.87 | -18.6%
Pole Replacements | 53 | 626236 | 1009358.34 | 383122.34 | 61.18%
Kiosk Replacements | 54 | 1001137 | 937053.82 | -64083.18 | -6.401%
Switchgear Replacements | 55 | 250000 | 205351.74 | -44648.26 | -17.86%
Subdivision Rehabilitation - Phase 1 | 59 | 245151 | 301743.09 | 56592.09 | 23.08%
Sub-Total |  | 6456990 | 5534912.91 | -922077.09
System Service
Heartland Road Extension - Brown Rd to Chippawa Creek | 61 | 114583 | 109606.52 | -4976.48 | -4.343%
Grid Modernization Program | 62 | 103000 | -47511.83 | -150511.83 | -146.1%
Glenholme to Franklin Ave - 600 MCM UG Install | 63 |  | 42618.31 | 42618.31 | 100%
Brown Road Extension - Montrose to Blackburn | 64 | 189664 | 77945.2 | -111718.8 | -58.9%
System Sustainment / Minor Betterments | 66 | 920000 | 1075853.7 | 155853.7 | 16.94%
Sub-Total |  | 1327247 | 1258511.9 | -68735.1
General Plant
Building |  | 492500 | 403007.02 | -89492.98 | -18.17%
Hardware |  | 401390 | 332121.28 | -69268.72 | -17.26%
Software |  | 1120860 | 710895.69 | -409964.31 | -36.58%
Vehicles |  | 695250 | 876512.72 | 181262.72 | 26.07%
General Equipment |  | 102000 | 116015.93 | 14015.93 | 13.74%
Sub-Total |  | 2812000 | 2438552.64 | -373447.36
Total |  | 14601241 | 14933016.509 | 331775.509

## 2018
Projects | Ref # | 2018 Budget | 2018 Actual | Difference Actual vs Budget ($) | Difference Actual vs Budget (%)
System Access
Customer Driven System Reinforcements for New Commercial Service Connections | 1 | 1269425 | 1104335.7858
Commercial Connection Projects Less Than Materiality | 2 |  | 1428763.1925
Fallsview Entertainment Complex | 7 |  | 204129.4255
Motor Vehicle Accidents | 9 |  | 179627.5042 | 1647430.908 | 129.8%
Metering | 10 | 665000 | 585647.8151 | -79352.1849 | -11.93%
Warren Woods Subdivision Phase 5 | 11 |  | 237426.5126
New Subdivision Projects Below Materiality | 11 |  | 448832.6581
New Connections in Existing Subdivisions | 11 | 899004 | 333344.7125 | 120599.8832 | 13.41%
Transfer of Expansion Facilities from Customers | 11 | 1000000 | 913711.35 | -86288.65 | -8.629%
Road Relocation Projects | 12 | 520813 | 125864.33 | -394948.67 | -75.83%
Miscellaneous | 22 |  | 431219.55 | 431219.55 | 100%
Sub-Total |  | 4354242 | 5992902.8364 | 1638660.8364
System Renewal
Downtown core PILCDSTA Decomissioning | 28 |  | 53355.43 | 53355.43 | 100%
Kalar TS Protection Equipment Refurbishment | 34 | 200000 | 128307.66 | -71692.34 | -35.85%
Thorold Stone Rd Rebuild - Montrose to Kalar | 37 | 457676 | 10017.15 | -447658.85 | -97.81%
Portage Rd. Rebuild - Mountain to Church's Lane | 38 | 383291 | 119863.29 | -263427.71 | -68.73%
Station 14 Voltage Conversion - Phase 1 | 41 |  | 2437.08 | 2437.08 | 100%
Station 14 Voltge Conversion Phase 2 | 41 | 971639 | 712832.04 | -258806.96 | -26.64%
Victoria Ave South of Fly Rd - Phase 1 | 42 | 401629 | 694068.93 | 292439.93 | 72.81%
Victoria Ave South of Fly Rd - Phase 2 | 42 | 558441 | 567881.55 | 9440.55 | 1.691%
Oakwood Drive - South of Smart Centre to QEW | 43 | 648476 | 583572.22 | -64903.78 | -10.01%
Dorchester Road Rebuild - Mountain to Riall | 44 |  | 204558.01 | 204558.01 | 100%
Chippawa Redundant Supply - Phase 1 | 45 |  | 67328.72 | 67328.72 | 100%
Chippawa Redundant Supply - River Crossing | 45 | 400396 | 492481.94 | 92085.94 | 23%
Pole Replacements | 53 | 624352 | 881937.57 | 257585.57 | 41.26%
Kiosk Replacements | 54 | 100407 | 122612.51 | 22205.51 | 22.12%
Switchgear Replacements | 55 | 257493 | 164315.81 | -93177.19 | -36.19%
Subdivision Rehabilitation Phase 2 | 59 | 361965 | 450650.72 | 88685.72 | 24.5%
Sub-Total |  | 5365765 | 5256220.63 | -109544.37
System Service
Grid Modernization Program | 62 | 201750 | 161240.29 | -40509.71 | -20.08%
Range Road 2 - East of Allen | 65 | 120655 | 38951.32 | -81703.68 | -67.72%
System Sustainment / Minor Betterments | 66 | 923400 | 931129.25 | 7729.25 | 0.837%
Willoughby Road Extension | 67 | 280737 | 259547.13 | -21189.87 | -7.548%
Greenlane Rd at Ontario - Tie Point | 69 | 160194 | 1008.32 | -159185.68 | -99.37%
Sub-Total |  | 1686736 | 1391876.31 | -294859.69
General Plant
Building |  | 1435000 | 1024864.22 | -410135.78 | -28.58%
Hardware |  | 291060 | 326559.05 | 35499.05 | 12.2%
Software |  | 368500 | 288890.79 | -79609.21 | -21.6%
Vehicles |  | 343000 | 518258.45 | 175258.45 | 51.1%
General Equipment |  | 142120 | 186335.44 | 44215.44 | 31.11%
Sub-Total |  | 2579680 | 2344907.95 | -234772.05
Total |  | 13986423 | 14985907.7264 | 999484.7264

## 2019
Projects | Ref # | 2019 Budget | 2019 Actual | Difference Actual vs Budget ($) | Difference Actual vs Budget (%)
System Access
Customer Driven System Reinforcements for New Commercial Service Connections | 1 | 1269425 | 1022511.6818
Commercial Connection Projects Less Than Materiality | 2 |  | 1509201.6099
Garner Road Line Rebuild to 3-Phase | 8 |  | 223043.9943
Motor Vehicle Accidents | 9 |  | 147214.1958 | 1632546.4818 | 128.6%
Metering | 10 | 401800 | 481484.22 | 79684.22 | 19.83%
Cherry Heights Extension | 11 |  | 341970.09
Vista Ridge Phase 1 | 11 |  | 237541.1639
Warren Woods Phase 5 Stage 2 | 11 |  | 166031.5902
Terravita Subdivision | 11 |  | 148562.4868
New Subdivision Projects Below Materiality | 11 |  | 660563.6866
New Connections in Existing Subdivisions | 11 | 899004 | 429566.3901 | 1085231.4076 | 120.7%
Transfer of Expansion Facilities from Customers | 11 | 1000000 | 2312131.93 | 1312131.93 | 131.2%
Road Relocation Projects | 12 | 517813 | 120411.98 | -397401.02 | -76.75%
KM3 - Link | 14 | 965719 | 11091.97 | -954627.03 | -98.85%
Kalar TS Additional Switchgear | 21 | 125000 | 110321 | -14679 | -11.74%
Miscellaneous | 22 |  | 52113.95 | 52113.95 | 100%
Sub-Total |  | 5178761 | 7973761.9394 | 2795000.9394
System Renewal
Downtown core PILCDSTA Decomissioning | 28 |  | 75377.08 | 75377.08 | 100%
Concession 2 Rd - Caistorville Rd to Westbrook Rd | 36 | 263333 | 157567.88 | -105765.12 | -40.16%
Thorold Stone Rd Rebuild - Montrose to Kalar | 37 | 427734 | 162767.84 | -264966.16 | -61.95%
Portage Rd. Rebuild - Mountain to Church's Lane | 38 | 420236 | 288298.22 | -131937.78 | -31.4%
Station 14 Voltage Conversion - Phase 3 | 41 | 1475867 | 816053.77 | -659813.23 | -44.71%
Murray TS - J Bus Metering | 46 | 672623 | 430258.41 | -242364.59 | -36.03%
Victoria Ave Rebuild - 7th Ave Phase 2 | 47 | 657678 | 232171.9 | -425506.1 | -64.7%
Campden DS Tx Failure | 48 |  | 150378.07 | 150378.07 | 100%
Mountain Road - St. Paul St. to Mewburn | 49 |  | 297197.95 | 297197.95 | 100%
Pole Replacements | 53 | 674777 | 962984.15 | 288207.15 | 42.71%
Kiosk Replacements | 54 | 51200 | 80094.5 | 28894.5 | 56.43%
Switchgear Replacements | 55 | 83000 | 308755.17 | 225755.17 | 272%
Subdivision Rehabilitation Phase 2 | 59 | 68585 | 69938.25 | 1353.25 | 1.973%
Montrose - Oakwood to Biggar |  | 794610 |  | -794610 | -100%
Sub-Total |  | 5589643 | 4031843.19 | -1557799.81
System Service
Grid Modernization Program | 62 | 146275 | 225928.64 | 79653.64 | 54.45%
System Sustainment / Minor Betterments | 66 | 892515 | 1274030.34 | 381515.34 | 42.75%
Kalar TS Power Transformer Dry Down Equipment | 68 | 70000 | 72501.16 | 2501.16 | 3.573%
Sub-Total |  | 1108790 | 1572460.14 | 463670.14
General Plant
Building |  | 1634373 | 2037896 | 403523 | 24.69%
Hardware |  | 322620 | 193148.85 | -129471.15 | -40.13%
Software |  | 548649 | 361772.67 | -186876.33 | -34.06%
Vehicles |  | 600233 | 599766.09 | -466.91 | -0.07779%
General Equipment |  | 139200 | 176544.04 | 37344.04 | 26.83%
Sub-Total |  | 3245075 | 3369127.65 | 124052.65
Total |  | 15122269 | 16947192.9194 | 1824923.9194

## 2020
Projects | Ref # | 2020 Bridge Year Budget | 2020 Bridge Year Projected | Difference Projected vs Original Application ($) | Difference Projected vs Original Application (%)
System Access
Customer Driven System Reinforcements for New Commercial Service Connections | 1 | 2003963.5 | 2714790 | 710826.5 | 35.47%
Metering | 10 | 397300 | 397321 | 21 | 0.005286%
New Connections in Existing Subdivisions | 11 | 901692.3 | 1305314 | 403621.7 | 44.76%
Transfer of Expansion Facilities from Customers | 11 | 1000000 | 1105600 | 105600 | 10.56%
Road Relocation Projects | 12 | 54389.75 | 518512 | 464122.25 | 853.3%
KM3 - Link | 14 | 876667.99 | 14374 | -862293.99 | -98.36%
Pin Oak Main Loop | 15 | 1224074.88 | 1079989 | -144085.88 | -11.77%
GPI Feeder Build | 16 | 807177.94 | 12447 | -794730.94 | -98.46%
Thorold Stone - Bridge Roundabout | 17 | 452235.2 |  | -452235.2 | -100%
Jordan UG Relocate | 18 | 1062995.43 | 596800 | -466195.43 | -43.86%
RR20 Roundabouts | 19 | 254825.04 | 36444 | -218381.04 | -85.7%
Fallsview UG Relocate | 20 | 452244.1 | 596534 | 144289.9 | 31.91%
Kalar TS Additional Switchgear | 21 |  | 470159 | 470159 | 100%
Miscellaneous | 22 |  | 152729 | 152729 | 100%
Sub-Total |  | 9487566.13 | 9001013 | -486553.13
System Renewal
Kalar TS Relay Upgrade | 34 | 75000 | 76551 | 1551 | 2.068%
Thorold Stone Rd Rebuild - Montrose to Kalar | 37 | 349274.1 | 445332 | 96057.9 | 27.5%
Station 14 Voltage Conversion - Phase 3 | 41 | 236611.24 | 452602 | 215990.76 | 91.29%
Mountain Road - St. Paul St. to Mewburn | 49 |  | 181055 | 181055 | 100%
Sinnicks Ave Rebuild - Thorold Stone to Swayze | 50 | 824145.14 | 130272 | -693873.14 | -84.19%
McRae St. Area Rebuild Ph 1 | 51 | 351194.1 |  | -351194.1 | -100%
King St. Rebuild Phase 1 - Bartlett Rd to Sann Rd. | 52 | 344678.79 | 436331 | 91652.21 | 26.59%
Pole Replacements | 53 | 700987.63 | 1245691 | 544703.37 | 77.71%
Kiosk Replacements | 54 | 52704 |  | -52704 | -100%
Switchgear Replacements | 55 | 86218 | 331154 | 244936 | 284.1%
Pole Mount Step Down Transformer Eliminations - Lincoln / West Lincoln | 56 | 600105.66 | 356567 | -243538.66 | -40.58%
Stanley TS - HONI Initiated | 58 | 625765.25 | 10563 | -615202.25 | -98.31%
Sub-Total |  | 4246683.91 | 3666118 | -580565.91
System Service
Grid Modernization Program | 62 | 168450 | 14156 | -154294 | -91.6%
System Sustainment / Minor Betterments | 66 | 873020 | 872827 | -193 | -0.02211%
Greenlane Rd at Ontario - Tie Point | 69 | 160278.09 |  | -160278.09 | -100%
Sub-Total |  | 1201748.09 | 886983 | -314765.09
General Plant
Building |  | 1768100 | 1680090 | -88010 | -4.978%
Hardware |  | 170100 | 173869 | 3769 | 2.216%
Software |  | 341000 | 197498 | -143502 | -42.08%
Vehicles |  | 190000 | 113650 | -76350 | -40.18%
General Equipment |  | 159000 | 269101 | 110101 | 69.25%
Sub-Total |  | 2628200 | 2434208 | -193992
Total |  | 17564198.13 | 15988322 | -1575876.13