## Capital Project Variances V5
Material Capital Projects Variance Table
Planned DSP Projects from 2015 to 2019 (exluding reactive, emerging & on-going piece-work programs)
| Material Capital Projects ( ≥ $100K) |  |  | Budget (Net Cost) |  |  | Completion Year |  | Variance Cause (for Projects Exceeding +/- 10%)
|  |  |  | Forecast | Actual | Variance | Forecast | Actual
SYSTEM RENEWAL
OVERHEAD
C15-200 |  |  | Park Rd Wentworth To Stone | 1300000 | 1330759.24 | 2.366% | 2015 | 2016 | Within Tolerance | 30759.24
C15-201 |  |  | Keewatin | 745000 | 673218.32 | -9.635% | 2015 | 2015 | Within Tolerance | -71781.68
C15-202 |  |  | Backyard Rear Lot Feed | 365000 | 347792.64 | -4.714% | 2015 | 2016 | Within Tolerance | -17207.36
C16-200 |  |  | Rossland | 550000 | 126423.11 | -77.01% | 2016 | TBD | In progress - On hold to coordinate with pending City work | -423576.89
C16-201 |  |  | Athabasca | 835000 | 590646.42 | -29.26% | 2016 | 2016 | Under - Inaccurate estimate based on generic costing per pole | -244353.58
C16-202 |  |  | Eastlawn,Winter,Mackenzie & Labrador | 360000 | 302927.17 | -15.85% | 2016 | 2016 | Under - Inaccurate estimate based on generic costing per pole | -57072.83
C16-203 |  |  | Bloor St | 510000 | 313465.13 | -38.54% | 2016 | 2016 | Under - Inaccurate estimate based on generic costing per pole | -196534.87
C17-200 |  |  | Central Park Blvd N | 575000 | 509996.42 | -11.3% | 2017 | 2018 | Under - Inaccurate estimate based on generic costing per pole | -65003.58
C17-201 |  |  | Landsdowne | 335000 | 258330.3 | -22.89% | 2017 | 2018 | Under - Inaccurate estimate based on generic costing per pole | -76669.7
C17-202 |  |  | Shakespeare | 480000 | 390984.57 | -18.54% | 2017 | 2017 | Under - Inaccurate estimate based on generic costing per pole | -89015.43
C17-203 |  |  | Fisher St | 250000 | 285629.71 | 14.25% | 2017 | 2017 | Over - Scope increase | 35629.71
C17-204 |  |  | GrenFell South of Gibb | 215000 | 240066.31 | 11.66% | 2017 | 2017 | Over - Scope increase | 25066.31
C18-200 |  |  | Julianna & Bernhard | 335000 | 258934.5 | -22.71% | 2018 | 2018 | Under - Inaccurate estimate based on generic costing per pole | -76065.5
C18-201 |  |  | Mary | 340000 | 270851.87 | -20.34% | 2018 | 2018 | Under - Inaccurate estimate based on generic costing per pole | -69148.13
C18-202 |  |  | Gibbons | 665000 | 590572.28 | -11.19% | 2018 | 2018 | Under - Inaccurate estimate based on generic costing per pole | -74427.72
C18-203 |  |  | Riverside South | 340000 | 239147.43 | -29.66% | 2018 | 2019 | Under - Inaccurate estimate based on generic costing per pole | -100852.57
C18-204 |  |  | Riverside North | 630000 | 462003.03 | -26.67% | 2018 | 2019 | Under - Inaccurate estimate based on generic costing per pole | -167996.97
C19-200 |  |  | King St E | 500000 | 498066.58 | -0.3867% | 2019 | 2019 | Within Tolerance | -1933.42
C19-201 |  |  | Vimy Ave & Lasalle Ave | 175000 | 158265.86 | -9.562% | 2019 | 2019 | Within Tolerance | -16734.14
C19-202 |  |  | Waverley | 1042000 | 1431630.79 | 37.39% | 2019 | 2019 | Over - Additional anchoring requirements in unfavourable soil | 389630.79
C19-203 |  |  | Grandview, Beaufort and Newbury | 200000 | 189166.09 | -5.417% | 2019 | 2019 | Within Tolerance | -10833.91
UNDERGROUND
C15-205 |  |  | Down Crescent | 130000 | 189142.84 | 45.49% | 2015 | 2016 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 59142.84
C15-207 |  |  | Camelot Dr | 250000 | 222902.52 | -10.84% | 2015 | 2015 | Under - Scope decrease | -27097.48
C14-225 |  |  | Rebuild Sorrento Ave | 150000 | 200759.86 | 33.84% | 2015 | 2016 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 50759.86
C14-228 |  |  | Southgate Dr | 140000 | 203893.92 | 45.64% | 2015 | 2016 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 63893.92
C15-211 |  |  | Cedar St | 260000 | 252672.94 | -2.818% | 2015 | 2015 | Within Tolerance | -7327.06
C16-205 |  |  | NorthDale Ave | 147000 | 95295.49 | -35.17% | 2016 | 2016 | Under - Scope decrease | -51704.51
C16-207 |  |  | 1100 Oxford St | 126000 | 118933.61 | -5.608% | 2016 | 2017 | Within Tolerance | -7066.39
C16-208 |  |  | Athabasca St | 138000 | 134774.82 | -2.337% | 2016 | 2016 | Within Tolerance | -3225.18
C16-209 |  |  | Aruba Cres | 338000 | 346060.05 | 2.385% | 2016 | 2016 | Within Tolerance | 8060.05
C17-205 |  |  | 1010 Glen St | 160000 | 176802.58 | 10.5% | 2017 | 2017 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 16802.58
C17-206 |  |  | Annandale St | 170000 | 138037.7 | -18.8% | 2017 | 2017 | Under - Scope decrease | -31962.3
C17-207 |  |  | CherryDown Dr | 185000 | 189840.73 | 2.617% | 2017 | 2017 | Within Tolerance | 4840.73
C17-208 |  |  | Birkdale St | 195000 | 191405.71 | -1.843% | 2017 | 2017 | Within Tolerance | -3594.29
C18-205 |  |  | Gladfern | 405000 | 491811.42 | 21.43% | 2018 | 2018 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 86811.42
C18-206 |  |  | Traddles | 321000 | 375980.58 | 17.13% | 2018 | 2018 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 54980.58
C18-207 |  |  | Outlet Dr | 195000 | 253740.56 | 30.12% | 2018 | 2018 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 58740.56
C15-210 |  |  | Marwood Dr Townhouse complex | 290000 | 67087.35 | -76.87% | 2015 | 2016 | Under - Scope decrease | -222912.65
C19-204 |  |  | Central Park Blvd N | 256000 | 420071.93 | 64.09% | 2019 | 2019 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 164071.93
C19-205 |  |  | Ormond Dr | 234000 | 299044.17 | 27.8% | 2019 | 2019 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 65044.17
C19-206 |  |  | Beaufort Court | 124000 | 151366.91 | 22.07% | 2019 | 2019 | Over - Inaccurate estimate based on generic costing per meter and additional City sidewalk remediation requirements | 27366.91
STATIONS
C15-260 / C16-260 |  |  | Substation Breaker Replacement | 350000 | 255328.44 | -27.05% | 2016 | 2016 | Under - Alternate breaker selection | -94671.56
C16-264 |  |  | 44kV oil circuit breakers replacement | 1500000 | 1510555.36 | 0.7037% | 2018 | 2018 | Within Tolerance | 10555.36
C14-263 |  |  | MS14 - Metalclad Switchgear | 1360000 | 1632383.19 | 20.03% | 2015 | 2015 | Over - Unforeseen civil work | 272383.19
C19-269 |  |  | MS10 T2 | 1000000 | 1073426 | 7.343% | 2019 | 2020 | Within Tolerance | 73426
SYSTEM ACCESS
MUNICIPAL & REGIONAL WORK
C14-213 |  |  | 407 Extension - Harmony Rd Int | 125000 | 203075.47 | 62.46% | 2015 | 2018 | Over - Scope increase driven by Third Party | 78075.47
C16-211 |  |  | Region Relocate - Harmony Rd N - Rossland to Taunton | 654000 | 231564.91 | -64.59% | 2015 | 2018 | Under - Scope decrease driven by Third Party | -422435.09
C14-216 |  |  | Region Relocate - Winchester & Harmony Int | 200000 | 197334.01 | -1.333% | 2015 | 2016 | Within Tolerance | -2665.99
C14-218 |  |  | Region Relocate - Harmony Rd N -Coldstream to Taunton | 480000 | 331771.33 | -30.88% | 2015 | 2016 | Under - Scope decrease driven by Third Party | -148228.67
C15-213 |  |  | Region relocate - Thornton Rd from Champlain | 470000 | 566148.11 | 20.46% | 2017 | 2018 | Over - Scope increase driven by Third Party | 96148.11
C13-209 |  |  | City Relocate - Conlin Rd - East of Stevenson to Founders | 255000 | 169061.46 | -33.7% | 2015 | 2015 | Under - Scope decrease driven by Third Party | -85938.54
SYSTEM SERVICE
STATIONS
C15-261 |  |  | Distribution Capacity - MS9 | 7000000 | 7319517.18 | 4.565% | 2018 | 2018 | Within Tolerance | 319517.18
C16-262 |  |  | HONI Contributions - Enfield TS | 4000000 | 4136704.74 | 3.418% | 2018 | 2019 | Within Tolerance | 136704.74
C16-263 |  |  | Neutral Reactors | 1500000 | 910174.76 | -39.32% | 2016 | 2018 | Under - Selected contractor provided better costing than initially estimated | -589825.24
GRID MODERNIZATION
C17-260 / C18-260 |  |  | Overhead Automated Switches | 955000 | 911417.92 | -4.564% | 2018 | 2019 | Within Tolerance | -43582.08
C16-265 / C14-256 / C15-251 |  |  | Downtown Self Healing Grid & Distribution Automation | 1255000 | 1742564.78 | 38.85% | 2016 | 2018 | Over - Unforeseen complications in UG commissioning and coordination of outages with downtown businesses | 487564.78
C15-263 |  |  | Smart Fault Indicators | 125000 | 114075.25 | -8.74% | 2019 | 2019 | Within Tolerance | -10924.75
C16-802 |  |  | Transmission Management | 175000 | 170750 | -2.429% | 2019 | 2019 | Within Tolerance | -4250
OVERHEAD
C18-211 /C18-213 / C18-214 |  |  | MS9 OH Feeders | 7560000 | 2627865.56 | -65.24% | 2018 | TBD | In progress - 3 feeders constructed and in service, additional feeder construction to be coordinated with regional/municipal work | -4932134.44
C18-209 / C18-208 |  |  | Enfield TS Egress & 44kV feeders | 6463000 | 4827914.75 | -25.3% | 2019 | TBD | In progress - additional intersection construction to be coordinated with regional/municipal work | -1635085.25
GENERAL PLANT
OPERATIONAL TECHNOLOGY
C14-801 |  |  | OMS Implementation | 920000 | 1183961.71 | 28.69% | 2017 | 2017 | Over - Unforseen additional system integration requirements | 263961.71
C16-812 / C19-821 |  |  | ODS Replacement | 400000 | 420022.14 | 5.006% | 2019 | 2019 | Within Tolerance | 20022.14