## Sheet1
Projects | 2016 |  |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 Bridge Year
| Plan Gross ($) | Actual Gross ($) | Variance (%) | Explanation | Date Variance | Plan Gross ($) | Actual Gross ($) | Variance (%) | Explanation | Date Variance | Plan Gross ($) | Actual Gross ($) | Variance (%) | Explanation | Date Variance | Plan Gross ($) | Actual Gross ($) | Variance (%) | Explanation | Date Variance | Plan Gross ($)
System Access
Technical Service Layouts | 376035.71 | 685792 | 82.37% | Additional transformation costs, contract labour during a maternity leave | n/a | 384684.5313 | 682868 | 77.51% | Primary drivers for this variance include timing of customers work versus when payments are received and cost of transformation which is not recovered, rather transformation is treated as a capital asset. |  | 393532.2756 | 966058 | 145.5% | Primary drivers for this variance include timing of customers work versus when payments are received and cost of transformation which is not recovered, rather transformation is treated as a capital asset. |  | 402583.5179 | 743161 | 84.6% | Primary drivers for this variance include timing of customers work versus when payments are received and cost of transformation which is not recovered, rather transformation is treated as a capital asset. |  | 530579
Subdivisions | 207000 | 59658 | -71.18% | This is customer driven work and in this year there was less than anticipated. |  | 244260 | 296871 | 21.54% | This is customer driven work and in this year there was more than anticipated due to new developments going into design. |  | 288226.8 | 360763 | 25.17% | This is customer driven work and in this year there was more than anticipated due to new developments going into design. |  | 340107.624 | 160640 | -52.77% | This is customer driven work and in this year there was less than anticipated. |  | 270183
Renewable Generation | 43734.54 | 191934 | 338.9% | Higher volume of applications than anticipated | n/a | 44609.2308 | 87377 | 95.87% | Higher than anticipated volume of applications |  | 45501.4154 | 80459 | 76.83% | Higher than anticipated volume of applications |  | 46411.4437 | 15922 | -65.69% | Reduction in applications due to cancellation of programs |  | 42224
Municipally Driven Projects | 357295 | 0 | -100% | Projects deferred by Region of Halton | Trafalgar Rd project deferred beyond 2020. Exact date not yet known. |  | 492 |  |  |  | 2426000 | 63909.69 | -97.37% | Region of Peel road improvement project on Winston Churchill Blvd. deferred | Unknown - Region of Peel has not proceeded at this time. |  | 21469 |  |  |  | 1143570
Metering | 159550 | 24252 | -84.8% | PMU replacements deferred due to possible customer changes to their services which would have affected the PMUs implemented |  | 194988 | 152049 | -22.02% | Meter exchange, upgrade and re-verification work was lower than anticipated. |  | 159550 | 301016 | 88.67% | Higher than anticipated new commercial service installs and commercial/residential meter replacements. Higher than anticipted costs associated to GS >50 kW meter replacements. New meter procurements and replacements were necessary to commence compliance sampling. |  | 159550 | 421185 | 164% | Higher than anticipated number of meter exchanges required. Costs for metering services contractor to train new apprentice meter technician due to staff turn over |  | 435914
Substation Projects |  | 0 |  |  |  |  | 0 |  |  |  |  | 294865 |  | Replacement of MS transformer. Adding 4th feeder infrastructure and Georgetown MS. |  |  | 314998 |  | Unbudgeted costs related to replacement of Silvercreek MS Transformer
System Renewal
Pole Replacements | 2000000 | 2141311 | 7.066% | Within 10% |  | 2000000 | 1864536 | -6.773% | Within 10% |  | 2000000 | 1947990 | -2.601% | Within 10% |  | 2000000 | 1321301 | -33.93% | Reduction in contract labour expense, number of poles replaced decreased - significant progress on backlog made in prior years |  | 715864
Poletrans Replacement Program | 538100 | 655716 | 21.86% | Over budget due to complexities of construction that were unknown at the time the budget was prepared |  | 603100 | 996718 | 65.27% | Over budget due to construciton complexities and evolving municipal requirements that were unknown when budgeting |  | 555500 | 895811 | 61.26% | Scope altered to accelerate project due to custome rimpacts, evolving municipal requirements such as tree protection and temporary restoration affected budget |  | 547125 | 1640316 | 199.8% | Scope altered to accelerate project due to custome rimpacts, evolving municipal requirements such as tree protection and temporary restoration affected budget |  | 1026848
Porcelain Insulator Replacement Program | 21686.11 | 20614 | -4.944% | < Materiality threshold |  | 22119.83 | 44544 | 101.4% | < Materiality threshold |  | 22562.23 | 8921 | -60.46% | < Materiality threshold |  | 23013.47 | 62443 | 171.3% | HHHI replaced more insulators than planned for in the DSP. Porcelain insulators represent a safety and reliability concern. |  | 49132
Transformer Replacement Program | 98689.44 | 134640 | 36.43% | The actual costs were higher than anticipated mostly due to contract labour costs related to civil work. |  | 178623.91 | 115133 | -35.54% | Project actuals were not as high as anticipated. |  | 108805.11 | 102772 | -5.545% | Within 10% |  | 217122.68 | 184143 | -15.19% | Budgeted transformer vault was not replaced |  | 84716
Substation Equipment | 1065071 | 677093 | -36.43% | 1. Cross MS switchgear received late in 2016 and deferring installation and commissioning to 2017 2. Design for Willow MS took longer than anticipated due to contracting the design to an outside firm due to a maternity leave. Construction was deferred to 2017, ensuring adequate preparation for construction. | Construction deferred to 2017 | 953352 | 524904 | -44.94% | Power transformer replacement project deferred in favour of completion of Cross MS switchgear and feeder egress at Mountainview MS | Power transformer replacement deferred |  | 0 |  |  |  | 484808 | 0 | -100% | Willow power transformer replacement deferred | Deferred to 2021 | 143037
Distribution Equipment Renewal |  | 0 |  |  |  |  | 2859 |  | < Materiality threshold |  | 91425 | 18052 | -80.25% | PMU replacements deferred due to possible customer changes to their services which would have affected the PMUs implemented |  | 72824.93 | 22576 | -69% | Fence grounding improvements at Glen Williams MS deferred | Deferred - date undetermined
Feeder Reinforcement |  | 0 |  |  |  | 22727.88 | 196398 | 764.1% | Unbudgeted local area distribution upgrade project for Lakeview Subdivision converting rear-lot distribution to front lot for improved reliability of supply to customers |  |  | 0 |  |  |  | 506452.25 | 0 | -100% | Acton feeder tie project did not proceed | Deferred to next DSP.
Vintage Replacements | 396011 | 1135736 | 186.8% | Vintage underground cable replacements were $217,928 under budget as a result of the scope of work for 2016 being less than originally anticipated to ensure project spending as a whole was paced accordingly | Some work deferred to 2018 | 446936 | 664363 | 48.65% | Actual cost increase due to unexpected complexities of construction in working on private property |  | 40000 | 958143 | 2295% | Conclusion of work started in 2016, some construction work moved forward, additional cost impacts due to vehicle access limitations on private lands | Deferral from 2016 | 40000 | 0 | -100% | < Materiality threshold |  | 50811
System Service
Feeder Improvements | 1281412 | 1027163 | -19.84% | Plan to rebuild and extend 27.6kV on Trafalgar Road north deferred due to Region of Halton Trafalgar Rd project delayed. Instead, project on Delrex Blvd brought forward from 2017 into 2016. |  | 1466813.32 | 618515 | -57.83% | Efficiencies gained during construction reduced the cost of this project | Moved forward to 2016 | 1021187.32 | 828604 | -18.86% | Delrex project moved forward to 2016, 4th line project deferred to 2019 due to permitting delays | one project moved up to 2016, one deferred to 2019 | 360805 | 363395 | 0.7178% | Within 10% |  | 270150
Voltage Conversion | 428336.7 | 402232 | -6.094% | Within 10% |  | 434963.28 | 340409 | -21.74% | Scope of work reduced and installation efficiencies reduced overall costs |  | 494612.42 | 431712 | -12.72% | Scope of work reduced and installation efficiencies reduced overall costs |  | 1661412.12 | 607962 | -63.41% | Construction of project was split into two (2) years, 2019 and 2020 to levelize spending. | 50% Deferred to 2020 | 939061
Substation Upgrades | 155629 | 0 | -100% | Construction deferred to 2019 | 2019 | 272525 | 94650 | -65.27% | River MS Feeder Egress was deferred | Deferred to next DSP. | 1111000 | 83024 | -92.53% | Construction of new municipal substation deferred indefinately | Deferral - date unknown | 936224 | 274854 | -70.64% | Construction of new municipal substation deferred indefinately - as a result, power transformers were not purchased in 2019 | Deferral - date unknown | 67559
Automated Switches & SCADA Integration | 437413.3 | 243887 | -44.24% | One switch was deferred to 2017 | Deferral to 2017 | 236985 | 282226 | 19.09% | Purchase of reclosers deferred from 2016 | Deferred from 2016 | 332036.03 | 252088 | -24.08% | manufacturer delays, one switch deferred |  | 362989.13 | 489670 | 34.9% | Integration of switches - implementing radio backhaul network - unbudgeted |  | 248475
General Plant
Equipment & Tools | 177000 | 208845 | 17.99% | Chassis ordered in 2016 not delivered until 2017 | Deferral to 2017 | 322000 | 527523 | 63.83% | Chassis ordered in 2016 not delivered until 2017 | Deferred from 2016 | 259000 | 249768 | -3.564% | Within 10% |  | 298000 | 238686 | -19.9% | One vehicle not replaced |  | 290000
Software & Systems | 245613 | 177003 | -27.93% | Spending in this area was reduced compared to budget |  | 38840 | 164099 | 322.5% | Individual software expenses below materiality threshold |  | 100000 | 95862 | -4.138% | Within 10% |  | 65000 | 207634 | 219.4% | Unbudgeted costs to upgrade computer and host replacements - MS Exchange and MS Office |  | 231290
Building Equipment | 355000 | 96013 | -72.95% | Parking lot paving was deferred | Has not been rescheduled | 118576 | 69864 | -41.08% | Roof replacement over engineering floor deferred |  | 62000 | 114023 | 83.91% | Unbudgeted GIS asset updates |  | 62000 | 99582 | 60.62% | Unexpected repairs to HVAC system required |  | 100000
Total | 8361000.8 | 8678156 | 3.793% |  |  | 8003876.4621 | 8555128.75 | 6.887% |  |  | 9529066.5306 | 8621568.93 | -9.523% |  |  | 8604919.6538 | 7856114.25 | -8.702% |  |  | 6741327