## SEC125-F2-1-1_Table 1
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-01-SEC-125
Attachment 1
Page 1 of 2
Table 1
Operating Costs Summary - Nuclear ($M)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Cost Item | Actual | Actual | Actual | Actual | Actual | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
OM&A:
Nuclear Operations OM&A
1 | Base OM&A | 1267.5 | 1301.1 | 1255.5 | 1265.6 | 1296.8 | 1311.3 | 1322.7 | 1313.3 | 1298.2 | 1069.5 | 616.3
2 | Project OM&A | 89.1 | 122.7 | 119.1 | 106.1 | 99.6 | 122.3 | 89.1 | 85 | 80.6 | 76.7 | 62
3 | Outage OM&A | 306.7 | 317.4 | 344.9 | 264.3 | 293.9 | 431.2 | 279.1 | 361.2 | 212.4 | 192.6 | 61.3
4 | Subtotal Nuclear Operations OM&A | 1663.4 | 1741.3 | 1719.4 | 1636 | 1690.2 | 1864.8 | 1690.9 | 1759.5 | 1591.2 | 1338.8 | 739.7
0
5 | Darlington Refurbishment OM&A | 3.1 | 36.1 | 31.3 | 1.7 | 19 | 42.9 | 24.2 | 23.6 | 29.3 | 25 | 8.4
6 | Darlington New Nuclear OM&A | 0.8 | 0.7 | 2.4 | 5 | 13.1 | 206 | 2.2 | 2.2 | 2.3 | 2.3 | 2.3
7 | Allocation of Corporate Costs | 360.5 | 377 | 368.6 | 361.7 | 370.1 | 396.1 | 387.9 | 380 | 375.3 | 334.3 | 252.9
8 | Allocation of Centrally Held Costs | 306 | 242.9 | 256.2 | 238.6 | 215.6 | 197.2 | 184.5 | 161.6 | 143.9 | 98.9 | 14.7
9 | Asset Service Fees1 | 34.1 | 35.6 | 37 | 47.8 | 55.6 | 54.6 | 51.5 | 55.2 | 65.1 | 69.7 | 65.3
10 | Subtotal Other OM&A | 704.5 | 692.3 | 695.6 | 654.8 | 673.4 | 896.8 | 650.3 | 622.6 | 615.9 | 530.2 | 343.6
11 | Total OM&A | 2367.9 | 2433.6 | 2415 | 2290.8 | 2363.6 | 2761.5 | 2341.2 | 2382 | 2207.1 | 1869 | 1083.3
12 | Nuclear Fuel Costs | 262.1 | 225.2 | 231.6 | 244.5 | 234.9 | 202.5 | 178.3 | 182.1 | 209.4 | 188.6 | 148.2
Other Operating Cost Items:
13 | Depreciation and Amortization | 281.6 | 366.1 | 324.1 | 333 | 454.1 | 545.2 | 553 | 471.5 | 578.7 | 521.6 | 568.6
14 | Income Tax | -39.5 | -27.7 | -4.2 | 33.1 | 152.5 | -17.6 | -16.5 | -16.3 | -16.4 | -16.1 | -15.9
15 | Property Tax | 14.1 | 13 | 12.7 | 12.5 | 12 | 12.6 | 12.9 | 13.2 | 13.6 | 12.7 | 9.8
16 | Total Operating Costs | 2886.2 | 3010.2 | 2979.2 | 2913.9 | 3217 | 3504.2 | 3068.9 | 3032.6 | 2992.4 | 2575.8 | 1793.9
Notes:
1 | Includes asset service fees of $2.3M (2022), $2.2M (2023), $2.0M (2024), $3.5M (2025) and $3.2M (2026) charged to Laurentis Energy Partners for the use of Darlington reactors to produce Molybdenum-99 (Ex. F3-1-4)

## SEC125-F2-1-1_Table 2
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-01-SEC-125
Attachment 1
Page 2 of 2
Table 2
Nuclear Staff Summary - Regular and Non-Regular (FTEs)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Group | Actual | Actual | Actual | Actual | Actual | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
NUCLEAR OM&A:
1 | Regular Staff | 5072.6 | 5034.6 | 4827.9 | 4571.9 | 4356.9 | 4209.7 | 3973.1 | 3865.2 | 3685.9 | 3069.2 | 2117
Non-Regular Staff
2 | Term and Extended Temporary | 12 | 91.1 | 223.8 | 378.5 | 584.4 | 787.2 | 885.3 | 875.1 | 881.6 | 600.7 | 0
3 | Temporary | 716.4 | 741.2 | 785 | 769.2 | 766.2 | 783.4 | 561 | 523.5 | 412.5 | 180.6 | 115.4
4 | EPSCA | 46.3 | 72.3 | 85 | 71.4 | 76.7 | 81.9 | 87.6 | 84.1 | 79.3 | 55.9 | 49.5
5 | Total Non-Regular Staff | 774.7 | 904.6 | 1093.7 | 1219.2 | 1427.3 | 1652.5 | 1533.9 | 1482.7 | 1373.5 | 837.2 | 164.9
6 | Subtotal Nuclear OM&A | 5847.4 | 5939.2 | 5921.7 | 5791 | 5784.2 | 5862.1 | 5507 | 5347.8 | 5059.4 | 3906.4 | 2281.9
NUCLEAR CAPITAL:
7 | Regular Staff | 228.8 | 251.8 | 237.3 | 227.2 | 222.1 | 242.8 | 220.5 | 221 | 224.7 | 207.7 | 186.7
Non-Regular Staff
8 | Term and Extended Temporary | 0 | 0.1 | 0.9 | 1 | 5.2 | 15.3 | 17 | 17.6 | 15.9 | 2.9 | 0
9 | Temporary | 32.8 | 39.7 | 41.3 | 48.8 | 51.1 | 88 | 85.4 | 83.3 | 82.8 | 76.7 | 72.2
10 | EPSCA | 24.2 | 26.1 | 25.6 | 39.6 | 26 | 52.7 | 44.1 | 36.6 | 22.9 | 21.9 | 20.6
11 | Total Non-Regular Staff | 57.1 | 65.9 | 67.7 | 89.4 | 82.2 | 155.9 | 146.5 | 137.4 | 121.6 | 101.5 | 92.8
12 | Subtotal Nuclear Capital | 285.9 | 317.7 | 305 | 316.6 | 304.3 | 398.7 | 367 | 358.4 | 346.2 | 309.2 | 279.5
DARLINGTON REFURBISHMENT:
13 | Regular Staff | 427.3 | 537.2 | 543.5 | 525.8 | 440.8 | 503.7 | 545 | 545.3 | 500.2 | 417.2 | 247.9
Non-Regular Staff
14 | Temporary | 41 | 59.7 | 81.3 | 131.3 | 118.1 | 154.5 | 155.8 | 161.2 | 142.5 | 96 | 52.6
15 | EPSCA | 73.1 | 187.6 | 249.8 | 200.8 | 128.6 | 221.7 | 243.1 | 284.6 | 215.6 | 149.1 | 55
16 | Total Non-Regular Staff | 114 | 247.3 | 331.1 | 332.1 | 246.7 | 376.2 | 398.9 | 445.7 | 358.2 | 245 | 107.5
17 | Subtotal Darlington Refurbishment | 541.3 | 784.6 | 874.6 | 857.9 | 687.5 | 879.9 | 944 | 991 | 858.4 | 662.2 | 355.4
NUCLEAR PROVISION:
18 | Regular Staff | 309.7 | 334 | 332.7 | 326.5 | 332 | 403.5 | 413.4 | 420.6 | 522.5 | 796.9 | 1432
Non-Regular Staff
19 | Term and Extended Temporary | 0.2 | 1.1 | 3.8 | 4.7 | 8.1 | 5 | 6 | 6 | 6 | 17.2 | 92
20 | Temporary | 30.6 | 38.2 | 38.7 | 43 | 44 | 43.7 | 45.6 | 45.5 | 49.9 | 42.3 | 35
21 | EPSCA | 1 | 3.5 | 4.3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
22 | Total Non-Regular Staff | 31.8 | 42.8 | 46.8 | 50.8 | 55 | 51.7 | 54.6 | 54.5 | 58.9 | 62.5 | 130
23 | Subtotal Nuclear Provision | 341.4 | 376.8 | 379.5 | 377.3 | 387.1 | 455.2 | 468 | 475.1 | 581.3 | 859.4 | 1562
NUCLEAR NON-ENERGY DIRECT:
24 | Regular Staff | 23 | 15.9 | 17.7 | 21.9 | 17.7 | 26 | 26 | 26 | 26 | 13 | 13.9
Non-Regular Staff
25 | Term and Extended Temporary | 0 | 0 | 0 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0
26 | Temporary | 4.5 | 6.1 | 6.1 | 2 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0
27 | Total Non-Regular Staff | 4.5 | 6.1 | 6.1 | 2 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0
28 | Subtotal Nuclear Non-Energy Direct | 27.5 | 22 | 23.9 | 23.9 | 19.5 | 26 | 26 | 26 | 26 | 13 | 13.9
29 | Total Nuclear | 7043.5 | 7440.2 | 7504.6 | 7366.8 | 7182.7 | 7621.9 | 7312 | 7198.4 | 6871.3 | 5750.2 | 4492.6

## SEC126-F2-2-1_Table 1
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-02-SEC-126
Attachment 1
Page 1 of 2
Table 1
Base OM&A - Nuclear ($M)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Function | Actual | Actual | Actual | Actual | Actual | Budget | Plan | Plan | Plan | Plan | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Nuclear Stations1
1 | Darlington NGS | 337.2 | 337.2 | 329.2 | 329.7 | 341.1 | 342.5 | 350.1 | 348.6 | 355.6 | 358 | 369.4
2 | Pickering NGS | 468.5 | 481.9 | 447.1 | 458.4 | 463.2 | 462 | 463.8 | 460 | 436.7 | 319.1 | 0
3 | Total Nuclear Stations | 805.7 | 819 | 776.3 | 788.1 | 804.3 | 804.5 | 813.9 | 808.6 | 792.3 | 677.1 | 369.4
Operations and Project Support1,2,3
4 | Enterprise Engineering | 218.3 | 224.9 | 205.5 | 212.1 | 215.7 | 219.4 | 231.1 | 229.8 | 236 | 187.9 | 112.1
5 | Security & Training | 146.8 | 152.5 | 152.5 | 151.7 | 160.4 | 162.4 | 163.6 | 165.4 | 161.7 | 125.7 | 78.2
6 | Integrated Fleet Management | 68.3 | 65.9 | 62.7 | 61.1 | 59.6 | 61 | 67 | 68.1 | 70.2 | 48.3 | 31.7
7 | Enterprise Projects | 6.8 | 9.8 | 10.7 | 10.7 | 13.8 | 10.5 | 12 | 11.1 | 10.6 | 9.9 | 9.3
8 | Other Support4 | 12.1 | 13.6 | 37.2 | 28.1 | 27.4 | 23.6 | 23.3 | 23.5 | 21.8 | 20.3 | 15.6
9 | Total Operations and Project Support | 452.3 | 466.7 | 468.6 | 463.7 | 477 | 476.9 | 497 | 497.8 | 500.2 | 392 | 246.9
CRVA Eligible Costs2
10 | Fuel Channel Life Extension Ongoing | 0 | 0.4 | 0.6 | 1.7 | 7.8 | 15 | 5.9 | 4.3 | 0.8 | 0.4 | 0
11 | Pickering Extended Operations Enabling | 9.6 | 14.9 | 10 | 12.1 | 7.2 | 10.3 | 0 | 0 | 0 | 0 | 0
12 | Optimization of Pickering Shutdown Enabling | 0 | 0 | 0 | 0 | 0.5 | 4.6 | 5.8 | 2.7 | 4.8 | 0 | 0
13 | Total CRVA Eligible Costs | 9.6 | 15.3 | 10.5 | 13.8 | 15.6 | 29.9 | 11.7 | 7 | 5.6 | 0.4 | 0
14 | Total Base OM&A | 1267.5 | 1301.1 | 1255.5 | 1265.6 | 1296.8 | 1311.3 | 1322.7 | 1313.3 | 1298.2 | 1069.5 | 616.3
Notes:
1 | The figures presented here are 2016 Actuals that have been restated for Nuclear organizational changes and transfers from Corporate Support ((See Ex. A1-3-1 Attachment 1 and Ex. F2-2-1, Attachment 1).
2 | CRVA Eligible Costs are shown separately, but were previously included in Operations and Project Support (which was called Nuclear Support in EB-2016-0152) with a footnote.
3 | Operations and Project Support has been allocated between Darlington and Pickering station:
|  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
| Darlington NGS | 187 | 197.2 | 192.7 | 193.1 | 208.7 | 218.5 | 222.5 | 227.6 | 227.1 | 220.6 | 246.9
| Pickering NGS | 265.3 | 269.6 | 275.9 | 270.5 | 267.1 | 258.5 | 274.6 | 270.2 | 273.1 | 171.4 | 0
4 | The2016 negative labour price variance reported in “Other Support” in EB-2016-0152, Ex. F2-2-2, p. 2, is now reflected in Centrally Held costs for both budget and actual.

## SEC126-F2-2-1_Table 2
Numbers may not add due to rounding. | [12 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-02-SEC-126
Attachment 1
Page 2 of 2
Table 2
Base OM&A - Nuclear ($M)
Line |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | IR Term
No. | Resource Type | Actual | Actual | Actual | Actual | Actual | Budget | Plan | Plan | Plan | Plan | Plan | Percentage1
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l)
1 | Labour | 826.1 | 849.3 | 819 | 796.3 | 782.2 | 760.7 | 755.4 | 739.5 | 736.7 | 607.6 | 422.4 | 58%
2 | Non-Regular Labour | 53.8 | 59 | 76.3 | 101 | 125.7 | 126.5 | 133.4 | 136.2 | 136.3 | 87.2 | 12.4 | 9%
3 | Overtime | 66.4 | 69.8 | 68.5 | 70.1 | 70.4 | 66.8 | 70.4 | 69.4 | 69.2 | 55.1 | 34.4 | 5.3%
4 | Augmented Staff | 12.3 | 14.5 | 11.6 | 11.8 | 13.3 | 11.7 | 11.2 | 11.1 | 10.7 | 3.6 | 1 | 0.7%
5 | Materials | 83 | 97.2 | 95.4 | 95.2 | 100.2 | 102.9 | 105 | 106.9 | 106.7 | 92.3 | 44.8 | 8.1%
6 | License Fees | 36 | 32.1 | 34.7 | 36 | 31.6 | 39.3 | 40.7 | 42.1 | 43.3 | 36.7 | 22.1 | 3.3%
7 | Other Purchased Services | 130.5 | 128.1 | 107.9 | 115.9 | 127.7 | 157.1 | 158.4 | 160.5 | 148.7 | 149.7 | 58 | 12%
8 | Other2 | 59.6 | 50.9 | 42.1 | 39.3 | 45.7 | 46.3 | 48.2 | 47.6 | 46.5 | 37.3 | 21.1 | 3.6%
9 | Total Base OM&A | 1267.5 | 1301.1 | 1255.5 | 1265.6 | 1296.8 | 1311.3 | 1322.7 | 1313.3 | 1298.2 | 1069.5 | 616.3 | 100%
Notes:
1 | IR Term Percentage = Sum of IR Term Resource Costs divided by Sum of IR Term Base OM&A.
2 | Other costs include Variable Low & Intermediate Level Waste fees:
|  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
|  | 2.2 | 4.8 | 5.9 | 5.1 | 6.9 | 5.8 | 4.8 | 5.1 | 5.5 | 4.8 | 3.5

## SEC131-F2_5_2 Table 1a
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-05-SEC-131
Attachment 1
Page 1 of 2
Table 1a
Comparison of Nuclear Fuel Costs ($M) 2016-2021
Line |  | 2016 | (c)-(a) | 2016 | (g)-(c) | 2017 | (g)-(e) | 2017 | (k)-(g) | 2018 | (k)-(i) | 2018
No. | Business Unit | Budget | Change | Actual | Change | OEB Approved | Change | Actual | Change | OEB Approved | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Uranium:
1 | Darlington NGS1 | 112.5 | 0.9 | 113.4 | -27.5 | 81.1 | 4.8 | 86 | 1.4 | 80.8 | 6.5 | 87.3
2 | Pickering NGS | 86 | -0.8 | 85.3 | 6.7 | 78.2 | 13.8 | 92 | -2.8 | 78.3 | 10.9 | 89.2
3 | Total Fuel Bundle Cost | 198.6 | 0.1 | 198.7 | -20.7 | 159.3 | 18.7 | 178 | -1.5 | 159.1 | 17.4 | 176.5
4 | Total Fuel Bundle Cost2 ($/MWh) | 4.24 |  | 4.36 |  | 4.18 |  | 4.37 |  | 4.14 |  | 4.31
5 | Used Fuel Storage & Disposal3,4 | 62 | -1 | 61 | -15.9 | 41.6 | 3.5 | 45.1 | -1.8 | 43.3 | 8.5 | 51.8
6 | Fuel Oil | 4.2 | -1.8 | 2.4 | -0.3 | 4.3 | -2.2 | 2.1 | 2.3 | 4.4 | -1.1 | 3.3
7 | Total Nuclear Fuel Costs | 264.8 | -2.7 | 262.1 | -36.9 | 205.2 | 20 | 225.2 | -1 | 206.8 | 24.8 | 231.6
Line |  | 2018 | (e)-(a) | 2019 | (e)-(c) | 2019 | (i)-(e) | 2020 | (i)-(g) | 2020 | (k)-(i) | 2021
No. | Business Unit | Actual | Change | OEB Approved | Change | Actual | Change | OEB Approved | Change | Actual | Change | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Uranium:
8 | Darlington NGS1 | 87.3 | -4 | 80.7 | 2.7 | 83.4 | 14.9 | 83.8 | 14.5 | 98.2 | -30.8 | 67.4
9 | Pickering NGS | 89.2 | 5.2 | 78 | 16.5 | 94.4 | -14.5 | 80.1 | -0.2 | 79.9 | -1.2 | 78.7
10 | Total Fuel Bundle Cost | 176.5 | 1.3 | 158.6 | 19.2 | 177.8 | 0.3 | 163.9 | 14.2 | 178.1 | -32 | 146.1
11 | Total Fuel Bundle Cost2 ($/MWh) | 4.31 |  | 4.07 |  | 4.08 |  | 4.39 |  | 4.07 |  | 3.81
12 | Used Fuel Storage & Disposal3,4 | 51.8 | 13.2 | 53.7 | 11.2 | 65 | -9.7 | 43.3 | 12 | 55.2 | -3.5 | 51.7
13 | Fuel Oil | 3.3 | -1.6 | 4.5 | -2.8 | 1.7 | -0.2 | 4.6 | -3.1 | 1.5 | 3.2 | 4.7
14 | Total Nuclear Fuel Costs | 231.6 | 12.9 | 216.9 | 27.6 | 244.5 | -9.6 | 211.8 | 23.1 | 234.9 | -32.4 | 202.5
Notes:
1 | Includes the impact of an initial fuel load required prior to unit start up of each of the refurbished Darlington units
2 | Nuclear Fuel Bundle Cost (2017-2021) reflects 2% downward adjustment per partial settlement as described in EB-2016-0152 Decision and Order, p. 52.
3 | From Ex. C2-1-1 Table 2, line 2, except for 2020 actual, which is from L-A1-02-Staff-002, Att.1, Table 7 col(a), line 2. Used Fuel Storage & Disposal is discussed in Ex. C2-1-1.
4 | Adjustments to used fuel storage and disposal variable expenses to reflect actual year-end 2016 asset retirement obligation adjustment and discount rate as reflected in Ex. J21.2 (OEB Decision and Order p. 98).

## SEC131-F2_5_2 Table 1b
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-05-SEC-131
Attachment 1
Page 2 of 2
Table 1b
Comparison of Nuclear Fuel Costs ($M) 2021-2026
Line |  | 2021 | (c)-(a) | 2021 | (e)-(c) | 2022 | (g)-(e) | 2023 | (i)-(g) | 2024 | (k)-(i) | 2025
No. | Business Unit | OEB Approved | Change | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Uranium:
15 | Darlington NGS1 | 70.4 | -3 | 67.4 | -13.9 | 53.5 | -13.2 | 40.3 | 19.8 | 60.1 | 7.5 | 67.6
16 | Pickering NGS | 78 | 0.7 | 78.7 | -4.9 | 73.8 | 7.9 | 81.7 | 4 | 85.7 | -14.1 | 71.6
17 | Total Fuel Bundle Cost | 148.4 | -2.3 | 146.1 | -18.8 | 127.3 | -5.3 | 122 | 23.8 | 145.8 | -6.6 | 139.2
18 | Total Fuel Bundle Cost2 ($/MWh) | 4.19 |  | 3.81 |  | 3.83 |  | 3.96 |  | 4.37 |  | 4.61
19 | Used Fuel Storage & Disposal3,4 | 43.9 | 7.9 | 51.7 | -5.5 | 46.2 | 9 | 55.2 | 3.3 | 58.6 | -14.4 | 44.1
20 | Fuel Oil | 4.7 | 0 | 4.7 | 0.1 | 4.8 | 0.1 | 5 | 0.1 | 5.1 | 0.1 | 5.2
21 | Total Nuclear Fuel Costs | 197 | 5.5 | 202.5 | -24.2 | 178.3 | 3.8 | 182.1 | 27.3 | 209.4 | -20.9 | 188.6
Line |  | 2025 | (c)-(a) | 2026
No. | Business Unit | Plan | Change | Plan
|  | (a) | (b) | (c)
Uranium:
22 | Darlington NGS1 | 67.6 | 36 | 103.7
23 | Pickering NGS | 71.6 | -71.6 | 0
24 | Total Fuel Bundle Cost | 139.2 | -35.5 | 103.7
25 | Total Fuel Bundle Cost2 ($/MWh) | 4.61 |  | 4.82
26 | Used Fuel Storage & Disposal3,4 | 44.1 | -1.2 | 42.9
27 | Fuel Oil | 5.2 | -3.6 | 1.6
28 | Total Nuclear Fuel Costs | 188.6 | -40.4 | 148.2
Notes:
1 | Includes the impact of an initial fuel load required prior to unit start up of each of the refurbished Darlington units
2 | Nuclear Fuel Bundle Cost (2017-2021) reflects 2% downward adjustment per partial settlement as described in EB-2016-0152 Decision and Order, p. 52.
3 | From Ex. C2-1-1 Table 2, line 2. Used Fuel Storage & Disposal is discussed in Ex. C2-1-1.
4 | Adjustments to used fuel storage and disposal variable expenses to reflect actual year-end 2016 asset retirement obligation adjustment and discount rate as reflected in Ex. J21.2 (OEB Decision and Order p. 98).

## SEC127-F2-2-2_Table 1a
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-02-SEC-127
Attachment 1
Page 1 of 2
Table 1a
Comparison of Nuclear Base OM&A by Function ($M)1, 2 2016-2021
Line |  | 2016 | (c)-(a) | 2016 | (g)-(c) | 2017 | (g)-(e) | 2017 | (k)-(g) | 2018 | (k)-(i) | 2018
No. | Business Unit | Budget | Change | Actual | Change | OEB Approved | Change | Actual | Change | OEB Approved | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Nuclear Stations
1 | Operations & Maintenance | 653.6 | -16.3 | 637.2 | 14.5 | 647.8 | 3.9 | 651.7 | -25 | 658.4 | -31.7 | 626.7
2 | - Operations | 219.1 | -8.5 | 210.6 | 0.2 | 222.3 | -11.5 | 210.8 | -1.8 | 227.7 | -18.6 | 209
3 | - Maintenance | 434.4 | -7.9 | 426.6 | 14.3 | 425.5 | 15.4 | 440.9 | -23.2 | 430.8 | -13.1 | 417.7
4 | Work Management | 34.1 | -5.7 | 28.4 | 0.6 | 34 | -5 | 29 | -0.5 | 33.6 | -5.1 | 28.5
5 | Site and Support Services | 109.2 | 14.4 | 123.6 | -2.9 | 110 | 10.7 | 120.6 | -19.4 | 114.9 | -13.7 | 101.2
6 | Tritium Removal Facility | 17.7 | -1.2 | 16.5 | 1.2 | 21 | -3.3 | 17.7 | 2.2 | 21.9 | -2 | 19.9
7 | Total Nuclear Stations | 814.5 | -8.8 | 805.7 | 13.4 | 812.7 | 6.3 | 819 | -42.7 | 828.8 | -52.5 | 776.3
Operations and Project Support
8 | Enterprise Engineering | 220.6 | -2.3 | 218.3 | 6.6 | 227.2 | -2.3 | 224.9 | -19.4 | 223.3 | -17.8 | 205.5
9 | Security & Training | 146.7 | 0.1 | 146.8 | 5.8 | 146.7 | 5.9 | 152.5 | 0 | 146.3 | 6.2 | 152.5
10 | Integrated Fleet Management | 73 | -4.7 | 68.3 | -2.5 | 69.8 | -3.9 | 65.9 | -3.2 | 69.5 | -6.8 | 62.7
11 | Enterprise Projects | 5.7 | 1.2 | 6.8 | 3 | 10.2 | -0.4 | 9.8 | 0.9 | 9.2 | 1.4 | 10.7
12 | Other Support4 | 14.1 | -2.1 | 12.1 | 1.6 | 15.3 | -1.6 | 13.6 | 23.6 | 24.6 | 12.6 | 37.2
13 | Total Operations and Project Support | 460.1 | -7.8 | 452.3 | 14.5 | 469.1 | -2.4 | 466.7 | 1.8 | 473 | -4.4 | 468.6
CRVA Eligible Costs
14 | Fuel Channel Life Extension Ongoing | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 0.4 | 0.2 | 5 | -4.4 | 0.6
15 | Pickering Extended Operations Enabling | 10.5 | -0.9 | 9.6 | 5.3 | 1 | 13.9 | 14.9 | -5 | 0 | 10 | 10
16 | Optimization of Pickering Shutdown Enabling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Total CRVA Eligible Costs | 10.5 | -0.9 | 9.6 | 5.7 | 1 | 14.3 | 15.3 | -4.8 | 5 | 5.5 | 10.5
18 | Total Base OM&A Before Adjustments | 1285.2 | -17.6 | 1267.5 | 33.6 | 1282.9 | 18.2 | 1301.1 | -45.7 | 1306.8 | -51.3 | 1255.5
19 | OEB Adjustments to Nuclear OM&A3 |  |  |  |  | -56.2 | 56.2 |  |  | -55.9 | 55.9
20 | Total Base OM&A Including Adjustments | 1285.2 | -17.6 | 1267.5 | 33.6 | 1226.7 | 74.4 | 1301.1 | -45.7 | 1250.9 | 4.6 | 1255.5
Line |  | 2018 | (e)-(a) | 2019 | (e)-(c) | 2019 | (i)-(e) | 2020 | (i)-(g) | 2020 | (k)-(i) | 2021
No. | Business Unit | Actual | Change | OEB Approved | Change | Actual | Change | OEB Approved | Change | Actual | Change | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Nuclear Stations
21 | Operations & Maintenance | 626.7 | 6.3 | 671.5 | -38.4 | 633.1 | 10.2 | 669.9 | -26.6 | 643.3 | -7.7 | 635.6
22 | - Operations | 209 | 3.5 | 231.7 | -19.2 | 212.6 | -1.4 | 224.8 | -13.6 | 211.2 | -4.1 | 207.1
23 | - Maintenance | 417.7 | 2.8 | 439.8 | -19.3 | 420.5 | 11.6 | 445.1 | -13 | 432.1 | -3.6 | 428.5
24 | Work Management | 28.5 | -0.1 | 34.1 | -5.7 | 28.4 | 2.8 | 34.6 | -3.4 | 31.2 | 0.8 | 32.1
25 | Site and Support Services | 101.2 | 7.6 | 116.3 | -7.5 | 108.8 | 1.6 | 120.4 | -10 | 110.4 | 1.9 | 112.3
26 | Tritium Removal Facility | 19.9 | -2.1 | 20.8 | -3 | 17.7 | 1.6 | 21.1 | -1.8 | 19.3 | 5.2 | 24.4
27 | Total Nuclear Stations | 776.3 | 11.7 | 842.7 | -54.6 | 788.1 | 16.2 | 846 | -41.8 | 804.3 | 0.2 | 804.5
Operations and Project Support
28 | Enterprise Engineering | 205.5 | 6.6 | 228.5 | -16.4 | 212.1 | 3.6 | 236.8 | -21.1 | 215.7 | 3.7 | 219.4
29 | Security & Training | 152.5 | -0.9 | 150.5 | 1.2 | 151.7 | 8.7 | 152.4 | 8 | 160.4 | 1.9 | 162.4
30 | Integrated Fleet Management | 62.7 | -1.5 | 71.5 | -10.4 | 61.1 | -1.5 | 73.6 | -13.9 | 59.6 | 1.3 | 61
31 | Enterprise Projects | 10.7 | 0 | 9.2 | 1.5 | 10.7 | 3.1 | 9.3 | 4.5 | 13.8 | -3.3 | 10.5
32 | Other Support4 | 37.2 | -9.1 | 17 | 11.1 | 28.1 | -0.7 | 16.7 | 10.6 | 27.4 | -3.8 | 23.6
33 | Total Operations and Project Support | 468.6 | -4.9 | 476.7 | -13.1 | 463.7 | 13.3 | 488.8 | -11.8 | 477 | 0 | 476.9
CRVA Eligible Costs
34 | Fuel Channel Life Extension Ongoing | 0.6 | 1.1 | 5 | -3.3 | 1.7 | 6.1 | 6 | 1.8 | 7.8 | 7.2 | 15
35 | Pickering Extended Operations Enabling | 10 | 2.2 | 0 | 12.1 | 12.1 | -4.9 | 0 | 7.2 | 7.2 | 3 | 10.3
36 | Optimization of Pickering Shutdown Enabling | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 0.5 | 4.1 | 4.6
37 | Total CRVA Eligible Costs | 10.5 | 3.3 | 5 | 8.8 | 13.8 | 1.7 | 6 | 9.6 | 15.6 | 14.3 | 29.9
38 | Total Base OM&A Before Adjustments | 1255.5 | 10.1 | 1324.4 | -58.9 | 1265.6 | 31.2 | 1340.8 | -44 | 1296.8 | 14.5 | 1311.3
37 | OEB Adjustments to Nuclear OM&A3 |  |  | -56 | 56 |  |  | -56.1 | 56.1
39 | Total Base OM&A Including Adjustments | 1255.5 | 10.1 | 1268.4 | -2.8 | 1265.6 | 31.2 | 1284.7 | 12.1 | 1296.8 | 14.5 | 1311.3
Notes:
1 | Bold italic font indicates variance of 10% or greater.
2 | All 2016-2021 values (Budget, Actuals, OEB Approved) have been restated for Nuclear organizational changes and transfers from Corporate Support (See Ex. A1-3-1 Attachment 1 and Ex. F2-2-1, Attachment 1).
3 | OEB Adjustments to approved values in 2017-2021 include the annual disallowance of $25M for nuclear Base OM&A (EB-2016-0152 Decision and Order, p. 55) and the annual $30M disallowed in compensation (EB-2016-0152 Decision and Order, p. 84). OEB adjusted values also include adjustments to low and intermediate level waste management variable expenses (EB-2016-0152 PAO Appendix A Table 1a/2a/3a/4a/5a, note 5b and per Ex. N1).
4 | The 2016 negative labour price variance reported in “Other Support” in EB-2016-0152, Ex. F2-2-2, p. 2, is now reflected in Centrally Held costs for both budget and actual.

## SEC127-F2-2-2_Table 1b
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-02-SEC-127
Attachment 1
Page 2 of 2
Table 1b
Comparison of Nuclear Base OM&A by Function ($M) 2021-2026
Line |  | 2021 | (c)-(a) | 2021 | (e)-(c) | 2022 | (g)-(e) | 2023 | (i)-(g) | 2024 | (k)-(i) | 2025
No. | Business Unit | OEB Approved | Change | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Nuclear Stations
40 | Operations & Maintenance | 669.5 | -33.9 | 635.6 | 10.3 | 646 | -6.9 | 639.1 | -9.1 | 630 | -105 | 525.1
41 | - Operations | 220.5 | -13.4 | 207.1 | -3.3 | 203.9 | -11.6 | 192.3 | -0.8 | 191.5 | -45.9 | 145.6
42 | - Maintenance | 449 | -20.5 | 428.5 | 13.6 | 442.1 | 4.7 | 446.8 | -8.3 | 438.5 | -59 | 379.5
43 | Work Management | 34.5 | -2.5 | 32.1 | -1.2 | 30.9 | -1.7 | 29.2 | -2.3 | 27 | -6.4 | 20.5
44 | Site and Support Services | 123.3 | -11 | 112.3 | 3.8 | 116.1 | 1 | 117.1 | -3.7 | 113.4 | -6.9 | 106.5
45 | Tritium Removal Facility | 22.1 | 2.4 | 24.4 | -3.5 | 21 | 2.2 | 23.2 | -1.3 | 21.9 | 3.1 | 25
46 | Total Nuclear Stations | 849.4 | -45 | 804.5 | 9.4 | 813.9 | -5.3 | 808.6 | -16.3 | 792.3 | -115.2 | 677.1
Operations and Project Support
47 | Enterprise Engineering | 244.5 | -25.1 | 219.4 | 11.7 | 231.1 | -1.3 | 229.8 | 6.2 | 236 | -48.2 | 187.9
48 | Security & Training | 156.6 | 5.8 | 162.4 | 1.3 | 163.6 | 1.7 | 165.4 | -3.7 | 161.7 | -36 | 125.7
49 | Integrated Fleet Management | 73.8 | -12.8 | 61 | 6 | 67 | 1.1 | 68.1 | 2.1 | 70.2 | -21.9 | 48.3
50 | Enterprise Projects | 7.3 | 3.2 | 10.5 | 1.5 | 12 | -0.9 | 11.1 | -0.5 | 10.6 | -0.7 | 9.9
51 | Other Support | 15.8 | 7.8 | 23.6 | -0.3 | 23.3 | 0.2 | 23.5 | -1.7 | 21.8 | -1.5 | 20.3
52 | Total Operations and Project Support | 498.1 | -21.2 | 476.9 | 20.1 | 497 | 0.7 | 497.8 | 2.5 | 500.2 | -108.2 | 392
CRVA Eligible Costs
53 | Fuel Channel Life Extension Ongoing | 6 | 9 | 15 | -9.1 | 5.9 | -1.6 | 4.3 | -3.5 | 0.8 | -0.4 | 0.4
54 | Pickering Extended Operations Enabling | 0 | 10.3 | 10.3 | -10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Optimization of Pickering Shutdown Enabling | 0 | 4.6 | 4.6 | 1.2 | 5.8 | -3.2 | 2.7 | 2.2 | 4.8 | -4.8 | 0
56 | Total CRVA Eligible Costs | 6 | 23.9 | 29.9 | -18.1 | 11.7 | -4.8 | 7 | -1.3 | 5.6 | -5.2 | 0.4
57 | Total Base OM&A Before Adjustments | 1353.5 | -42.3 | 1311.3 | 11.4 | 1322.7 | -9.4 | 1313.3 | -15.1 | 1298.2 | -228.6 | 1069.5
58 | OEB Adjustments to Nuclear OM&A3 | -56.2 | 56.2
59 | Total Base OM&A Including Adjustments | 1297.3 | 14 | 1311.3 | 11.4 | 1322.7 | -9.4 | 1313.3 | -15.1 | 1298.2 | -228.6 | 1069.5
Line |  | 2025 | (c)-(a) | 2026
No. | Business Unit | Plan | Change | Plan
|  | (a) | (b) | (c)
Nuclear Stations
60 | Operations & Maintenance | 525.1 | -237.9 | 287.2
61 | - Operations | 145.6 | -59.2 | 86.4
62 | - Maintenance | 379.5 | -178.7 | 200.8
63 | Work Management | 20.5 | -7.7 | 12.9
64 | Site and Support Services | 106.5 | -59.1 | 47.4
65 | Tritium Removal Facility | 25 | -3 | 22
66 | Total Nuclear Stations | 677.1 | -307.7 | 369.4
Operations and Project Support
67 | Enterprise Engineering | 187.9 | -75.7 | 112.1
68 | Security & Training | 125.7 | -47.5 | 78.2
69 | Integrated Fleet Management | 48.3 | -16.5 | 31.7
70 | Enterprise Projects | 9.9 | -0.6 | 9.3
71 | Other Support4 | 20.3 | -4.7 | 15.6
72 | Total Operations and Project Support | 392 | -145 | 246.9
CRVA Eligible Costs
73 | Fuel Channel Life Extension Ongoing | 0.4 | -0.4 | 0
74 | Pickering Extended Operations Enabling | 0 | 0 | 0
75 | Optimization of Pickering Shutdown Enabling | 0 | 0 | 0
76 | Total CRVA Eligible Costs | 0.4 | -0.4 | 0
77 | Total Base OM&A | 1069.5 | -453.2 | 616.3
Notes:
1 | Bold italic font indicates variance of 10% or greater.
2 | All 2016-2021 values have been restated for Nuclear organizational changes and transfers from Corporate Support (See Ex. A1-3-1 Attachment 1 and Ex. F2-2-1, Attachment 1).
3 | OEB Adjustments to approved values in 2017-2021 include the annual disallowance of $25M for nuclear Base OM&A (EB-2016-0152 Decision and Order, p. 55) and the annual $30M disallowed in compensation (EB-2016-0152 Decision and Order, p. 84). OEB adjusted values also include adjustments to low and intermediate level waste management variable expenses (EB-2016-0152 PAO Appendix A Table 1a/2a/3a/4a/5a, note 5b and per Ex. N1).

## SEC128-F2-4-2_Table 1a
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-04-SEC-128
Attachment 1
Page 1 of 2
Table 1a
Comparison of Outage OM&A - Nuclear ($M)1 2016-2021
Line |  | 2016 | (c)-(a) | 2016 | (g)-(c) | 2017 | (g)-(e) | 2017 | (k)-(g) | 2018 | (k)-(i) | 2018
No. | Business Unit | Budget | Change | Actual | Change | OEB Approved | Change | Actual | Change | OEB Approved | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Darlington Outages
1 | Darlington NGS | 93.6 | -3.4 | 90.2 | 33.3 | 135.5 | -12 | 123.5 | 13.4 | 123.7 | 13.2 | 136.9
2 | Operations and Project Support2 | 31.6 | -6.4 | 25.2 | -12.5 | 37.1 | -24.4 | 12.7 | -0.1 | 21.7 | -9.1 | 12.6
3 | Total Darlington Outages | 125.2 | -9.8 | 115.4 | 20.8 | 172.6 | -36.4 | 136.2 | 13.3 | 145.3 | 4.1 | 149.5
Pickering Outages
4 | Pickering NGS | 129 | -0.7 | 128.3 | -24.2 | 134.3 | -30.2 | 104.1 | 17 | 139.9 | -18.8 | 121.1
5 | Operations and Project Support2 | 66.7 | -3.7 | 63 | -20.7 | 57.6 | -15.2 | 42.4 | 9.8 | 44.7 | 7.5 | 52.1
6 | Total Pickering Outages | 195.7 | -4.4 | 191.3 | -44.8 | 191.9 | -45.4 | 146.5 | 26.8 | 184.6 | -11.3 | 173.3
CRVA Eligible Costs2
7 | Fuel Channel Life Extension Ongoing | 0.3 | -0.3 | 0 | 31.6 | 8 | 23.6 | 31.6 | -18.8 | 26.6 | -13.8 | 12.8
8 | Pickering Extended Operations Enabling | 0 | 0 | 0 | 3.2 | 22.1 | -18.9 | 3.2 | 6.1 | 37.3 | -28 | 9.3
9 | Optimization of Pickering Shutdown Enabling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Total CRVA Eligible Costs | 0.3 | -0.3 | 0 | 34.8 | 30 | 4.8 | 34.8 | -12.7 | 63.9 | -41.7 | 22.1
11 | Total Outage OM&A | 321.2 | -14.5 | 306.7 | 10.8 | 394.6 | -77.1 | 317.4 | 27.4 | 393.8 | -48.9 | 344.9
Line |  | 2018 | (e)-(a) | 2019 | (e)-(c) | 2019 | (i)-(e) | 2020 | (i)-(g) | 2020 | (k)-(i) | 2021
No. | Business Unit | Actual | Change | OEB Approved | Change | Actual | Change | OEB Approved | Change | Actual | Change | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Darlington Outages
12 | Darlington NGS | 136.9 | -46.3 | 118.6 | -28 | 90.6 | -47.9 | 150.7 | -107.9 | 42.7 | 160.4 | 203.1
13 | Operations and Project Support2 | 12.6 | 2.8 | 18 | -2.6 | 15.4 | -8.2 | 27.9 | -20.7 | 7.2 | 35.1 | 42.3
14 | Total Darlington Outages | 149.5 | -43.5 | 136.5 | -30.5 | 106 | -56.1 | 178.6 | -128.7 | 49.9 | 195.5 | 245.4
Pickering Outages
15 | Pickering NGS | 121.1 | -33.1 | 128.6 | -40.6 | 88.1 | 58.4 | 100.2 | 46.2 | 146.4 | -51.1 | 95.3
16 | Operations and Project Support2 | 52.1 | -28.8 | 32.9 | -9.6 | 23.3 | 6.6 | 21.7 | 8.2 | 29.9 | 1.5 | 31.5
17 | Total Pickering Outages | 173.3 | -61.9 | 161.5 | -50.2 | 111.4 | 65 | 121.9 | 54.4 | 176.4 | -49.6 | 126.8
CRVA Eligible Costs2
18 | Fuel Channel Life Extension Ongoing | 12.8 | 9.5 | 28.6 | -6.3 | 22.3 | -2 | 8.4 | 11.9 | 20.3 | 5 | 25.2
19 | Pickering Extended Operations Enabling | 9.3 | 15.4 | 88.7 | -64 | 24.7 | 22.6 | 85.5 | -38.3 | 47.3 | -14.7 | 32.5
20 | Optimization of Pickering Shutdown Enabling | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | 0.1 | 1.2 | 1.2
21 | Total CRVA Eligible Costs | 22.1 | 24.8 | 117.2 | -70.3 | 46.9 | 20.7 | 93.9 | -26.3 | 67.6 | -8.6 | 59
22 | Total Outage OM&A | 344.9 | -80.6 | 415.3 | -151 | 264.3 | 29.6 | 394.4 | -100.6 | 293.9 | 137.3 | 431.2
Notes:
1 | 2016-2021 values have been restated for Nuclear organizational changes and transfers from Corporate Support (See Ex. A1-3-1 Attachment 1 and Ex. F2-2-1, Attachment 1). In addition, the figures have been restated to separately identify FCLE ongoing costs consistent with amounts set out in EB-2016-0152 Ex L-4.1.1 Staff-24 pp. 1-2 as approved in the EB-2016-0152 Decision and Order p. 23
2 | CRVA Eligible Costs are shown separately, but were previously included in Operations and Project Support (which was called Nuclear Support in EB-2016-0152) with a footnote.

## SEC128-F2-4-2_Table 1b
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-04-SEC-128
Attachment 1
Page 2 of 2
Table 1b
Comparison of Outage OM&A - Nuclear ($M)1 2021-2026
Line |  | 2021 | (c)-(a) | 2021 | (e)-(c) | 2022 | (g)-(e) | 2023 | (i)-(g) | 2024 | (k)-(i) | 2025
No. | Business Unit | OEB Approved | Change | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Darlington Outages
23 | Darlington NGS | 54.1 | 149 | 203.1 | -129.5 | 73.6 | 85.5 | 159.1 | -77.1 | 81.9 | 75 | 156.9
24 | Operations and Project Support2 | 10.2 | 32.1 | 42.3 | -26.5 | 15.8 | 12.3 | 28.1 | -15.4 | 12.7 | 23 | 35.7
25 | Total Darlington Outages | 64.3 | 181.1 | 245.4 | -156 | 89.4 | 97.7 | 187.2 | -92.5 | 94.7 | 97.9 | 192.6
Pickering Outages
26 | Pickering NGS | 169.2 | -73.9 | 95.3 | 24 | 119.3 | -12.5 | 106.8 | -29.2 | 77.5 | -77.5 | 0
27 | Operations and Project Support2 | 73.5 | -42 | 31.5 | 6.6 | 38 | 12.5 | 50.6 | -24.2 | 26.4 | -26.4 | 0
28 | Total Pickering Outages | 242.7 | -115.9 | 126.8 | 30.5 | 157.3 | 0.1 | 157.4 | -53.4 | 104 | -104 | 0
CRVA Eligible Costs2
29 | Fuel Channel Life Extension Ongoing | 1.5 | 23.7 | 25.2 | 4.6 | 29.8 | -15.3 | 14.5 | -14.2 | 0.3 | -0.3 | 0
30 | Pickering Extended Operations Enabling | 0 | 32.5 | 32.5 | -32.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Optimization of Pickering Shutdown Enabling | 0 | 1.2 | 1.2 | 1.3 | 2.6 | -0.3 | 2.2 | 11.3 | 13.5 | -13.5 | 0
32 | Total CRVA Eligible Costs | 1.5 | 57.5 | 59 | -26.6 | 32.4 | -15.7 | 16.7 | -2.9 | 13.8 | -13.8 | 0
33 | Total Outage OM&A | 308.5 | 122.6 | 431.2 | -152 | 279.1 | 82.1 | 361.2 | -148.8 | 212.4 | -19.8 | 192.6
Line |  | 2025 | (c)-(a) | 2026
No. | Business Unit | Plan | Change | Plan
|  | (a) | (b) | (c)
Darlington Outages
34 | Darlington NGS | 156.9 | -99.1 | 57.8
35 | Operations and Project Support2 | 35.7 | -32.1 | 3.5
36 | Total Darlington Outages | 192.6 | -131.2 | 61.3
Pickering Outages
37 | Pickering NGS | 0 | 0 | 0
38 | Operations and Project Support2 | 0 | 0 | 0
39 | Total Pickering Outages | 0 | 0 | 0
CRVA Eligible Costs2
40 | Fuel Channel Life Extension Ongoing | 0 | 0 | 0
41 | Pickering Extended Operations Enabling | 0 | 0 | 0
42 | Optimization of Pickering Shutdown Enabling | 0 | 0 | 0
43 | Total CRVA Eligible Costs | 0 | 0 | 0
44 | Total Outage OM&A | 192.6 | -131.2 | 61.3
Notes:
1 | 2016-2021 values have been restated for Nuclear organizational changes and transfers from Corporate Support (See Ex. A1-3-1 Attachment 1 and Ex. F2-2-1, Attachment 1). In addition, the figures have been restated to separately identify FCLE ongoing costs consistent with amounts set out in EB-2016-0152 Ex L-4.1.1 Staff-24 pp. 1-2 as approved in the EB-2016-0152 Decision and Order p. 23
2 | CRVA Eligible Costs are shown separately, but were previously included in Operations and Project Support (which was called Nuclear Support in EB-2016-0152) with a footnote.

## SEC134-F2-3-2_Table 1a
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-03-SEC-134
Attachment 1
Page 1 of 2
Table 1a
Comparison of Project OM&A - Nuclear ($M) 2016-2021
Line |  | 2016 | (c)-(a) | 2016 | (g)-(c) | 2017 | (g)-(e) | 2017 | (k)-(g) | 2018 | (k)-(i) | 2018
No. | Business Unit | Budget | Change2 | Actual | Change | OEB Approved 1 | Change | Actual | Change | OEB Approved 1 | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Portfolio Projects (Allocated)
1 | Darlington NGS | 29.2 | -10.5 | 18.8 | 4.2 | 23.1 | -0.1 | 23 | -8 | 24.1 | -9.2 | 15
2 | Pickering NGS | 13.4 | -6.3 | 7.1 | 5.9 | 10.3 | 2.8 | 13 | -2.2 | 11.9 | -1.1 | 10.8
3 | Operations and Project Support | 9.4 | -5.4 | 4 | -1.7 | 4.7 | -2.4 | 2.3 | 2.2 | 0.3 | 4.1 | 4.4
4 | Subtotal Portfolio Projects (Allocated) | 52 | -22.2 | 29.9 | 8.4 | 38 | 0.3 | 38.3 | -8.1 | 36.4 | -6.2 | 30.2
5 | Infrastructure | 35.8 | 5.3 | 41.1 | 28.8 | 44 | 25.9 | 69.9 | -3.4 | 37 | 29.6 | 66.5
6 | Portfolio Projects (Unallocated) | -11.8 | 11.8 | 0 | 0 | 11.6 | -11.6 | 0 | 0 | 15.7 | -15.7 | 0
7 | Subtotal Project OM&A (Portfolio) | 76 | -5.1 | 70.9 | 37.2 | 93.5 | 14.6 | 108.2 | -11.5 | 89 | 7.6 | 96.7
8 | Pickering Extended Operations | 4 | -2.8 | 1.2 | -1 | 2.5 | -2.3 | 0.2 | 6.1 | 18 | -11.7 | 6.3
9 | Pickering Optimization of Shutdown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Fuel Channel Life Cycle Mgmt Project | 0.4 | -0.1 | 0.3 | -0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Fuel Channel Life Extension Project | 15.6 | -0.7 | 14.9 | -3.9 | 12.3 | -1.3 | 11 | -2.9 | 0.7 | 7.4 | 8.1
12 | Darlington Spacer Retrieval 3 | 2.2 | -0.4 | 1.8 | -0.6 | 5.4 | -4.2 | 1.2 | -0.5 | 1.4 | -0.7 | 0.7
13 | Darlington Spacer Life Management 4 | 0 | 0 | 0 | 2.1 | 0 | 2.1 | 2.1 | 4.8 | 0 | 6.9 | 6.9
14 | Darlington Unit 3 F/C Comp Retrieval 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0.4 | 0.4
15 | Total Project OM&A | 98.2 | -9.1 | 89.1 | 33.6 | 113.7 | 9 | 122.7 | -3.6 | 109.1 | 10 | 119.1
Line |  | 2018 | (e)-(a) | 2019 | (e)-(c) | 2019 | (i)-(e) | 2020 | (i)-(g) | 2020 | (k)-(i) | 2021
No. | Business Unit | Actual | Change | OEB Approved 1 | Change | Actual | Change | OEB Approved 1 | Change | Actual | Change | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Portfolio Projects (Allocated)
16 | Darlington NGS | 15 | 3.3 | 7.6 | 10.7 | 18.3 | -4.3 | 0.8 | 13.2 | 13.9 | 18 | 32
17 | Pickering NGS | 10.8 | -1.6 | 0 | 9.2 | 9.2 | -8.2 | 0 | 1 | 1 | 1.1 | 2
18 | Operations and Project Support | 4.4 | -0.4 | 0 | 4 | 4 | 3.8 | 0 | 7.8 | 7.8 | -3.8 | 4
19 | Subtotal Portfolio Projects (Allocated) | 30.2 | 1.3 | 7.6 | 23.9 | 31.5 | -8.8 | 0.8 | 22 | 22.7 | 15.3 | 38
20 | Infrastructure | 66.5 | -26 | 37 | 3.5 | 40.5 | 0.5 | 33 | 8 | 41 | 3 | 44
21 | Portfolio Projects (Unallocated) | 0 | 0 | 37.2 | -37.2 | 0 | 0 | 47.8 | -47.8 | 0 | 10.8 | 10.8
22 | Subtotal Project OM&A (Portfolio) | 96.7 | -24.7 | 81.7 | -9.8 | 72 | -8.3 | 81.5 | -17.8 | 63.7 | 29.1 | 92.8
24 | Non Portfolio Projects
25 | Pickering Extended Operations | 6.3 | 19.1 | 18.4 | 7 | 25.4 | 4.6 | 18.7 | 11.3 | 30 | -12.4 | 17.6
26 | Pickering Optimization of Shutdown | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0.3 | 0.3 | 1.7 | 2
27 | Fuel Channel Life Cycle Mgmt Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Fuel Channel Life Extension Project | 8.1 | -4.2 | 0 | 3.9 | 3.9 | -3.2 | 0 | 0.7 | 0.7 | 3.7 | 4.4
29 | Darlington Spacer Retrieval 3 | 0.7 | -0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Darlington Spacer Life Management 4 | 6.9 | -3.2 | 0 | 3.7 | 3.7 | -0.7 | 0 | 3 | 3 | 0.1 | 3.1
31 | Darlington Unit 3 F/C Comp Retrieval 5 | 0.4 | 0.8 | 0 | 1.2 | 1.2 | 0.8 | 0 | 1.9 | 1.9 | 0.6 | 2.5
32 | Total Project OM&A | 119.1 | -13 | 100.1 | 6 | 106.1 | -6.6 | 100.2 | -0.6 | 99.6 | 22.8 | 122.3
Notes:
1 | As OEB Approved adjustments are applied to Base OM&A in Ex. F2-2-2 Table 1a and Table 1b, the figures presented here are 2017 Plan - 2021 Plan (from EB-2016-0152, Ex. F2-3-2, Table 1)
2 | Bold italic font indicates variance of 10% or greater.
3 | Project #80112 DN X-750 Spacer Retrieval
4 | Project #83280 - DN Annulus Spacer Life Mgmt
5 | Project #83926 - IRI DNRU3 FC Component Retrieval

## SEC134-F2-3-2_Table 1b
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
F2-03-SEC-134
Attachment 1
Page 2 of 2
Table 1b
Comparison of Project OM&A - Nuclear ($M) 2021-2026
Line |  | 2021 | (c)-(a) | 2021 | (e)-(c) | 2022 | (g)-(e) | 2023 | (i)-(g) | 2024 | (k)-(i) | 2025
No. | Business Unit | OEB Approved 1 | Change | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Portfolio Projects (Allocated)
33 | Darlington NGS | 0 | 32 | 32 | -13 | 19 | -4.8 | 14.2 | -7.1 | 7.1 | -2.5 | 4.6
34 | Pickering NGS | 0 | 2 | 2 | -1.5 | 0.6 | -0.6 | 0 | 0 | 0 | 0 | 0
35 | Operations and Project Support | 0 | 4 | 4 | -2.2 | 1.8 | -1.8 | 0 | 0 | 0 | 0 | 0
36 | Subtotal Portfolio Projects (Allocated) | 0 | 38 | 38 | -16.6 | 21.4 | -7.1 | 14.2 | -7.1 | 7.1 | -2.5 | 4.6
37 | Infrastructure | 29 | 15 | 44 | -2.5 | 41.5 | 7.5 | 49 | 0 | 49 | -2.5 | 46.5
38 | Portfolio Projects (Unallocated) | 57.9 | -47.1 | 10.8 | 7.2 | 18 | 3.8 | 21.8 | 2.7 | 24.5 | 1.1 | 25.6
39 | Subtotal Project OM&A (Portfolio) | 86.9 | 5.9 | 92.8 | -12 | 80.8 | 4.2 | 85 | -4.4 | 80.6 | -3.9 | 76.7
41 | Non Portfolio Projects
42 | Pickering Extended Operations | 0 | 17.6 | 17.6 | -17.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Pickering Optimization of Shutdown | 0 | 2 | 2 | 5.8 | 7.8 | -7.8 | 0 | 0 | 0 | 0 | 0
44 | Fuel Channel Life Cycle Mgmt Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Fuel Channel Life Extension Project | 0 | 4.4 | 4.4 | -4 | 0.4 | -0.4 | 0 | 0 | 0 | 0 | 0
46 | Darlington Spacer Retrieval 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Darlington Spacer Life Management 4 | 0 | 3.1 | 3.1 | -3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Darlington Unit 3 F/C Comp Retrieval 5 | 0 | 2.5 | 2.5 | -2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | Total Project OM&A | 86.9 | 35.4 | 122.3 | -33.3 | 89.1 | -4.1 | 85 | -4.4 | 80.6 | -3.9 | 76.7
Line |  | 2025 | (c)-(a) | 2026
No. | Business Unit | Plan | Change | Plan | [5 empty] | `
|  | (a) | (b) | (c)
Portfolio Projects (Allocated)
46 | Darlington NGS | 4.6 | -3.8 | 0.8
47 | Pickering NGS | 0 | 0 | 0
48 | Operations and Project Support | 0 | 0 | 0
49 | Subtotal Portfolio Projects (Allocated) | 4.6 | -3.8 | 0.8
50 | Infrastructure | 46.5 | -4 | 42.5
51 | Portfolio Projects (Unallocated) | 25.6 | -6.9 | 18.7
52 | Subtotal Project OM&A (Portfolio) | 76.7 | -14.7 | 62
53 | Non Portfolio Projects
54 | Pickering Extended Operations | 0 | 0 | 0
55 | Pickering Optimization of Shutdown | 0 | 0 | 0
56 | Fuel Channel Life Cycle Mgmt Project | 0 | 0 | 0
57 | Fuel Channel Life Extension Project | 0 | 0 | 0
58 | Darlington Spacer Retrieval 3 | 0 | 0 | 0
59 | Darlington Spacer Life Management 4 | 0 | 0 | 0
60 | Darlington Unit 3 F/C Comp Retrieval 5 | 0 | 0 | 0
61 | Total Project OM&A | 76.7 | -14.7 | 62
Notes:
1 | As OEB Approved adjustments are applied to Base OM&A in Ex. F2-2-2 Table 1a and Table 1b, the figures presented here are 2017 Plan - 2021 Plan (from EB-2016-0152, Ex. F2-3-2, Table 1)
2 | Bold italic font indicates variance of 10% or greater.
3 | Project #80112 DN X-750 Spacer Retrieval
4 | Project #83280 - DN Annulus Spacer Life Mgmt
5 | Project #83926 - IRI DNRU3 FC Component Retrieval

## SEC61-D2-1-2_Table 4a
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-061
Attachment 1
Page 1 of 2
Table 4a
Comparison of Capital Expenditures - Nuclear Operations ($M) 2016-2021 | [12 empty] | Variance percentages for working copy
Delete prior to filing
Line |  | 2016 | (c)-(a) | 2016 | (g)-(c) | 2017 | (g)-(e) | 2017 | (k)-(g) | 2018 | (k)-(i) | 2018 | (c)-(a) | (e)-(c) | (g)-(e) | (i)-(g) | (k)-(i)
No. | Business Unit | Budget | Change | Actual | Change | OEB Approved1 | Change | Actual | Change | OEB Approved1 | Change | Actual | Change | Change | Change | Change | Change
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (b) | (d) | (f) | (h) | (j)
Portfolio Projects (Allocated)
1 | Darlington NGS | 203.8 | -33 | 170.8 | 51.9 | 166.2 | 56.4 | 222.6 | 49.4 | 127 | 145.1 | 272 | -16.19% | 30.39% | 33.94% | 22.19% | 114.3%
2 | Pickering NGS | 88.7 | -7.5 | 81.2 | 1.5 | 21.6 | 61.2 | 82.7 | -36.7 | 2 | 44 | 46.1 | -8.455% | 1.847% | 283.3% | -44.38% | 2200%
3 | Operations and Project Support | 18.6 | 2.1 | 20.6 | 7.6 | 16.3 | 11.9 | 28.2 | 11.1 | 14.4 | 24.9 | 39.3 | 11.29% | 36.89% | 73.01% | 39.36% | 172.9%
4 | Subtotal Portfolio Projects (Allocated) | 311 | -38.4 | 272.6 | 60.9 | 204.1 | 129.5 | 333.5 | 23.8 | 143.4 | 214 | 357.4 | -12.35% | 22.34% | 63.45% | 7.136% | 104.9%
5 | Portfolio Projects (Unallocated) | 4.8 | -4.8 | 0 | 0 | 48.8 | -48.8 | 0 | 0 | 94.6 | -94.6 | 0 | -100% | #DIV/0! | -100% | #DIV/0! | -100%
6 | Subtotal Project Capital (Portfolio) | 315.8 | -43.2 | 272.6 | 60.9 | 252.9 | 80.6 | 333.5 | 23.8 | 238 | 119.4 | 357.4 | -13.68% | 22.34% | 31.87% | 7.136% | 47.21%
7 | Darlington New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Darlington Spacer Retrieval 2, 3 | 6.2 | -1.4 | 4.8 | -3.8 | 0.2 | 0.8 | 1 | -1 | 0 | 0 | 0
10 | Pickering Extended Operations 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8 | 0 | 2.8 | 2.8
11 | Minor Fixed Assets | 31 | -7.9 | 23.1 | -3.3 | 26 | -6.2 | 19.8 | 2 | 20 | 1.7 | 21.7 | -25.48% | -14.29% | -23.85% | 10.1% | 8.5%
12 | Total Nuclear Operations Capital | 353 | -52.5 | 300.5 | 53.9 | 279.1 | 75.2 | 354.3 | 27.6 | 258 | 123.9 | 381.9 | -14.87% | 17.94% | 26.94% | 7.79% | 44.39%
Line |  | 2018 | (e)-(a) | 2019 | (e)-(c) | 2019 | (i)-(e) | 2020 | (i)-(g) | 2020 | (k)-(i) | 2021 | (c)-(a)
No. | Business Unit | Actual | Change | OEB Approved1 | Change | Actual | Change | OEB Approved1 | Change | Budget | Change | Budget | Change
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (b)
Portfolio Projects (Allocated)
13 | Darlington NGS | 272 | 5.5 | 88.6 | 188.9 | 277.6 | 28.4 | 37.4 | 268.6 | 305.9 | 50.8 | 356.7 | 213.2%
14 | Pickering NGS | 46.1 | -7.4 | 0 | 38.6 | 38.6 | -11.6 | 0 | 27 | 27 | -17.7 | 9.3 | #DIV/0!
15 | Operations and Project Support | 39.3 | -10.1 | 0 | 29.2 | 29.2 | 17.4 | 0 | 46.6 | 46.6 | 15.3 | 61.9 | #DIV/0!
16 | Subtotal Portfolio Projects (Allocated) | 357.4 | -12 | 88.6 | 256.8 | 345.4 | 34.1 | 37.4 | 342.1 | 379.5 | 48.4 | 427.9 | 289.8%
17 | Portfolio Projects (Unallocated) | 0 | 0 | 159.4 | -159.4 | 0 | -18.5 | 221.6 | -240.1 | -18.5 | -28.8 | -47.4 | -100%
18 | Subtotal Project Capital (Portfolio) | 357.4 | -12 | 248 | 97.4 | 345.4 | 15.6 | 259 | 102 | 361 | 19.6 | 380.6 | 39.27%
19 | Darlington New Fuel | 0 | 16.8 | 15.3 | 1.5 | 16.8 | -16.8 | 0 | 0 | 0 | 0 | 0
20 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Darlington Spacer Retrieval 2, 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Pickering Extended Operations 3 | 2.8 | 6.2 | 0 | 9 | 9 | 9 | 0 | 18 | 18 | -15.1 | 2.9
23 | Minor Fixed Assets | 21.7 | 2.4 | 19.1 | 5 | 24.1 | -2.1 | 19.5 | 2.6 | 22 | 2 | 24.1 | 26.18%
24 | Total Nuclear Operations Capital | 381.9 | 13.4 | 282.4 | 112.9 | 395.3 | 5.7 | 278.5 | 122.6 | 401 | 6.5 | 407.5 | 39.98%
Notes
1 | Amounts per EB-2016-0152, Ex. D2-1-2 Table 4 with exception of 2017 and 2018 Projects Portfolio (Allocated) that have been adjusted for reclassification of projects from Darlington to Operations and Project Support.
2 | Project #82949 DN X-750 Spacer Retrieval CMFA.
3 | OEB Approved amounts for Darlington Spacer Retrieval and Pickering Extended Operations per EB-2016-0152, Ex. L-04.1 Staff -024

## SEC61-D2-1-2_Table 4b
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-061
Attachment 1
Page 2 of 2
Table 4b
Comparison of Capital Expenditures - Nuclear Operations ($M) 2021-2026 | [12 empty] | Variance percentages for working copy
Delete prior to filing
Line |  | 2021 | (c)-(a) | 2021 | (e)-(c) | 2022 | (g)-(e) | 2023 | (i)-(g) | 2024 | (k)-(i) | 2025
No. | Business Unit | OEB Approved1 | Change | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
Portfolio Projects (Allocated)
25 | Darlington NGS | 30.2 | 326.5 | 356.7 | 4.4 | 361.1 | -69.4 | 291.8 | -30.4 | 261.3 | -46.9 | 214.4
26 | Pickering NGS | 0 | 9.3 | 9.3 | -8.9 | 0.4 | -0.4 | 0 | 0 | 0 | 0 | 0
27 | Operations and Project Support | 0 | 61.9 | 61.9 | -43 | 18.8 | -14.3 | 4.6 | -2.8 | 1.8 | 1.3 | 3.1
28 | Subtotal Portfolio Projects (Allocated) | 30.2 | 397.7 | 427.9 | -47.6 | 380.4 | -84 | 296.3 | -33.2 | 263.2 | -45.6 | 217.5
29 | Portfolio Projects (Unallocated) | 149.8 | -197.1 | -47.4 | 60.4 | 13 | 35.5 | 48.5 | -14.9 | 33.6 | 33.1 | 66.7
30 | Subtotal Project Capital (Portfolio) | 180 | 200.6 | 380.6 | 12.8 | 393.3 | -48.5 | 344.8 | -48.1 | 296.7 | -12.5 | 284.2
31 | Darlington New Fuel | 0 | 0 | 0 | 0 | 0 | 16.5 | 16.5 | 0.4 | 16.9 | -16.9 | 0
32 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6 | 138.6 | -138.6 | 0
33 | Darlington Spacer Retrieval 2, 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Pickering Extended Operations 3 | 0 | 2.9 | 2.9 | -2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | Minor Fixed Assets | 19.3 | 4.7 | 24.1 | -4.4 | 19.6 | 1.4 | 21 | 8.2 | 29.2 | -10.6 | 18.7
36 | Total Nuclear Operations Capital | 199.3 | 208.2 | 407.5 | 5.4 | 413 | -30.6 | 382.3 | 99.1 | 481.4 | -178.5 | 302.9
Line |  | 2025 | (c)-(a) | 2026
No. | Business Unit | Plan | Change | Plan
|  | (a) | (b) | (c)
Portfolio Projects (Allocated)
37 | Darlington NGS | 214.4 | -79.5 | 134.9
38 | Pickering NGS | 0 | 0 | 0
39 | Operations and Project Support | 3.1 | -3.1 | 0
40 | Subtotal Portfolio Projects (Allocated) | 217.5 | -82.6 | 134.9
41 | Portfolio Projects (Unallocated) | 66.7 | -9.9 | 56.9
42 | Subtotal Project Capital (Portfolio) | 284.2 | -92.5 | 191.8
43 | Darlington New Fuel | 0 | 18.1 | 18.1
44 | Darlington Water Treatment Plant Lease | 0 | 0 | 0
45 | Darlington Spacer Retrieval 2 | 0 | 0 | 0
46 | Pickering Extended Operations | 0 | 0 | 0
47 | Minor Fixed Assets | 18.7 | -7.3 | 11.4
48 | Total Nuclear Operations Capital | 302.9 | -81.7 | 221.2
Notes
1 | Amounts per EB-2016-0152, Ex. D2-1-2 Table 4 with exception of 2017 and 2018 Projects Portfolio (Allocated) that have been adjusted for reclassification of projects from Darlington to Operations and Project Support.
2 | Project #82949 DN X-750 Spacer Retrieval CMFA.
3 | OEB Approved amounts for Darlington Spacer Retrieval and Pickering Extended Operations per EB-2016-0152, Ex. L-04.1 Staff -024

## SEC62-D2-1-3_Table 1a
Numbers may not add due to rounding. | [19 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 1 of 12
Table 1a
Capital Project Listing - Nuclear Operations Facility Projects
Projects ≥ $20M Total Project Cost1
[7 empty] | Total | Total | 1st Execution Business Case5 | 1st Execution Business Case- EB-2016-01525
[6 empty] | Final | Project | Project |  |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Start | In-Service | Cost2 | Cost - EB-2016-0152 |  |  | In-Service | LTD14 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Date | Date13 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r) | (s) | (t)
ONGOING PROJECTS FROM EB-2016-0152
1 | DN | DN Class II Uninterruptible Power Supply Replacement | 31412 | Sustaining | 2011-01-11 | 2025-03-24 | 63.6 | 55.1 | 38.4 | 38.4 | 62 | 29.2 | 25.2 | 0 | 7.5 | 13.9 | 5.9 | 0 | 5.4 | 0.1
2 | DN | DN Fuel Handling Inverter Replacement | 31426 | Sustaining | 2011-11-15 | 2021-04-29 | 26.2 | 14.4 | 13.9 | n/a | 26.1 | 23.7 | 0 | 1 | 2.5 | 0 | 0 | 0 | 0 | 0
3 | DN | DN Station Fluorescent Lighting Fixtures Retrofit | 31516 | Sustaining | 2012-12-11 | 2023-01-03 | 20.7 | 11.4 6 | 16.9 | n/a | 19.8 | 9.6 | 3.9 | 3.1 | 3.2 | 1.4 | 2.5 | 0 | 0 | 0
4 | DN | DN Restore Emergency Service Water and Firewater Margins | 31518 | Regulatory | 2012-12-11 | 2019-08-05 | 28.5 | 47.1 | 28.5 | n/a | 10.5 | 9.7 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0
5 | DN | DN Station Roofs Replacement | 31524 | Sustaining | 2012-11-20 | 2027-11-14 | 116.9 | 36.3 7 | n/a | n/a | 116.8 | 21.5 | 66.2 | 11.9 | 12.7 | 12.8 | 12 | 14.2 | 15.2 | 12
6 | DN | DN Powerhouse Water Air Condition Units Replacement | 31532 | Sustaining | 2012-10-25 | 2023-01-06 | 38.2 | 26.6 8 | 26.6 | 26.6 | 30.7 | 13.9 | 3.1 | 3.7 | 10.2 | 2.9 | 0.2 | 0 | 0 | 0
7 | DN | DN Water Treatment Plant Interconnections | 31535 | Sustaining | 2011-09-04 | 2024-09-27 | 53.2 | 57.8 | n/a | n/a | 53.2 | 0 | 53.2 | 0 | 0 | 0 | 0 | 53.2 | 0 | 0
8 | DN | DN Transformer Multi-Gas Analyzer Installation | 31542 | Sustaining | 2012-10-13 | 2020-12-05 | 23.8 | 22.7 | 15.2 | 15.2 | 22.5 | 22.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | DN | DN Radiation Detection Equipment Obsolescence | 31544 | Sustaining | 2014-01-14 | 2023-09-29 | 45 | 46.9 | n/a | n/a | 41.3 | 0 | 22.3 | 0 | 19 | 15 | 7 | 0.3 | 0 | 0
10 | DN | DN Shutdown Cooling Heat Exchanger Replacement | 31710 | Sustaining | 2012-11-30 | 2021-12-29 | 111.4 | 112.8 9 | 56.1 | 56.1 | 74.1 | 72.1 | 0 | 0 | 1.8 | 0 | 0 | 0 | 0 | 0
11 | DN | DN Neutron Over-Power Ion Chamber & In-Core Flux Detector Amplifier Replacement (Reactor Regulating System, Shutdown System 1 & Shutdown System 2) | 31716 | Sustaining | 2013-07-25 | 2027-04-01 | 23.8 | 17.7 | 23.8 | n/a | 17.9 | 1.2 | 9.6 | 1.6 | 2.5 | 1.6 | 1.4 | 2 | 2.2 | 2.4
12 | DN | DN Replacement of Emergency Power Supply Uninterruptible Power Supply | 33258 | Sustaining | 2010-02-12 | 2022-02-01 | 24.6 | 16.6 | 15.2 | 15.2 | 24.8 | 13.9 | 2.1 | 1.7 | 7.1 | 2.1 | 0 | 0 | 0 | 0
13 | DN | DN Air Conditioning Unit Replacement for Secondary Control Area | 33621 | Sustaining | 2009-02-11 | 2025-08-25 | 36 | 28.3 | 12.3 | 12.3 | 34.1 | 24.4 | 9.6 | 0 | 0 | 5.1 | 2.2 | 0 | 2.2 | 0.2
14 | DN | DN Chiller Replacement to Reduce Chloroflurocarbon Emissions | 33631 | Regulatory | 2004-01-07 | 2017-12-15 | 30 | 30 | 14.9 | 14.9 | 21.6 | 21.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | DN | DN Major Pump-sets Vibration Monitoring System Upgrades | 33819 | Sustaining | 2006-03-17 | 2026-11-20 | 55.4 | 23.8 | 12.8 | n/a | 48.2 | 10.4 | 18 | 11.2 | 9 | 5 | 5 | 4 | 2 | 2
16 | DN | DN Standby Generator Controls Replacement | 33973 | Sustaining | 2006-12-15 | 2021-03-05 | 46.3 | 39.6 | 21.8 | 21.8 | 46.1 | 44.1 | 0.4 | 0 | 1.6 | 0.4 | 0 | 0 | 0 | 0
17 | DN | DN Digital Control Computer Replacement / Refurbishment / Upgrades | 33977 | Sustaining | 2003-09-30 | 2021-12-31 | 26.5 | 24.9 | 22.1 | 22.1 | 26.5 | 23.1 | 0.3 | 1.1 | 2.1 | 0.3 | 0 | 0 | 0 | 0
18 | DN | DN Auxiliary Heating System - Phases 1 & 2 Alternative Heating | 34000 | Regulatory | 2006-03-23 | 2018-06-28 | 107.1 | 107.2 10 | 45.6 | 45.6 | 102.1 | 102.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | DN | DN Zebra Mussel Mitigation Improvements | 38948 | Sustaining | 2012-11-30 | 2021-12-05 | 36.6 | 29.3 12 | 21.5 | 21.5 | 36.5 | 34.8 | 0 | 1.4 | 0.4 | 0 | 0 | 0 | 0 | 0
20 | DN | DN RS Primary Heat Transport Pump Motor Replacement4 | 73566 | Sustaining | 2015-07-15 | 2021-05-15 | 84 | 129.5 | 26.7 | 26.7 | 71.4 | 68 | 0.2 | 0 | 3.1 | 0.2 | 0 | 0 | 0 | 0
21 | DN | DN OH180 Aging Management Hardware Installation | 80022 | Sustaining | 2014-12-09 | 2028-06-28 | 60.9 | 90 11 | 60.9 | n/a | 38 | 11.6 | 16 | 3.1 | 5.9 | 4.1 | 3.9 | 2.9 | 2.1 | 2.9
22 | DN | DN Steam Generator Level Control Valve Replacement | 80023 | Sustaining | 2015-01-21 | 2026-06-30 | 38.6 | 16.3 | n/a | n/a | 38.5 | 0 | 38.5 | 0 | 0 | 0 | 9.6 | 9.6 | 9.6 | 9.6
23 | DN | DN R22 Refrigerant Air Conditioning Unit Replacement | 80036 | Regulatory | 2015-12-29 | 2026-01-20 | 36.1 | 14.9 | n/a | n/a | 37.8 | 2 | 27.1 | 2.9 | 5.9 | 2.3 | 6.7 | 7.1 | 6.5 | 4.5
24 | DN | DN Standby Generators Protective Relay Replacement | 80063 | Sustaining | 2015-12-04 | 2023-02-24 | 20 | 9.9 | n/a | n/a | 15.8 | 0 | 15.8 | 0 | 0 | 11.7 | 3 | 0.7 | 0.3 | 0
25 | DN | DN Digital Control, Common Process and Sequence of Events Monitoring Computer Aging Management | 80078 | Regulatory | 2015-11-24 | 2028-02-29 | 77.5 | 47.3 | n/a | n/a | 56.5 | 0.9 | 42.2 | 0 | 0 | 2 | 4.7 | 7.1 | 18.5 | 9.9
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Projects 31508, 49158 and 49299 are combined in a single Business Case Summary.
4 | Projects 73566 ($84.0M), 36001 ($27.6M) and 80144 ($53.3M) are combined in a single Business Case Summary ($164.9M). In EB-2016-0152
project 73566 and project 80144 were included in Ex D2-1-3 Table 1 with a combined project cost of $129.5M, while #36001 project cost was $30.8M. First execution BCS amounts are derived from the combined amount
5 | The designation of "n/a" means the project has not advanced to a First Execution BCS
6 | EB-2016-0152 L-04.4-15 SEC 048
7 | Total project cost set out in EB-2016-0152, Ex. D2-1-3, Table 1 incorrectly identified total project cost for Project #31524 as $38.3M.
8 | EB-2016-0152 L 04.2-2 Staff 028
9 | EB-2016-0152 J15.5 Attachment 1
10 | EB-2016-0152 L-04.4-15 SEC 046
11 | EB-2016-0152 J15.5 Attachment 3
12 | EB-2016-0152 J15.5 Attachment 2
13 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
14 | Life Time to Date (LTD) means in service amounts as of Dec 31, 2019

## SEC62-D2-1-3_Table 1b
Numbers may not add due to rounding. | [19 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 2 of 12
Table 1b
Capital Project Listing - Nuclear Operations Facility Projects
Projects ≥ $20M Total Project Cost1
[7 empty] | Total | Total | 1st Execution Business Case5 | 1st Execution Business Case EB-2016-01525
[6 empty] | Final | Project | Project |  |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Start | In-Service | Cost2 | Cost - EB-2016-0152 |  |  | In-Service | LTD11 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Date | Date10 | (M$) | (M$) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r) | (s) | (t)
ONGOING PROJECTS FROM EB-2016-0152
26 | DN | DN Primary Heat Transport Pump Motor Overhaul 7 | 80144 | Sustaining | 2015-07-15 | 2021-10-19 | 53.3 | 129.5 | 102.8 | 102.8 | 43.8 | 34.1 | 0 | 3.5 | 6.2 | 0 | 0 | 0 | 0 | 0
27 | PN | PB Emergency Power Generator and Main Output Power Protective Relay Replacement | 40691 | Sustaining | 2012-02-08 | 2019-10-23 | 29.7 | 11 | 7.5 | 7.5 | 25.2 | 25.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 |  | Subtotal |  |  |  |  | 1314 | [5 empty] | 353.3 | 46.9 | 100.8 | 80.8 | 64 | 101.1 | 63.9 | 43.6
COMPLETED/DEFERRED/CANCELLED FROM EB-2016-0152
29 | DN | DN Operations Support Building Refurbishment | 25619 | Sustaining | 2009-03-04 | 2015-11-05 | 61.3 | 62.7 | 47.8 | 47.8 | 59.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | DN | DN Fukushima Phase 1 Beyond Design Basis Event Emergency Mitigation Equipment 3 | 31508 | Regulatory | 2011-09-21 | 2018-04-05 | 55.5 | 52.9 | 29.1 | 27.3 | 55.5 |  | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
31 | DN | DN Condenser Circulating Water and Low Pressure Service Water Travelling Screens Replacement | 31552 | Sustaining | 2013-05-14 | 2018-11-05 | 37.6 | 37.6 | 24.4 | 24.4 | 33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | DN | DN Improve Maintenance Facilities at Darlington (Capital) | 31717 | Sustaining | 2007-08-01 | 2013-11-05 | 35.6 | 43.2 | 49.8 | 49.8 | 33.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | DN | DN Fukushima Phase 2 Beyond Design Basis Event Emergency Mitigation Equipment 9 | 32202 | Regulatory | 2012-10-31 | 2018-05-05 | 23.1 | 28 | 28 | 28 | 21.9 |  | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0
34 | DN | Shutdown System Computer Aging Management | 33955 | Sustaining | 2006-11-30 | 2015-12-05 | 20.3 | 20.3 | 17.2 | 17.2 | 20.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | DN | DN Purchase of Primary Heat Transport Pump Motor Capital Spares | 36001 | Sustaining | 2010-04-09 | 2015-10-05 | 27.6 | 30.8 | 12 | 12 | 27.6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | DN | DN Holt Road Interchange Upgrade | 73706 | Value Enhancing | 2013-11-19 | 2016-08-05 | 26.7 | 28.6 | 31 | 31 | 26.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | DN | DN Generator Stator Core Spare | 80111 | Sustaining | 2015-09-30 | 2019-07-16 | 43 | 35 | 35 | 35 | 30.8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | PN | PB Fuel Handling Reliability Modifications | 40976 | Sustaining | 2012-08-29 | 2018-12-30 | 30.8 | 37.3 | 29 | 29 | 39.3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | PN | Unit 1 & 4 Fuel Channel East Pressure Tube Shift Tooling 4 | 41023 | Sustaining | 2012-10-10 | 2016-12-20 | 27.7 | 38.6 | 22 | 22 | 27.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | PN | PN Fukushima Phase 2 Beyond Design Basis Event Emergency Mitigation Equipment 9 | 41027 | Regulatory | 2012-10-31 | 2017-11-05 | 49.7 | 46.3 | 46.3 | 46.3 | 49.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | PN | PA Fuel Handling Single Point of Vulnerabilty Equipment Reliability Improvement Project - Capital | 46634 | Sustaining | 2011-02-27 | 2018-12-05 | 21.2 | 27.3 | 27 | 27 | 20.9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | PN | PB Fukushima Phase 1 Beyond Design Basis Event Emergency Mitigation Equipment 3 | 49158 | Regulatory | 2011-09-21 | 2017-10-05 | 41.7 | 58 6 | 29.3 | 29.3 | 41.7 |  | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0
43 | SEC | Physical Barrier System | 25609 | Regulatory | 2005-11-17 | 2013-12-05 | 67.2 | 67.2 | 37 | 37 | 67.2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | IRI | PN Machine Delivered Scrape | 66600 | Value Enhancing | 2014-02-21 | 2018-10-26 | 27 | 26.1 8 | 24.9 | 24.9 | 27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 |  | Subtotal |  |  |  |  | 596.1 | [5 empty] | 0 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Projects 31508, 49158 and 49299 are combined in a single Business Case Summary of $70M. First execution BCS amounts are derived from the combined amount.
4 | Projects 41023 and 49247 are combined in a single Business Case Summary. Project 49247 is from Ex. D2-1-3 Table 2 in EB-2013-0321
First execution BCS amounts are derived from the combined amount
5 | The designation of "n/a" means the project has not advanced to a First Execution BCS
6 | Project 49158 was combined with Project 49299 and Project 31508. Total project cost for project 49158 was $44.0M
7 | Projects 73566 ($84.0M), 36001 ($27.6M) and 80144 ($53.3M) are combined in a single Business Case Summary ($164.9M). In EB-2016-0152
project 73566 and project 80144 were included in Ex D2-1-3 Table 1 with a combined project cost of $129.5M, while #36001 project cost was $30.8M. First execution BCS amounts are derived from the combined amount
8 | EB-2016-0152 L-04.2-1 Staff 043
9 | Projects 41027 and 32202 were combined into a single BCS. First execution BCS amounts are derived from the combined amount
10 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
11 | Life Time to Date (LTD) means in service amounts as of Dec 31, 2019

## SEC62-D2-1-3_Table 1c
Numbers may not add due to rounding. | [17 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 3 of 12
Table 1c
Capital Project Listing - Nuclear Operations Facility Projects
Projects ≥ $20M Total Project Cost1
[7 empty] | Total | 1st Execution Business Case3
[6 empty] | Final | Project |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Start | In-Service | Cost2 |  | In-Service | LTD5 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Date | Date4 | (M$) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r)
PROJECTS NOT IN EB-2016-0152
46 | DN | DN Main Power Output Protection System Replacement | 80122 | Sustaining | 2016-09-01 | 2027-08-10 | 65 | n/a | 88.4 | 0 | 75 | 0 | 0 | 0 | 15 | 20 | 20 | 20
47 | DN | DN Group II Pressure Transmitter Replacement | 80123 | Sustaining | 2016-01-21 | 2028-01-14 | 47.7 | n/a | 37.5 | 0 | 29 | 0 | 2 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8
48 | DN | DN Obsolete Controller Replacement | 80124 | Sustaining | 2017-06-04 | 2026-12-18 | 38 | 38 | 28.5 | 5.4 | 13.1 | 4.9 | 4.8 | 3.9 | 3 | 3.7 | 2 | 0.5
49 | DN | DN Emergency Power Generator 1 and 2 Replacement | 80126 | Regulatory | 2017-02-07 | 2022-05-26 | 176.2 | 176.2 | 180.8 | 19.4 | 89.4 | 72 | 0 | 89.4 | 0 | 0 | 0 | 0
50 | DN | DN Fuel Handling Computer Input/Output Subsystem and Interprocessor Communication Replacement | 80148 | Sustaining | 2015-12-22 | 2027-04-21 | 23.4 | n/a | 22.1 | 0 | 21 | 0 | 0 | 1.6 | 0.4 | 2 | 14 | 3
51 | DN | DN Fire Resistant Fluid Pump Improvement | 80150 | Sustaining | 2016-01-11 | 2025-11-03 | 30 | n/a | 25 | 0 | 25 | 0 | 0 | 8.5 | 6.5 | 5 | 5 | 0
52 | DN | DN Class 1 Rectifier Replacement | 82883 | Sustaining | 2018-05-28 | 2032-12-31 | 42.3 | n/a | 36.3 | 0 | 17 | 0 | 0 | 3 | 3.5 | 3.5 | 3.5 | 3.5
53 | DN | DN Main Power Output and Class IV Transformer Control Cabinet Wiring Replacement | 82890 | Sustaining | 2019-01-03 | Deferred | 26.8 | n/a | 24.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | DN | DN Fuel Handling Head Major Component Replacement | 82947 | Sustaining | 2018-10-12 | 2027-05-25 | 98 | n/a | 60.9 | 0 | 59 | 0 | 0 | 0 | 20 | 13 | 13 | 13
55 | DN | DN Copper Piping Replacement | 83049 | Sustaining | 2016-08-19 | 2022-12-30 | 45.1 | 29.3 | 43.7 | 28.7 | 6 | 2.7 | 6.3 | 6 | 0 | 0 | 0 | 0
56 | DN | DN Fuel Handling Power and Signal Cable Catenary Replacement | 83052 | Sustaining | 2019-04-26 | 2027-01-01 | 24.6 | n/a | 11.9 | 0 | 8.7 | 0 | 2.5 | 8.5 | 0.2 | 0 | 0 | 0
57 | DN | DN Powerhouse Upper Level Service Water Piping Replacement | 83053 | Sustaining | 2016-10-31 | 2025-01-23 | 75.2 | 55.7 | 66.7 | 16.2 | 50.5 | 1.9 | 0 | 13 | 16.5 | 2.5 | 16 | 2.5
58 | DN | DN Phase 2 Station Battery Replacement | 83076 | Sustaining | 2016-08-10 | 2028-12-01 | 34.5 | 18.9 | 26.2 | 0.3 | 18.6 | 1.3 | 2.7 | 4.9 | 3.9 | 3.5 | 3.2 | 3
59 | DN | DN Main Output Transformer & Unit Service Transformer Replacement | 83296 | Sustaining | 2018-07-17 | 2024-06-13 | 170.1 | 170.1 | 131.2 | 0 | 98.4 | 0 | 32.8 | 65.6 | 28.7 | 4 | 0.1 | 0
60 | DN | DN Large Moderator Temperature Control Valve Replacement | 83297 | Sustaining | 2018-11-26 | 2026-06-30 | 36.9 | n/a | 31.2 | 0 | 26.2 | 0 | 5 | 5 | 9 | 5 | 7.2 | 0
61 | DN | DN Secondary System High Priority Control Valve Replacement | 83298 | Sustaining | 2018-03-27 | 2027-12-23 | 35.4 | n/a | 29.6 | 0 | 26.5 | 0 | 3.2 | 3.2 | 9.5 | 8.5 | 5.3 | 0
62 | DN | DN Condenser Steam Discharge Valve Control System Replacement | 83299 | Sustaining | 2019-01-03 | 2027-12-01 | 29.7 | n/a | 22.8 | 0 | 18.5 | 0 | 0 | 5.3 | 2.6 | 7.9 | 2.6 | 0
63 | DN | DN 4kV Motor Refurbishment and Replacement | 83480 | Sustaining | 2018-10-19 | 2028-06-26 | 278.8 | n/a | 172.1 | 0 | 89.8 | 0 | 0 | 11.8 | 19 | 15 | 17 | 27
64 | DN | DN Isolated Phase Bus Refurbishment | 83484 | Sustaining | 2020-07-14 | 2028-06-29 | 62.4 | n/a | 36.5 | 0 | 22.9 | 0 | 0 | 0 | 0 | 8.8 | 0 | 14.2
65 | DN | DN Turbine Hall Crane Controls Upgrade | 83556 | Sustaining | 2017-12-05 | 2020-12-08 | 23.6 | 19.7 | 23.1 | 0 | 0 | 22.2 | 0 | 0 | 0 | 0 | 0 | 0
66 | DN | DN Fuel Handling Service Area Bridge F5 Ball Screw Assembly Replacement | 83558 | Sustaining | 2018-03-06 | 2025-06-06 | 28.2 | n/a | 12.5 | 0 | 11.8 | 0 | 0 | 0 | 4.6 | 5.4 | 1.8 | 0
67 | DN | DN East Irradiated Fuel Bay Permanent Fuel Inspection Equipment | 83559 | Regulatory | 2018-03-06 | 2022-05-30 | 25 | 25 | 17.9 | 0 | 8.9 | 0 | 9 | 8.9 | 0 | 0 | 0 | 0
68 | DN | DN Unit 2 Turbine Control & Aux Systems Upgrade | 83664 | Sustaining | 2019-12-23 | 2025-07-31 | 112.7 | n/a | 102.2 | 0 | 102.1 | 0 | 0 | 0 | 0 | 0 | 102.1 | 0
69 | DN | DN Fuel Handling Replacement of Fuelling Machine Calibration Facility | 83916 | Sustaining | 2019-02-22 | 2025-07-18 | 22.4 |  | 22.4 | 0 | 22.4 | 0 | 0 | 0 | 2.5 | 9.9 | 9.9 | 0
70 | DN | DN Air Operated Valve Replacement | 84009 | Sustaining | 2020-03-08 | 2028-12-30 | 85.7 | n/a | 82.9 | 0 | 39.5 | 0 | 0 | 12.5 | 0 | 8 | 13.5 | 5.5
71 | DN | DN Primary Heat Transport Liquid Relief Valve Modifications (Waterhammer) | 84235 | Regulatory | 2019-01-09 | 2026-07-06 | 86.8 | 85.9 | 70.5 | 24.4 | 43.5 | 2.6 | 0 | 11.5 | 13.7 | 2.9 | 12.2 | 3.3
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts include minor removal costs and reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | The designation of "n/a" means the project has not advanced to a First Execution BCS
4 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
5 | Life Time to Date (LTD) means in service amounts as of Dec 31, 2019

## SEC62-D2-1-3_Table 2a
Numbers may not add due to rounding. | [15 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 4 of 12
Table 2a
Capital Project Listing - Nuclear Operations Facility Projects
Projects $5M - $20M Total Project Cost1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost2 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Description | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
ONGOING PROJECTS FROM EB-2016-0152
1 | DN | DN Active Liquid Waste System Upgrade | 31403 | Regulatory | Add aeration and chemical addition to the active liquid waste management system to ensure compliance with discharge criteria. | 2009-11-03 | 2022-12-15 | 12.1 | 6.9 | 0 | 0 | 6.6 | 0.4 | 0 | 0 | 0
2 | DN | DN Dryer Programmable Logic Controller Replacement | 31420 | Sustaining | Replace obsolete programmable logic controllers. | 2014-02-05 | 2024-08-10 | 12.2 | 4.2 | 3.3 | 1.4 | 0.7 | 1.6 | 1.4 | 0.5 | 0
3 | DN | DN Pressurizer Heaters & Controllers Replacement Project | 31422 | Sustaining | Replace electrical heaters in pressurizers that are at the end of their expected life. | 2011-04-11 | 2021-12-13 | 13.9 | 0.1 | 0 | 1 | 0.1 | 0 | 0 | 0 | 0
4 | DN | DN Containment Button-up Activity Monitors Replacement | 31432 | Sustaining | Replace aging and obsolete radioactivity monitors used to button up the Negative Pressure Containment System on high activity. | 2013-11-22 | 2021-03-22 | 9.9 | 0 | 1.9 | 2 | 0 | 0 | 0 | 0 | 0
5 | DN | DN Computer Upgrade for Heavy Water Management System (Tritium Removal Faclity / Site Upgrader) | 31436 | Sustaining | Upgrade obsolete Heavy Water Management System computers that control Tritium Removal Facility and Station Upgrader operations. | 2012-10-17 | 2021-11-17 | 8.2 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0
6 | DN | DN Replacement of Obsolete Online Chemistry Analysers | 31520 | Sustaining | Replace obsolete online chemistry analysers | 2012-10-28 | 2021-01-18 | 16.7 | 0 | 3.9 | 1.9 | 0 | 0 | 0 | 0 | 0
7 | DN | DN Tritium Removal Facility Deuterium Make-up System Electrolyzer Replacement | 31522 | Sustaining | Replace aged and obsolete TRF DMS Electrolyzer, to ensure reliability to the end of facility operation. | 2012-11-02 | 2019-10-02 | 14.5 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
8 | DN | DN Feeder Scanner Replacement | 31526 | Sustaining | Replace the equipment that scans the feeders to locate channels containing failed fuel bundles. | 2012-12-11 | 2022-08-31 | 18.9 | 2.3 | 0 | 3 | 2.3 | 0 | 0 | 0 | 0
9 | DN | DN Reactor Regulating System Logic Module Redesign | 31534 | Sustaining | Redesign the Regulator Regulating System logic modules to address spurious rod movements as well as addressing obsolescence of current modules. | 2013-12-30 | 2023-04-15 | 9.9 | 1.2 | 0 | 2.9 | 0 | 1.2 | 0 | 0 | 0
10 | DN | DN Turbine-Generator Lube Oil Purifier Replacement | 31536 | Sustaining | Replace obsolete turbine lubricating oil purifier used to remove contaminants and metal from lubricating oil during operation. | 2012-11-05 | 2018-04-05 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | DN | DN Feedwater Chemistry Control Improvements | 31548 | Sustaining | Install improved feedwater chemistry monitoring and connections for portable filtration. | 2013-11-26 | 2020-02-07 | 14 | 0 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0
12 | DN | DN Tritium Removal Facility Cryogenic Refrigeration System Turbine Oil Supply System / Turbine Replacement | 31701 | Sustaining | Replace the Tritium Removal Facility Cryogenic Refrigeration System turbine oil supply system and hydrogen expander turbine with a dynamic gas bearing (oilfree) turbine | 2014-01-13 | 2025-06-30 | 12.9 | 3.1 | 0 | 0 | 0 | 0 | 0 | 3.1 | 0
Table continues on Ex. D2-1-3 Table 2b
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).

## SEC62-D2-1-3_Table 2b
Numbers may not add due to rounding. | [15 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 5 of 12
Table 2b
Capital Project Listing - Nuclear Operations Facility Projects
Projects $5M - $20M Total Project Cost1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost2 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Description | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
ONGOING PROJECTS FROM EB-2016-0152 (Continued from Ex. D2-1-3 Table 2a)
13 | DN | DN Fuel Handling Power Track Platform & Maintenance Cut Out | 31702 | Sustaining | Construct a working platform and modify the power track structure to allow the power track equipment to be maintained during Unit 1 or Unit 4 outages as well as Unit 2 and Unit 3 outages. | 2013-12-10 | 2019-11-30 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | DN | DN Fuel Handling Obsolete Control Relay Re-Engineer/Replacement | 31704 | Sustaining | Replace the obsolete Fuel Handling control relays with relays of equal quality and near identical installation to mitigate challenges to FH System reliability. | 2013-10-22 | 2024-07-30 | 5.8 | 5.4 | 1.1 | 1.5 | 0 | 3.1 | 2.3 | 0 | 0
15 | DN | DN Vapour Recovery Button-Up Valve Replacements | 31706 | Sustaining | Replace aging vapour recovery containment buttonup valves with new design less prone to passing. | 2013-12-06 | 2024-02-05 | 16.2 | 16.2 | 0 | 0 | 0 | 15.2 | 0.9 | 0.1 | 0
16 | DN | DN Auxiliary Boiler Feed Pump Seal Cooling | 33224 | Sustaining | lnstall Gland Injection Cooling flush at both pump mechanical seals, for all eight ABFPs, as well as two new mechanical seals and two heat exchanger skids at each pump. | 2014-03-06 | 2021-12-15 | 9.7 | 1 | 0.9 | 1 | 1 | 0 | 0 | 0 | 0
17 | DN | DN Hydrogen Cooling Temperature Control Valve TCV20 Redesign | 33228 | Sustaining | Replace Hydrogen Cooling temperature control system butterfly valve with a new type of control valve and controller, to address the reliability of the system during seasonal lake water temperature fluctuations. | 2012-11-27 | 2021-06-20 | 16.2 | 0.3 | 0 | 1 | 0.3 | 0 | 0 | 0 | 0
18 | DN | Fuel Handling Computer Replacement | 33815 | Sustaining | Replace obsolete components of the fuel handling system control computers. | 2005-08-29 | 2021-11-30 | 15.6 | 0.4 | 0 | 0.7 | 0.4 | 0 | 0 | 0 | 0
19 | DN | DN Central Services Area Sewage Line and Sump Emergency Connections | 38466 | Sustaining | Replace corroded and degraded sewage piping from Central Services Area and add emergency connections to allow sewage truck to empty sump in emergencies. | 2013-07-25 | 2028-12-05 | 7.9 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0.3 | 1.3
20 | DN | DN Tritium Removal Facility Cold Box Vacuum System Obsolescence | 80020 | Sustaining | Address poor reliability and obsolescence of the TRF Cold Box Vacuum System that maintains high vacuum conditions for insulation and leak detection around the Low and High Tritium Distillation and Cryogenic Refrigeration systems. | 2016-01-06 | 2022-12-10 | 9.6 | 9.1 | 0 | 0 | 8.7 | 0.4 | 0 | 0 | 0
21 | DN | DN Feeder Scanner Replacement | 80070 | Sustaining | Replace permanent feeder scanner equipment with portable system that can be setup outside of containment prior to use. | 2014-05-26 | 2022-08-31 | 18.9 | 2.1 | 0 | 5.5 | 2.1 | 0 | 0 | 0 | 0
22 | DN | DN Fire Hazard Assessment and Fire Safe Shutdown Analysis Modifications | 80151 | Regulatory | Implement modifications required for compliance to Canadian Standards Association N29307 Fire Protection for Nuclear Power Plants identified during the Integrated Safety Review and committed in the Integrated Implementation Plan. | 2015-11-19 | 2021-09-10 | 20 | 0.5 | 0 | 11.7 | 0.5 | 0 | 0 | 0 | 0
23 | DN | DN Vault Cooling Coil Replacement | 82816 | Regulatory | Replace leaking and degraded cooling coils in the containment vault, which impairs the functions of maintaining vault temperatures during normal operation and removing heat from the steam-laden atmosphere in Loss of Coolant Accident conditions. | 2015-12-03 | 2019-07-31 | 17.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | DN | DN Irradiated Fuel Discharge Mechanism Major Component Replacement | 82841 | Sustaining | Replace the shuttle cylinders and other major components of the Irradiated Fuel Discharge system which are approaching end of design life. | 2015-11-27 | 2024-02-01 | 5.9 | 2.3 | 0 | 1.7 | 0 | 0 | 2.3 | 0 | 0
Table continues on Ex. D2-1-3 Table 2c
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).

## SEC62-D2-1-3_Table 2c
Numbers may not add due to rounding. | [15 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 6 of 12
Table 2c
Capital Project Listing - Nuclear Operations Facility Projects
Projects $5M - $20M Total Project Cost1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost2 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Description | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
ONGOING PROJECTS FROM EB-2016-0152 (Continued from Ex. D2-1-3 Table 2a)
25 | PN | PA Standby Generator Reliability Upgrades | 40972 | Sustaining | Improve reliability and availability of the unit 012/034 Standby Generators (SG) by addressing obsolescence, lack of spare parts, maintenance and performance issues. | 2012-04-17 | 2021-12-08 | 19 | 0 | 4.7 | 6.7 | 0 | 0 | 0 | 0 | 0
26 | PN | PNGS Daily Tritium Sampler Replacement | 40977 | Regulatory | Replace unreliable, inaccurate and obsolete Airborne Tritium Samplers with improved models having silica gel column, to ensure reliable airborne tritium monitoring to the end of facility operation. | 2012-04-13 | 2018-08-05 | 6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | PN | PN Replacement of Obsolete Online Chemistry Analysers | 40985 | Sustaining | Replace obsolete online chemistry analyzers. | 2013-03-26 | 2019-08-15 | 18.5 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0
28 | PN | PA Replacement of Auxiliary Irradiated Fuel Bay Supertool | 40987 | Sustaining | Replace the Auxiliary Irradiated Fuel Bay (AIFB) Supertool, which is a telescopic lifting tool used to irradiated fuel baskets and storage modules within the AIFB. Unavailability impacts fuelling activities and the movement of fuel into Dry Storage Modules. | 2012-05-09 | 2020-12-31 | 5.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0
29 | PN | PA Standby Generator Protective Relay Upgrade | 41044 | Sustaining | Replace obsolete electromechanical protective relays with digital units. | 2014-01-07 | 2019-10-31 | 11.4 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
30 | PN | PB Replacement of Obsolete Instrumentation and Control Equipment | 49154 | Sustaining | Replace critical obsolete instrumentation and control equipment. | 2011-08-24 | 2021-03-31 | 6.8 | 0 | 1.9 | 0.9 | 0 | 0 | 0 | 0 | 0
31 | PN | PB Fukushima Emergency Telecommunications Enhancement | 49161 | Regulatory | Install a new telecommunications system that is portable and rapidly deployable at all onsite and offsite locations required for emergency response during a beyond design basis event. | 2012-06-14 | 2017-12-21 | 5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | IRI | DN Feeder and Fuel Channel Baseline Inspections | 83051 | Sustaining | Develop inspection capability, via procurement and assembly of inspection tooling and material handling equipment, to perform baseline inspections of feeders and fuel channels prior to the restart of refurbished Darlington units. | 2016-08-04 | 2018-10-01 | 6.7 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
33 |  | Subtotal | [5 empty] | 379.5 | 56.8 | 21.7 | 45.4 | 22.7 | 22 | 7 | 3.9 | 1.3
Table continues on Ex. D2-1-3 Table 2d
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).

## SEC62-D2-1-3_Table 2d
Numbers may not add due to rounding. | [15 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 7 of 12
Table 2d
Capital Project Listing - Nuclear Operations Facility Projects
Projects $5M - $20M Total Project Cost1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost2 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Description | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
COMPLETED/CANCELLED PROJECTS FROM EB-2016-0152
34 | DN | DN Passive Auto-Catalytic Recombiners | 31306 | Regulatory | Install passive autocatalytic recombiners for longterm postaccident hydrogen mitigation. | 2009-12-12 | 2018-11-05 | 5.8 | 0 | -0.1 | 0 | 0 | 0 | 0 | 0 | 0
35 | DN | DN Tritium Removal Facility Cryogenic Refrigeration System Hydrogen Compressors Condition Monitoring System | 31410 | Value Enhancing | Install a realtime condition monitoring system on the Cryogenic Refrigeration System (CRS) Hydrogen Compressors for predictive maintenance, to allow proactive intervention and thereby extend the operation time between planned TRF outages potentially from every 1.5 years to a target of every 2 years. | 2012-10-22 | 2017-10-05 | 6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | DN | DN Fukushima Emergency Telecommunications Enhancement | 31512 | Regulatory | Install a new telecommunications system that is portable and rapidly deployable at all onsite and offsite locations required for emergency response during a beyond design basis event. | 2012-06-14 | 2017-12-05 | 7.4 | 0 | -0.1 | 0 | 0 | 0 | 0 | 0 | 0
37 | DN | DN Permanent Detectors for Startup Instrumentation | 31528 | Value Enhancing | Install permanent startup instrumentation detectors, thereby eliminating outage time and worker dose to install and remove temporary detectors. | 2013-10-31 | Cancelled | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | DN | DN Main Output Transformer / Unit Service Transformer / System Service Transformer /10MVA Spare Transformer Storage Facility | 31530 | Sustaining | Construct a transformer storage facility within the unzoned area of the protected area, to ensure transportation to an affected unit within 5 days and minimize the impact of surveillance routines as well as periodic maintenance on spare transformers. | 2012-12-19 | 2017-05-05 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | DN | Replacement of Obsolete Computer Components | 33509 | Sustaining | Replace obsolete components of the digital control computers. | 2000-06-15 | 2019-06-05 | 9.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | DN | DN Installation of partial discharge monitors | 33623 | Sustaining | Provide a means of assessing stator winding conditions in the Main Generator and Primary Heat Transport Pump Motors. | 2007-05-04 | 2014-02-05 | 5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | DN | DN Main Outpur Transforment Capital Spares | 36002 | Sustaining | Mitigate the risk of a forced outage due to Main Output Transformer failure by acquiring two spare transformer phases to facilitate a planned refurbishment programme. | 2011-08-27 | 2017-03-05 | 8.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | DN | DN Emergency Power Generator Power Turbine Capital Spare | 36004 | Regulatory | Purchase a spare Emergency Power Generator power turbine to mitigate risk of engine failure. | 2013-05-31 | Cancelled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | DN | Tritium Removal Facility Tritium Emissions Reduction Project | 38942 | Sustaining | Install an adsorbent dryer system and improved stack monitoring to reduce tritium emissions | 2012-10-09 | 2016-04-04 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | DN | DN Emergency Service Water Pipe and Component Replacement | 73397 | Sustaining | Replacement of degraded Emergency Service Water piping, valves and tanks during the 2015 Vacuum Building Outage. | 2014-02-04 | 2016-01-05 | 6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | DN | DN BU55/56 Maintenance | 73399 | Sustaining | Perform refurbishment of 0-553150-BU55 and -BU56, whose condition assessment identified the risk of failure due to connection/joint and insulation age-related degradation. | 2013-06-01 | Cancelled | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | DN | DN Condensate Extraction Pump Pump Motor Spare | 80117 | Sustaining | Acquire a capital spare motor for the Condensate Extraction Pumps. | 2015-01-09 | 2018-12-20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | DN | DN DX-750 Spacer Retrieval CFFA | 82949 | Regulatory | Develop tooling for the retrieval of fuel channel spacer during unit refurbishment | 2020-09-15 | 2020-11-18 | 6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | PN | PB Main Generator Automatic Voltage Regulator and Protective Relay Upgrade | 40680 | Sustaining | Replace analog automatic voltage regulator and electromechanical protective relays with new digital devices. | 2010-02-22 | 2015-07-05 | 18.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | PN | PB Machine Guarding Improvement on Low Risk Equipment | 40983 | Regulatory | Install machine guarding on equipment to comply with Ministry of Labour requirements. | 2012-11-19 | 2018-04-05 | 5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | PN | PA Emergency Core Injection Strainer Capacity Margin | 40984 | Regulatory | Improve capacity of the emergency coolant injection system strainers to improve design margins. | 2012-05-08 | 2013-05-05 | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | PN | PN Emergency Power Generator Engine Replacement | 41043 | Sustaining | Replace the Emergency Power Generator gas turbine engines. | 2014-12-18 | 2016-12-21 | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table continues on Ex. D2-1-3 Table 2e
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).

## SEC62-D2-1-3_Table 2e
Numbers may not add due to rounding. | [15 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 8 of 12
Table 2e
Capital Project Listing - Nuclear Operations Facility Projects
Projects $5M - $20M Total Project Cost1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost2 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Description | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
COMPLETED/CANCELLED PROJECTS FROM EB-2016-0152
52 | PN | PA Passive Auto-Catalytic Recombiners | 46605 | Regulatory | Install passive autocatalytic recombiners for longterm postaccident hydrogen mitigation. | 2010-01-13 | 2014-05-05 | 12.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | PN | PB SG/EPG Fire Detection Upgrade and CO2 Suppression Removal | 49116 | Sustaining | Ensure fire compliance for the Standby Generator, Standby Generator Oil Pump and Emergency Water & Power System buildings including a reliiable and maintainable fire detection system. | 2010-02-19 | 2016-04-05 | 8.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | PN | PB RBSW Dechlorination & MISA Cleanup | 49132 | Regulatory | Replace temporary dechlorination system for the Reactor Building Service Water discharge with a permanent system with improved sampling points. | 2010-02-08 | 2016-11-05 | 15.1 | 0 | -0.1 | 0 | 0 | 0 | 0 | 0 | 0
55 | PN | PB Replacement of Containment Box-up Monitors | 49134 | Sustaining | Replace obsolete ventilation exhaust radioactivity monitors | 2010-12-20 | 2015-05-05 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | PN | PB Screenhouse Trash Bar Screen Replacement | 49140 | Sustaining | Upgrade trash bar screens to handle the debris currently experienced from Lake Ontario. | 2011-03-08 | 2015-07-05 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | PN | PN Fire Code Compliance for Relocatable Structures in Un-Zoned Area for Pickering Station | 49146 | Regulatory | Ensure compliance with Canadian Standards Association N29307 Fire Protection for CANDU Nuclear Plants for relocatable structures in the unzoned area. | 2011-12-12 | 2018-12-05 | 19.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | PN | Unit 1 & 4 Fuel Channel East Pressure Tube Shift Tooling | 49247 | Sustaining | Develop and implement tooling for the repositioning and reconfiguration of the Unit 1 & 4 pressure tubes. | 2009-11-09 | 2017-09-05 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | PN | PN Standby Boiler Capacity Improvement | 49267 | Regulatory | Provide reliable backup heating steam. | 2008-12-12 | 2015-11-05 | 6.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | PN | PN Administration Building Rehab | 49284 | Sustaining | Complete rehabilitation of the Administration Building to support operations and postoperations activities. | 2009-11-09 | 2014-12-05 | 18.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | PN | PA Class II Emergency Lighting | 49296 | Regulatory | Upgrade emergency lighting to meet electrical codes and address employee safety concerns. | 2011-08-25 | 2015-08-05 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | PN | PA Replacement of Unit 1, Unit 4 and Irradiated Fuel Bay-A Stack Monitors | 49298 | Sustaining | Replace obsolescent stack monitors with monitors used in Pickering B. | 2012-11-02 | 2018-05-05 | 12.4 | 0 | -0.2 | 0 | 0 | 0 | 0 | 0 | 0
63 | PN | PA Fukushima Phase 1 Beyond Design Basis Event Emergency Mitigation Equipment | 49299 | Regulatory | Provide capability to respond to Beyond Design Basis Events following the events at Fukushima Daiichi Nuclear Power Plant | 2011-09-21 | 2017-12-05 | 16.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | PN | PA Firewater Buried Ring Header Replacement (North Loop) | 80069 | Sustaining | Proactively replace buried sections of the Pickering Units 1 to 4 fire water header subject to frequent failures due to poor material selection. | 2014-11-10 | 2019-07-05 | 9.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | SEC | Security Project A | 25918 | Regulatory | Security Protected | 2012-06-25 | 2017-12-05 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | IRI | IMS CIGAR (Channel Inspection and Gauging Apparatus for Reactors) Gap System and Drive Reliability | 66594 | Sustaining | Improve the reliabiity, operability and functionality of CIGAR (Channel Inspection and Gauging Apparatus for Reactors) system. | 2012-06-01 | 2018-09-05 | 11.7 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
66 |  | Subtotal | [5 empty] | 277.7 | 0 | -0.2 | 0 | 0 | 0 | 0 | 0 | 0
Table continues on Ex. D2-1-3 Table 2f
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).

## SEC62-D2-1-3_Table 2f
Numbers may not add due to rounding. | [15 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 9 of 12
Table 2f
Capital Project Listing - Nuclear Operations Facility Projects
Projects $5M - $20M Total Project Cost1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost2 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Description | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
PROJECTS NOT IN EB-2016-0152
67 | DN | DN Liquid Zone Control Valve Positioner Replacement | 80113 | Sustaining | Replace the positioners and current-to-pressure transducers on the Liquid Zone Control System control valves with digital positioners. | 2015-12-17 | 2023-04-27 | 17 | 4.3 | 0 | 5.5 | 2 | 2 | 0.3 | 0 | 0
68 | DN | DN Fuel Handling Trolley Major Auxiliary Component Replacement | 82842 | Sustaining | Replace various major auxiliary components on the Fuel Handling trolleys that are approaching the end of their design lives. Component failures impact on fuelling availability and nuclear safety. | 2017-01-27 | 2024-02-05 | 18.3 | 15.6 | 0 | 2 | 3.4 | 4 | 8.3 | 0 | 0
69 | DN | DN Buried Piping Sacrificial Anode Replacement | 82881 | Sustaining | Replace depleted cathodic protection anodes on buried piping systems, which could result in pipe degradation and failures if not addressed. | 2018-06-25 | 2025-11-15 | 12.2 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0
70 | DN | DN Fuel Handling Motor Replacement | 82886 | Sustaining | Replace fuel handing system motors critical for the operation of various fuel handling systems that are nearing the end of their design lives. | 2017-01-04 | 2023-04-21 | 16.9 | 16.5 | 0 | 0.3 | 0.3 | 2 | 7 | 7.2 | 0
71 | DN | DN Liquid Injection Safey System Ball Position Detection System Replacement | 82887 | Regulatory | Replace obsolescent components of the Liquid Injection Safety System tank ball position detection system, which provides the main control room indication of the operational state of Shutdown System 2. | 2017-12-08 | 2021-03-01 | 5 | 1.4 | 0 | 0.4 | 0.6 | 0.6 | 0.1 | 0 | 0
72 | DN | DN Post-Accident Water Cooling System Heat Exchanger Replacement | 82891 | Sustaining | Replace the heat exchangers which are degraded, with leaks and reduced thermal efficiency. Further degradation may result in unavailability of the heat exchangers, which could force a 4 unit shutdown. | 2018-11-21 | 2023-03-05 | 6.3 | 0 | 2.4 | 0.1 | 0 | 0 | 0 | 0 | 0
73 | DN | DN Tritium Removal Facility Analyzer and Cryogenic Temperature Equipment Replacement | 82893 | Sustaining | Replace the oxygen analyzer and cryogenic temperature equipment, which are obsolescent, have legacy operational issues and are required for compliance with hydrogen codes and standards. | 2018-07-30 | 2025-01-03 | 5.1 | 3.5 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0
74 | DN | DN Heavy Water Management System Computer Distributed Control Units Replacement | 83288 | Sustaining | Upgrade and/or replace the Distributed Control Units required for the monitoring and control of TRF, Upgrader and Heavy Water Management Building systems. | 2018-01-30 | 2024-09-03 | 18.8 | 8.4 | 0 | 2.4 | 0 | 4.5 | 0 | 3.9 | 0
75 | DN | DN Irradiated Fuel Bay Cooling and Purification Pump Replacement | 83483 | Sustaining | Replace the pumps used to circulate Irradiated Fuel Bay water through the cooling circuits and thereby remove the decay heat generated by the irradiated fuel. | 2017-12-04 | 2021-09-27 | 6.9 | 6.1 | 0 | 0.7 | 0 | 3.5 | 2.6 | 0 | 0
76 | DN | DN Tritium Removal Facility Water Air Conditioning Units Replacement | 83560 | Sustaining | Replace the air conditioning units used to provide cooling for the environment in the control room and equipment rooms. | 2018-05-24 | 2019-12-06 | 10 | 3.4 | 0 | 0 | 3.3 | 0.1 | 0 | 0 | 0
77 | DN | DN Tritium Removal Facility Training Simulator | 83650 | Sustaining | Development and installation of a Tritium Removal Facility training simulator. | 2017-11-15 | 2025-08-25 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | DN | DN Radiation Detection Equipment Obsolescence - Moderator Cover Gas Monitors & Fixed Area Alarming Gamma Monitors | 84399 | Sustaining | Replace both systems with new and modern equipment, since the existing equipment is obsolete and approaching the end of their useful design life. | 2019-11-22 | 2023-12-10 | 18 | 11.3 | 0 | 0 | 0 | 11.3 | 0 | 0 | 0
79 | DN | DN Radiation Detection Equipment Obsolescence - Active Liquid Waste Liquid Effluent Monitor, D2O in H2O & Online Gas Chromatograph | 84400 | Sustaining | Replace the three systems with new and modern equipment, since the existing equipment is obsolete and approaching the end of their useful design life. | 2019-11-22 | 2023-09-19 | 15 | 14.1 | 0 | 0 | 13 | 1.1 | 0 | 0 | 0
80 | DN | DN Shutdown System 1 and Reactor Regulating System Ion Chamber Replacements | 83937 | Sustaining | Replace the aging Shutdown System 1 and Reactor Regulating System ion chambers that measure neutron flux in the reactor for trip parameter and reactor regulation purposes. | 2018-12-03 | 2028-12-01 | 11.3 | 2.3 | 0 | 0.4 | 0.4 | 0.4 | 0.5 | 0.6 | 0.4
Table continues on Ex. D2-1-3 Table 2g
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).

## SEC62-D2-1-3_Table 2g
Numbers may not add due to rounding. | [15 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 10 of 12
Table 2g
Capital Project Listing - Nuclear Operations Facility Projects
Projects $5M - $20M Total Project Cost1
Total
[7 empty] | Final | Project | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Project | Start | In-Service | Cost2 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Description | Date | Date3 | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p)
PROJECTS NOT IN EB-2016-0152
81 | DN | DN Fuelling Maching Duct & Central Service Area Air Conditioning Unit Replacement | 84006 | Sustaining | Replace aging and degraded fan motors and cooling coils for the Fuelling Machine Duct and Central Service Area Air Conditioning Units (ACUs) nto ensure reliable operation. | 2019-08-28 | 2021-08-10 | 18.3 | 0 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
82 | DN | DN Emergency Power System Enhancements | 84378 | Sustaining | Install improvements to Darlington Emergency Power Generator EPG3, to enhance operation and ensure long term reliability of the EPG3 machine for a safe station operation. | 2019-04-07 | 2024-04-29 | 10.2 | 0.1 | 0 | 5.8 | 0.1 | 0 | 0 | 0 | 0
83 | DN | DN Containment Penetrations and Fiber Optics Installation | 84586 | Sustaining | Install new containment penetrations, with fibre optics and 120V power, to improve bandwidth and expand coverage of the existing communications network. | 2019-09-26 | 2026-10-30 | 9 | 4.9 | 0 | 2.5 | 1.4 | 1.1 | 2.5 | 0 | 0
84 | DN | DN Main Power Output Transformer Fire Containment System Upgrade | 86055 | Sustaining | Install upgraded Darlington Main Power Output Transformers Fire Containment System to improve deluge functionality and comply with Fire Codes. | 2020-07-21 | 2021-08-10 | 20 | 20 | 0 | 0 | 0 | 3.9 | 3.9 | 8.4 | 3.9
85 | PN | PN Emergency and Mobile Satellite Communication Systems Replacement | 80130 | Sustaining | Replace the obsolescent Emergency and Mobile Satellite Communication systems required for on- and off-site communications in the event of emergencies. | 2016-02-16 | 2021-03-31 | 9.1 | 0 | 0 | 3.8 | 0 | 0 | 0 | 0 | 0
86 | PN | PN Stator Cooling Water Alkalization and Make-up Deoxygenation | 83061 | Sustaining | Install Alkalization and Makeup Water Deoxygenation for the Stator Cooling Water system, to reduce copper oxide fouling of copper conductors. | 2016-12-22 | 2024-02-28 | 12.6 | 0 | 2.7 | 1.3 | 0 | 0 | 0 | 0 | 0
87 | IRI | PN SLAR (Spacer Location And Reposition) System Sustainability | 83564 | Sustaining | Upgrade obsolete components of the Spacer Location and Reposition system, by procuring a new control centre and transformer cart with cables, upgrading the existing control centre, and replacing associated computers. | 2019-01-31 | 2022-04-21 | 6.1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
88 | IRI | PN ANDE (Advanced Non-Destructive Examination) Reliability Improvements | 83565 | Sustaining | Improve the reliability of the Advanced Non-Destructive Examination system used to inspect fuel channels in Pickering Units 5 - 8 to minimize outage delays. | 2017-12-20 | 2022-01-31 | 6.7 | 1.4 | 0 | 5.2 | 1.4 | 0 | 0 | 0 | 0
89 | IRI | PN Circumferential Wet Scrape Tool (CWEST) Enhancements | 84140 | Sustaining | Implement Circumferential Wet Scrape Tool (CWEST) enhancements, to address high priority areas for improvement and address CWEST Project #66600 open issues. | 2019-11-11 | 2022-12-15 | 18.6 | 2.4 | 4.2 | 10.1 | 2.4 | 0 | 0 | 0 | 0
90 | IRI | IRI Steam Generator Manipulator & Automated Tube Plug | 84888 | Sustaining | Procure manipulators and automated tube plugging equipment, to address all obsolescence issues, reduce outage delays, improve productivity and allow for future equipment advancements. | 2020-03-10 | 2020-05-06 | 8.2 | 3.6 | 1.6 | 1.2 | 3.5 | 0.1 | 0 | 0 | 0
91 |  | Subtotal | [5 empty] | 286 | 119.4 | 11.8 | 42.4 | 31.9 | 38.1 | 25 | 20 | 4.3
92 |  | Total | [5 empty] | 943.2 | 176.2 | 33.3 | 87.8 | 54.6 | 60 | 32 | 23.9 | 5.5
DIVISION TOTALS:
93 |  | Darlington | [6 empty] | 168.7 | 14.7 | 58.6 | 47.3 | 59.9 | 32 | 23.9 | 5.5
94 |  | Pickering | [6 empty] | 0 | 11.8 | 12.6 | 0 | 0 | 0 | 0 | 0
95 |  | Operations and Project Support | [6 empty] | 7.5 | 6.8 | 16.5 | 7.4 | 0.1 | 0 | 0 | 0
96 |  | Total | [6 empty] | 176.2 | 33.3 | 87.8 | 54.6 | 60 | 32 | 23.9 | 5.5
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).

## SEC62-D2-1-3_Table 4a
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 11 of 12
Table 4a
Comparison of In-Service Capital Additions - Nuclear Operations ($M) 2016-2021
Line |  | 2016 | (c)-(a) | 2016 | (g)-(c) | 2017 | (g)-(e) | 2017 | (k)-(g) | 2018 | (k)-(i) | 2018
No. | Business Unit | Budget | Change | Actual | Change | OEB Approved1 | Change | Actual | Change | OEB Approved1 | Change | Actual
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
1 | Darlington NGS | 325.9 | -105.6 | 220.3 | -16.3 | 226.1 | -22.1 | 204.1 | 81.8 | 216.4 | 69.5 | 285.8
2 | Pickering NGS | 146 | -98 | 47.9 | 132.4 | 172.8 | 7.5 | 180.3 | -113.9 | 47.5 | 18.9 | 66.4
3 | Operations and Project Support2 | 36 | -34.2 | 1.8 | 40.8 | 49.2 | -6.6 | 42.6 | -26.2 | 45.9 | -29.5 | 16.4
4 | Subtotal | 507.9 | -237.8 | 270.1 | 156.9 | 448.2 | -21.2 | 427 | -58.4 | 309.8 | 58.8 | 368.6
5 | Supplemental In-Service Forecast3 | -41.8 | 41.8 | 0 | 0 | -1.6 | 1.6 | 0 | 0 | 24.9 | -24.9 | 0
6 | Total Portfolio In-Service Forecast | 466 | -195.9 | 270.1 | 156.9 | 446.6 | -19.6 | 427 | -58.4 | 334.7 | 33.9 | 368.6
7 | Darlington New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Darlington Spacer Retrieval 4 | 0 | 0 | 0 | 5.8 | 6.4 | -0.6 | 5.8 | -5.8 | 0 | 0 | 0
10 | Pickering Extended Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Minor Fixed Assets | 31 | -14.7 | 16.3 | 15.4 | 26 | 5.6 | 31.6 | -9.9 | 20 | 1.7 | 21.7
12 | In-Service Capital Additions before Disallowance | 497 | -210.7 | 286.4 | 178 | 479 | -14.6 | 464.4 | -74.1 | 354.7 | 35.6 | 390.3
13 | OEB Disallowance |  |  |  |  | -47.9 |  |  |  | -35.5
14 | Total In-Service Capital Additions | 497 | -210.7 | 286.4 | 178 | 431.1 | 33.3 | 464.4 | -74.1 | 319.2 | 71.1 | 390.3
Line |  | 2018 | (e)-(a) | 2019 | (e)-(c) | 2019 | (i)-(e) | 2020 | (i)-(g) | 2020 | (k)-(i) | 2021
No. | Business Unit | Actual | Change | OEB Approved1 | Change | Actual | Change | OEB Approved1 | Change | Budget | Change | Budget
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
15 | Darlington NGS | 285.8 | -25.3 | 295.7 | -35.2 | 260.5 | -84.4 | 101.3 | 74.9 | 176.1 | 63.4 | 239.5
16 | Pickering NGS | 66.4 | -29.6 | 9.7 | 27 | 36.8 | -1.8 | 29.7 | 5.2 | 34.9 | -14.1 | 20.9
17 | Operations and Project Support2 | 16.4 | -11.9 | 44.3 | -39.8 | 4.5 | 16.6 | 0 | 21.1 | 21.1 | 44.3 | 65.4
18 | Subtotal | 368.6 | -66.8 | 349.8 | -48 | 301.8 | -69.6 | 131 | 101.1 | 232.1 | 93.6 | 325.8
19 | Supplemental In-Service Forecast3 | 0 | 0 | 16.6 | -16.6 | 0 | -20.4 | 78.8 | -99.2 | -20.4 | -2.7 | -23.1
20 | Total Portfolio In-Service Forecast | 368.6 | -66.8 | 366.3 | -64.5 | 301.8 | -90 | 209.8 | 1.9 | 211.7 | 90.9 | 302.7
21 | Darlington New Fuel | 0 | 0 | 0 | 0 | 0 | 17.1 | 15.3 | 1.7 | 17.1 | -17.1 | 0
22 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Darlington Spacer Retrieval4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Pickering Extended Operations | 0 | 0.8 | 0 | 0.8 | 0.8 | 30.7 | 0 | 31.5 | 31.5 | -26.4 | 5.1
25 | Minor Fixed Assets | 21.7 | 1.8 | 19.1 | 4.5 | 23.5 | -1.7 | 19.5 | 2.4 | 21.9 | 2.2 | 24.1
26 | Total In-Service Capital Additions | 390.3 | -64.2 | 385.4 | -59.3 | 326.1 | -43.9 | 244.7 | 37.6 | 282.2 | 49.6 | 331.8
27 | OEB Disallowance |  |  | -38.5 |  |  |  | -24.5
28 | Total In-Service Capital Additions | 390.3 | -64.2 | 346.9 | -20.8 | 326.1 | -43.9 | 220.2 | 62 | 282.2 | 49.6 | 331.8
Notes:
1 | In-service additions per EB-2016-0152, Ex. J21.1, Attachment 2, Table 2. Amounts in this schedule do not reflect OEB-ordered reductions for: Auxiliary Heating System in-service amount (EB-2016-0152 Decision and Order, p. 21); Operations Support Building in-service amount (EB-2016-0152 Decision and Order, p. 22). These reductions are reflected in total nuclear rate base amounts in Ex. B3-2-1, Table 1. The 2017-2020 sub-components within the total portfolio in service forecast has also been adjusted for reclassification of projects from Darlington to Operations and Projects Support with no change to total amount.
2 | Includes Engineering, Inspection and Reactor Innovation, and Security & Emergency Services.
3 | Supplemental forecast to reconcile BCS in-service estimates to final business plan (see Ex. D2-1-3, Section 4.0).
4 | Project #82949 DN X-750 Spacer Retrieval CMFA. OEB Approved amounts for Darlington Spacer Retreival per EB-2016-0152, Schedule 1, Staff-024, which were reflected in EB-2016-0152 Ex. J21.1, Attachment 2, Table 1.

## SEC62-D2-1-3_Table 4b
Numbers may not add due to rounding. | [11 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-SEC-062
Attachment 1
Page 12 of 12
Table 4b
Comparison of In-Service Capital Additions - Nuclear Operations ($M) 2021-2026
Line |  | 2021 | (c)-(a) | 2021 | (e)-(c) | 2022 | (g)-(e) | 2023 | (i)-(g) | 2024 | (k)-(i) | 2025
No. | Business Unit | OEB Approved1 | Change | Budget | Change | Plan | Change | Plan | Change | Plan | Change | Plan
|  | (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k)
1 | Darlington NGS | 62.1 | 177.5 | 239.5 | 170.2 | 409.7 | -92.2 | 317.6 | -26 | 291.6 | 82.7 | 374.3
2 | Pickering NGS | 0 | 20.9 | 20.9 | -20.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Operations and Project Support2 | 0 | 65.4 | 65.4 | -52 | 13.4 | 80.4 | 93.8 | -93.8 | 0 | 29.5 | 29.5
4 | Subtotal | 62.1 | 263.7 | 325.8 | 97.4 | 423.1 | -11.8 | 411.3 | -119.7 | 291.6 | 112.3 | 403.9
5 | Supplemental In-Service Forecast3 | 100.2 | -123.4 | -23.1 | 14.6 | -8.5 | 37.7 | 29.2 | -16.1 | 13.1 | 24.8 | 37.9
6 | Total Portfolio In-Service Forecast | 162.3 | 140.4 | 302.7 | 112 | 414.7 | 25.9 | 440.5 | -135.8 | 304.7 | 137.1 | 441.8
7 | Darlington New Fuel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.5 | 16.5 | 0.4 | 16.9
8 | Darlington Water Treatment Plant Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.6 | 138.6 | -138.6 | 0
9 | Darlington Spacer Retrieval4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Pickering Extended Operations | 0 | 5.1 | 5.1 | -5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Minor Fixed Assets | 19.3 | 4.7 | 24.1 | -4.4 | 19.6 | 1.4 | 21 | 8.2 | 29.2 | -10.6 | 18.7
12 | Total In-Service Capital Additions | 181.6 | 150.2 | 331.8 | 102.5 | 434.3 | 27.3 | 461.6 | 27.4 | 489 | -11.7 | 477.3
13 | OEB Disallowance | -18.2
14 | Total In-Service Capital Additions | 163.5 | 168.3 | 331.8 | 102.5 | 434.3 | 27.3 | 461.6 | 27.4 | 489 | -11.7 | 477.3
Line |  | 2025 | (c)-(a) | 2026
No. | Business Unit | Plan | Change | Plan
|  | (a) | (b) | (c)
15 | Darlington NGS | 374.3 | -205.4 | 168.9
16 | Pickering NGS | 0 | 0 | 0
17 | Operations and Project Support2 | 29.5 | -29.5 | 0
18 | Subtotal | 403.9 | -234.9 | 168.9
19 | Supplemental In-Service Forecast3 | 37.9 | 112 | 149.9
20 | Total Portfolio In-Service Forecast | 441.8 | -123 | 318.8
21 | Darlington New Fuel | 16.9 | 1.2 | 18.1
22 | Darlington Water Treatment Plant Lease | 0 | 0 | 0
23 | Darlington Spacer Retrieval4 | 0 | 0 | 0
24 | Pickering Extended Operations | 0 | 0 | 0
25 | Minor Fixed Assets | 18.7 | -7.3 | 11.4
26 | Total In-Service Capital Additions | 477.3 | -129 | 348.3
Notes:
1 | In-service additions per EB-2016-0152, Ex. J21.1, Attachment 2, Table 2. Amounts in this schedule do not reflect OEB-ordered reductions for: Auxiliary Heating System in-service amount (EB-2016-0152 Decision and Order, p. 21); Operations Support Building in-service amount (EB-2016-0152 Decision and Order, p. 22). These reductions are reflected in total nuclear rate base amounts in Ex. B3-2-1, Table 1. The 2017-2020 sub-components within the total portfolio in service forecast has also been adjusted for reclassification of projects from Darlington to Operations and Projects Support with no change to total amount.
2 | Includes Engineering, Inspection and Reactor Innovation, and Security & Emergency Services.
3 | Supplemental forecast to reconcile BCS in-service estimates to final business plan (see Ex. D2-1-3, Section 4.0).
4 | Project #82949 DN X-750 Spacer Retrieval CMFA. OEB Approved amounts for Darlington Spacer Retreival per EB-2016-0152, Schedule 1, Staff-024, which were reflected in EB-2016-0152 Ex. J21.1, Attachment 2, Table 1.

## AMPCO71-D2-1-3_Table 1d
Numbers may not add due to rounding. | [17 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-01-AMPCO-071
Attachment 1
Table 1d
Capital Project Listing - Nuclear Operations Facility Projects
Projects ≥ $20M Total Project Cost1
[7 empty] | Total | 1st Execution Business Case3
[6 empty] | Final | Project |  | Total | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service
Line |  |  | Project |  | Start | In-Service | Cost2 |  | In-Service | LTD5 | IR Term | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
No. | Facility | Project Name | Number | Category | Date | Date4 | (M$) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r)
PROJECTS NOT IN EB-2016-0152
72 | DN | DN Motor Operated Valve Replacement | 84551 | Sustaining | 2020-03-08 | 2028-12-30 | 44.5 | n/a | 37.5 | 0 | 29.3 | 0 | 0 | 7 | 7 | 5.3 | 7 | 3.2
73 | DN | DN Primary Heat Transport Pump Rotor Inspection and Replacement | 84799 | Sustaining | 2020-05-22 | 2026-10-15 | 89.2 | 89.2 | 46.4 | 0 | 46.4 | 0 | 0 | 0 | 15.3 | 12.5 | 18.4 | 0.2
74 | DN | DN Revenue Metering Transformer Replacement | 84939 | Regulatory | 2020-04-14 | 2026-10-01 | 35.9 | n/a | 25.5 | 0 | 25.5 | 0 | 0 | 0 | 0 | 3.4 | 6.9 | 15.2
75 | PN | PN P58 Buried Blowdown Piping Replacement | 83072 | Sustaining | 2016-11-24 | 2020-12-05 | 20.9 | 20.9 | 16.6 | 0 | 0 | 16.6 | 0 | 0 | 0 | 0 | 0 | 0
76 | PN | PA Low Pressure Feedwater Heat Exchanger Replacement | 83088 | Sustaining | 2016-05-09 | 2018-05-05 | 22 | 19.4 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | PN | PN High Pressure Turbine Spindle Capital Spares | 83668 | Sustaining | 2017-11-13 | 2019-08-26 | 21.3 | 23.4 | 21.3 | 21.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | SEC | Security Project B | 82929 | Sustaining | 2016-06-03 | 2021-09-17 | 32.7 | 32.7 | 28.8 | 0.8 | 0.1 | 3.1 | 24.8 | 0.1 | 0 | 0 | 0 | 0
79 | SEC | Security Project C | 82930 | Sustaining | 2016-06-03 | 2021-03-01 | 22.9 | 22.9 | 18.9 | 0 | 0 | 3.1 | 15.8 | 0 | 0 | 0 | 0 | 0
80 | IRI | DN Rapid Delivery Machine | 83039 | Sustaining | 2014-11-03 | 2025-05-30 | 162.2 | n/a | 118.4 | 0 | 113.2 | 5.2 | 0 | 0 | 83.6 | 0 | 29.5 | 0
81 | ENG | Fleet Monitoring Initiative (Monitoring & Diagnostic Centre) | 83828 | Sustaining | 2018-03-01 | 2023-07-23 | 29.3 | n/a | 23.7 | 0 | 16 | 2.7 | 5 | 6 | 10 | 0 | 0 | 0
82 |  | Subtotal |  |  |  |  | 2205.8 |  |  |  | 1153.2 | 138.2 | 114 | 281.4 | 280.4 | 155.6 | 316 | 119.8
83 |  | Total |  |  |  |  | 4115.9 |  |  |  | 1506.584 | 187 | 214.8 | 362.2 | 344.4 | 256.7 | 379.9 | 163.4
DIVISION TOTALS:
84 |  | Darlington | [8 empty] | 1377.384 | 155.6 | 169.2 | 356.2 | 250.7 | 256.7 | 350.4 | 163.4
85 |  | Pickering | [8 empty] | 0 | 17.3 | 0 | 0 | 0 | 0 | 0 | 0
86 |  | Operations and Project Support | [8 empty] | 129.2 | 14.2 | 45.6 | 6 | 93.6 | 0 | 29.5 | 0
87 |  | Total | [8 empty] | 1506.584 | 187 | 214.8 | 362.2 | 344.4 | 256.7 | 379.9 | 163.4
Notes:
1 | Projects with expenditures during IR term OR In-Service Amounts in Bridge or IR term, AND Completed/Deferred Projects at the time of preparing the Amended 2020-2026 Business Plan (from EB-2016-0152 or subsequent).
2 | Total Project Cost reflects BCS amounts at the time of preparing the Amended 2020-2026 Business Plan, with the exception of Completed/Deferred/Cancelled Projects (for which actual costs are shown). BCS amounts include minor removal costs and reflect
point estimates or, if range estimate or no estimate is provided in lieu of a point estimate, the current estimate of total project cost
3 | The designation of "n/a" means the project has not advanced to a First Execution BCS
4 | Final In-Service Date means either the current forecast of the final date for in-service and close out of project, or the historical final project in-service date (but not the final project close out date which may not have yet occurred).
5 | Life Time to Date (LTD) means in service amounts as of Dec 31, 2019

## SEC80-D2-2-7_Chart 2
Numbers may not add due to rounding. | [9 empty] | FIled: 2021-04-19
EB-2020-0290
Exhibit L
D2-02-SEC-80
Attachment 1
L-D2-02-SEC-80 Attachment 1: Revised Ex. D2-02-07 Chart 2, including Unit 2 and U0/D/F/S Costs to end March 2021
# | Bundle / Category | Unit 3 | % | Unit 1 | % | Unit 4 | % | UD/0/F/S | Unit 2 | U2EE
|  | 2024 I/S |  | 2025 I/S |  | 2026 I/S |  | LTD Mar 2021 Act I/S | LTD Mar 2021 Act I/S | Budget
1 | Retube & Feeder Replacement | 1072.6 | 43% | 798 | 42% | 837.4 | 41% | 905.4 | 1629.5 | 1176.2
2 | Turbine Generators | 291.5 | 12% | 206.3 | 11% | 230.9 | 11% | 43.7 | 231 | 227
3 | Balance of Plant | 242 | 10% | 188.3 | 10% | 197.6 | 10% | 60.8 | 501.7 | 382.3
4 | Fuel Handling/Defueling | 17.3 | 1% | 8.5 | 0% | 5.4 | 0% | 45.7 | 39.7 | 52.4
5 | Steam Generators | 43.3 | 2% | 42.8 | 2% | 46.2 | 2% | 6.4 | 61 | 54.5
6 | Subtotal Major Work Bundles | 1666.8 | 67% | 1243.9 | 65% | 1317.5 | 65% | 1061.9 | 2462.9 | 1892.5
7 | Facility and Infrastructure Projects | 0 | 0% | 0 | 0% | 0 | 0% | 826 | 0 | 0
8 | Safety Improvement Opportunities | 0 | 0% | 0 | 0% | 0 | 0% | 308 | 0 | 0
9 | Subtotal F&IP/ SIO | 0 | 0% | 0 | 0% | 0 | 0% | 1134.1 | 0 | 0
10 | Project Execution | 70.4 | 3% | 49.7 | 3% | 47.5 | 2% | 13.2 | 125.5 | 164.9
11 | Contract Management | 11.9 | 0% | 7.8 | 0% | 10.9 | 1% | 11.8 | 11.7 | 18.6
12 | Engineering | 75.6 | 3% | 48.9 | 3% | 57 | 3% | 84.4 | 104.7 | 83.1
13 | Managed Systems Oversight | 2.8 | 0% | 1.9 | 0% | 2.2 | 0% | 18.6 | 9.8 | 12.8
14 | Planning and Controls | 25.6 | 1% | 20.9 | 1% | 26 | 1% | 86.3 | 52.5 | 51.2
15 | Nuclear Safety | 11.4 | 0% | 8.3 | 0% | 11.1 | 1% | 44.1 | 23.9 | 23.1
16 | Program Fees and Other Support | 73.3 | 3% | 56.1 | 3% | 65.9 | 3% | 62 | 103 | 101.3
17 | Supply Chain | 12.4 | 0% | 11.3 | 1% | 14.8 | 1% | 18.7 | 15.2 | 36.5
18 | Work Control | 30.7 | 1% | 27.1 | 1% | 33.2 | 2% | 0 | 47.6 | 36.1
19 | Operations and Maintenance | 285 | 11% | 218 | 11% | 249.8 | 12% | 54.9 | 382.8 | 274.6
20 | Early Release 3 | 0 | 0% | 0 | 0% | 0 | 0% | 10.6 | 0 | 0
21 | Early Release 4 | 0 | 0% | 0 | 0% | 0 | 0% | 146.9 | 0 | 0
22 | Subtotal OPG Functions | 599.1 | 24% | 449.9 | 24% | 518.4 | 26% | 551.7 | 876.8 | 802.1
23 | Contingency | 238.1 | 10% | 215 | 11% | 194 | 10% | 0 | 0 | 677.5
24 | Total High Confidence Unit I/S Estimates and LTD Actuals | 2504 | 100% | 1908.8 | 100% | 2029.8 | 100% | 2747.7 | 3339.6 | 3372.1
25 | Total Envelope I/S Amount for Remaining units |  |  | 6442.6
Notes:
1. U0/D/F/S means Unit 0, Definition Phase, Early In-Service Projects, Facility and Infrastructure Projects and Safety Improvement Opportunities.
2. Actuals are U0/D/F/S and Unit 2 I/S amounts are to the end of March 2021. As a result of on-going project closeout activities and accruals, there will be minor changes to the final I/S amounts.
3. Original footnote to Chart 2 continues to apply, i.e. In-Service amount forecasts for Units 3, 1, and 4 are inclusive of minor early in-service amounts totalling $3.0M as follows: (i) The Unit 1 amount of $1,908.8M includes $1.4M for an Early In-Service Project placed in-service in 2023; (ii) the Unit 4 amount of $2,029.8M includes $1.6M for an Early In-service Project placed in-service in 2024.