## Sheet1
D2O Cost Estimates
| Date of Estimate | Total Estimated Cost ($M) | Entity that Provided the Estimate | General Contractor | Total Cost Expended on the Project At Date of Estimate ($M) | Notes | Evidence Reference
Faith+Gould | Early 2012 |  | Faith & Gould (OPG) | N/A |  | "F&G’s estimated overnight cost for construction only was $64.6M, basedon the project information available at the time" | D2-2-10, p.43
2012 Full Release Definition BCS | 2012-06-01 | 108 | OPG Project Team | B&M | 3 |  | D2-2-SEC-94, Chart 1
2012 Partial Release Execution BCS | 2012-08-01 | 108 | OPG Project Team | B&M | 3 |  | D2-2-SEC-94, Chart 1
2013 Full Release Execution BCS | 2013-05-01 | 110 | OPG Project Team | B&M | 12.7 |  | D2-2-SEC-94, Chart 1
B&M Estimate | 2014-01-01 |  | B&M | B&M |  | EPC Contract at completion estimate $123.5 | D2-2-10, p.66, Chart 3
B&M Estimate | 2014-02-01 |  | B&M | B&M |  | EPC Contract at completion estimate $133.1 | D2-2-10, p.66, Chart 3
B&M Estimate | 2014-04-01 |  | B&M | B&M |  | EPC Contract at completion estimate $224.9 | D2-2-10, p.66, Chart 3
B&M Estimate | 2014-05-01 |  | B&M | B&M |  | EPC Contract at completion estimate $253.7 | D2-2-10, p.66, Chart 3
B&M Estimate | 2014-07-01 |  | B&M | B&M |  | EPC Contract at completion estimate $282.1 | D2-2-10, p.66, Chart 3
2014 F+G Estimate | 2014-07-01 | 345 | F+G/OPG/B&M | B&M |  |  | D2-2-10, p.66
B&M Estimate | 2014-09-01 |  | B&M | B&M |  | EPC Contract at completion estimate $286.1 | D2-2-10, p.66, Chart 3
2015 Superseding Release Execution BCS | 2015-03-01 | 381 | OPG Project Team | CanAtom | 123.1 |  | D2-2-SEC-94, Chart 1
High Bridge Estimate | 2017-03-01 |  | High Bridge (OPG) | CanAtom |  | "High Bridge’s final estimate of the cost to complete the project was $99.5M plus $9M in 20 contingency." | D2-2-10, p.93
2018 Superseding Release Execution BCS | 2018-02-01 | 510 | OPG Project Team | CanAtom | 381.1 |  | D2-2-SEC-94, Chart 1