## Sheet1
SCR # | SCR Date | Status | Title | Res Cat Sig Lvl
P-2008-24552 | 2008/10/17 | CLOSED | Design EC Revision Not Clear | D4
N-2020-16403 | 2020/11/03 | COMPLETE | DNR - D20 - Project 16-31555 - Multiple EC closeout extensions beyond 6 months | D3
N-2020-09538 | 2020/07/13 | COMPLETE | Project 16-31555 D2O Storage Project – ASME Code Case 1518-5 and 2055-2 requiring CNSC acceptance | C3-NFE
N-2020-01498 | 2020/01/29 | CLOSED | DNR - Project 16-31555: CatID 999871 – Repair and VTD - HWMB West Annex | D4
N-2019-15978 | 2019/09/18 | CLOSED | DNR - Proj 16-31555 HWMB West Annex – Omission in NK38-MDR-38000-10003 R04 | D4
N-2019-08116 | 2019/04/24 | CLOSED | DNRU2 - Project #31555 D2O - Adverse impact on workforce and schedule due to OCOT Non-Acceptance of Fees | D4
N-2019-06816 | 2019/04/02 | CLOSED | 16-31555 – NCR 360 – Material traceability lost on support HS1383 - bypassed witness point | D4
N-2019-06814 | 2019/04/02 | CLOSED | 16-31555 – NCR 325 – Spool installed by passed ANI witness point | D4
N-2018-16779 | 2018/08/01 | CLOSED | P#16-31555 (D2O): Need supporting RDL documents during EC revision submissions (EC 120615, 120421, 120423, HWMB West Annex) | D4
N-2018-13572 | 2018/06/12 | CLOSED | P#16-31555 (D2O) Construction Proceeded without Regulatory Approval of Alternate Code Compliances | C3
N-2018-04024 | 2018/02/15 | CLOSED | P#16-31555 - QA concerns regarding OTEK Level Indicating Meters (D2O Storage Project, HWMB West Annex) | C3-NFE
N-2017-14114 | 2017/06/14 | CLOSED | D2O Project 16-31555 – Contractor rented tools taken from Sea Can. | D4
N-2017-12609 | 2017/05/26 | CLOSED | 16-31555 - Soil Void Discovered | D3
N-2017-07247 | 2017/03/27 | CLOSED | DNRU2 D2O Storage 16-31555 - New quorum members for EC 120421/120422/120423/120424 COMS | D4
N-2017-06692 | 2017/03/20 | CLOSED | DNRU2 Un-monitored flattened cardboard box put into the RFRISA office area (zone 1) garbage bin | D4
N-2017-06126 | 2017/03/13 | CLOSED | DNRU2 D2O Storage Project, ENA Hold TCD deferred for Valve Packing Data Sheets | D4
N-2017-04885 | 2017/02/27 | CLOSED | D2O Project 16-31555 –Concrete Trucks Alarmed Exploranium | D4
N-2017-04171 | 2017/02/17 | CLOSED | 16-31555- D2O Storage Project Worker makes contact with I-beam | D3
N-2017-03295 | 2017/02/08 | CLOSED | DNRU2 - Project 16-31555 - D2O Storage Project - Vendor NCR 2015-66 on CatID 704876-1 | D4
N-2017-02354 | 2017/01/28 | CLOSED | D2O Storage Project 16-31555: Leak detected during an OPT of Domestic Water | D4
N-2017-02081 | 2017/01/25 | CLOSED | D2O Storage Project #16-31555 - Worker Bumped Mouth | D3
N-2017-00788 | 2017/01/12 | CLOSED | DNRU2 - Vendor Relief Valve Calibration Records may not be acceptable as record for OPG Relief Valve Program | C3-NFE
N-2016-31402 | 2016/12/20 | CLOSED | DNRU2 – Strat IV Mgr Deviation Approval - EC 120494 - Project 16-31555 D2O Storage Project | D4
N-2016-30473 | 2016/12/08 | CLOSED | D2O Storage Project 16-31555: Worker strained ankle | D4
N-2016-30370 | 2016/12/07 | CLOSED | Project 16- 31555 -Damaged EWP / Lack of Reporting | D4
N-2016-29860 | 2016/12/01 | CLOSED | Project 16-31555 - D2O Storage Project - DEC 120402 - D2O Supply PHT Tie-in - No ENA Hold to support VPDS creation - Immediate support was required | D3
N-2016-29258 | 2016/11/24 | CLOSED | DNRU2 EC 120494 R00 Hold by Refurb Design – Project 16-31555 D2O Storage Project | D4
N-2016-26786 | 2016/10/28 | CLOSED | Adverse Trend - Discovery Issues with OLW for the D2O Storage Project | C3-NFE
N-2016-23480 | 2016/09/20 | CLOSED | Stakeholder Meetings Open Items - HWMB West Annex | D4
N-2016-23154 | 2016/09/16 | CLOSED | Open Item - HWMB West Annex Project - Design EC Release | D4
N-2016-21219 | 2016/08/24 | CLOSED | EC127218 ITF file not updated after work is transferred to another project | D4
N-2016-21100 | 2016/08/23 | CLOSED | Project #16-31555 - D2O Storage project: Civil Design Issues and rework | C3-NFE
N-2016-18575 | 2016/07/20 | CLOSED | Project #16-31555 D2O Storage: PO#250735 - Vendor not qualified in our ASL to act as an Agent | D4
N-2016-18227 | 2016/07/15 | CLOSED | D2O Storage Project 16-31555 – ASME Code Case N-62-7 applied without CNSC acceptance | D4
N-2016-16068 | 2016/06/16 | CLOSED | 16-31555 D2O Storage Project - Subcontractor Supervision lacking qualifications | D4
N-2016-14910 | 2016/06/03 | CLOSED | 16-31555 - D2O Storage Project Scope Change | D4
N-2016-14904 | 2016/06/03 | CLOSED | 16-31555 - D2O Storage Project Scope Change | D4
N-2016-13832 | 2016/05/24 | CLOSED | Procurement Oversight - 16-31555 D2O Storage Project - Drum Heeling Vacuum Tanks In-process Inspection - ITP non-conformance | D4
N-2016-12890 | 2016/05/13 | CLOSED | Procurement Oversight - 16-31555 D2O Storage Project - Limited ASL access, inadequate contractor procedures, and procedural non-compliance | D4
N-2016-11793 | 2016/05/04 | CLOSED | Excessive time spent supporting the contract issuance of Refurbishment Project Work | D4
N-2016-06608 | 2016/03/14 | CLOSED | 16-31555 - Vendor charging against PO when no work is ongoing | D4
N-2016-05662 | 2016/03/03 | CLOSED | D20 Project 16-31555 - unable to excavate as planned | D4
N-2016-04551 | 2016/02/19 | CLOSED | D2O Storage Project 16-31555 - Engineering Change EC 120784 R003, Active Plant Drainage Change Papers Rejected. | D4
N-2016-04173 | 2016/02/16 | CLOSED | 16-31555 - Issuance of contract took longer than anticipated, resulting in costs incurred prior to contract issued | D4
N-2016-02919 | 2016/02/02 | CLOSED | D2O Storage Project - 16-31555 - Minor Spill | D4
N-2016-00809 | 2016/01/12 | CLOSED | D2O Storage Project 16-31555: Employee slipped on snowy surface striking his Elbow | D3
N-2016-00371 | 2016/01/06 | CLOSED | Procurement Oversight - 16-31555 D2O Storage Project | C3-NFE
N-2015-29011 | 2015/12/10 | CLOSED | D2O Storage Project 16-31555: Unauthorized use of waste bin - repeat event | D4
N-2015-28652 | 2015/12/07 | CLOSED | D2OStorage Project 16-31555: Pumper truck leak | D4
N-2015-28404 | 2015/12/03 | CLOSED | 31555- D2O Storage Project - Original PO missed portion of Fixed Price subcontract value | D4
N-2015-28361 | 2015/12/03 | CLOSED | Project 16-31555 - D2O Storage Project - TSSA Registration Response Package cannot be found by Design Agency | C3
N-2015-27967 | 2015/11/29 | CLOSED | D2O Storage Project 16-31555: Glycol Pump issue | D4
N-2015-23820 | 2015/10/16 | CLOSED | D2O Storage Project 16-31555: Overflow of TRF Box Drain Water from Settling Tank | D4
N-2015-22804 | 2015/10/06 | CLOSED | D2O Storage Project 16-31555: Temporary dewatering system discharge | D4
N-2015-21156 | 2015/09/22 | CLOSED | D2O Storage Project: 16-31555 - desk damaged | D4
N-2015-20644 | 2015/09/17 | CLOSED | D2O Storage Project 16-31555, Pumps' Overpressure Protection Inadequate | D4
N-2015-20027 | 2015/09/10 | CLOSED | D2O Storage Project 16-31555, EC 120421 R001, ASME Code Violations at 0-38110-NV1259 | C3
N-2015-19524 | 2015/09/02 | CLOSED | D2O Storage Project 16-31555, EC 120421 R001, Overpressure Protection Deficient at 0-38110-NV1249 | D4
N-2015-19325 | 2015/08/31 | CLOSED | Project 16-31555 - D2O storage project - DEC 122212 - Oxygen Relocation - Discovered Valve CAT ID not set to READY during Closeout of DEC | D4
N-2015-19245 | 2015/08/28 | CLOSED | D2O Storage Project 16-31555 - Concrete pour delayed due to access water | D4
N-2015-19130 | 2015/08/27 | CLOSED | Project 16-31555 - D2O Storage Project - Delay in Issuance of Accepted Documents into AS7 since April 2015 | D4
N-2015-19055 | 2015/08/26 | CLOSED | D2O Storage Project 16-31555 - Late reporting of an FME event | D4
N-2015-19046 | 2015/08/26 | CLOSED | D2O Storage Project 16-31555 - Location/Orientation of crane has potential impact to traffic and nearby equipment | D3
N-2015-18707 | 2015/08/21 | CLOSED | D2O Storage project - 16-31555 - Unable to use lift | D4
N-2015-18644 | 2015/08/20 | CLOSED | D2O Storage Project 16-31555 – Procedural Non-compliance | D4
N-2015-18046 | 2015/08/12 | CLOSED | 16-31555 D2O Project: PO# 238558 increase greater than 20% of Oringinal PO value | D4
N-2015-17678 | 2015/08/07 | CLOSED | D2O Storage Project 16-31555 - Crane obstructed Sally Port | D4
N-2015-17609 | 2015/08/06 | CLOSED | D2O Storage Project 16-31555 - delay due to undersized crane | D4
N-2015-16192 | 2015/07/15 | CLOSED | 16-31555 D2O Storage Project: Design and Construction manual N-STM-01110-10009 contradicts with the National Plumbing Code of Canada 2010 | D4
N-2015-12909 | 2015/06/04 | CLOSED | RFRISA - 10-73810 Project Change Authorization | D4
N-2015-10276 | 2015/05/06 | CLOSED | Latest Proliance Import File (PIF) loaded for D2O Storage project has incorrect planned values | D4
N-2015-08788 | 2015/04/17 | CLOSED | Project #16-31555 - Delays to the D2O Piping | D4
N-2015-07158 | 2015/03/25 | CLOSED | 16-31555 D2O Project: PO# 225561 increase greater than 20% of Oringinal PO value | D4
N-2015-06679 | 2015/03/19 | CLOSED | PROJ 16-13555: ECC Governance Deviations Required to progress DECs without Vendor Info due to lack of Proj Funding for POs | D4
N-2015-06196 | 2015/03/13 | CLOSED | Project#16-31555: TRF Oxygen tank relocate AFS not completed within permitted period after system energization | D4
N-2015-05643 | 2015/03/06 | CLOSED | 16-31555 D2O Storage Project: DEC 121146 Rev 000 Package uploaded with wrong information | D4
N-2015-02451 | 2015/02/02 | CLOSED | D2O Storage Project 16-31555 - Grout Line failure - multiple occasions | D4
N-2015-02447 | 2015/02/02 | CLOSED | D2O Storage Project 16-31555 - Unable to mobilize drill rig | D4
N-2015-02444 | 2015/02/02 | CLOSED | D2O Storage Project 16-31555 - Unable to grout due to extreme cold tempertures | D4
N-2015-01329 | 2015/01/20 | CLOSED | Project 16-31555 - Change Paper NK38-DRAW-23940-10001 Issued as Rev.000 in Asset Suite | D4
N-2014-33897 | 2014/12/08 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120488 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-33895 | 2014/12/08 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120489 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-33816 | 2014/12/08 | CLOSED | PROJ 16-31555 Design Requirements for Grounding of Construction Power for HWMB-WA (Within PA) from 0-53600-T11 (External Power Supply) not available | C3-NFE
N-2014-32760 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 121133 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32759 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120557 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32758 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120720 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32757 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120493 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32756 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120428 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32755 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120402 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32754 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120401 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32753 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120424 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32752 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120423 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32751 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120422 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32750 | 2014/11/25 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120421 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-32204 | 2014/11/20 | CLOSED | D2O Storage Project 31555 - Delay to Tie Back stressing due to water in excavation | D4
N-2014-31599 | 2014/11/13 | CLOSED | 16-31555 - D2O Storage Project risk to T1501 milestones | D4
N-2014-30705 | 2014/11/04 | CLOSED | Project 16-31555 - D2O Storage Project DEC 121327 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-30704 | 2014/11/04 | CLOSED | Project 16-31555 - D2O Storage Project DEC 121147 - N-GUID-00700-10000 Section 1.4.1.7 and 1.4.5 Deviations | D4
N-2014-30700 | 2014/11/04 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120643 N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-29467 | 2014/10/21 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120784 - Misalignment between Vendor Projects and Vendor Engineering | D4
N-2014-29464 | 2014/10/21 | CLOSED | Project 16-31555 - D2O Storage Project DEC 120784 - Active Drainage N-GUID-00700-10000 Section 1.4.1.7, 1.4.4.1 and 1.4.5 Deviations | D4
N-2014-28825 | 2014/10/14 | CLOSED | Project # 16-31555 D2O Storage Project EC:121736 WO:2948853-10 Power Cable conduit trench interference | D4
N-2014-28319 | 2014/10/08 | CLOSED | 16-31555 D2O Storage Project, TMOD For Construction Water Work Rescheduled Because Down Stream Isolation Can Not Be Guaranteed WO 2948380 | D4
N-2014-28190 | 2014/10/07 | CLOSED | Project # 16-31555 Delay to D2O Storage Project- Tie Back Drilling and Dewatering due to Thunderstorms and Lightening in the area | D4
N-2014-27858 | 2014/10/03 | CLOSED | Project # 16-31555 D2O Storage Project - Oily Sheen/Foamy substance in weir tanks | D4
N-2014-27838 | 2014/10/03 | CLOSED | Project #16-31555 D2O Storage Project -Box Drain Sump pumping air quality issue | D4
N-2014-26939 | 2014/09/24 | CLOSED | 16-31555 D2O Storage Project Delay to Stressing Tie-Backs | D4
N-2014-26808 | 2014/09/23 | CLOSED | 16-31555 D2O Storage Project Delay to Stressing Tie backs | D4
N-2014-26802 | 2014/09/23 | CLOSED | 16-31555 D2O Storage Project Delay to drilling tie backs | D4
N-2014-26468 | 2014/09/19 | CLOSED | 16-31555 D2O Storage Project, Late Issue Of Schedule | D3
N-2014-26387 | 2014/09/18 | CLOSED | 16-31555 D2O Storage Project, Delays To Tie Back Drilling, Machine Required Mechanical Repairs | D4
N-2014-26236 | 2014/09/17 | CLOSED | 16-31555, D2O Storage Project, Drilling Of Tie Backs Suspended Due To Water Ingress At Tie Back #39 | D4
N-2014-25565 | 2014/09/10 | CLOSED | 16-31555 D2O Storage Project, Non Issue Of P6 Schedule | D4
N-2014-25552 | 2014/09/10 | CLOSED | 16-31555 D2O Storage Project, Employees Sent Home Early, Waiting For Resolution Of SCR-N-2014-25313 Before Excavation Entry Authorized | D4
N-2014-25313 | 2014/09/08 | CLOSED | 16-31555 D2O Storage Project, Work On Hold For Review And Discussion Of OPG Engineering Concerns With Caisson Walls | D4
N-2014-25194 | 2014/09/05 | CLOSED | D2O Storage Project, One Tie Back Completed, Resources Working On Retrieving Disconnected Rock Hammer Drill | D4
N-2014-25045 | 2014/09/04 | CLOSED | 16-31555 D2O Storage Project, Delay In Receiving New Rock Hammer Drill Resulted In One Tie Back Being Installed | D4
N-2014-24888 | 2014/09/03 | CLOSED | 16-31555: D2O Storage Project, Shortage Of 1L Nalgene Bottles For Dewatering Sample Submission To Lab | D4
N-2014-24591 | 2014/08/28 | CLOSED | 16-31555 - D2O Storage Project - Approved DEC 120493 Drawings PDFs in Asset Suite are cut off. | D4
N-2014-23046 | 2014/08/08 | CLOSED | 16-31555 D2O Storage Project, EK Hold On Work Package at T-16 | D4
N-2014-23031 | 2014/08/08 | CLOSED | 16-31555 D2O Storage Project, Water Ingress Into Excavation Through Tie Back Drilled Hole | D3
N-2014-22609 | 2014/08/01 | CLOSED | 16-31555 D2O Storage Project , EK Hold Still On Between T-12 and T16 Work Rescheduled | D4
N-2014-22302 | 2014/07/29 | CLOSED | 16-31555 - D2O Storage Project DEC 120401 Rev.00 - Wrong Code Classification and CSA N285 edition on Flow Diagram - Corrected | D4
N-2014-22224 | 2014/07/29 | CLOSED | 16-31555 - Delay to Schedule - D2O Storage Project - CNSC Approval for Fire Alternate Compliance (PA DEC 120352/Fire Detection DEC 120351) | D4
N-2014-21904 | 2014/07/24 | CLOSED | 16-31555 D2O Storage Project, WO 2922411 TIE-IN TO EXISTING STATION DEMIN WATER Has EK Hold On At T-16 For Work Plan | D4
N-2014-21704 | 2014/07/22 | CLOSED | 16-31555 D2O Storage Project, WO 2922410 DEC 120720 TIE-IN TO EXISTING FIRE PROT WATER SUPPPLY Has Eng Hold At T-16 | D4
N-2014-21600 | 2014/07/21 | CLOSED | 16-31555 D2O Storage Project, Delays At VSF Affecting The Number Of Trucks Removing Soil To F1 | D4
N-2014-21427 | 2014/07/18 | CLOSED | 16-31555 D2O Storage Project, Delay In Turn Around Time For Getting Work Plan Approval Signatures | D4
N-2014-21350 | 2014/07/17 | CLOSED | 16-31555 D2O Storage Project, Water Leak At F1 Soil Storage Area | D4
N-2014-21156 | 2014/07/15 | CLOSED | 16-31555 D2O Storage Project, Welding Suspended 2 Hours Because Of Rain | D4
N-2014-21012 | 2014/07/14 | CLOSED | 16-31555 D2O Storage Project, Engineering Hold On Reconfiguration Of D2O Clean Up System WO 2989699, At T-13 | D4
N-2014-20893 | 2014/07/12 | CLOSED | Project#16-31555: Construction schedule provided by EPC vendor shows delay to critical path | D3
N-2014-20634 | 2014/07/09 | CLOSED | 16-31555 D2O Storage Project, Delay In Receiving Fire & Smoke Detection For PA Trailers Work Plan Signatures | D4
N-2014-20610 | 2014/07/09 | CLOSED | 16-31555 Increase PO #217807 (D2O Storage Project) Greater than 20% Of Original Contract | D4
N-2014-20447 | 2014/07/07 | CLOSED | 16-31555 D2O Storage Project, Reschedule Work Plan Review Meetings | D4
N-2014-20192 | 2014/07/03 | CLOSED | 16-31555 D2O Storage Project , EK Hold On Work Order At T-13 | D4
N-2014-20121 | 2014/07/02 | CLOSED | 16-31555 D2O Storage Project, Delay To Strut #5 Installation Due To Strut Being Cut Shorter Than Required Length | D4
N-2014-20038 | 2014/06/30 | CLOSED | Project 16-31555 - D2O Storage Project Descoping Lessons Learned to date | D4
N-2014-19483 | 2014/06/24 | CLOSED | 16-31555 D2O Storage Project Tote Truck Driver observed under vehicle | D4
N-2014-19465 | 2014/06/24 | CLOSED | Project#16-31555: Project#16-31555: Delay to EC due to lack of funds to issue PO to OEM | D4
N-2014-19270 | 2014/06/20 | CLOSED | 16-31555 D2O Storage Project , Front End Loader Hydralic Hose Leak | D4
N-2014-19235 | 2014/06/20 | CLOSED | 16-31555 D2O Storage Project, Delay To Wailer Installation TCD | D4
N-2014-19223 | 2014/06/20 | CLOSED | 16-31555 D2O Storage Project, D9 SATM Extension Area Approval Required. | D4
N-2014-19009 | 2014/06/18 | CLOSED | 16-31555 D2O Storage Project, Risk To Wailer Installation TCD Due To Disposition Of NCR #11 | D4
N-2014-18901 | 2014/06/17 | CLOSED | 16-31555 D2O Storage Project, Wailer Installation At Risk Waiting For Approval For NCR #10 | D4
N-2014-18703 | 2014/06/15 | CLOSED | 16-31555 - Delay to Schedule - OPG review of DEC 120423 | D4
N-2014-18466 | 2014/06/12 | CLOSED | 16-31555 D2O Storage Project,, DEC: 120483 Tie In To Existing Computer Systems Under WO 2917066 Has Holds At T-13 | D4
N-2014-18371 | 2014/06/11 | CLOSED | 16-31555 D2O Storage Project, Day Shift Work On Wailer And Support Brackets Suspended Due To Weather | D4
N-2014-18112 | 2014/06/09 | CLOSED | 16-31555 D2O Storage Project, F1 Groundwater Samples Above Back Ground For Tritium | D4
N-2014-18104 | 2014/06/09 | CLOSED | 16-31555 - Delay to Schedule - OPG review of DEC 120423 | D4
N-2014-18018 | 2014/06/06 | CLOSED | 16-31555 Delay to Heat Tracing EC 124304 Impacting Dewatering Activities | D4
N-2014-17990 | 2014/06/06 | CLOSED | 16-31555 D2O Storage Project, Overdue Bioassay Submission Worker Incorrectly Set Up As "NEW" | D4
N-2014-17812 | 2014/06/05 | CLOSED | 16-31555 DNGS HWMB West Annex - Schedule Miss D2O Storage Project - Line Item ENG 78440 - OPG/B&M Accept RCO | D4
N-2014-17772 | 2014/06/04 | CLOSED | 16-31555 D2O Storage Project, Wailer & Strut Advance Copy Drawing Found In Field | D3
N-2014-17754 | 2014/06/04 | CLOSED | 16-31555 DNGS HWMB West Annex - Schedule Miss D2O Storage Project - CNSC Response to Letter #3 | D4
N-2014-17673 | 2014/06/03 | CLOSED | 16-31555 D2O Storage Project, Shipment Of Totes Out Of PA On Hold For UTP | D4
N-2014-17672 | 2014/06/03 | CLOSED | 16-31555 D2O Storage Project, Welding Of Wailer Support Bracket's On Hold | D3
N-2014-17593 | 2014/06/03 | CLOSED | 16-31555 D2O Storage Project, Discrepancy In Wailer Support Bracket Field Weld Compared To Drawings | D3
N-2014-17259 | 2014/05/30 | CLOSED | 16-31555 D2O Storage Project Delay To Start Of De Watering | D4
N-2014-15904 | 2014/05/16 | CLOSED | 16-31555 D2O Storage Project, Caisson Drilling /Installation Start Of Work Delayed Because Of Weather | D4
N-2014-15831 | 2014/05/15 | CLOSED | 16-31555 D2O Storage Project, Caisson Drilling Work Stopped, Rig Requires Repairs | D4
N-2014-15813 | 2014/05/15 | CLOSED | 16-31555 D2O Storage Project, Level Switch & Indicator For New Oxygen Tank Not Compatible With Design | D4
N-2014-15780 | 2014/05/15 | CLOSED | 16-31555, D2O Storage Project, Continuous Use Lockers Not Available | D4
N-2014-15727 | 2014/05/15 | CLOSED | 16-31555 D2O Storage Project, Caisson Drilling/Installation Work Suspended Due To Weather, 3 Out Of 4 Scheduled Caissons Completed | D4
N-2014-15621 | 2014/05/14 | CLOSED | 16-31555, D2O Storage Project, Work Suspended On Caisson Drilling/Installation Due To Lightning And Heavy Rain. 3 Of 4 Schd Caissons Installed | D4
N-2014-15402 | 2014/05/12 | CLOSED | Project#16-31555: Delay to DCSs acceptance | D4
N-2014-15339 | 2014/05/12 | CLOSED | 16-31555 D2O Storage Project , Caisson Drilling/Installation Work Suspended Due To Weather. 3 Out Of 4 Scheduled Caissons Completed | D4
N-2014-14712 | 2014/05/06 | CLOSED | 16-31555 D2O Storage Project, Delay's In Processing Of UTP's Are Affecting Transfer Of Totes From The PA And Soil Transfer From F1 | D4
N-2014-14559 | 2014/05/05 | CLOSED | 13-31555: PO Revision Greater then 20% | D4
N-2014-14555 | 2014/05/05 | CLOSED | 16-31555 D2O Storage Project, Worked in Excess Of 10 Hr Shift To Provide Escourt Duties | D4
N-2014-14310 | 2014/05/02 | CLOSED | 16-31555, D2O Storage Project, Did Not Provide CA/CMO With Proper Over Time Request For Subcontractors | D4
N-2014-14048 | 2014/04/30 | CLOSED | 16-31555, D2O Storage Project, C13 Decommissioning/ Cleanup Work Suspended Due To Weather | D4
N-2014-13983 | 2014/04/30 | CLOSED | 16-31555 D2O Storage Project, Caisson Drilling/Installation Work Suspended Due To Weather | D4
N-2014-13862 | 2014/04/29 | CLOSED | 16-31555 D2O Storage Project, Caisson Drilling/ Installation Work Suspended Due To Weather | D4
N-2014-13705 | 2014/04/28 | CLOSED | 16-31555 D2O Storage Project, Work Started On F10 Degrubbing Prior To Receiving Work Authorization | D4
N-2014-13683 | 2014/04/28 | CLOSED | 16-31555 D2O Storage Project Caissons #3 And #9 Will Requiring Re-Drilling | D4
N-2014-13675 | 2014/04/28 | CLOSED | 16-31555 D2O Storage Project, Caisson Installation Work Suspended Due To Rain And Winds, 3 Out Of 4 Scheduled Caisson Installations Completed. | D4
N-2014-13426 | 2014/04/25 | CLOSED | 16-31555, D2O Storage Project, Continued Delays In Processing UTP's For Transfer Of Totes From C13 Affecting Turnover Of Area To RWPB Project | D4
N-2014-13167 | 2014/04/23 | CLOSED | 16-31555, D2O Storage Project, DEC: 120405 TIE-IN TO/FROM D2O CLEANUP SYSTEM WO 2910084-01 Has Holds At T-13 | D4
N-2014-13166 | 2014/04/23 | CLOSED | 16-31555 D2O Storage Project, DEC: 121835 TMOD FOR CONSTRUCTION WATER WO 2948380-24 Has Holds At T-13 | D4
N-2014-13059 | 2014/04/23 | CLOSED | 16-31555, D2O Storage Project, Delays In Processing UTP's For Transfer Of Totes From C13 Affecting Turnover Of Area To RWPB Project | D4
N-2014-13028 | 2014/04/22 | CLOSED | Delay in submission of Design ECs for D2O West Annex Project | D4
N-2014-12975 | 2014/04/22 | CLOSED | 16-31555, D2O Storage Project, Task Not Closed Out In Work Week Scheduled | D4
N-2014-12957 | 2014/04/22 | CLOSED | 16-31555 D2O Storage Project, Caisson Drilling Work Delayed Due To Weather | D4
N-2014-12919 | 2014/04/22 | CLOSED | 16-31555 D2O Storage Project, 3 Out Of 4 Scheduled Caissons Installed | D4
N-2014-12835 | 2014/04/21 | CLOSED | 16-31555 D2O Storage Project, Due To Shortage Of Empty Totes, Caisson Excavated Soil Below 12 meters Will Be Transfered To C13 | D4
N-2014-12455 | 2014/04/16 | CLOSED | 16-31555 D2O Storage Project, DEC:120402 TIEIN TO/FROM HT D2O SUPP/TRANSFER SYS, WO 02910081 has Holds At T-13 | D4
N-2014-12195 | 2014/04/15 | CLOSED | 16-31555 D2O Storage Project, Caisson Installation Work Suspended Due To Heavy Rains And Wind | D4
N-2014-11890 | 2014/04/11 | CLOSED | 16-31555 - Inability to access documents for review in EDMS | D4
N-2014-11192 | 2014/04/07 | CLOSED | Environment – D2O Storage Project - Waste Manifest Errors (RS72130-9) | D4
N-2014-11018 | 2014/04/04 | CLOSED | 16-31555, D2O Storage Project Outside Work Stopped Because Of High Winds And Rain | D4
N-2014-09736 | 2014/03/25 | CLOSED | 16-31555 Breakplan Fit Test Training Required Due to Emergent Field Conditions | D4
N-2014-08336 | 2014/03/13 | CLOSED | 16-31555 - D2O Storage Project - Rejected Vouchers in Oncore due to disallowed costs per ES-MSA | D4
N-2014-08245 | 2014/03/12 | CLOSED | 16-31555 - 100% Design Complete & AFS schedule slippage | D4
N-2014-08053 | 2014/03/11 | CLOSED | 16-31555 - D2O Storage Project - Rejected Vouchers in Oncore due to disallowed costs per ES-MSA | D4
N-2014-07967 | 2014/03/10 | CLOSED | 16-31555 Steam leak from vac truck | D3
N-2014-07768 | 2014/03/08 | CLOSED | 16-31555 - D2O Storage Project - Rejected Vouchers in Oncore due to disallowed costs per ES-MSA | D4
N-2014-07767 | 2014/03/08 | CLOSED | 16-31555 - D2O Storage Project - Rejected Vouchers in Oncore due to disallowed costs per ES-MSA | D4
N-2014-07766 | 2014/03/08 | CLOSED | 16-31555 - D2O Storage Project - Rejected Vouchers in Oncore due to disallowed costs per ES-MSA | D4
N-2014-07753 | 2014/03/08 | CLOSED | 16-31555 - D2O Storage Project - Rejected Vouchers in Oncore due to disallowed costs per ES-MSA | D4
N-2014-06830 | 2014/02/28 | CLOSED | Project 16-31555 - Scope issue regarding analysis support for code classification request for the D2O Storage Project | D4
N-2014-06765 | 2014/02/28 | CLOSED | 16-31555 - 100% Design Complete & AFS schedule slippage | D4
N-2014-06499 | 2014/02/26 | CLOSED | 16-31555 D2O Storage Project, Delay's To Connecting LAN Services | D4
N-2014-06404 | 2014/02/25 | CLOSED | 16-31555 - D2O Storage Project - Rejected Voucher in Oncore due to disallowed costs per ES-MSA | D4
N-2014-05934 | 2014/02/21 | CLOSED | 16-31555 D2O Storage Project, Dose Control Device Accidently Placed Through X-ray Machine | D4
N-2014-05285 | 2014/02/15 | CLOSED | 16-31555:D2O Storage Project - Impact to ASB Sally Port due to delay/additional concrete trucks | D4
N-2014-04624 | 2014/02/10 | CLOSED | 16-31555 D2O Storage: OLW status updates being incorrectly reported by vendor. | D4
N-2014-04384 | 2014/02/07 | CLOSED | 16-31555, D2O Storage Project Work Delayed Because TRF TIS Window Rescheduled | D4
N-2014-03772 | 2014/02/03 | CLOSED | D2O Storage Project 16-31555, Delay To Application Of Feed And Product Permit | D4
N-2014-01353 | 2014/01/14 | CLOSED | D2O Storage Project 16-31555- TCD For Oxygen Work Plan (EC 122212) Delayed To 21 Jan 2014 | D4
N-2014-01333 | 2014/01/14 | CLOSED | 16-31555 - 100% Design Complete & AFS schedule slippage | D4
N-2014-00520 | 2014/01/07 | CLOSED | 16-31555 D2O Storage Project, Majority Of The Crew Sent Home After 6 Hours Based On The Weather. | D4
N-2014-00516 | 2014/01/07 | CLOSED | 16-31555 D2O Storage Project, Delay To Testing Of Foam Fire Line Due To Cold Weather | D4
N-2014-00481 | 2014/01/07 | CLOSED | Employee misplaced prox card outside of the operating island. D2O Storage Project 16-31555 | D4
N-2013-22373 | 2013/11/27 | CLOSED | D2O Storage Project 16-31555, Two Operator Tasks Scoped Into Schedule At T-1 | D4
N-2013-22286 | 2013/11/27 | CLOSED | Project#16-31555 - Breakplan civil maintenance support needed | D4
N-2013-22218 | 2013/11/26 | CLOSED | Project 16-31555 - New MEL Tag Generated by Contractor without OPG Drawing Office Involvement | C3-NFE
N-2013-21632 | 2013/11/20 | CLOSED | D2O Storage Project 16-31555 Unsecured Load Slid Forward and Contacted the Ground | D3
N-2013-21414 | 2013/11/19 | CLOSED | Delay to D2O Storage Project 16-31555 due to high winds ( crane operations terminated) | D4
N-2013-18602 | 2013/10/24 | CLOSED | Project#16-31555: Drawing/field mismatch for line 7911-W6APAB on yard services drawing | D4
N-2013-18316 | 2013/10/23 | CLOSED | Schedule Impact - Directed Change to TRF T1301 P6 Outage Logic Schedule – Project#16-38401 TRF ACS/GBCS Modification | D3
N-2013-17877 | 2013/10/19 | CLOSED | Project #16-31555 - Chemistry Lab not given adequate notification of weekend resource requirments | D4
N-2013-17769 | 2013/10/18 | CLOSED | Project # 16-31555 D2O storage project delay to Yard Drainage work | D4
N-2013-17091 | 2013/10/12 | CLOSED | Project 16-31555 D2O Storage Project ( Crane developed small hydraulic leak) | D4
N-2013-16837 | 2013/10/10 | CLOSED | Proj. 16-31555: Trend of oil leaks from construction equipment in operation (Category D4, potential/exempt, non-reportable spills) | D4
N-2013-16808 | 2013/10/10 | CLOSED | SCHEDULE - Vendor's schedule update data not received in a timely fashion Project 31555 D2O Storage Project_Repeat of D-2013-16279 *NEW* | D4
N-2013-16623 | 2013/10/09 | CLOSED | Project 16-31555 Delay to D2O storage project | D4
N-2013-16258 | 2013/10/07 | CLOSED | Project 16-31555 Delay issues due to the discovery of "K-Crete" in the LPSW footprint | D4
N-2013-16179 | 2013/10/05 | CLOSED | 16:31555: D2O Storage project, modify LPSW line W/0 2817137. Hydraulic Leak On Vac Truck. | D4
N-2013-16021 | 2013/10/04 | CLOSED | D2O Storage Project 16-31555, Work To Remove Argon Concrete Pad Not Completed In Work Week Scheduled | D4
N-2013-15568 | 2013/10/01 | CLOSED | Project#16-31555 D2O Storage Project | D4
N-2013-15189 | 2013/09/28 | CLOSED | 16:31555: D2O Storage Project, Modify LPSW line W/O 2817137 - Employee Twisted Knee | D4
N-2013-15112 | 2013/09/27 | CLOSED | 16-31555: D2O Storage Project, Argon Pad Grounding Rescheduled From WW39 To WW40 | D4
N-2013-14719 | 2013/09/24 | CLOSED | 16-31555: D2O Storage Project Tie In Work Moved Out Of WW41 At T-2 | D4
N-2013-13629 | 2013/09/16 | CLOSED | Late request for service from IMS by D2O storage Project B&M | D4
N-2013-13291 | 2013/09/13 | CLOSED | 16-31555: D2O Project Date Missed For Issue Of Work Plan For Inactive Plant Drainage EC 121579 | D4
N-2013-12904 | 2013/09/10 | CLOSED | Project#16-31555 - Failure of temporary argon trailer | NE0
N-2013-12891 | 2013/09/10 | CLOSED | 16-31555:D2O Storage Project Holds On At T-10 For Relocation Of Argon Storage Tank PMOD, WO 2817132 | D4
N-2013-12866 | 2013/09/10 | CLOSED | D2O Storage Project Date Missed For Issuance Of Outgoing and Incoming Tanks and Oxygen Work Plans | D4
N-2013-12523 | 2013/09/06 | CLOSED | 16:31555: D2O Storage Project W/O 2817137 hydraulic leak on new zoom boom | D4
N-2013-12449 | 2013/09/06 | CLOSED | 16-31555:D2O Stoage Project, modify LPSW Line W/O2817137 Damage to 2" conduit | D4
N-2013-11518 | 2013/08/27 | CLOSED | Challenge to D2O Storage Project #16-31555 ( SGTMOD) | D4
N-2013-04468 | 2013/08/23 | CLOSED | 16-31555: D2O Storage Project #31555 Temporary Argon Tank did not pass receipt inspection | D4
N-2013-04456 | 2013/08/23 | CLOSED | 16-31555: D2O Storage Project, Date Missed For Issuance Of Work Plan For Oxygen Tank & Line Relocate | D4
N-2013-04454 | 2013/08/23 | CLOSED | 16-31555: D2O Storage Project, Date Missed For Issuance Of Work Plan For Inactive Drainage Line Relocate | D4
N-2013-04380 | 2013/08/21 | CLOSED | 16-31555: D2O Storage Project #31555 | D4
N-2013-04315 | 2013/08/15 | CLOSED | 16-31555: D2O Storage Project, Delay In TCD For Work Plan For Fire Protection Foam Line | D4
N-2013-04314 | 2013/08/15 | CLOSED | 16-31555: D2O Storage Project,, Delays For TCD For Work Plan For LPSW LIne Relocate | D4
N-2013-04312 | 2013/08/15 | CLOSED | 16-31555: D2O Storage Project,, Delay In TCD For Work Plan for Yard Drainage TMOD WO 2895259 | D4
N-2013-04311 | 2013/08/15 | CLOSED | 16-31555: D2O Storage Project, , Delays In TCD For Inactive Drain Line Relocate Work Plan WO 2817136 | D4
N-2013-04206 | 2013/08/09 | CLOSED | Nuclear Refurbishment use of ASME BPVC Code Cases and Non-Mandatory Appendicies | C3-NFE
N-2013-04154 | 2013/08/07 | CLOSED | 16-31555: WW41, D2O Storage Project , TRF Tie In WO's Have Holds At T-10 | D4
N-2013-04139 | 2013/08/06 | CLOSED | 16-31555: D2O Storage Project, Modify LPSW Line WO 2817137 Holds On At T-8 | D4
N-2013-04118 | 2013/08/02 | CLOSED | 16-31555 D2O Storage Project Date Missed For Issuance Of LPSW Line Relocate Work Plan | D4
N-2013-04032 | 2013/07/29 | CLOSED | 16-31555: D2O Storage Project Date Missed For Issuance Of LPSW Line Relocate Work Plan | D4
N-2013-04030 | 2013/07/29 | CLOSED | 16-31555: D2O Storage Project Dates Missed For Scope Change Approval / Installation | D4
N-2013-03601 | 2013/07/08 | CLOSED | Configuration Management Issue Identified During Walkdown | C3-NFE
N-2013-03526 | 2013/07/03 | CLOSED | Delays in performing procurement oversight on D2O storage project, as a result of vendor not providing requested documentation on time. | D4
N-2013-03004 | 2013/06/06 | CLOSED | 16-31555 - Near miss to installation of an unapproved modification in field | D4
N-2013-02940 | 2013/06/04 | CLOSED | 16-31555: Challenge to D2O storage project 48070014-1 | D4
N-2013-02488 | 2013/05/15 | CLOSED | Project 16-31555: Significant Oncore Back charges submitted for approval | D4
N-2013-02418 | 2013/05/13 | CLOSED | Project 16-31555: Passport notes panel cut off the title when printing | D4
N-2013-02374 | 2013/05/09 | CLOSED | Worker Hit Head Getting into Truck - D2O Storage Project | D3
N-2013-02364 | 2013/05/09 | CLOSED | Project 16-31555: Design EC set to approved without DA release | D4
N-2013-01498 | 2013/03/27 | CLOSED | 16-31555 D2O Storage Project: Vapour Recovery System MDR initiated for RFP in OSS was cancelled | D4
N-2013-00853 | 2013/02/19 | CLOSED | Project 16-31555 Area for improvement identified around OPG ECC form templates | D4
N-2013-00850 | 2013/02/19 | CLOSED | Project 16-31555 MDR Challenge Meeting vs. Verification process not managed well | D4
N-2013-00848 | 2013/02/19 | CLOSED | Project 16-31555 OPG commenting process for EPC vendor submittals | D4
N-2013-00297 | 2013/01/17 | CLOSED | D2O Storage Project 16-31555: Contractor Over-Accrued $1.5M in 2012 | D4
N-2012-05627 | 2012/11/09 | CLOSED | 16-31555: Insufficient vehicle access to protected area to support D2O Project construction schedule | D4
N-2012-05266 | 2012/10/24 | CLOSED | Project 16-31555 OPG resources to support EPC Contract in excess of what is outlined in the ES-MSA Contract and COIR | D4
N-2012-05234 | 2012/10/23 | CLOSED | Project 16-31555: Vendor schedule rejected due to quality concerns | D4
N-2012-03914 | 2012/08/08 | CLOSED | Project #16-31555 Delay to Schedule Due to MDR Rejection | D4
N-2012-00198 | 2012/01/16 | CLOSED | Project #16-31555 D2O Storage Delay - Cancellation of Request for Proposal for Engineering Services | C3
N-2011-06441 | 2011/11/25 | CLOSED | Inaccurate Drawing References | D4
N-2011-05854 | 2011/10/26 | CLOSED | Meeting started late | D4
N-2011-05638 | 2011/10/17 | CLOSED | Project #16-31555: Delay in D2O Storage Project proposal evaluation process | D4
N-2011-04783 | 2011/09/01 | CLOSED | Specifying QA program and Pressure Boundary (BP) requirements on N-FORM-10029, Services - Request For Purchasing. | C3-NFE
N-2011-04605 | 2011/08/23 | CLOSED | Benchmarking: Bruce Power Lessons Learned for 16-31555 D2O Storage Project | D4
N-2011-03157 | 2011/06/01 | CLOSED | 16-31555 Value Engineering Lessons Learned & Project Scope Additon | D4
N-2011-03150 | 2011/06/01 | CLOSED | N-PCH-09701-10001-R001 submitted for approval using outdated document template | D4
N-2011-01414 | 2011/03/08 | CLOSED | Project 16-31555 Challenge to Schedule: Change to Fixed End Date | D4
D-2018-17229 | 2018/08/09 | CLOSED | T1801 Scope Change | D4
D-2016-31104 | 2016/12/15 | CLOSED | Fire at D2O Storage Project (10Dec2016) | D3
D-2016-27195 | 2016/11/02 | CLOSED | D2O Storage Project Late application for work protection | D4
D-2016-19646 | 2016/08/04 | CLOSED | 16-31555 D2O Storage Project - Red Badge workers observed without escort | D4
D-2016-15489 | 2016/06/09 | CLOSED | Inadvertently wore wrong TLD into Unzoned Area. | D4
D-2016-11115 | 2016/04/28 | CLOSED | TRF/HWMB - Delay to Oxygen Delivery | D4
D-2016-01812 | 2016/01/22 | CLOSED | 16-31555 D2O Storage Project - Gas Bottle improperly tied-off | D4
D-2016-00878 | 2016/01/13 | CLOSED | 16-31555 D2O Storage Project - Lost Tools | D4
D-2015-27145 | 2015/11/19 | CLOSED | D2O Storage Project 16-31555 - Concrete bin removed from PA without proper approvals | D3
D-2015-26386 | 2015/11/11 | CLOSED | Inconsistent behaviour of alarms discovered during commissioning of HWMS Computers | C3
D-2015-18676 | 2015/08/20 | CLOSED | Non-event - SCR raised in wrong database | NE0
D-2015-06827 | 2015/03/20 | CLOSED | Project#16-31555: TRF Oxygen signage not installed | D3
D-2014-32289 | 2014/11/20 | CLOSED | TRF: Lack of Project Readiness Significant Risk to T1501 Outage | C3-NFE
D-2014-27469 | 2014/09/30 | CLOSED | ECC Modification process deviation has been found in 15 out of 49 Design ECs being performed for D2O Storage Project. | C3
D-2014-22791 | 2014/08/05 | CLOSED | Issues with ABB software for HWMS Computer Upgrade Stage 2 (Master EC 119650) Update | D3
D-2014-19141 | 2014/06/19 | CLOSED | PCB degradation on HWMS Hardware Maintenance System (0-69791-SPARES) | D4
D-2014-17724 | 2014/06/04 | CLOSED | 16-31555 D2O Storage Project, Light Standard Knocked Over By Truck (Duplicate Of N-2014-15070) | C2
D-2014-16295 | 2014/05/21 | CLOSED | PCB failure on HWMS Hardware Maintenance System (0-69791-SPARES) | D4
D-2014-06812 | 2014/02/28 | CLOSED | D2O Storage Project (16-31555) - Deferral of TRF Incoming & Outgoing Tie-ins (EC 120406) from T1301 to T1501 due to T1301 Outage Impact | D4
D-2014-04964 | 2014/02/12 | CLOSED | TRF: Field/Flowsheet/Database Discrepancy, NK38-FEX-75550-0501 | C4-NFE
D-2013-24454 | 2013/12/18 | CLOSED | TRF Stack emissions exceeded target | C3-NFE
D-2013-24229 | 2013/12/17 | CLOSED | TRF: T1301 TIS Window Delay relating to ACS Project Work & Resourcing | D4
D-2013-23323 | 2013/12/07 | CLOSED | 16-31555 TRF Feed & Product Tie-in Work Rescheduled | D4
D-2013-22329 | 2013/11/27 | CLOSED | Project 16-31555 – EC 120406 (Tie-in TRF Incoming/Outgoing) Tie-in NV1188 & V1075 Removal | D4
D-2013-21573 | 2013/11/20 | CLOSED | TRF Proactive SCR - New D2O storage building is not going to have an elevator or janitorial closets on the upper and lower elevations | D4
D-2013-21569 | 2013/11/20 | CLOSED | T1301 Late Scope Added For D2O Storage Project Work 16-31555 | D4
D-2013-21147 | 2013/11/15 | CLOSED | Project 16-31555 – D2O Storage Project – Non-Compliance with Modification Process (COMS) | C3-NFE
D-2013-21146 | 2013/11/15 | CLOSED | Chemistry - Lack of notice challenging the Chem labs ability to support D2O storage project | D4
D-2013-20769 | 2013/11/13 | CLOSED | TRF / HWMB - Lack of Support for Workplan markup from D2O storage Project | D4
D-2013-19987 | 2013/11/05 | CLOSED | Delay to project 16-31555 D2O Storage Project EC#120719 Steam And Condesate Tie in. Permit not applied as per schedule | D4
D-2013-19472 | 2013/10/31 | CLOSED | D2O Storage Project 16-31555, TRF Outgoing and Incoming Tanks Work Plan TCD Extended | D4
D-2013-19466 | 2013/10/31 | CLOSED | D2O Storage Project 16-31555, TRF Feed and Product Work Plan TCD Extended | D4
D-2013-19253 | 2013/10/30 | CLOSED | TRF D2O Storage Project Challenging TRF Operations Assessing and Work Planning | D4
D-2013-19100 | 2013/10/29 | CLOSED | T1301 further delays relating to D2O storage project | B2
D-2013-18372 | 2013/10/23 | CLOSED | T1301 extension due to D2O storage project readiness | CO2
D-2013-18196 | 2013/10/22 | CLOSED | Project 16-31555 - Dewatering Line installed in path of Emergency Mitigating Route 3 documented in NK38-EME-09013-ERG-02 Appendix B. | C3-NFE
D-2013-16279 | 2013/10/07 | CLOSED | SCHEDULE - Vendor's schedule update data not received in a timely fashion Project 31555 D2O Storage Project - Cancel Reference N-2013-16808 | NE0
D-2013-15900 | 2013/10/03 | CLOSED | SATM Requred With Less Than 21 Days Notice. D2O Storage Project | D4
D-2013-13697 | 2013/09/17 | CLOSED | Project#16-31555: TRF Temporary argon supply trailer issues | D4
D-2013-13694 | 2013/09/17 | CLOSED | Project#16-31555-Vendor started work without work authorization | D4
D-2013-13507 | 2013/09/15 | CLOSED | Project#16-31555 - Failure of temporary argon trailer | D4
D-2013-12404 | 2013/09/06 | CLOSED | 16-31555:D2O Stoage Project, modify LPSW Line W/O2817137 Damage to 2" conduit | NE0
D-2013-07582 | 2013/07/29 | CLOSED | WW40 Work Has Holds At T-10 For Work Plan | D4
D-2013-07379 | 2013/07/23 | CLOSED | Undetermined Material Found While Daylighting Buried Services - AHS Facility Project#16-34000 | D4
D-2013-04625 | 2013/05/02 | CLOSED | Project 16-31555 HWMB D2O Storage | D4
D-2013-02772 | 2013/03/11 | CLOSED | D2O Storage Project - Unknown Obstruction Encountered During Bore Hole Drilling | D4
D-2013-02304 | 2013/02/28 | CLOSED | D2O Storage Project 16-31555 - Lanyard with badges came detached in unzone area | D4
D-2013-01571 | 2013/02/12 | CLOSED | D2O Storage Project - Trailer Removal / Borehole Readiness Meeting Less Than Adequate | D4
D-2012-04114 | 2012/04/11 | CLOSED | TRF/HWMB Less Than Adequate Storage - D2O Drum Issues | D4
D-2008-06087 | 2008/05/14 | CLOSED | Inter-Departmental miscommunication on Project Scope. | D4
N-2012-03854 | 2012-08-01 | CLOSED | Document produced by EPC contractor rejected | D4
N-2012-05069 | 2012-10-15 | CLOSED | Design Quality - Verification Errors, NK38-MDR-38000-10004 | D4
D-2012-08890 | 2012-09-07 | CLOSED | Project #16-31555 D2O Storage: Lack of schedule from contractor | C3
N-2012-05237 | 2012-10-23 | CLOSED | Project 16-31555 OPG resources to support EPC Contract in excess of what was planned | D4
D-2012-10625 | 2012-10-30 | CLOSED | Project 16-31555: The D2O Project Team did not meet scheduling milestone requirements of N-PROC--MA-0022 as related to Tminus 12 | D4
D-2012-10620 | 2012-10-30 | CLOSED | 16-1555: The D2O project team did not meet the scheduling milestone requirements of N-PROC-MA-0022 for T minus 8 | D4
D-2012-10764 | 2012-11-02 | CLOSED | Project 16-31555: D2O Project Team did not meet schedule milestone as per N-PROC-MA--0022 as related to Tminus 26 | D4
N-2012-05956 | 2012-11-27 | CLOSED | 16-31555: Modification Planning Complete Milestone Recovery Date Missed | D4
N-2012-05812 | 2012-11-20 | CLOSED | Project 16-31555: Vendor schedule rejected due to quality concerns | D4
N-2012-06082 | 2012-12-04 | CLOSED | Project 16-31555: Modification Planning Complete Milestone Recovery Date Missed | D4
D-2013-00696 | 2013-01-22 | CLOSED | Project 16-3155, Late EC Submittal for LPSW Relocation | D4
D-2013-01121 | 2013-02-01 | CLOSED | 16-31555: Work did not meet N-PROC-MA-0022 Milestones | D4
D-2013-01651 | 2013-02-14 | CLOSED | Project 16-31555 Design Package Rejection | D4
N-2013-00847 | 2013-02-19 | CLOSED | Project 16-31555 Modification Outline / Master EC process/quality issue | D4
N-2013-04031 | 2013-07-29 | CLOSED | 16-31555: D2O Project, Date Missed For Issuance Of Argon Tank & Line Relocate Work Plan | D4
N-2013-04186 | 2013-08-08 | CLOSED | PROJ 16-31555, OPG Direction to reduce COMs frequency will adversely impact schedule for affected Design Deliverables. | D4
N-2013-04195 | 2013-08-08 | CLOSED | PROJ 16-31555, Schedule for Design EC HFE Analyses delayed for TRF Staff Support | D4
D-2012-10298 | 2012-10-22 | CLOSED | West Annex Project # 16-31555, Detailed Design COMS for SG Cable Duct Bank Relocation delayed due to failure to achieve Quorum | D4
D-2013-01653 | 2013-02-14 | CLOSED | Project 16-31555 Submiited MDR Missing Requirement | D4
N-2013-00851 | 2013-02-19 | CLOSED | Project 16-31555 Scoping COMS process issue | D4
D-2011-08229 | 2011/07/14 | CLOSED | Break Plan Modification: ECR # 19361 - Phase II ESA for IWST Spill | D4
D-2012-10297 | 2012/10/22 | CLOSED | DNGS West Annex Project # 16-31555, Design COMS for Relocation of Buried Services rescheduled due to failure to achieve quorum prior to the meeting. | D4
D-2012-11444 | 2012/11/21 | CLOSED | Project 16-31555 ES-MSA Staff not qualified to perform walk downs | D4
D-2012-12056 | 2012/12/10 | CLOSED | DNGS West Annex Project # 16-31555, NK38-MDR-38000-10003, "Modification Design Requirement for HWMB West Annex Project, PMOD", Comment Disposition Not | D4
D-2012-12105 | 2012/12/11 | CLOSED | Configuration issue with documentation for panel 0-56284-RP4184 | D4
D-2012-12209 | 2012/12/14 | CLOSED | DNGS West Annex Project # 16-31555, Master EC 118880 set to "CANCELLED" status by accident | D4
D-2013-00065 | 2013/01/03 | CLOSED | COMS for tie-in to the Instrument Air & Service Air System inside HWMB for the West Annex Building (DNGS West Annex Project # 16-31555) postponed | D4
D-2013-00170 | 2013/01/07 | CLOSED | DNGS West Annex Project # 16-31555, Darlington GS Unit 0 Site Plan "Site Improvement & Maintenance Powerhouse & Vicinity South West Area Finished Grad | D4
D-2013-00382 | 2013/01/14 | CLOSED | Unidentified light post on South Side of road West of SG1 building (Bldg #38) | D4
D-2013-00395 | 2013/01/14 | CLOSED | Operational Flow Sheet missing load designations | C3-NFE
D-2013-00825 | 2013/01/25 | CLOSED | Late start of COMS meeting due to unavailability of Quorum member | D4
D-2013-00852 | 2013/01/25 | CLOSED | Discrepancy in dimensions of Heavy Water Management System Building between drawings | C3-NFE
D-2013-01004 | 2013/01/30 | CLOSED | DNGS West Annex Project # 16-31555, Issue Tracking File (ITF) not up to date | D4
D-2013-01119 | 2013/02/01 | CLOSED | 16-31555: Late identification of work for TRF Outage | D4
D-2013-01624 | 2013/02/13 | CLOSED | TRF: Project# 16-31555 Cancellation of Task to apply TRF Trailer work protection isolation | D4
D-2013-01625 | 2013/02/13 | CLOSED | TRF: Project #16-31555 Trailer removal readiness meeting did not include TRF group | D4
D-2013-01683 | 2013/02/14 | CLOSED | 16-31555: D2O Project team rescheduled TRF trailer removal due to incomplete ITP preparation | CO4
D-2013-01836 | 2013/02/19 | CLOSED | Project 16-31555 - D2O Storage - PO 217807 - Oncore entries submitted without a budget | D4
D-2013-02138 | 2013/02/25 | CLOSED | 16-31555, EC120340 delayed for New Item CatID & EBOM Header | D4
D-2013-02153 | 2013/02/25 | CLOSED | DNGS West Annex Project # 16-31555, COMS Presentations sent late to Stakeholders | D4
D-2013-02159 | 2013/02/25 | CLOSED | PROJ 16-31555, EC120400 delayed for New Item CatIDs | D4
D-2013-02253 | 2013/02/27 | CLOSED | PROJ 16-31555, EC120341 delayed for New Item CatID not READY | D4
D-2013-02405 | 2013/03/03 | CLOSED | 16-31555 Design Package Rejection | C3-NFE
D-2013-02439 | 2013/03/04 | CLOSED | DNGS West Annex Project # 16-31555, Design COMS for West Annex PA, Tele & LAN rescheduled due to failure to achieve quorum at the time of the meeting | D4
D-2013-02940 | 2013/03/15 | CLOSED | TRF: Project # 16-31555 Co-ordination for bulk Gas delivery | D4
D-2013-03145 | 2013/03/20 | CLOSED | TRF Project # 16-31555 inadequate COMS for TRF West Annex Steam and Condensate system | D4
D-2013-03651 | 2013/04/05 | CLOSED | TRF Project # 16-31555 inadequate COMS for Instrument/Service air | D4
D-2013-03965 | 2013/04/15 | CLOSED | Project 16-31555 DNGS HWMB West Annex - DEC 120471 late for OPG submission | D4
D-2013-04425 | 2013/04/26 | CLOSED | Project 16-31555: Errors in contractor design analysis documents | D4
D-2013-04429 | 2013/04/26 | CLOSED | Project 16-31555 (D2O storage building): Missing inputs in engineering analysis documents | D4
D-2013-04599 | 2013/05/01 | CLOSED | NR Design Engineering: D2O Management Building (Project 16-31555); New D2O Supply System Safety Related? | D4
D-2013-04793 | 2013/05/07 | CLOSED | PJ#16-31555 D2O Storage - SG TMOD Tasks past T-8 with Holds on Plan at Risk. | D4
D-2013-04993 | 2013/05/13 | CLOSED | Project 16-31555: Configuration Management of Class II Receptacle 0-62321-RE110 | D4
D-2013-05021 | 2013/05/13 | CLOSED | Project 16-31555: Configuration management of EOL device 0-67870-CAP134 | D4
D-2013-05132 | 2013/05/15 | CLOSED | Project 16-31555: Missing sheet (68) from issued Design Manual NK38-DM-67870 R010 in Asset Suite | D4
D-2013-06039 | 2013/06/11 | CLOSED | Project# 16-31555 - Design EC 120340 is in Active Status without DA Release | D4
D-2013-06554 | 2013/06/27 | CLOSED | 16-31555 Configuration Management issue regarding dimensions of SG Fuel Tank 0-77200-TK1&2 Berm | C3-NFE
D-2013-07337 | 2013/07/23 | CLOSED | Project#16-31555 Asbestos found on Buried services. | D3
D-2013-07403 | 2013/07/24 | CLOSED | Project 16-31555 Document Control Process Failure | D4
D-2013-08049 | 2013/08/15 | CLOSED | Approved and Released Project DEC for Nuclear grade piping system prepared by non-engineer | NE5
D-2013-11442 | 2013/08/27 | CLOSED | PROJ 16-31555, D2O Foundation Wall Design Calculation | C3-NFE
D-2013-12141 | 2013/09/04 | CLOSED | 16-31555: 0-77200-TK1 Sump full | D4
D-2013-12669 | 2013/09/09 | CLOSED | Project# 16-31555 - MEC 118632 - Failure to perform Fire Protection Impact re-evaluation in Detailed Design as requested in Mod Outline Package | D4
D-2013-12905 | 2013/09/10 | CLOSED | Project# 16-31555 - DEC 120415 – Final AFS meeting delayed one day prior to meeting | D4
D-2013-12907 | 2013/09/10 | CLOSED | Project# 16-31555 - DEC 120415 – Final AFS meeting delayed for a second time on the scheduled date. | D4
D-2013-13087 | 2013/09/11 | CLOSED | Destabilized crushed stone cover of the south embankment of SG fuel tank (TK2) berm observed during walkdown | D4
D-2013-13504 | 2013/09/15 | CLOSED | Project#16-31555-Temporary argon supply causing low pressure alarm | D4
D-2013-18032 | 2013/10/21 | CLOSED | Chemistry - Project work challenging chemistry resources (project # 16-31555) | D3
D-2013-18905 | 2013/10/28 | CLOSED | PROJ 16-31555, EC122212, Discovery of Configuration Management Issue of TRF Oxygen Distribution Line Caps (1/2/3/4-75510-L711) | C3-NFE
D-2013-19748 | 2013/11/03 | CLOSED | EPC Project 16-31555, Oversight review of Black & McDonald ITP found no Design Approval for Modification | D4
D-2013-20151 | 2013/11/06 | CLOSED | Delay to Project 16-31555 D2O Storage bldg Steam and Condensate Tie In ( No permit available for 2nd day) | D4
D-2013-21027 | 2013/11/14 | CLOSED | TRF - D2O Modification Project - Newly installed valve suspected to be passing (0-73680-V918) - Project 16-31555 | D4
D-2013-22651 | 2013/12/01 | CLOSED | 16-31555 Human Performance Issue Holder left lock on | D4
D-2013-22679 | 2013/12/01 | CLOSED | 16-31555 - Lost TLD and Prox Card | D4
D-2013-22778 | 2013/12/02 | CLOSED | Project 16-31555 Vendor ITP references incorrect Design Flow Diagram and Design Conditions | D3
D-2013-23233 | 2013/12/06 | CLOSED | Project# 16-31555 – DEC 120448 - Line location discrepancy between design flow diagram and operations flowsheet | C3-NFE
D-2013-23239 | 2013/12/06 | CLOSED | TRF: Project 16-31555 – Argon (ECs 122210, 120670) Workplan R01 Review Meeting Preparedness | D4
D-2014-01576 | 2014/01/16 | CLOSED | Resource Issue: TRF Tritium Emission Reduction 16-38942 | D4
D-2014-05679 | 2014/02/20 | CLOSED | 16-31555; Legacy Configuration Discrepancy found for wiring of 0-67555-PS1 on Vendor Supplied TRF Argon Bulk Storage Unit | C3-NFE
D-2014-07379 | 2014/03/05 | CLOSED | TRF T1501 Outage Milestone Impacted by late Factory Acceptance Testing (FAT) | D4
D-2014-15397 | 2014/05/12 | CLOSED | 16-31555 D2O Annex Project - CDS for Workplan Not Incorporated | D4
D-2014-16387 | 2014/05/22 | CLOSED | PROJ 16-31555, Excavation revealed presence ofa valve (broken), not shown on avaliable drawings | C3-NFE
D-2014-20432 | 2014/07/07 | CLOSED | 16-31555 – HWMB West Annex Project – Comment received on close-out drawings for DEC 120719 which is not in agreement with accepted design | D4
D-2014-21813 | 2014/07/23 | CLOSED | No Prior Notification Given on Project Work Project 16-31555 | D4
D-2014-22632 | 2014/08/01 | CLOSED | 16-31555 - HWMB Workplan Schedule Not Correct | D4
D-2014-24323 | 2014/08/25 | CLOSED | 16-31555 DNGS HWMB West Annex -Legacy issue with in-correct process fluid specilied in SCL and Flow Diagram. | D4
D-2014-27741 | 2014/10/02 | CLOSED | 16-31555 – HWMB West Annex Project – DEC 122212 Concerns over config of O2 piping runs installed on West wall of HWMB | C3-NFE
D-2014-33825 | 2014/12/08 | CLOSED | Proj# 16-31555 EC122212 Material shown in stock in DN E warehouse isn't there | D4
D-2015-01188 | 2015/01/19 | CLOSED | Project 16-31555 DNGS HWMB West Annex – SCI 72700 Domestic Water System not listed in List of Pressure Boundary Legacy Systems | NE0
D-2015-04099 | 2015/02/19 | CLOSED | TRF: DNGS West Annex Project 16-31555 – Rejected FS Markup due to Mismatch in Approved DEC 120406 Flow Diagram and Piping Isometric | D4
D-2015-08760 | 2015/04/16 | CLOSED | 16-31555 - Oil Spill from Rental Service Equipment | D4
D-2015-09375 | 2015/04/23 | CLOSED | False fire alarm in VB basement - CFVS Project#16-73365 | D4
D-2015-11464 | 2015/05/20 | CLOSED | D2O Project#16-31555 Punctured Dewatering Hose | D4
D-2015-16089 | 2015/07/14 | CLOSED | SATM Permit Required With Less Than 21 Days Notice - D2O Project#16-31555 | D4
D-2015-18919 | 2015/08/24 | CLOSED | DNGS D20 Storage Facility- TLD sent through security X-ray machine. Project#16-31555. | D4
D-2015-20260 | 2015/09/14 | CLOSED | D20- Project # 16-31555 pump truck did not complete outbound scan of truck with RP | D3
D-2015-21905 | 2015/09/29 | CLOSED | Project #16-31555 DNGS D2O Storage Building - Rain Delay. (Trending) Job 15-5126 7010 | D4
D-2015-22925 | 2015/10/07 | CLOSED | D2O Project 16-31555 Dewatering pump replacement concern | D4
D-2015-29377 | 2015/12/15 | CLOSED | D20 Project 16-31555 Delay Work Space Not Available | D4
D-2016-00531 | 2016/01/08 | CLOSED | DNGS D2O Storage Building- Employee TLD sent through ASB X-ray equipment. Project# 16-31555. | D4
D-2016-01420 | 2016/01/19 | CLOSED | Availability of SAMS and Whole Body Monitors at ASB. 16-31555 | D4
D-2016-04213 | 2016/02/16 | CLOSED | D2O Storage, Project 16-31555, Engineering Change EC 120734, Active Plant DRAinage,Revision 003 Change Papers Rejected | NE0
D-2016-04907 | 2016/02/24 | CLOSED | D2O Project 16-31555 Unable to obtain WA, computer systems down. | D4
D-2016-07506 | 2016/03/23 | CLOSED | D2O project 16-31555 Worker TLD missing from rack at ASB | D4
D-2016-09383 | 2016/04/13 | CLOSED | D2O Project 16-31555- Worker Consuming Hard Candy in PA | CO3
D-2016-09679 | 2016/04/15 | CLOSED | D2O Project 16-31555 Food found inside PA - Adverse Trend | C3
D-2016-11233 | 2016/04/29 | CLOSED | D2O Project 16-31555 EPD put through X-ray machine | D4
D-2016-11735 | 2016/05/04 | CLOSED | Project# 16-31555 - Worker inadvertently put TLD badge through X-ray machine upon enter ASB | D4
D-2016-12067 | 2016/05/06 | CLOSED | # 16-31555-D20 Worker grabbed wrong TLD Badge from rack. | D4
D-2016-12072 | 2016/05/06 | CLOSED | 16-31555-D20 project TLD badge inadvertently put through X-Ray machine. | D4
D-2016-12445 | 2016/05/10 | CLOSED | D20 Project 16-31555 Expediated approval requested for SATM at RFRISA Building | D4
D-2016-13230 | 2016/05/17 | CLOSED | D20 Project delay 16-31555 – HWMB Workers stood down due to D20 transfer from unit. | D4
D-2016-13433 | 2016/05/19 | CLOSED | Project 16-31555-D20 Worker inadvertently put TLD through the x-ray machine | D4
D-2016-13736 | 2016/05/22 | CLOSED | 16-31555 – D20 project TLD badge inadvertently put through X-Ray | D4
D-2016-13904 | 2016/05/24 | CLOSED | D2O Project 16-31555 Food inadvertantly taken inside PA to the RFRISA Bldg | CO3
D-2016-14449 | 2016/05/30 | CLOSED | D2O Project- 16-31555- Worker's TLD through X-Ray | D4
D-2016-15596 | 2016/06/10 | CLOSED | D20 West Annex New Construction Project #16-31555. Minor Back Strain Injury, medical attention declined by worker | D3
D-2016-16572 | 2016/06/23 | CLOSED | D20 Project #16-31555- HWMB unable to preform planned/ scheduled project tasks | NE0
D-2016-18903 | 2016/07/25 | CLOSED | Project 16-31555- D20 West Annex- Worker Unwell | NE0
D-2016-21392 | 2016/08/26 | CLOSED | 16-31555 D2O West Annex Electrical Design Issues | NE0
D-2016-21401 | 2016/08/26 | CLOSED | Project 16-31555: Discrepancy Found Between Flow Diagram and Field for HWMB Domestic Water System EC #120427 | D3
D-2016-22059 | 2016/09/06 | CLOSED | D2O Project 16-31555 Construction Delay for missing materials | D4
D-2016-23800 | 2016/09/23 | CLOSED | TLD put through RPO Scanner D20 project 16-31555 | D4
D-2016-26405 | 2016/10/25 | CLOSED | Workers PROX card wouldn't work attempting to exit PA into RPO(16-31555) | D4
D-2016-26437 | 2016/10/25 | CLOSED | Workers PROX card would not work while attempting to exit PA into RPO (16-31555) | D4
D-2016-26658 | 2016/10/26 | CLOSED | Workers Prox card failed to work while exiting the PA going to RPO (16-31555) | D4
D-2016-26883 | 2016/10/29 | CLOSED | 16-31555 Delay due to contaminated work force at whole body monitors at RPO | D4
D-2016-28861 | 2016/11/21 | CLOSED | 16-31555 HWMB Dock leveler relocate broken wire | D4
D-2016-29246 | 2016/11/24 | CLOSED | P#16-31555: SCR to document deviation of Section 1.5.9 N-PROC-MP-0090 | D3
D-2017-00545 | 2017/01/10 | CLOSED | 16-31555 Strong Diesel Smell in HWMB | D4
D-2017-01144 | 2017/01/16 | CLOSED | Project# 16-31555, D2O Managment bld. ITP A00004-E6-127532-W56100- QS review | NE0
D-2017-01186 | 2017/01/17 | CLOSED | 16-31555 delay unable to leave or enter the PA with prox card | NE0
D-2017-01835 | 2017/01/23 | CLOSED | 16-31555 Worker stuck in elevator | D4
D-2017-02279 | 2017/01/27 | CLOSED | Proj #16-31555: D20 Project worker trips on stairs | D3
D-2017-02915 | 2017/02/03 | CLOSED | D2O Project 16-31555 –delivered masonry blocks do not meet tech specs delaying work | D4
D-2017-04631 | 2017/02/23 | CLOSED | TRF: Just in Time Assessing: WO# 2910084, DEC# 120405, 38410 Tie-in To/From West Annex/HWMB D2O Cleanup System - Poject # 16-31555 | D4
D-2017-04906 | 2017/02/27 | CLOSED | TRF: Project # 16-31555 Documentation not available to complete authoring of West Annex Procedures | D4
D-2017-06743 | 2017/03/21 | CLOSED | SATM Permits Required With Less Than 21 Days Notice. D2O West Annex Project#16-31555 | D4
D-2017-08735 | 2017/04/11 | CLOSED | DNRU2 Project # 16-31555 TRF - Support requirements not identified for CTFD | D4
D-2017-12108 | 2017/05/19 | CLOSED | D20 West Annex Project 16-31555- DH Worker lost his TLD badge | D4
D-2017-23374 | 2017/10/11 | CLOSED | 16-31555 - Worker scratched forearm - late reporting | D3
D-2017-23895 | 2017/10/17 | CLOSED | D20 Project # 16-31555 Late reporting by worker to contractor | D3
D-2017-24091 | 2017/10/19 | CLOSED | D20 Project # 16-31555 Safety observation | D4
D-2017-24611 | 2017/10/25 | CLOSED | D20 Project 16-31555 - Worker cut finger - late reporting | D3
D-2017-28404 | 2017/12/07 | CLOSED | D20 Project # 16-31555 TWE powerwashed inside PA | NE0
D-2018-08479 | 2018/04/10 | CLOSED | D2O Project 16-31555 – Station resources burdened by last minute request for support | D3
D-2018-08506 | 2018/04/11 | CLOSED | D20 Project 16-31555 - Employee discovered TLD was missing at workface | D4
D-2018-10877 | 2018/05/07 | CLOSED | T1801 Scope removal WO 3139146 Project 16-31555 | D4
D-2018-15659 | 2018/07/13 | CLOSED | Worker entered PA without TLD (Project # 16-31555) | D3
D-2018-18435 | 2018/08/28 | CLOSED | Configuration discrepancies identified during the HWMS Computers Startup. Project #16-31555 | C3-NFE
D-2018-18623 | 2018/08/30 | CLOSED | 16-31555, D20 -Worker lost TLD badge | D4
D-2018-19901 | 2018/09/19 | CLOSED | D2O Storage Facility Project 16-31555 - Backup Power (GEN SET) Cable Installation without the use of protective bushing. | NE0
D-2018-19920 | 2018/09/19 | CLOSED | 16-31555 D2O Storage Facility - Improper use of Vender Procedures. WO: 3139139 EC: 120477 | NE0
D-2018-20602 | 2018/09/27 | CLOSED | D20 Project 16-31555 Missing TLD Badge | NE0
D-2019-00956 | 2019/01/16 | CLOSED | D20 Project 16-31555 Foreign Material entered Tank | NE0
D-2019-03040 | 2019/02/12 | CLOSED | 16-31555 Dropped Object While Traversing Off A Scaffold On The 107' Of The D20 Building | NE0
D-2019-08779 | 2019/05/06 | CLOSED | D20 Project 16-31555 -TLD was inadvertently put through X-Ray at ASB | D4
D-2019-08966 | 2019/05/09 | CLOSED | HWMB WEST ANNEX D20 STORAGE BUILDING generator commissioning expanded scope Project #16-31555 | D4
D-2019-18140 | 2019/10/21 | COMPLETE | Project 16-31555, MEC 88528: DEC 136717 DCC Computer Patches Require Revision Due to Findings During Installation Planning Phase | C3-NFE
D-2020-16786 | 2020/11/10 | COMPLETE | West Annex Storage Building HT Commissioning. Passing valve/ Leak Project#16-31555, EC 120421 | D4
N-2011-03953 | 2011/07/13 | CLOSED | Project # 16-31555: Potential Risks in Completing TRF Trailers Demolition as per Project Schedule | D4
N-2012-04626 | 2012/09/20 | CLOSED | COST - Actuals in BCS do not align with NFRA Project 16-31555 | D4
N-2012-04931 | 2012/10/09 | CLOSED | Project 16-31555: ES-MSA Staff not qualified to perform site walk downs | D4
N-2012-05467 | 2012/11/01 | CLOSED | Project 16-31555: Proposed vapour recovery system not acceptable to operations/environment stakeholders | C3
N-2012-05614 | 2012/11/09 | CLOSED | 16-31555: Modification Planning Complete Milestone Missed | D4
N-2013-00398 | 2013/01/23 | CLOSED | 16-31555: Oncore charges rejected | D4
N-2013-01041 | 2013/03/01 | CLOSED | Project 16-31555 - IT has not been made involved in the HWMB West Annex project | D4
N-2013-01170 | 2013/03/07 | CLOSED | 16-31555: Oncore charges exceeded cost buckets under PO 217807 Line 2 | D4
N-2013-01253 | 2013/03/13 | CLOSED | 16-31555 Project Communication Protocal Not Following When Communicating with DA | D4
N-2013-01291 | 2013/03/14 | CLOSED | 16-31555 OPG Reviewer not made aware of additional changes made to document during C&D Process | D4
N-2013-01755 | 2013/04/10 | CLOSED | PROJ 16-31555 - Dispositoned comments not incorporated into DEC 120428 | D4
N-2013-01854 | 2013/04/15 | CLOSED | Project 16-31555: Problems with SharePoint wrt Supplier Document Hub | D4
N-2013-01855 | 2013/04/15 | CLOSED | Project 16-31555: Problems with SharePoint wrt Supplier Document Hub | D4
N-2013-01963 | 2013/04/19 | CLOSED | 16-31555 Schedule delays due to hold up in Supplier Document Hub | D4
N-2013-01996 | 2013/04/22 | CLOSED | Project 16-31555: Problems with SharePoint wrt Supplier Document Hub | D4
N-2013-02183 | 2013/05/01 | CLOSED | Project 16-31555: Delays with SharePoint wrt Supplier Document Hub | D4
N-2013-02273 | 2013/05/06 | CLOSED | Project 16-31555: Design submit extra round of comments on NK38-MDR-38000-10004 R01 | D4
N-2013-02487 | 2013/05/15 | CLOSED | 16-31555 Error in MEC 88528 Rev.000 resulting in omission in Modification Outline of a Safety Related SCI impacting Nuclear Safety Risk Level review. | D4
N-2013-02542 | 2013/05/16 | CLOSED | 16-31555 - Wrong use of SCI 38410 for portions of the new Downgraded D2O Transfer System resulting in system boundary issues | D4
N-2013-02635 | 2013/05/22 | CLOSED | Project 16-31555: Contractor submitted Design EC prior to receiving CDF | D4
N-2013-02854 | 2013/05/30 | CLOSED | Install of Soil laydown area on hold Project #16-31555 | D4
N-2013-03123 | 2013/06/12 | CLOSED | Project# 16-31555 - Design EC 120340 is in Active Status without DA Release | D4
N-2013-03153 | 2013/06/13 | CLOSED | Project #16-31555: EC 120401 needed update and resubmission | D4
N-2013-03160 | 2013/06/13 | CLOSED | Project #16-31555: EC 120405 closed due to issues | D4
N-2013-03167 | 2013/06/13 | CLOSED | Project #16-31555: EC 120523 Delayed Acceptance | D4
N-2013-03249 | 2013/06/18 | CLOSED | Project #16-31555: Human Performance - Cancellation of OSS Task Request in RFP Stage | D4
N-2013-03343 | 2013/06/21 | CLOSED | Project #16-31555 HWMB West Annex: Lost two OPG accepted Documents from Design EC 120404 | D4
N-2013-03426 | 2013/06/26 | CLOSED | Project 16-31555 Box Drain Hose | D4
N-2013-03560 | 2013/07/04 | APPROVED | Project 16-31555 Box Drain Hose not installed per work order task instructions | C3
N-2013-03563 | 2013/07/04 | CLOSED | Project 16-31555 - Damaged hoses for box drain sump pump out W/O# 2631271 | D4
N-2013-03717 | 2013/07/12 | CLOSED | Tote damaged while adjacent tote being moved. Project #16-31555 | D4
N-2013-03829 | 2013/07/18 | CLOSED | Project 16-31555 As found configuration of piping found during excavation | D4
N-2013-03831 | 2013/07/18 | CLOSED | PROJ 16-31555, Design ECs delayed for ONL Wiring package processing (DNGS) | D4
N-2013-03832 | 2013/07/18 | CLOSED | PROJ 16-31555, Design ECs delayed for Lengthy Equipment Tag Requests Processing | D4
N-2013-03851 | 2013/07/19 | CLOSED | Delayed getting W.A for WO#2631271 Project #16-31555 | D4
N-2013-03877 | 2013/07/22 | CLOSED | Project #16-31555 WO#2631271 Box drain pump out workplan revision | D4
N-2013-03878 | 2013/07/22 | CLOSED | Flowmeter failure during box drain pump out Project # 16-31555 | D4
N-2013-03911 | 2013/07/24 | CLOSED | 16-31555: Training Requirements Meeting Cancelled | D4
N-2013-03922 | 2013/07/24 | CLOSED | 16-31555:Work Plan quality issue for TMOD Yard Drainage Relocation | D4
N-2013-04008 | 2013/07/29 | CLOSED | PROJ 16-31555, FICREQ Processing not per Governance | D4
N-2013-04065 | 2013/07/31 | CLOSED | 16-31555 D2O Project, Inactive Drain Line Relocate Work Plan Issued Date Missed | D4
N-2013-04070 | 2013/07/31 | CLOSED | Project 16-31555 - Copper Line Found | D4
N-2013-04121 | 2013/08/02 | CLOSED | 16-31555 D2O Project, Date Missed For Issue Of Design Doc's For Oxygen Tank & Line Relocate | D4
N-2013-04123 | 2013/08/02 | CLOSED | PROJ 16-31555, Outstanding/Late OPG review for submitted EPC Deliverables | D4
N-2013-04180 | 2013/08/08 | CLOSED | Aditional equipment added to Satm Project #16-31555 | D4
N-2013-04183 | 2013/08/08 | CLOSED | Project 16-31555 - Item(s) Placed on F1 Prior to Approved Date | D4
N-2013-04184 | 2013/08/08 | CLOSED | Project 16-31555 -Trailer Placed on F1 without Work Authorization | CO3
N-2013-04185 | 2013/08/08 | APPROVED | Project 16-31555 - N-INS-29000-10000-R001 | C3-NFE
N-2013-04309 | 2013/08/15 | CLOSED | 16-31555: D2O Project , Holds For Work Plans On WW41 T-8 Schedule | D4
N-2013-04338 | 2013/08/19 | CLOSED | 16-31555: Oncore Charges Rejected | D4
N-2013-04358 | 2013/08/19 | CLOSED | Work stopped due to TRF transient Project # 16-31555 | D4
N-2013-04474 | 2013/08/25 | CLOSED | Trench starting to undermine. Project # 16-31555 | D4
N-2013-04475 | 2013/08/25 | CLOSED | Buried tech cable found during excavation. Project#16-31555 | D4
N-2013-11589 | 2013/08/28 | CLOSED | Project 16-31555 - Yard Inactive Drainage EC120400 , RV's found on field walkdown not documented on OPG flowsheets | NE0
N-2013-11609 | 2013/08/28 | CLOSED | Workers failed to follow fall arrest requirements - Project 16-31555 | D4
N-2013-12393 | 2013/09/05 | CLOSED | Project # 16-31555- Fluid leak from Zoom Boom Detected | D4
N-2013-12518 | 2013/09/06 | CLOSED | Project 16-31555 Fluid leak from Tow Truck | D4
N-2013-12555 | 2013/09/07 | CLOSED | Work stopped due to the weather conditions. Project #16-31555 | D4
N-2013-13125 | 2013/09/12 | CLOSED | 16-31555: Inadequate vendor equipment (tanks) resulting in re-work | D3
N-2013-13209 | 2013/09/12 | CLOSED | Incomplete training for incoming employees. Project 16-31555 | D4
N-2013-13216 | 2013/09/12 | CLOSED | Work Stopped Due to Weather Conditions - Project #16-31555 | D4
N-2013-14112 | 2013/09/19 | CLOSED | Project # 16-31555 - Delayed Entry into Protected Area | D4
N-2013-14585 | 2013/09/23 | CLOSED | Project #16-31555 - Hydraulic Leak from Excavator | D4
N-2013-14589 | 2013/09/23 | CLOSED | Project #16-31555 As Found condition Pile Vibrating machine unable to install piles past ~ 14 feet | D4
N-2013-14955 | 2013/09/26 | CLOSED | Project #16-31555 Delays due to Days Shift Manager unavailability due to pre-scheduled training | D4
N-2013-15297 | 2013/09/29 | CLOSED | Project#16-31555 delayed entry to asb | D4
N-2013-15299 | 2013/09/29 | CLOSED | Project#16-31555 delayed in obtaining work authorization | D4
N-2013-15952 | 2013/10/03 | CLOSED | Project#16-31555-Lack of place keeping and adherence to master workplan | D4
N-2013-16259 | 2013/10/07 | CLOSED | Project #16-31555 Equipment inspections | D4
N-2013-16823 | 2013/10/10 | CLOSED | Project 16-31555 - Late Identification of Required Training | D4
N-2013-17621 | 2013/10/17 | CLOSED | Training no show's project # 16-31555 STE 209670 Fall arrest | D4
N-2013-17768 | 2013/10/18 | CLOSED | Project #16-31555 D2O Storage Facility Delay to Construction | D4
N-2013-17771 | 2013/10/18 | CLOSED | Delay to project #16-31555 D2O storage building delay to Foam Fire workplan | D4
N-2013-17859 | 2013/10/19 | CLOSED | Delay to Project 16-31555 D2O Storage Bldg Foam Fire permit | D4
N-2013-17873 | 2013/10/19 | CLOSED | Project 16-31555 | D4
N-2013-17874 | 2013/10/19 | CLOSED | Project #16-31555 Fire protection line permit not available. | D4
N-2013-17875 | 2013/10/19 | CLOSED | Project #16-31555 work suspended at LPSW excavation due to weather | D4
N-2013-18163 | 2013/10/22 | CLOSED | 16-31555 work suspended at LPSW excavation due to permit and weather | D4
N-2013-18557 | 2013/10/24 | CLOSED | 16-31555 Late Identification of Required Training - Work Protection Level 2 | D4
N-2013-18564 | 2013/10/24 | CLOSED | 16-31555 work suspended at LPSW excavation due to permit | D4
N-2013-18574 | 2013/10/24 | CLOSED | 16-31555 PPT not approved for removal of FIreline spools. | D4
N-2013-18757 | 2013/10/25 | CLOSED | 16-31555 Undersized Generators | D4
N-2013-18803 | 2013/10/26 | CLOSED | 16-31555 Continued problems with Generators | D4
N-2013-18849 | 2013/10/27 | CLOSED | 16-31555 Hydraulic Leak on Boom Truck | D4
N-2013-18948 | 2013/10/28 | CLOSED | 16-31555 LPSW Tie-In Delay | D4
N-2013-18951 | 2013/10/28 | CLOSED | Project#16-31555 - Unable to install temporary connections on SG fuel tanks 1 & 2 | D4
N-2013-19151 | 2013/10/29 | CLOSED | Project # 16-31555 Survey Benchmarks Takeout of Sequence | D4
N-2013-19236 | 2013/10/30 | CLOSED | PROJ 16-31555: Flow Diagram Updated to resolve legacy configuration issue outside EC122212 scope without field verification | D4
N-2013-19351 | 2013/10/31 | CLOSED | 16-31555 Delay in dewatering due to lab issues with results | D4
N-2013-19492 | 2013/10/31 | CLOSED | 16-31555 Dewatering delays | D4
N-2013-19644 | 2013/11/01 | CLOSED | Proj. 16-31555: Walkdown observed inadequate catch containment dikes and ladder against groundwater monitoring well | D4
N-2013-19734 | 2013/11/03 | CLOSED | EPC Issue: Project #16-31555: Pressure Test Conditions Not Identified on Contractor ITP Impacting Review | D4
N-2013-20021 | 2013/11/05 | CLOSED | 16-31555 Unapproved Scope Added via MDR Revision | D4
N-2013-20504 | 2013/11/10 | CLOSED | 16-31555 Project excavation delayed due to high winds. | D4
N-2013-20586 | 2013/11/11 | CLOSED | Project # 16-31555 : Darlington F1 Site Preparation; Scope of Work Increased following EAC Request | D4
N-2013-20711 | 2013/11/12 | CLOSED | 16-31555 Overflow on Dewatering System | D4
N-2013-21007 | 2013/11/14 | CLOSED | Project 16-31555 delay to issuance of the WPL for EC 120406 "Tie-in for TRF Outgoing and Incoming" | D4
N-2013-21014 | 2013/11/14 | CLOSED | 16-31555 Leaking sampling valve | D4
N-2013-21028 | 2013/11/14 | CLOSED | Project#16-31555 - Leak on Vac Truck | D4
N-2013-21101 | 2013/11/15 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2013-21134 | 2013/11/15 | CLOSED | Scaffold material staged in TRF for D2O project# 16-31555 removed | D4
N-2013-21319 | 2013/11/18 | CLOSED | 16-31555 Failure to provide notification of extended hours | D4
N-2013-21794 | 2013/11/22 | CLOSED | CNO AFS Milestone/Schedule Impact - 2nd Directed Change to TRF T1301 P6 Outage Logic Schedule – Project#16-38401 TRF ACS/GBCS Modification | D4
N-2013-21954 | 2013/11/24 | CLOSED | 16-31555 - D20 Project Fuel Spill | D4
N-2013-22011 | 2013/11/25 | CLOSED | Resource allocation for resolving work protection issues in field for EPC Contracts (Project 16-31555) | C3
N-2013-22048 | 2013/11/25 | CLOSED | 16-31555: Transfer of realized billings on the D2O Project 16-31555 from PO 217807 Line 0002 to PO 217807 Line 0003 | D4
N-2013-22217 | 2013/11/26 | CLOSED | 16-31555 ITP's not ready | D4
N-2013-22311 | 2013/11/27 | CLOSED | PROJ 16-31555, MEL Equipment Minor Revsions Created in Error (DEC120719) | D4
N-2013-22330 | 2013/11/27 | CLOSED | D20 Project Delay 16-31555, Client uncertainty on Scope of EC 120406 | D4
N-2013-22347 | 2013/11/27 | CLOSED | 16-315555: Employee hit head and wrenched neck. | D4
N-2013-22376 | 2013/11/27 | CLOSED | 16-31555 Feed and Prouduct, second flow scan required for 0-39320-MV1338 | D4
N-2013-22480 | 2013/11/28 | CLOSED | 16-31555 Glycol leak from Vac truck | D4
N-2013-22492 | 2013/11/28 | CLOSED | 16-31555 LPSW materials missing paperwork | D4
N-2013-22705 | 2013/12/02 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2013-23356 | 2013/12/08 | CLOSED | 16-31555- Delay in LPSW Painting Due to CCW Swap | D4
N-2013-23837 | 2013/12/12 | CLOSED | 16-31555: Employee Struck Finger with Hammer | D4
N-2013-24033 | 2013/12/14 | CLOSED | 16-31555: Contractor personnel with possible frost bite on nose. | D4
N-2013-24039 | 2013/12/14 | CLOSED | D2O Project # 16-31555 Delays due to inclement weather. | D4
N-2013-24316 | 2013/12/17 | CLOSED | 16-31555 Discovery of Temperature Classification Issue with TRF Helium and Oxygen Supply Systems | D4
N-2013-24720 | 2013/12/21 | CLOSED | 16-31555- Worker falls in parking lot on ice | D4
N-2013-24984 | 2013/12/30 | CLOSED | 16-31555 previously broken conduit [as noted in N-2013-12449 ] appears to have frozen and cracked at new location | D4
N-2014-00055 | 2014/01/02 | CLOSED | 16-31555- Delay in LPSW back fill due to TIS Window Movement | D4
N-2014-00076 | 2014/01/02 | CLOSED | TRF: Delay to Establishing TIS Argon outage required for Project 16-31555 | D4
N-2014-00150 | 2014/01/03 | CLOSED | 16-31555 Delay to project due to frozen gate at ASB | D4
N-2014-00226 | 2014/01/04 | CLOSED | 16-31555 small hydraulic leak, no release to environment | D4
N-2014-00249 | 2014/01/05 | CLOSED | Project #16-31555. Hydraulic leak from crane | D4
N-2014-00397 | 2014/01/07 | CLOSED | 16-31555 – HWMB West Annex Project – DEC 120719 Ops Acceptance Completed prior to issued revisions to Operational Flow Sheets | D4
N-2014-00575 | 2014/01/08 | CLOSED | 16-31555: Extreme cold weather | D4
N-2014-00607 | 2014/01/08 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2014-00657 | 2014/01/08 | CLOSED | 16-31555 Scope Addition Now Required for Foam Fire Flush Test | D4
N-2014-01007 | 2014/01/11 | CLOSED | 16-31555 Schedule challenge for start of Caissons | D4
N-2014-01253 | 2014/01/14 | CLOSED | 16-31555 Weather delays on F1 Project | D4
N-2014-01348 | 2014/01/14 | CLOSED | 16-31555 HWMB West Annex. C13 Laydown area water runoff | C3
N-2014-01481 | 2014/01/15 | CLOSED | 16-31555: Late Reporting, Employee Twisted Knee | D4
N-2014-01764 | 2014/01/17 | CLOSED | 16-31555 The D2O Project Team did not provide the CA/ CMO with the proper Overtime request to work in exess of 10 hours | D4
N-2014-01792 | 2014/01/17 | CLOSED | 16-31555 HWMB west annex project. hydraulic leak at the building footprint. | D4
N-2014-02164 | 2014/01/21 | CLOSED | 16-31555 HWMB West Annex project. Delay due to weather. | D4
N-2014-02166 | 2014/01/21 | CLOSED | 16-31555 HWMB West Annex. Delay due to cold weather | D4
N-2014-02334 | 2014/01/22 | CLOSED | 16-31555 Weather delay on D20 | D4
N-2014-02336 | 2014/01/22 | CLOSED | 16-31555 work delay on D20 Argon Temporary Tie in | D4
N-2014-02589 | 2014/01/24 | CLOSED | 16-31555: Missed Training | D4
N-2014-02825 | 2014/01/27 | CLOSED | 16-31555: Schedule delay due to weather | D4
N-2014-02830 | 2014/01/27 | CLOSED | 16-31555 Weather delays | NE0
N-2014-02832 | 2014/01/27 | CLOSED | 16-31555 Weather delays on F1 Project | D4
N-2014-02833 | 2014/01/27 | CLOSED | 16-31555 Weather delays | D4
N-2014-02837 | 2014/01/27 | CLOSED | 16-31555 Weather conditions cause delay in Argon trailer pickup | D4
N-2014-02985 | 2014/01/28 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2014-03034 | 2014/01/28 | CLOSED | 16-31555 Weather delays | D4
N-2014-03059 | 2014/01/28 | CLOSED | 16-31555 lost TLD in unzoned area | D4
N-2014-03505 | 2014/01/31 | CLOSED | 16-31555, Feed and Product Work Plan revision requested. | D4
N-2014-03547 | 2014/01/31 | CLOSED | First Aid - cut finger tip PO #217807 / Project 16-31555 | D4
N-2014-03714 | 2014/02/03 | CLOSED | 16-31555 Weather delays | D4
N-2014-03801 | 2014/02/03 | CLOSED | Project# 16-31555 ~ 6hr Delay to establishing work protection permit for 0-39340-V2893 (EC120448) | NE0
N-2014-03962 | 2014/02/04 | CLOSED | Vendor delay in providing approved documentation to HWMS Computer Software Development Team | D4
N-2014-03993 | 2014/02/05 | CLOSED | 16-31555 two workers slipped on snow covered ice | D4
N-2014-04125 | 2014/02/05 | CLOSED | Project 16-31555 Delay due to weather HWMB west annex | D4
N-2014-04141 | 2014/02/05 | CLOSED | 16-31555 Discovery of concrete slab interference | D4
N-2014-04298 | 2014/02/06 | CLOSED | Project 16-31555: Damaged Telephone Cable Box During snow clearing | D4
N-2014-04351 | 2014/02/07 | CLOSED | 16-31555 Lost TLD Badge | D4
N-2014-04404 | 2014/02/07 | CLOSED | 16-31555: F1 - spill from ground heater | C3-NFE
N-2014-04406 | 2014/02/07 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2014-04435 | 2014/02/07 | CLOSED | 16-31555 delay to WO# 2910086 | D4
N-2014-04441 | 2014/02/07 | CLOSED | Project 16-31555: Slip and fall | D4
N-2014-04527 | 2014/02/09 | CLOSED | 16-31555 Discovery of Legacy Temperature Classification Issue with TRF Argon Supply | D4
N-2014-04535 | 2014/02/09 | CLOSED | 16-31555 TSSA Delay in Re-registration of TRF Argon Supply System & associated delay to EC122210 Revision | D4
N-2014-04542 | 2014/02/09 | CLOSED | 16-31555; DBOM GOV does not align w OLW requirements regarding use of Cable CatIDs when procured by EPC Vendors, Delays EC120488 & EC120489 | C3-NFE
N-2014-04684 | 2014/02/10 | CLOSED | TRF: 16-31555 Delay in Document Transmittal due to EPC Vendor Doc Control | D4
N-2014-04685 | 2014/02/10 | CLOSED | 16-31555: Ground heater leak - F1 (D20 Storage Project) | CO3
N-2014-04692 | 2014/02/10 | CLOSED | Project 16-31555 - DEC 120643 Not Accepted by OPG Refurbishment Design | NE0
N-2014-04946 | 2014/02/12 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2014-05116 | 2014/02/13 | CLOSED | Project 16-31555 - DEC 120643 Not Accepted by OPG Refurbishment Design | D4
N-2014-05239 | 2014/02/14 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2014-05430 | 2014/02/18 | CLOSED | 16-31555: Unallowed costs being submitted by vendor | C3-NFE
N-2014-05434 | 2014/02/18 | CLOSED | 16-31555 Weather delay to the project. | D4
N-2014-05452 | 2014/02/18 | CLOSED | 16-31555 Schedule Compliance Affected By Delays In Argon System Work | D4
N-2014-05481 | 2014/02/18 | CLOSED | 16-31555 DIOTS Permit strategy in Work plan rejected by field TRF Operations | D4
N-2014-05622 | 2014/02/19 | CLOSED | 16-31555 HWMB West Annex. Argon Relocate EC120670 Delay. | NE0
N-2014-05976 | 2014/02/21 | CLOSED | Project - 16-31555 - OPG Material Support Required | D4
N-2014-06342 | 2014/02/25 | CLOSED | Project # 16-31555: F1 - cut to chin | D3
N-2014-06469 | 2014/02/26 | CLOSED | 16-31555 D2O Storage: Delay in submission of EC 120483 to OPG for Acceptance | D4
N-2014-06565 | 2014/02/26 | CLOSED | 16-31555 Mandatory Personnel not in Attendance at Mandatory F1 SMP Roll Out Meeting | D4
N-2014-07010 | 2014/03/03 | CLOSED | 16-31555: Tractor Trailer in approriately parked on Holt Road blocking traffic | C3-NFE
N-2014-07063 | 2014/03/03 | CLOSED | 16-31555: Lack of Extended Shift Notice | D4
N-2014-07220 | 2014/03/04 | CLOSED | 16-31555 (D20 Storage- HWMB) potential soft tissue injury, left upper back area | D3
N-2014-07334 | 2014/03/05 | CLOSED | 16-31555 Glycol leak on Vac truck at C13 | D4
N-2014-07347 | 2014/03/05 | CLOSED | 16-31555 Worker reports swollen hand | D4
N-2014-07596 | 2014/03/06 | CLOSED | 16-31555 Non work related illness | D4
N-2014-08554 | 2014/03/14 | CLOSED | 16-31555 strong smell of deisel from Caisson excavation. | D4
N-2014-09613 | 2014/03/24 | CLOSED | 16-31555 HWMB West Annex. Caisson installation on hold due to soil results. | D4
N-2014-09624 | 2014/03/24 | CLOSED | 16-25619 - OSB Refurbishment Project - Rejected Vouchcers in Oncore due to disallowed costs per ES-MSA | D4
N-2014-10341 | 2014/03/31 | CLOSED | 16-31555 SG Fuel Tank Foam Fire Protection Return To Service Rescheduled Two Weeks Later, WO 3044931 | D4
N-2014-10832 | 2014/04/03 | CLOSED | 16-31555: Break Plan Training Request - Late Identification of Required Training | D4
N-2014-10844 | 2014/04/03 | CLOSED | 16-31555 Material outside of approved SATM area | D4
N-2014-11201 | 2014/04/07 | CLOSED | 16-31555 Missed training | D4
N-2014-11565 | 2014/04/09 | CLOSED | 16-31555 water leak at F-1 holding area | D4
N-2014-11573 | 2014/04/09 | CLOSED | 16-31555, clean water dumped in wrong location | D4
N-2014-11820 | 2014/04/11 | CLOSED | 16-31555 Caisson Drilling Rig Equipment Breakdown Resulting In Delays To Scheduled Drilling | D4
N-2014-13171 | 2014/04/23 | CLOSED | 16-31555 plastic bottles discarded into Zone 2 Waster Labelled D20 | D4
N-2014-13835 | 2014/04/29 | CLOSED | Project 16-31555: Worker felt twinge in Back | D3
N-2014-14580 | 2014/05/05 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 122210, R06 late | D4
N-2014-14603 | 2014/05/05 | CLOSED | 16-31555 Lockers for sub contractor's working caissons | D4
N-2014-14605 | 2014/05/05 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121326, R0 On Hold | D4
N-2014-14620 | 2014/05/05 | CLOSED | Project 16-31555 DNGS HWMB West Annex – Work Plan Schedule Error | D4
N-2014-14626 | 2014/05/05 | CLOSED | 16-31555: D2O Annex Design Engineering Change Package Schedule Delay - EC 120479 | CO4
N-2014-14627 | 2014/05/06 | CLOSED | 16-31555: D2O Annex Design Engineering Change Package Schedule Delay - EC 120588 | CO4
N-2014-14628 | 2014/05/06 | CLOSED | 16-31555: D2O Annex Design Engineering Change Package Schedule Delay - EC 120424 | CO4
N-2014-14631 | 2014/05/06 | CLOSED | 16-31555: D2O Annex Engineering Scope of Work Revision Delay - EC 123676 | CO4
N-2014-14653 | 2014/05/06 | CLOSED | 16-31555 Caisson lost due to flowing water | D4
N-2014-14676 | 2014/05/06 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120784: Missed Schedule Date | D4
N-2014-14687 | 2014/05/06 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120343, Missed Schedule Date | D4
N-2014-14693 | 2014/05/06 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120421, Missed Schedule Date | D4
N-2014-14876 | 2014/05/07 | CLOSED | Follow up on SCR N-2014-13705, 16-31555 D20 Storage Project, Work started on F10 Degrubbing Prior to receiving work authorization. | D4
N-2014-15058 | 2014/05/08 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121146, 123130, 121323 Schedule Slip: Late 3rd Party Fire Review / Certification | D4
N-2014-15070 | 2014/05/09 | CLOSED | 16-31555 Light Standard Knocked Over by Truck | NE0
N-2014-15154 | 2014/05/09 | CLOSED | 16-31555 missed schedule date | D4
N-2014-15259 | 2014/05/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – Detail Commissioning Specification (DCS) Schedule Risk for DEC 120557 Phase 2 DCS | D4
N-2014-15260 | 2014/05/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – Detail Commissioning Specification (DSC) Schedule Slip DEC 120483 | D4
N-2014-15262 | 2014/05/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – OPG DEC Review Sched ule Slip, Due to Fragmented DEC Submittal | D4
N-2014-15378 | 2014/05/12 | CLOSED | 16-31555 D2O Storage: Workplan transmitted to OPG without comments incorporated | D4
N-2014-15543 | 2014/05/13 | CLOSED | 16-31555 D2O Storage: Delays in document processing through EDMS | D4
N-2014-15547 | 2014/05/13 | CLOSED | 16-31555 D2O Storage: EDMS Submission Rejection - Documents differ from transmittal | D4
N-2014-15551 | 2014/05/13 | CLOSED | 16-31555 D2O Storage: Documents submitted in EDMS for incorrect review | D4
N-2014-15716 | 2014/05/15 | CLOSED | Project 16-31555 DNGS HWMB-WA – Funding Constraints delay Material POs and DEC Detail Designs requiring Vendor Info | D4
N-2014-15722 | 2014/05/15 | CLOSED | Project 16-31555 DNGS HWMB WA, DEC Schedule Activity Slips, No adverse impact to overall project schedule | D4
N-2014-15782 | 2014/05/15 | CLOSED | 16-31555 D2O Storage: Schedule Activity Incorrectly Reported Complete | D4
N-2014-15850 | 2014/05/15 | CLOSED | 16-31555 Missed Schedule Date for EC Comment Disposition Acceptance - D20 Project | D4
N-2014-15917 | 2014/05/16 | CLOSED | Project 16-31555 Schedule dates incorrect. | D4
N-2014-16081 | 2014/05/19 | CLOSED | Project#16-31555: Delay to ECs schedule due to scope change requests | D4
N-2014-16182 | 2014/05/20 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120341 late | D4
N-2014-16186 | 2014/05/20 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120784: Missed Schedule Date | D4
N-2014-16189 | 2014/05/20 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120426, Missed Schedule Date | D4
N-2014-16194 | 2014/05/20 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 124304, Missed Schedule Date | D4
N-2014-16264 | 2014/05/21 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DCS#67: Missed Schedule Date | D4
N-2014-16467 | 2014/05/22 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120341 late | D4
N-2014-16478 | 2014/05/22 | CLOSED | 16-31555 – HWMB West Annex Project – DEC 120448 AR 28165096 Assignment 6 due date missed | D4
N-2014-16484 | 2014/05/22 | CLOSED | 16-31555 – HWMB West Annex Project – DEC 121579 Closeout AR Not Prepared Immediately Following Ops Acceptance for Modification | D4
N-2014-16632 | 2014/05/24 | CLOSED | Project#16-31555: EC schedule delays | D4
N-2014-16733 | 2014/05/26 | CLOSED | 16-31555 D2O Storage: Delay to DEC review due to late submission | D4
N-2014-16766 | 2014/05/26 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616, Missed Schedule Date | D4
N-2014-16767 | 2014/05/26 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120493, Missed Schedule Date | D4
N-2014-16800 | 2014/05/26 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120428, Missed Schedule Date | D4
N-2014-16801 | 2014/05/26 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120426, Missed Schedule Date | D4
N-2014-16824 | 2014/05/26 | CLOSED | 16-31555 D2O Storage: Delay to entrance of ASB due to fukushima drill | D4
N-2014-16885 | 2014/05/27 | CLOSED | 16-31555 D2O: EC 120471 Isherwood DWGS & Calc Submission Cancelled | D4
N-2014-16888 | 2014/05/27 | CLOSED | 16-31555: Transmittal for EC 120471 (Seismic Dyke) was delayed due to EDMS. | D4
N-2014-16893 | 2014/05/27 | CLOSED | 16-31555 D2O Storage: EC submission containing wrong documentation | D4
N-2014-16917 | 2014/05/27 | CLOSED | 16-31555 D2O Storage: Risk with EDMS Electronic Acceptance | D4
N-2014-16918 | 2014/05/27 | CLOSED | 16-31555 HWMB West Annex. MR#2869255 Set to cancelled. Project has potential to be delayed due to lack of welding consumables. | D4
N-2014-16928 | 2014/05/27 | CLOSED | 16-31555 D2O Storage: Tech Spec Incorrectly Reported With OPG | D4
N-2014-17015 | 2014/05/28 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123130, Missed Schedule Date | D4
N-2014-17020 | 2014/05/28 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120341 Schedule Date Missed | D4
N-2014-17021 | 2014/05/28 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123679 Schedule Date Missed | D4
N-2014-17062 | 2014/05/28 | CLOSED | 16-31555 D2O Storage: ENG Activity delays due to EDMS processing delays | D4
N-2014-17223 | 2014/05/30 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120643, Missed Schedule Date | D4
N-2014-17224 | 2014/05/30 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120492, Missed Schedule Date | D4
N-2014-17555 | 2014/06/03 | CLOSED | 16-31555 D2O Storage: OPG Drawing Office Acitivity deadline missed | D4
N-2014-17583 | 2014/06/03 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616: Missed Schedule Date | D4
N-2014-17587 | 2014/06/03 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120615: Missed Schedule Date | D4
N-2014-17595 | 2014/06/03 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120493: Missed Schedule Date | D4
N-2014-17699 | 2014/06/04 | CLOSED | 16-31555 DNGS HWMB West Annex - OPG DEC 121323 Review Schedule missed | D4
N-2014-17766 | 2014/06/04 | CLOSED | Project 16-31555 DNGS HWMB WA – "MCC RFP Update" Schedule Slip | D4
N-2014-17815 | 2014/06/05 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616: Missed Schedule Date | D4
N-2014-17820 | 2014/06/05 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120523: Missed Schedule Date | D4
N-2014-17831 | 2014/06/05 | CLOSED | 16-31555 De-Watering well sleeve out of alignment | D4
N-2014-17882 | 2014/06/05 | CLOSED | 16-31555 - HWMB Workplan Schedule Not Correct | D4
N-2014-18111 | 2014/06/09 | CLOSED | 16-31555 Wailer Splice Detail requires disposition | D4
N-2014-18134 | 2014/06/09 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120343, Missed Schedule Date | D4
N-2014-18139 | 2014/06/09 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120428: Missed Schedule Date | D4
N-2014-18160 | 2014/06/09 | CLOSED | 16-31555 D2O Project schedule not updated with POD updates | D4
N-2014-18318 | 2014/06/10 | CLOSED | Project#16-31555: Rework during EC documentation closeout | D4
N-2014-18352 | 2014/06/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123130, Missed Schedule Date | D4
N-2014-18430 | 2014/06/11 | CLOSED | 16-31555 DNGS HWMB West Annex - OPG DEC 121323 Review Schedule missed again | D4
N-2014-18571 | 2014/06/13 | CLOSED | 16-31555 Projects submitted TPAR which contains incorrect information | D4
N-2014-18588 | 2014/06/13 | CLOSED | 16-31555 – HWMB West Annex Project – DEC 120448 Closeout Drawing Package misplaced at Design Agency offices after being delivered from the drawing off | D4
N-2014-18789 | 2014/06/16 | CLOSED | 16-31555 D2O Storage Facility, Installation Of Wailers Delayed One Hour Due To Weather | D4
N-2014-18796 | 2014/06/16 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121146, Missed Schedule Date | D4
N-2014-18801 | 2014/06/16 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120426, Missed Schedule Date | D4
N-2014-18839 | 2014/06/17 | CLOSED | Project 16-31555 DNGS HWMB West Annex – Procurement Activity Schedule Slip | D4
N-2014-18841 | 2014/06/17 | CLOSED | Project 16-31555 DNGS HWMB West Annex – Procurement Activity Schedule Slip | D4
N-2014-18842 | 2014/06/17 | CLOSED | 16-31555 - HWMB Workplan Schedule Not Correct | D4
N-2014-18924 | 2014/06/17 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120343, Missed Schedule Date | D4
N-2014-18926 | 2014/06/17 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123130, Missed Schedule Date | D4
N-2014-18933 | 2014/06/17 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616, Missed Schedule Date | D4
N-2014-18934 | 2014/06/17 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120421, Missed Schedule Date | D4
N-2014-18939 | 2014/06/17 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120784, Missed Schedule Date | D4
N-2014-18962 | 2014/06/17 | CLOSED | D20 Project # 16-31555 Delay to wailer installation and tote removal due to severe weather conditions | D4
N-2014-18978 | 2014/06/18 | CLOSED | 16-31555 - HWMB Schedule Non-compliance | D4
N-2014-19166 | 2014/06/19 | CLOSED | Project 16-31555 - EC 122210 - AFS Deadline Missed | D4
N-2014-19511 | 2014/06/24 | CLOSED | D2O Project 16-31555, work plan signatures delayed due to unavailability of Unit 0 PCC Operations Spoc | D4
N-2014-19578 | 2014/06/24 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121146: Missed Schedule Date | D4
N-2014-19580 | 2014/06/24 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120426: Missed Schedule Date | D4
N-2014-19595 | 2014/06/24 | CLOSED | 16-31555 - HWMB Schedule Non-compliance | D4
N-2014-19596 | 2014/06/24 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616 and 120615 Schedule Date Missed | D4
N-2014-19597 | 2014/06/24 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123679, Missed Schedule Date | D4
N-2014-19610 | 2014/06/24 | CLOSED | 16-31555 - HWMB Schedule Non-compliance | D4
N-2014-19611 | 2014/06/24 | CLOSED | 16-31555 - Rejection of invoice due to inclusion of unapproved charges and disallowed costs | D4
N-2014-19683 | 2014/06/25 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120471: Missed Schedule Date | D4
N-2014-19692 | 2014/06/25 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DCS#48 Schedule Date Missed | D4
N-2014-19707 | 2014/06/25 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120523: Missed Schedule Date | D4
N-2014-19826 | 2014/06/26 | CLOSED | Drawing detail resulted in pipe installed at wrong elevation at D20 Project (16-31555) | D4
N-2014-19866 | 2014/06/27 | CLOSED | Project 16-31555 Delay to work plan for 36.2 Tie In To Upgrader | D4
N-2014-19867 | 2014/06/27 | CLOSED | Project 16-31555 Delay to work plan for 37 Tie In To Moderator | D4
N-2014-19868 | 2014/06/27 | CLOSED | Project 16-31555 Delay to work plan for 39 Tie In To heat transport | D4
N-2014-19922 | 2014/06/27 | CLOSED | 16-31555 HWMB West Annex scheduled excavation delayed. | D4
N-2014-20036 | 2014/06/30 | CLOSED | Project 16-31555 Delay to Schedule CNSC Code Class Approval for Instrument Air and Service Air | D4
N-2014-20118 | 2014/07/02 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123679, Missed Schedule Date | D4
N-2014-20169 | 2014/07/03 | CLOSED | Project 16-31555 DNGS HWMB WA – RV RFP Schedule Slip | D4
N-2014-20217 | 2014/07/03 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616: Missed Schedule Date | D4
N-2014-20223 | 2014/07/03 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120471, Missed Schedule Date | D4
N-2014-20306 | 2014/07/04 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120343, Missed Schedule Date | D4
N-2014-20308 | 2014/07/04 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123130, Missed Schedule Date | D4
N-2014-20438 | 2014/07/07 | CLOSED | 16-31555 delay to work on strut welding due to weather | D4
N-2014-20465 | 2014/07/07 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120426, Missed Schedule Date | D4
N-2014-20471 | 2014/07/07 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DCS#32: Missed Schedule Date | D4
N-2014-20479 | 2014/07/07 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121146 Schedule off track | D4
N-2014-20496 | 2014/07/07 | CLOSED | 16-31555 - HWMB Workplan Schedule non-compliance | D4
N-2014-20501 | 2014/07/07 | CLOSED | 16-31555 - HWMB Schedule Non-Compliance | D4
N-2014-20573 | 2014/07/08 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123679 Schedule Date Missed | D4
N-2014-20590 | 2014/07/08 | CLOSED | Project 16-31555 DNGS HWMB west annex rain delay | D4
N-2014-20624 | 2014/07/09 | CLOSED | 16-31555 Projects submitted TPAR which requires clarification | D4
N-2014-20653 | 2014/07/09 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120471 and 120426 Schedule Date Missed | D4
N-2014-20733 | 2014/07/10 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121327, Missed Schedule Date | D4
N-2014-20823 | 2014/07/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120474 Schedule Date Missed | D4
N-2014-20842 | 2014/07/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123679 Schedule Date Missed | D4
N-2014-20843 | 2014/07/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120557 Schedule Date Missed for DCS | D4
N-2014-20876 | 2014/07/11 | CLOSED | 16-31555 DNGS HWMB west annex = TLD badge passed through X-ray machine | D4
N-2014-20896 | 2014/07/12 | CLOSED | 16-31555: D20 - Contact with Dewatering header pipe | D4
N-2014-21052 | 2014/07/15 | CLOSED | 16-31555 - HWMB Schedule Non-compliance | D4
N-2014-21180 | 2014/07/15 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616 & 120615 Schedule Date Missed | D4
N-2014-21232 | 2014/07/16 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120784 Schedule Date Missed | NE0
N-2014-21234 | 2014/07/16 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120421 Schedule Date Missed | NE0
N-2014-21260 | 2014/07/16 | CLOSED | 16-31555 - HWMB Schedule Non-compliane | D4
N-2014-21279 | 2014/07/17 | CLOSED | Project 16-31555 Delay to work plan for 67 Computer Tie In | D4
N-2014-21401 | 2014/07/18 | CLOSED | 16-31555 - HWMB Schedule Non-compliance | D4
N-2014-21432 | 2014/07/18 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG review of workplan | D4
N-2014-21476 | 2014/07/18 | CLOSED | 16-31555 - individual mistakenly took TLD badge through security scanners | D4
N-2014-21500 | 2014/07/19 | CLOSED | 16-31555 DNGS HWMB west annex delay due to weather | D4
N-2014-21537 | 2014/07/21 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120784 Schedule Date Was Not Missed | NE0
N-2014-21572 | 2014/07/21 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120421 Schedule Date Was Not Missed | NE0
N-2014-21698 | 2014/07/22 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DCS#66 D2O Leak Detection System: Missed Schedule Date | D4
N-2014-21771 | 2014/07/23 | CLOSED | 16-31555 - Schedule Delay to Line Item ENG-53610 - "OPG Accept CDS for DEC 120423" | C3-NFE
N-2014-21850 | 2014/07/23 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120616 Schedule Date Missed | D4
N-2014-21872 | 2014/07/24 | CLOSED | 16-31555 - HWMB schedule Non-compliance | D4
N-2014-21890 | 2014/07/24 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120474 Schedule Date Missed | D4
N-2014-21893 | 2014/07/24 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120492 Schedule Date Missed for DCS | D4
N-2014-21920 | 2014/07/24 | CLOSED | D2O Project 16-31555, work plan For EC 120483, delayed due to unresolved actions | D4
N-2014-22003 | 2014/07/25 | CLOSED | 16-31555 DNGS HWMB West Annex- Quality of TSSA Submission NK38-CORR-00554-10448 Less Than Adequate | D4
N-2014-22018 | 2014/07/25 | CLOSED | 16-31555 DNGS HWMB West Annex- Quality of EC 120426 R002, Transfer of Sewage, Less Than Adequate | D4
N-2014-22038 | 2014/07/25 | CLOSED | 16-31555 Individual mistakenly took TLD badge through security scanners | D4
N-2014-22059 | 2014/07/26 | CLOSED | 16-31555 hwmb west annex. Dewatering Line leak at the PA west gate | D4
N-2014-22119 | 2014/07/28 | CLOSED | 16-31555 delay to Excavation due to weather | D4
N-2014-22223 | 2014/07/29 | CLOSED | 16-31555 - Delay to Schedule - Line Item ENG-52030 CNSC Code Class Approvals are granted | D4
N-2014-22321 | 2014/07/29 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120343 and 120577: Missed Schedule Date | D4
N-2014-22322 | 2014/07/29 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120784 Schedule Date Missed | D4
N-2014-22390 | 2014/07/30 | CLOSED | SATM Permit's Required With Less Than 21 Days Notice (16-31555) | D4
N-2014-22456 | 2014/07/31 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121146 Schedule Date Missed | D4
N-2014-22457 | 2014/07/31 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 123130 Schedule Date Missed | D4
N-2014-22530 | 2014/07/31 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-22534 | 2014/07/31 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-22612 | 2014/08/01 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120474 Schedule Date Missed | D4
N-2014-22726 | 2014/08/05 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 121319, Missed Schedule Date | D4
N-2014-22792 | 2014/08/05 | CLOSED | 16-31555 - Delay to Schedule - Line Item ENG-53630 - OPG Accepted CDS - DEC 120424 | D4
N-2014-22793 | 2014/08/05 | CLOSED | 16-31555 - Delay to Schedule - Line Item ENG-53610 - OPG Accepted CDS - DEC 120423 | D4
N-2014-22795 | 2014/08/05 | CLOSED | 16-31555 - Delay to Schedule - Line Item ENG-53650 - OPG Accepted CDS - DEC 120422 | D4
N-2014-22803 | 2014/08/05 | CLOSED | 16-31555 - HWMB Schedule Non-Compliance | D4
N-2014-22824 | 2014/08/06 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Detailed Commissioning Spec | D4
N-2014-22849 | 2014/08/06 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120474 Schedule Date Missed | D4
N-2014-22850 | 2014/08/06 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 127218 Schedule Date Missed | D4
N-2014-23020 | 2014/08/08 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-23213 | 2014/08/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-23229 | 2014/08/11 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120343 Schedule Date Missed | D4
N-2014-23277 | 2014/08/12 | CLOSED | Project 16-31555 DNGS HWMB-WA: Incorrect revision of a document was submitted for acceptance & issuance in AS7 through EDMS | D4
N-2014-23304 | 2014/08/12 | CLOSED | 16-31555 - HWMB Schedule Non-compliance | D4
N-2014-23442 | 2014/08/13 | CLOSED | Project 16-31555 TLD Placed in X ray Machine | D4
N-2014-23545 | 2014/08/14 | CLOSED | Project 16-31555 DNGS HWMB-WA: Incorrect title was input for an SCR and did not accurately describe the occurence. | D4
N-2014-23611 | 2014/08/15 | CLOSED | Project 16-31555 TLD Placed in X ray Machine | D4
N-2014-23798 | 2014/08/19 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-23800 | 2014/08/19 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-23809 | 2014/08/19 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-23815 | 2014/08/19 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Workplan | D4
N-2014-23874 | 2014/08/19 | CLOSED | Project 16-31555 DNGS HWMB West Annex: Schedule Slip for OPG Review of Commissioning Spec | D4
N-2014-23953 | 2014/08/20 | CLOSED | 16-31555 - Issues Identified Regarding Weather Enclosures around Dewatering Skids | CO3
N-2014-24009 | 2014/08/21 | CLOSED | Project 16-31555 DNGS HWMB West Annex – DEC 120343 Schedule Date Missed | D4
N-2014-24073 | 2014/08/21 | CLOSED | 16-31555 Paint removed from oxygen tank without written confirmation of content | D4
N-2014-24162 | 2014/08/22 | CLOSED | 16-31555 Oxygen tank weld fault found on lifting lug. | D4
N-2014-24633 | 2014/08/29 | CLOSED | 48070089- Work delayed lost shipment of cabling Project 16-31555 | D4
N-2014-24938 | 2014/09/03 | CLOSED | 16-31555, D20 Storage Project, Tie Back Rock Hammer Drill Bit Disconnected At Bottom Of Tie Back #3 | D4
N-2014-26127 | 2014/09/16 | CLOSED | Project#16-31555 - Engineering rework to EC#121736 | D4
N-2014-26669 | 2014/09/22 | CLOSED | 16-31555 HWMB West Annex excavation delayed due to water. | D4
N-2014-26744 | 2014/09/23 | CLOSED | 16-31555 HWMB West Annex visble sheen on water entering excavation. | D4
N-2014-26906 | 2014/09/24 | CLOSED | Project 16-31555 DNGS HWMB-WA: Incorrect completion notes submitted by vendor | D4
N-2014-27369 | 2014/09/29 | CLOSED | 16-31555 D2O HWMB contractor clothing thrown out from change room area | D4
N-2014-27475 | 2014/09/30 | CLOSED | 16-31555 HWMB West Annex. Stressing of tie backs delayed. | D4
N-2014-28570 | 2014/10/10 | CLOSED | Project # 16-31555--- D2O Project- --Hard substance encountered while drilling at tie back #31 | D4
N-2014-29063 | 2014/10/16 | CLOSED | Project 16-31555 - F1 Site - Hydralic Oil Spill from Vac Truck | D4
N-2014-29749 | 2014/10/24 | CLOSED | Project # 16-31555 - Cancellation of Break Plan Training Request | D4
N-2014-29750 | 2014/10/24 | CLOSED | Project # 16-31555 - "Break Plan" Training Request | D4
N-2014-29771 | 2014/10/24 | CLOSED | Project #16-31555 Delay to Soil Trucks between ASB Sally Port and F-1 SATM Area | D4
N-2014-30016 | 2014/10/27 | CLOSED | 16-31555 D2O HWMB individual inadvertently put TLD through xray at ASB | D4
N-2014-30034 | 2014/10/27 | CLOSED | Project 16-31555 - Hose inadvertently drained | D3
N-2014-30652 | 2014/11/03 | CLOSED | 16-31555 D2O HWMB individual exposed to falling hazard | C2
N-2014-30863 | 2014/11/05 | CLOSED | D20 #16-31555: vehicle damage incident in Sally Port | D4
N-2014-30906 | 2014/11/05 | CLOSED | 16-31555 HWMB work plans not reviewed or signed by OPG stakeholders in a timely manner | D4
N-2014-31029 | 2014/11/06 | CLOSED | D20 Project 16-31555 inappropriate safety behaviors observed | D3
N-2014-32132 | 2014/11/19 | CLOSED | 16-31555 D2O HWMB Overflow of dewatering system weif tank | D4
N-2014-32235 | 2014/11/20 | CLOSED | D2O Excavation Water Delay - Proj#16-31555 | D4
N-2014-32236 | 2014/11/20 | CLOSED | F1 Winterization Wind Delay - Proj#16-31555 | D4
N-2014-32273 | 2014/11/20 | CLOSED | 16-31555 Contractor failed to notify Field engineering of task execution requiring ITP witness point | D4
N-2014-32342 | 2014/11/21 | CLOSED | D2O Excavation Communication Delay - Proj#16-31555 | D4
N-2014-32853 | 2014/11/26 | CLOSED | HWMB (D20) Project #16-31555: Excavation Materials Setting off Exploranium in Sally Port | D4
N-2014-33194 | 2014/12/01 | CLOSED | D2O Excavation Delay to misc support trades - Proj#16-31555 | D4
N-2014-33371 | 2014/12/02 | CLOSED | HWMB (D20) Project #16-31555: Dump Truck Contacts Parked Excavator at F3 | D3
N-2014-33378 | 2014/12/02 | CLOSED | HWMB (D20) Project #16-31555: Excavation Materials Alarming Exploranium in Sally Port | D4
N-2014-33380 | 2014/12/02 | CLOSED | HWMB (D20) Project # 16-31555: Insufficient Lighting at F3 to Dump Material | D4
N-2014-33663 | 2014/12/05 | CLOSED | 16-31555 D2O Management bldg Contractor required rework to establish test conditions for Sacrificial Rock anchors performance test | D4
N-2014-33932 | 2014/12/09 | CLOSED | D2O Excavation Delay to misc support trades - Proj#16-31555 | D4
N-2014-34095 | 2014/12/10 | CLOSED | D20 HWMB P# 16-31555 Individual tripped and fell, with no injury reported | D4
N-2014-34278 | 2014/12/12 | CLOSED | 16-31555; Approved Radiation Source Term Design Requirements for HWMB-WA are not available from OPG Design | C3-NFE
N-2014-34310 | 2014/12/12 | CLOSED | HWMB (D2O) Project #16-31555: Lost prox card | D4
N-2014-34318 | 2014/12/12 | CLOSED | HWMB (D2O) Project #16-31555: Individual inadvertently put TLD through xray at ASB | D4
N-2014-34380 | 2014/12/14 | CLOSED | D2O Project Delay to misc support trades - Proj#16-31555 | D4
N-2014-34624 | 2014/12/17 | CLOSED | D20 Project 16-31555 - Training No-show | D4
N-2014-34886 | 2014/12/19 | CLOSED | D20 Project 16-31555 - Failure to obtain HAZMAT approval in a timely fashion | D4
N-2014-34975 | 2014/12/22 | CLOSED | PROJ 16-31555 Grounding Separation Design Requirements for Main Power Supply (13.8 KV) to HWMB-WA from Substation 0-53800-DS5 are not available | C3-NFE
N-2016-00117 | 2016/01/04 | CLOSED | Project # 16-31555 D2O Storage: FIC for DEC 120476 is required | D4
N-2016-00251 | 2016/01/05 | CLOSED | Project # 16-31555 D2O Storage: FIC for DEC 120493 is required | D4
N-2016-00252 | 2016/01/05 | CLOSED | Project # 16-31555 D2O Storage: FIC for DEC 120493 is required | D4
N-2016-00516 | 2016/01/08 | CLOSED | D2O Project#16-31555 Delay - Availability of SAMs and WBM at ASB | D4
N-2016-00691 | 2016/01/11 | CLOSED | Project # 16-31555 D2O Storage: FIC for DEC 120577 is required | D4
N-2016-00701 | 2016/01/11 | CLOSED | Project # 16-31555 D2O Storage: FIC for DEC 120479 is required | D4
N-2016-00791 | 2016/01/12 | CLOSED | 16-31555: Weather delays due to late installation of tent enclosure | D4
N-2016-00811 | 2016/01/12 | CLOSED | D2O Project 16-31555 Delay Inclement Weather | D4
N-2016-01102 | 2016/01/15 | CLOSED | Project # 16-31555 D2O Storage: FIC for DEC 120477 is required | D4
N-2016-01290 | 2016/01/18 | CLOSED | DNGS D2O Storage Facility– DIOT's tie-in spools (EC 120406) rescheduled to WW4. (delay) Project# 16-31555. | D4
N-2016-01775 | 2016/01/21 | CLOSED | D2O Project 16-31555 Medical Response at D2O Facility | D4
N-2016-02405 | 2016/01/28 | CLOSED | D2O Project 16-31555 Foreign Material in Workers Eye | D3
N-2016-02761 | 2016/02/01 | CLOSED | DNGS D2O Storage Facility– Work Protection Permit for DIOT tie-in spools unavailable. (EC 120406). Project# 16-31555. | D4
N-2016-02781 | 2016/02/01 | CLOSED | D2O Project 16-31555 - Rework - Hangers out of Tolerance | D4
N-2016-02837 | 2016/02/01 | CLOSED | DNGS D2O Storage Building- HWMB Access Qualifications Not Input in TIMS. (Trending) Project# 16-31555 | D4
N-2016-02988 | 2016/02/03 | CLOSED | D20 Project 16-31555 Dewatering system leak | D4
N-2016-03088 | 2016/02/03 | CLOSED | D2O Project 16-31555 Worker slipped on stairs | D4
N-2016-03095 | 2016/02/03 | CLOSED | D2O Storage Building- 16-31555: TRF piping system water level impacting pipe DIOTS tie-in tasks. (Delay) | D4
N-2016-03187 | 2016/02/04 | CLOSED | D2O Project 16-31555- Altair 5X-CO Alarm, D2O Evacuated as precaution | D3
N-2016-03708 | 2016/02/10 | CLOSED | D20 Project 16-31555 Delay- Workers uncovered catch basin below grade in support of D20 electrical excavations | D4
N-2016-03810 | 2016/02/11 | CLOSED | 16-31555: Change in NDE Methodology | D4
N-2016-03835 | 2016/02/11 | CLOSED | Project 16-31555: EC Revision Submission Rejection | D4
N-2016-04224 | 2016/02/16 | CLOSED | Project 16-31555: HWM West Annex MEC 88528 and 118880 - Change in COMS Stakeholders | D4
N-2016-04733 | 2016/02/22 | CLOSED | D2O Project 16-31555 Refueling Equipment Left Unattended | D4
N-2016-04958 | 2016/02/24 | CLOSED | D2O Project 16-31555- Delay Inclement Weather | D4
N-2016-06444 | 2016/03/11 | CLOSED | 16-31555 - Vendor missing accruals on project | D4
N-2016-06448 | 2016/03/11 | CLOSED | D20 Project 16-31555 Back Out due to Changing RP Conditions | D4
N-2016-06829 | 2016/03/16 | CLOSED | 16-31555: Unable to Load tanks on trailer in F5 pressure boundary due to high winds | D4
N-2016-06906 | 2016/03/16 | CLOSED | D20 Project 16-31555 Cut Ground Cable While Coring | D3
N-2016-07069 | 2016/03/18 | CLOSED | Project 16-31555: Unable to unload spool delivery. | D4
N-2016-07125 | 2016/03/18 | CLOSED | D20 Project 16-31555 - Back Out due to Changing RP Conditions | D4
N-2016-07348 | 2016/03/22 | CLOSED | D20 Project 16-31555 Worker without proper PPE | D3
N-2016-07406 | 2016/03/22 | CLOSED | Project # 16-31555 D2O Storage: Cable Tray Riser Design EC 120577 | D4
N-2016-07942 | 2016/03/29 | CLOSED | D2O Project 16-31555 FME event D20 Recovery Drainage system | D3
N-2016-07953 | 2016/03/29 | CLOSED | D2O Project 16-31555 FME event Embedded Pipe sleeves | D3
N-2016-07990 | 2016/03/30 | CLOSED | D20 Project 16-31555 material taken out of locked cabinet in the new RFRISA building | D4
N-2016-08274 | 2016/04/01 | CLOSED | Project 16-31555 - Shield Wire Numbers missing on Two Drawings under EC 120485/ MEC 88528 | D4
N-2016-08615 | 2016/04/05 | CLOSED | Project # 16-31555 D2O Storage: DEC 121146 R002 not bookmarked | D4
N-2016-08727 | 2016/04/06 | CLOSED | Project 16-31555: EC120476 R002 AS7 Bookmark Missing Page 8 for Change Paper NK38-BOM-57684-10001 | D4
N-2016-09097 | 2016/04/11 | CLOSED | 16-31555 - RTM not included in scope of work | D4
N-2016-09098 | 2016/04/11 | CLOSED | 16-31555 - Beetle Clip Install not included in SOW | D4
N-2016-09147 | 2016/04/11 | CLOSED | D2O Facility: Process Issue - Vendor QA Process Not Followed (Project # 16-31555) | CO3
N-2016-09267 | 2016/04/12 | CLOSED | 16-31555 - Dyke Monitoring not included in scope of work | D4
N-2016-09513 | 2016/04/14 | CLOSED | D2O Facility: Product Quality Issue - Pipe Spools exhibiting signs of rust in the weld/heat affected zones - (Project # 16-31555) | CO3
N-2016-09558 | 2016/04/14 | CLOSED | Project #16-31555 - Beetle Clip Weld Repairs | D3
N-2016-09669 | 2016/04/15 | CLOSED | PROJ 16-31555 HWMB-WA; Error in Assignment of OPG Doc Number for Code Registration forms, N-FORM-10971 & N-FORM-11003 for EC120616 | D4
N-2016-09725 | 2016/04/16 | CLOSED | D2O Facility: Human Performance - Bypass of OPG FME witness activity during installation of spools - (Project # 16-31555) | CO3
N-2016-09909 | 2016/04/18 | CLOSED | DNGS D20 Storage Facility- Beetle Drain electrical probe clip installation TIG welding issues. (Trending) Project# 16-31555. | D4
N-2016-10476 | 2016/04/22 | CLOSED | D2O Project 16-31555 EPD put through X-ray machine | NE0
N-2016-11614 | 2016/05/03 | CLOSED | D2O Project 16-31555- OE Asleep in Crane | NE0
N-2016-11624 | 2016/05/03 | COMPLETE | Inproper Support documents (On Line Wiring) Provided in D2O west Annex Beetles Installation CWP for Project 16-31555. | CO3
N-2016-12063 | 2016/05/06 | CLOSED | D2O Project 16-31555- Lack of Supervision | D4
N-2016-12065 | 2016/05/06 | CLOSED | D2O Project 16-31555- Lack of Supervision | D4
N-2016-12068 | 2016/05/06 | CLOSED | D2O Project 16-31555- Nightshift working without WA/Informing CMO of Work | D4
N-2016-12449 | 2016/05/10 | CLOSED | D2O Facility: Quality Assurance Trend SCR - Quality & Process Concerns (Proj: 16-31555) | C3
N-2016-13220 | 2016/05/17 | CLOSED | D2O Project 16-31555 Weir tank overflow to ground surface | D4
N-2016-14254 | 2016/05/27 | CLOSED | D2O Project- 16-31555- Worker's TLD through X-Ray | NE0
N-2016-14542 | 2016/05/31 | CLOSED | D2O Storage Facility: Human Performance - Lack of Attention to Detail - By-pass OPG witness activity (Project # 16-31555) | CO3
N-2016-14771 | 2016/06/02 | CLOSED | D2O Project- 16-31555- Worker drilled through empty conduit | D3
N-2016-14905 | 2016/06/03 | CLOSED | 16-31555 - D2O Storage Facility Scope Change | D4
N-2016-15149 | 2016/06/06 | CLOSED | D2O Project 16-31555- No Access to HWMB/TRF Due to Transfer with Station | D4
N-2016-15173 | 2016/06/06 | CLOSED | 16-31555 - D20 West Annex New Construction - Lightning in vicinity | D4
N-2016-15479 | 2016/06/09 | CLOSED | D2O 16-31555- Subcontractor injury to finger | D3
N-2016-15855 | 2016/06/14 | CLOSED | 16-31555-D20 Project Falling Object | D3
N-2016-15863 | 2016/06/14 | CLOSED | 16-31555 – D20 Project Saftey Observation | D3
N-2016-15971 | 2016/06/15 | CLOSED | D2O Project 16-31555 training gap identified | D4
N-2016-16412 | 2016/06/21 | CLOSED | Project # 16-31555 D2O Storage: Asset Suite status for OLW updates | D4
N-2016-16641 | 2016/06/24 | CLOSED | DNGS - D2O - HWMB West Annex D2O Fire Alarm Tie-in - OPG Project #16-31555 | D4
N-2016-16643 | 2016/06/24 | CLOSED | DNGS - D2O - HWMB West Annex D2O Fire Alarm Tie-in - OPG Project #16-31555 | D4
N-2016-16687 | 2016/06/24 | CLOSED | Project #16-31555 D2O Storage: Material Request Required to support vendor procurement issues | D4
N-2016-16893 | 2016/06/28 | CLOSED | 16-31555: Worker poked finger | D3
N-2016-16992 | 2016/06/29 | CLOSED | DNGS - Delay D2O Storage Facility Construction Support OPG Project#16-31555 | D3
N-2016-17056 | 2016/06/29 | CLOSED | #16-31555 -HWMB unable to preform planned/scheduled project tasks | NE0
N-2016-17063 | 2016/06/29 | CLOSED | 16-31555 D20- Project Material Handling Incident | D3
N-2016-17074 | 2016/06/29 | CLOSED | Project # 16-31555: Increase PO #250914 Greater than 20% Of Original Contract | D4
N-2016-17281 | 2016/07/04 | CLOSED | D20 Project #16-31555- HWMB unable to preform planned/ scheduled project tasks | D4
N-2016-17343 | 2016/07/05 | CLOSED | D20 West Annex New Construction Job#16-31555 Delay - Due to OPG Safety Stand Down | NE0
N-2016-17643 | 2016/07/08 | CLOSED | 16-31555-D20 Crack in Beam Pocket | D3
N-2016-17731 | 2016/07/08 | CLOSED | 16-31555 – HWMB unable to perform planned/scheduled project tasks | D4
N-2016-17754 | 2016/07/09 | CLOSED | D2O West Annex New Comstruction Job# 16-31555 Inclement Weather Reporting | D4
N-2016-17775 | 2016/07/10 | CLOSED | D20 West Annex New Build #16-31555 Worker Tweaked back, due to falling backwards on stairs descending Mobile Washroom facility | D3
N-2016-17828 | 2016/07/11 | CLOSED | Project #16-31555 D2O Storage: Material Request Required to support vendor procurement issues (Material for 100 El. Slab) | D4
N-2016-17873 | 2016/07/11 | CLOSED | D20 Project 16-31555 Training gap identified | D4
N-2016-17919 | 2016/07/12 | CLOSED | D2O Project 16-31555- Cracks forming at Beam pockets | D4
N-2016-17927 | 2016/07/12 | CLOSED | DNGS - D2O Storage Facility Construction Support OPG Project#16-31555 | D4
N-2016-18003 | 2016/07/13 | CLOSED | D2O West Annex New Construction # 16-31555 - Smouldering Hot Spot | D4
N-2016-18046 | 2016/07/13 | CLOSED | Project 16-31555 D2O Less than adequate rigging practices | D3
N-2016-18094 | 2016/07/14 | CLOSED | D20 West Annex #16-31555 Lightning delay of 1 hour | D4
N-2016-18192 | 2016/07/15 | CLOSED | D20 West Annex #16-31555 Lightning delay of 1 hour | D4
N-2016-18219 | 2016/07/15 | CLOSED | #16-31555 – Extended Shift required | D4
N-2016-18325 | 2016/07/18 | CLOSED | D2O West Annex New Construction # 16-31555 Worker Lost TLD | D4
N-2016-18336 | 2016/07/18 | CLOSED | Procedural Non-compliance - Contractor deviating from the N-PROC-MP-0090; Project # 16-31555 (D2O Storage) | CO3
N-2016-18645 | 2016/07/21 | CLOSED | #16-31555-D2O project delay transfer in the HWMB | D4
N-2016-18647 | 2016/07/21 | CLOSED | D20 Project 16-31555 worker slipped on rebar | D3
N-2016-18726 | 2016/07/22 | CLOSED | D20 Project#-16-31555 Fire detection installation delay due to as found conditions | D4
N-2016-18837 | 2016/07/25 | CLOSED | D20 Project # 16-31555 Delay Tritium alarm in HWMB | NE0
N-2016-18914 | 2016/07/25 | CLOSED | D2O Facility: Mechanical ITP review & rejection - (Project 16-31555) | CO3
N-2016-18933 | 2016/07/26 | CLOSED | Weather Dealy -Scaffolding Crew reassigned due to inclement weather D20 Project # 16-31555 | D4
N-2016-19014 | 2016/07/26 | CLOSED | D20 West Annex Project 16-31555- - Worker Felt Unwell | D3
N-2016-19017 | 2016/07/26 | CLOSED | Project 16-31555- D20 West Annex Weather Delay | D4
N-2016-19027 | 2016/07/26 | CLOSED | Project # 16-31555 D2O Storage: Overtime not pre-approved | D4
N-2016-19036 | 2016/07/26 | CLOSED | D2O Facility: Mechanical ITP review & rejection - (Project 16-31555) | CO3
N-2016-19037 | 2016/07/26 | CLOSED | D20 Project #16-31555. Hilti Drill "Kicked Back" on a worker | D3
N-2016-19094 | 2016/07/27 | CLOSED | Electricians unavailable to support work in field Project #16-31555, Job #15-5126, EC #121726 | D4
N-2016-19151 | 2016/07/28 | CLOSED | D2O West Annex New Construction Job# 16-31555 Inclement Weather Reporting To Document | D4
N-2016-19331 | 2016/07/29 | CLOSED | COMS – Lack of Quorum for COMS Meeting for Design EC 120491 (Stack Monitoring) Project # 16-31555 | D4
N-2016-19507 | 2016/08/02 | CLOSED | D2O Facility: Mechanical ITP review & rejection - (Project 16-31555) | CO3
N-2016-19619 | 2016/08/04 | CLOSED | D2O Facility: Mechanical ITP review & rejection - (Project 16-31555) | CO3
N-2016-19707 | 2016/08/05 | CLOSED | D2O Facility: Mechanical ITP review & rejection - (Project 16-31555) | CO3
N-2016-19754 | 2016/08/05 | CLOSED | 16-31555, D2O Storage Facility, Vendor bypassed ITP witness step. | CO3
N-2016-19813 | 2016/08/05 | CLOSED | D2O Project 16-31555 Safety observation fall potential | D3
N-2016-20014 | 2016/08/09 | CLOSED | # 16-31555 – Exceeded Approved Shift Hours | D4
N-2016-20070 | 2016/08/09 | CLOSED | D2O Project 16-31555- Oxygen and Helium Line Exposed | D3
N-2016-20489 | 2016/08/15 | CLOSED | 16-31555 – Back out due to Abnormal Condition | D4
N-2016-20525 | 2016/08/15 | CLOSED | Project 16-31555: ECC Guide Except | D4
N-2016-20559 | 2016/08/16 | CLOSED | 16-31555 - D2O Storage Facility provided funding for setting up electrical power in RFRISA building | D4
N-2016-20752 | 2016/08/18 | CLOSED | Project 16-31555 - EC121318 Submitted for Acceptance With Unresolved Pending Issues | D4
N-2016-20770 | 2016/08/18 | CLOSED | D2O Facility: Product Quatity Issue: Errors and omissions in CWP/ITP during OPG approval - Project # 16-31555 (D2O Storage) | D4
N-2016-20800 | 2016/08/18 | CLOSED | 16-31555 Lost TLD badge | D4
N-2016-20851 | 2016/08/19 | CLOSED | Project number16-31555 – Project scaffold teardown and rebuild | D4
N-2016-20857 | 2016/08/19 | CLOSED | Project # 16-31555 D2O Storage: Overtime not pre-approved | D4
N-2016-20934 | 2016/08/19 | CLOSED | D20 West Annex New COnstruction Job#16-31555 - Worker bumped Lip | D3
N-2016-20953 | 2016/08/20 | CLOSED | 16-31555 D20 West Annex New Construction - Temporary (600V) Power Supply Cable was PINCHED during excavation. Safety GFI-Breaker "tripped" | C3-NFE
N-2016-21124 | 2016/08/23 | CLOSED | Project # 16-31555 D2O Storage: Typographical error in EC 120493 submission | D4
N-2016-21167 | 2016/08/23 | CLOSED | OPG Project #16-31555 - Worker drilled hole outside of scanned area at SG1 | D4
N-2016-21183 | 2016/08/24 | CLOSED | D2O West Annex New Construction Job# 16-31555 Hydraulic Hose Failure on Loader | D4
N-2016-21313 | 2016/08/25 | CLOSED | 16-31555: Worker wore another employee's TLD badge in PA | D4
N-2016-21377 | 2016/08/25 | CLOSED | Project 16-31555 - EC120488 and 120489 Changes to Change Papers Required Post Acceptance Submission | D4
N-2016-21390 | 2016/08/26 | CLOSED | D2O Project 16-31555- Worker bumped head | D3
N-2016-21436 | 2016/08/26 | CLOSED | 16-31555 D2O West Annex Electrical Design Issues | C3-NFE
N-2016-21528 | 2016/08/29 | CLOSED | D2O Project 16-31555- Material issued from stores on EPC contract | D4
N-2016-21579 | 2016/08/29 | CLOSED | D20 West Annex New Construction Job #16-31555 - Worker reported discomfort in Ribs while handling material | D3
N-2016-21676 | 2016/08/30 | CLOSED | D20 West Annex New Construction DNGS Job #16-31555 - Worker stung by bee while attending OPG training offsite | D4
N-2016-21677 | 2016/08/30 | CLOSED | Project # 16-31555 D2O Storage: Overtime not pre-approved | D4
N-2016-21832 | 2016/09/01 | CLOSED | D2O Project16-31555- Crane Failure Causing Stranded Load | D4
N-2016-21957 | 2016/09/02 | CLOSED | DNGS West Annex New Construction #16-31555. Workers were observed not using proper access/egress route | D4
N-2016-22037 | 2016/09/06 | CLOSED | D2O West Annex New Construction DNGS Job # 16-31555 - Worker Cut on Forehead | C3
N-2016-22227 | 2016/09/07 | CLOSED | D2O Project 16-31555- Dropped Object | D3
N-2016-22251 | 2016/09/08 | CLOSED | D2O WestAnnex New Construction Job# 16-31555 Intial Welding Arc Flash Thought and Reported - Vendor Categorized as a Non Occupational Injury to Worker | NE0
N-2016-22319 | 2016/09/08 | CLOSED | D20 Project 16-31555 Rework Required to Remove and Reinstall Ductwork | D4
N-2016-22368 | 2016/09/09 | CLOSED | DNGS- D2O Wesyt Annex New Construction Job# 16-31555 - RFRISA Fire Alarm System Disengaged by SERM, Due to false Alarmings | D3
N-2016-22611 | 2016/09/12 | CLOSED | 16-31555 D2O Stair Anchor Bolts Installation Missed in 100m Slab Pour | D3
N-2016-22695 | 2016/09/12 | CLOSED | Project 16-31555: Lesson Learned - MDR Revision Required | D4
N-2016-23004 | 2016/09/15 | CLOSED | Project 16-31555- D20 West Annex -Minor Foot Injury | D3
N-2016-23050 | 2016/09/15 | CLOSED | Project # 16-31555 D2O Storage: DEC 121323 HVAC System - Steam Supply to VFHX: Missing Steam Traps and condensate collection | D3
N-2016-23052 | 2016/09/15 | CLOSED | Project # 16-31555 D2O Storage: HVAC / Chilled Water System Design Deficiencies – Multiple DECs require revision | D3
N-2016-23195 | 2016/09/17 | CLOSED | Project 16-31555- D20 West Annex Fuel Smell in Pipe Chase Excavation | D4
N-2016-23196 | 2016/09/17 | CLOSED | # 16-31555 RP unable to supply adequate support for HWMB | D4
N-2016-23348 | 2016/09/19 | CLOSED | Project # 16-31555 D2O Storage: DEC 120492 Fixed Area Alarming Tritium Monitors (FAATM) requires revision | D3
N-2016-23409 | 2016/09/20 | CLOSED | # 16-31555 Delay for D2O transfer in HWMB | D4
N-2016-23507 | 2016/09/21 | CLOSED | D2O Project 16-31555 Delay - Wrong cable for the power up of PA trailers / wash car shipped from the vendor. | D4
N-2016-23521 | 2016/09/21 | CLOSED | # 16-31555 D2O project delay to planned work | D4
N-2016-23522 | 2016/09/21 | CLOSED | 16-31555 D2O transfer unable to continue with planned work | D4
N-2016-23699 | 2016/09/22 | CLOSED | 16-31555 D20 West Annex - Project Inadequate Quality Control Documentation | D3
N-2016-23723 | 2016/09/22 | CLOSED | Worker put TLD through X-RAY machine at RPO - D20 Project 16-31555 | NE0
N-2016-23872 | 2016/09/23 | CLOSED | 16-31555 - DNGS D20 West Annex New Construction - Worker in Tunnel Excavation - PPE non-compliance | D4
N-2016-23966 | 2016/09/25 | CLOSED | DNGS - D20 West Annex New Construction job #16-31555 Worker felt discomfort in his lower back after moving material | D3
N-2016-24062 | 2016/09/26 | CLOSED | 16-31555 D2O Delay From Vac Truck Sent Offsite | D4
N-2016-24069 | 2016/09/26 | CLOSED | 16-31555 Less than Adequate Planning | D4
N-2016-24121 | 2016/09/27 | CLOSED | 16-31555 Rebar Dowels Bent without Engineering Approval | D3
N-2016-24535 | 2016/09/30 | CLOSED | DNGS - D20 West Annex New Construction. Job#16-31555 - Drilling Machine Gasket Malfunction Delay | D4
N-2016-24665 | 2016/10/03 | CLOSED | 16-31555 Delay of One Day to Critical Path of Structural Steel Erection | D4
N-2016-24668 | 2016/10/03 | CLOSED | 16-31555 Delay of 1.5 Days to Critical Path for Structural Steel Erection | D4
N-2016-24704 | 2016/10/03 | CLOSED | D20 West Annex New Construction - #16-31555 - Encountered Foul-Smelling Water during Drilling of Micropile | D4
N-2016-24845 | 2016/10/05 | CLOSED | D20 West Annex 16-31555 Work Coordination issue | D4
N-2016-24918 | 2016/10/06 | CLOSED | D20 West Annex job#16-31555 - Drill Machine Malfunction Delay | D4
N-2016-25026 | 2016/10/07 | CLOSED | 16-31555 - delay of planned work | D4
N-2016-25030 | 2016/10/07 | CLOSED | 16-31555 Delay to planned work | D4
N-2016-25037 | 2016/10/07 | CLOSED | 16-31555 - unable to access planned work | D4
N-2016-25318 | 2016/10/12 | CLOSED | D2O Project 16-31555 - Unable to pour concrete | D4
N-2016-25584 | 2016/10/14 | CLOSED | Project 16-31555: ECC Guide Exception | D4
N-2016-25585 | 2016/10/14 | CLOSED | 16-31555 - Delay to planned work | D4
N-2016-25676 | 2016/10/17 | CLOSED | Project # 16-31555: Human Performance - Missing FME caps on pipe spools during field walkdown - D2O Storage Facility | D3
N-2016-25677 | 2016/10/17 | CLOSED | Project # 16-31555: Human Performance - S.S. Piping Resting on C.S. Hanger (galvanic corrosion) - D2O Storage Facility | D3
N-2016-25679 | 2016/10/17 | CLOSED | Product Quatity Issue: Error in Engineering Change during OPG CWP prior approval - Project # 16-31555 (D2O Storage) | D4
N-2016-25770 | 2016/10/18 | CLOSED | D2O Project 16-31555- Mechanical Failure Causing Delay to Critical Path | D4
N-2016-25792 | 2016/10/18 | CLOSED | DNRU2: Project # 16-31555 D2O Storage: EC 120474 approval without a formal grounding calculation report | D4
N-2016-25824 | 2016/10/18 | CLOSED | 16-31555 Transfer of D2O - delay of planned work | D4
N-2016-25826 | 2016/10/18 | CLOSED | 16-31555 D20 Project - Contractor bypassed Hold points and are not following Contractor's ITP | D3
N-2016-25962 | 2016/10/19 | CLOSED | Project # 16-31555 D2O Storage: 13.8kV/600V Metal Enclosed Switchgear and Transformer - Technical Specification requires revision | D3
N-2016-26036 | 2016/10/20 | CLOSED | 16-31555 Transfer of D2O delay of planned work | D4
N-2016-26055 | 2016/10/20 | CLOSED | Project # 16-31555: Human Perfromance - Bypass of ANI Material Inspection Witness Activity Prior to Installation of Spools. | D3
N-2016-26059 | 2016/10/20 | CLOSED | 16-31555 Delay due to weather | D4
N-2016-26122 | 2016/10/21 | CLOSED | 16-31555 D2O Rework > Removal of Ductwork installed out of sequence | D3
N-2016-26158 | 2016/10/21 | CLOSED | 16-31555 - Contractor personnel not using Mitre Finch | D3
N-2016-26422 | 2016/10/25 | CLOSED | 16-31555, D20 Storage Building - Procedural Non-Compliance - Tape used as FME Barrier | D3
N-2016-26434 | 2016/10/25 | CLOSED | 16-31555, D2O Storage Facility - Procedural and ITP Non-compliance | D3
N-2016-26454 | 2016/10/25 | CLOSED | Project 16-31555: Lesson Learned - MDR Revision Required | D4
N-2016-26481 | 2016/10/25 | CLOSED | D20 Project # 16-31555 construction delay | D4
N-2016-26485 | 2016/10/25 | CLOSED | D20 Project # 16-31555 construction delay/FME issue | D4
N-2016-26689 | 2016/10/27 | CLOSED | 16-31555 Delay to Critical path steel Erection | D4
N-2016-26780 | 2016/10/28 | CLOSED | D20 Project 16-31555 -Delay for Planned work | D4
N-2016-26888 | 2016/10/29 | CLOSED | 16-31555, D2O Storage Facility - Found Comprehensive Work Package with major deficiencies. | D3
N-2016-27086 | 2016/11/01 | CLOSED | 16-31555, D2O - Lack of FME controls during installation of 0-38110-NV1261 & NV1185 & Spool 23-1C. | D3
N-2016-27093 | 2016/11/01 | CLOSED | 16-31555, D2O - Lack of attention to detail - Procedural Non-Compliance. | D3
N-2016-27156 | 2016/11/01 | CLOSED | Project 16-31555: Delay ESM ll computor system not working | D4
N-2016-27528 | 2016/11/05 | CLOSED | 16-31555 Delay of planed work in HWMB | D4
N-2016-27553 | 2016/11/06 | CLOSED | DNGS West Annex New Construction #16-31555. Worker Pinches finger while Material Handling. | D3
N-2016-27595 | 2016/11/07 | CLOSED | 16-31555, D2O - Electrical Distribution Lighting- Process Issue; Not following FIC process | D3
N-2016-27688 | 2016/11/07 | CLOSED | Project #16-31555 - Worker complained of stiffness and swelling in knee | D4
N-2016-27726 | 2016/11/08 | CLOSED | 16-31555, D2O Storage Facility - Lack of Attention to Detail - Procedural Non Adherence - By-pass OPG witness activity | D3
N-2016-27768 | 2016/11/08 | CLOSED | Project # 16-31555 D2O – Design deficiencies for Demineralized Water System - EC# 120428 (HWMB West Annex) | D3
N-2016-27821 | 2016/11/08 | CLOSED | Project 16-31555 - Loss of Quality Control of Nuclear Class 3 DIOTS Valve 0-38110-V1001 | CO3
N-2016-27884 | 2016/11/09 | CLOSED | Project 16-31555: Deviation from N-PROC-MP-0090 to allow HWMB system energization (EC 120452) | D4
N-2016-28005 | 2016/11/10 | CLOSED | 16-31555 D2O Delay to Structural Steel Completion | D4
N-2016-28067 | 2016/11/11 | CLOSED | D2O Project 16-31555- Worker observed standing on handrail of EWP | D3
N-2016-28146 | 2016/11/12 | CLOSED | 16-31555 Delay of planned work in HWMB | D4
N-2016-28226 | 2016/11/14 | CLOSED | 16-31555 Delay of planned work in HWMB | D4
N-2016-28283 | 2016/11/14 | CLOSED | 16-31555, D20 - Procedural Non-Compliance - Bypass of QC & ANI Material Inspection/Reciept Inspection Activities Prior to Installation of Spools. | D3
N-2016-28285 | 2016/11/14 | CLOSED | 16-31555, D2O - Procedural Non-Compliance - Bypass of ANI Material Witness Activity Prior to Subdividing of Material. | D4
N-2016-28423 | 2016/11/15 | CLOSED | 16-31555 - Unapproved Material on site | D3
N-2016-28457 | 2016/11/16 | CLOSED | 16-31555 Delay of planed work in HWMB | D4
N-2016-28598 | 2016/11/17 | CLOSED | 16-31555, D2O - Procedural Non-Compliance-CL3 shop welds plan to be installed without a system pressure test deviating from N285.0-08;Clause 14.7.1.1 | D4
N-2016-28697 | 2016/11/18 | CLOSED | Project 16-31555 (D2O Storage Facility): 0-38110-V949 and -V947 potentially loose manufactured locking feature | D3
N-2016-28701 | 2016/11/18 | CLOSED | Project 16-31555 (D2O Storage Facility): Challenges in completing shielding analysis | D3
N-2016-28727 | 2016/11/18 | CLOSED | DNGS 16-31555 HWMB un-authorized removal of SATM area for Nuclear Class 3 DIOTS Valve 0-38110-V1001 | C3-NFE
N-2016-28880 | 2016/11/21 | CLOSED | 16-31555, D2O - Procedural Non-Compliance - No material subdividing identified in the ITP / Bypass of FE witness point. | D4
N-2016-28884 | 2016/11/21 | CLOSED | 16-31555, D2O - Quality Oversight CWP Deficiency | D3
N-2016-28915 | 2016/11/21 | CLOSED | 16-31555, D2O - Process Not Followed - Installation of Ducting without QA/QC Vendor oversight. | D3
N-2016-28999 | 2016/11/22 | CLOSED | D20 Project 16-31555: Scaffold worker metal flake in eye | D3
N-2016-29000 | 2016/11/22 | CLOSED | 16-31555 Improper Resource Allocation | D4
N-2016-29001 | 2016/11/22 | CLOSED | Safety Observation D2O Project 16-31555 | D3
N-2016-29010 | 2016/11/22 | CLOSED | D20 Project 16-31555 Scaffold worker metal flake in eye | NE0
N-2016-29312 | 2016/11/24 | CLOSED | Paired Behaviour Based Observation project 16-31555 | D3
N-2016-29329 | 2016/11/25 | CLOSED | # 16-31555 Delay due to inclement weather. | D4
N-2016-29564 | 2016/11/28 | CLOSED | Project # 16-31555 D2O Storage: Additional FICREQs required for EC 123130 | D4
N-2016-29607 | 2016/11/28 | CLOSED | 16-31555, D20 - Procedural Non-Compliance - Sign-off of ITP Hold/Witness point prior to quaility records being completed. | D3
N-2016-29998 | 2016/12/02 | CLOSED | P#16-31555: Commissioning Report Signed Before Completion of All Activities (D2O Project, HWMB West Annex) | D3
N-2016-30026 | 2016/12/03 | CLOSED | D2O West Annex New Construction DNGS Job#16-31555- Aerial Lift Contact with Compressor | D3
N-2016-30211 | 2016/12/06 | CLOSED | 16-31555:D2O Procedural Non-Compliance - Deck Welding Hold Point Bypassed | D3
N-2016-30216 | 2016/12/06 | CLOSED | 16-31555 D2O; Ductwork Relocation due to Electrical Cable Tray Clash | D4
N-2016-30295 | 2016/12/06 | CLOSED | D2O West Annex New Construction DNGS Job# 16-31555 - Inclement Weather | D4
N-2016-30427 | 2016/12/08 | CLOSED | 16-31555, D2O - M&TE Pressure Test Gauges returned to FEE in bad condition. | D3
N-2016-30584 | 2016/12/09 | CLOSED | 16-31555 Missing TLD badge from RPO badge rack | D4
N-2016-30594 | 2016/12/09 | CLOSED | 16-31555: Worker Tweaked Back | D4
N-2016-30630 | 2016/12/10 | CLOSED | 16-31555 - Fumes in TRF building due to Generator | D4
N-2016-30632 | 2016/12/10 | CLOSED | 16-31555 - Sparks Ignited tarp Causing fire (WER) | C3-NFE
N-2016-30659 | 2016/12/11 | CLOSED | D2O West Annex New Construction DNGS Job# 16-31555 - Delay Due To Inclement Weather | D4
N-2016-30938 | 2016/12/14 | CLOSED | D2O Project 16-31555 > Contract Management Process > Oversight Observation | D3
N-2016-31008 | 2016/12/15 | CLOSED | P#16-31555 (HWMB West Annex): Deviation from Requirements on Availability of Critical Spare Parts (EC 120402) | D3
N-2016-31042 | 2016/12/15 | CLOSED | 16-31555: Missing/Switched Radiation Alarm Units (EC 120492) - West Annex | D3
N-2016-31222 | 2016/12/16 | CLOSED | D2O West Annex New Construction DNGS Job# 16-31555 - Inclement Weather | D4
N-2016-31450 | 2016/12/20 | CLOSED | 16-31555 D2O Improper Tie-off Point | D4
N-2016-31451 | 2016/12/20 | CLOSED | 16-31555 Late Incident Reporting > Slip at D9 trailers | D4
N-2016-31482 | 2016/12/20 | CLOSED | 16-31555 D2O Concurrent Delay Due to Bolting Quality Issues | D3
N-2016-31597 | 2016/12/21 | CLOSED | D20 West Annex New Construction job#16-31555. Worker noticed their TLD badge was not in Rack at ASB | D4
N-2016-31603 | 2016/12/22 | CLOSED | D20 West Annex New Construction job#16-31555. Worker noticed their TLD badge was not in the rack at the RPO | D4
N-2016-31624 | 2016/12/22 | CLOSED | 16-31555 – Hot Work suspended in HWMB | D4
N-2016-31647 | 2016/12/22 | CLOSED | P#16-31555: COMS and ITF non-compliance with governance on HWMB West Annex project | D4
N-2016-31657 | 2016/12/22 | CLOSED | P#16-31555 (D2O): Miscommunication about system energization: EC120428 Demin Water (West Annex) | D3
N-2016-31768 | 2016/12/23 | CLOSED | 16-31555 D2O Missed Trade Coordination causing standby of backfill crew | D3
N-2017-00038 | 2017/01/02 | CLOSED | DNGS West Annex New Construction job#16-31555. Late Reporting : Worker complained of sore neck. | D4
N-2017-00092 | 2017/01/03 | CLOSED | P# 16-31555: Issues Regarding Procedure Action Requests (TPARs), D2O Storage (West Annex) Project | D4
N-2017-00095 | 2017/01/03 | CLOSED | P# 16-31555: Field Initiated Change (FIC) not in Asset Suite - Procedural Non-Compliance (D2O storage, West Annex ) | D4
N-2017-00298 | 2017/01/06 | CLOSED | 16-31555 Delay to planned work | D4
N-2017-00299 | 2017/01/06 | CLOSED | 16-31555 Hand Geomertry not working to allow access to PA causing delay | D4
N-2017-00302 | 2017/01/06 | CLOSED | 16-31555 Contractors choice of hoisting equipment inappropriate for task | D4
N-2017-00491 | 2017/01/09 | CLOSED | P# 16-31555 (D2O) - Risk Associated with Inactive Plant Drainage System connection to HWMB LPSW discharge line (West Annex, EC#120643) | D4
N-2017-00514 | 2017/01/09 | CLOSED | P#: 16-31555 Late Identification of Tie-in Workplans (West Annex, D2O Project) | D3
N-2017-00548 | 2017/01/10 | CLOSED | Project 16-31555 Worker received small skin abrasion on forearm | D3
N-2017-00647 | 2017/01/10 | CLOSED | DNGS West Annex New Conctruction. Job#16-31555 - Inclement Weather Hoisting Delay | D4
N-2017-00733 | 2017/01/11 | CLOSED | 16-31555 D2O Workers not Aware of CWP Requirements | D4
N-2017-00798 | 2017/01/12 | CLOSED | 16-31555, D2O - Procedural Non-Compliance - Design deviation outside of installation tolerances and ITP signed off accepting deviation. | D3
N-2017-00894 | 2017/01/13 | CLOSED | 16-31555 D20 Project Structural Steel Elevations Incorrect delay slab pour | D4
N-2017-00955 | 2017/01/13 | CLOSED | 16-31555 D2O Insufficient Hoarding on 107-2 Slab Pour | D4
N-2017-01016 | 2017/01/14 | CLOSED | 16-31555, D2O Storage Fac. - CWP signed as accepted before suporting documents signed as approved. | D3
N-2017-01024 | 2017/01/14 | CLOSED | D2O Project 16-31555 --Fall Protection Equipment Inspection Dates | D3
N-2017-01105 | 2017/01/16 | CLOSED | 16-31555 D2O West Annex - Procedural Non-Compliance – Drilling without a CDAC | C3-NFE
N-2017-01178 | 2017/01/17 | CLOSED | DNGS - West Annex New Construction. Job #16-31555. Worker rolled ankle on walkway | D3
N-2017-01232 | 2017/01/17 | CLOSED | 16-31555, D2O Storage Fac. - QS Oversight report of vendor ITP deficiencies. | D4
N-2017-01298 | 2017/01/18 | CLOSED | DNGS D20 West Annex New Construction. Job #16-31555 Inclement Weather (wind and rain) | D4
N-2017-01402 | 2017/01/18 | CLOSED | D20 project 16-31555 Worker Felt Discomfort In Right Eye | D3
N-2017-01692 | 2017/01/21 | CLOSED | 16-31555, D2O Storage Fac. - Vendor CWP is not FME procedurally compliant. | D4
N-2017-01762 | 2017/01/23 | CLOSED | 16-31555 D2O Delay of Panel Install on Elev 115 by One day | D4
N-2017-01887 | 2017/01/24 | CLOSED | 16-31555 D2O Storage Facility - New stainless piping found to be rusting | D3
N-2017-01888 | 2017/01/24 | CLOSED | 16-31555 D2O West Annex - Non Compliance to Design Drawings - Wrong anchors installed for handrail installation | D3
N-2017-02179 | 2017/01/26 | CLOSED | P# 16-31555 (D2O Storage): use of obsolete drop-in anchors (change not communicated to design agencies) | D3
N-2017-02274 | 2017/01/27 | CLOSED | Project # 16-31555 D2O Storage: TMOD Removed before Ops Acceptance | D4
N-2017-02307 | 2017/01/27 | CLOSED | DNRU2 - Proj. 16-31555 - Deviation to request to allow energization of EC120427 - Domestic Water Tie-in without FIC incorporation | D4
N-2017-02314 | 2017/01/27 | CLOSED | DNGS West Annex New Construction #16-31555. Inclement Weather - High Winds. No Crane-Hoisting tonight | D4
N-2017-02376 | 2017/01/29 | CLOSED | 16-31555, D2O Storage Fac. - Vendor CWP is not FME procedurally compliant. | D4
N-2017-02563 | 2017/01/31 | CLOSED | P#16-31555 - Inactive and Active Plant Drainage System require flushing (HWMB West Annex) | D4
N-2017-02739 | 2017/02/01 | CLOSED | 16-31555 D20 Project > Delay to Backfill of Pipe Chase | D4
N-2017-03047 | 2017/02/06 | CLOSED | P#16-31555: Delay to Tie-in for Fire Protection Water Supply (0-78110-V552, DEC120720) | D4
N-2017-03096 | 2017/02/06 | CLOSED | Project # 16-31555 D2O Storage: Delay in entering FIC Attributes in Asset Suite | D4
N-2017-03113 | 2017/02/07 | CLOSED | 16-31555 D20 Project HWMB delay >RP modifications to Rep | D4
N-2017-03117 | 2017/02/07 | CLOSED | D20 project 16-31555 Cross Contamination of Stainless Material From Improper Storage | D4
N-2017-03125 | 2017/02/07 | CLOSED | D20 project 16-31555 Delay of Precast Installation Because of missing Structural Steel | D4
N-2017-03162 | 2017/02/07 | CLOSED | 16-31555, D2O west annex - Review of Contractors ITP found to be Unacceptable. | D3
N-2017-03272 | 2017/02/08 | CLOSED | 16-31555 D2O Project: Abrasion Hazard due to Metallic Wire | D4
N-2017-03362 | 2017/02/09 | CLOSED | D20 project 16-31555 > 3day Delay to Precast Panel Installation Due to inadequate Subcontract Management/Planning | D4
N-2017-03398 | 2017/02/09 | CLOSED | D20 Project 16-31555 Worker pinched finger in garbage can lid | D3
N-2017-03518 | 2017/02/10 | CLOSED | 16-31555: D20 Project - Safety Observation - Unapproved Rigging Practice | D3
N-2017-03541 | 2017/02/10 | CLOSED | D20 Project 16-31555 EC Design fall protection gate removed to add kick plate during precast hoisting/installation | D3
N-2017-03544 | 2017/02/10 | CLOSED | D20 Project> 16-31555 2 Day Delay to Masonry Walls because of missing dowels | D4
N-2017-03549 | 2017/02/10 | CLOSED | 16-31555 Delay to Precast panel Installation at HVU5 Louvre (Part 2) | D4
N-2017-03557 | 2017/02/10 | CLOSED | 16-31555 - Someone else's TLD badge in badge rack (ASB) | D4
N-2017-03627 | 2017/02/13 | CLOSED | 16-31555 Winter jacket taken from RPO coat storage | D4
N-2017-03938 | 2017/02/15 | CLOSED | D20 project > 16-31555 Delay to Precast Installation at D2O | D4
N-2017-04089 | 2017/02/16 | CLOSED | D20 Storage Project 16-31555: Cross contamination of stainless material due to improper storage - Repeat event | D4
N-2017-04438 | 2017/02/21 | CLOSED | D20 Construction Project #16-31555 - Worker felt slight discomfort in middle back | D3
N-2017-04456 | 2017/02/22 | CLOSED | 16-31555, D20 - Human Performance Issue - over-pressurization of spool test / process not followed | D3
N-2017-04459 | 2017/02/22 | CLOSED | 16-31555 D2O Structural Steel Fabrication Incorrect | D4
N-2017-04491 | 2017/02/22 | CLOSED | DNRU2 EPC submitted HDOC with Design Report for NC3 valve not sent for OPG acceptance | D4
N-2017-04729 | 2017/02/24 | CLOSED | 16-31555 D2O Late Radiography Shot Plan Causes Delay of Upgrader Tie-in | D4
N-2017-05055 | 2017/02/28 | CLOSED | 16-31555 Transfer of D2O delay of planned work | D4
N-2017-05069 | 2017/02/28 | CLOSED | Project # 16-31555 HWMB West Annex - Newly installed manual diaphragm valves require adjustment of travel stop | C3-NFE
N-2017-05238 | 2017/03/02 | CLOSED | 16-31555 High Tritium Count Abnormal Condition | D4
N-2017-05260 | 2017/03/02 | CLOSED | 16-31555, D2O West Annex - Review of contractors CWP/ITP was found to be unacceptable. | D4
N-2017-05280 | 2017/03/02 | CLOSED | 16-31555, D2O - Product Quality Issue - Installed pipe spools require rework due to incorrect weld-o-lets installed. | D3
N-2017-05282 | 2017/03/02 | CLOSED | 16-31555, D2O - Product Quality Issue - Rework weld-o-let due to insufficient weld. | D3
N-2017-05308 | 2017/03/02 | CLOSED | DNGS - D20 West Annex New Construction Job #16-31555 - Inclement Weather, High Winds | D4
N-2017-05358 | 2017/03/03 | CLOSED | Non work related medical issue - 16-31555 | D4
N-2017-05399 | 2017/03/03 | CLOSED | DNGS west annex new construction job# 16-31555 High winds- crane shut down | D4
N-2017-05583 | 2017/03/07 | CLOSED | 16-31555 High Tritium Count Abnormal Condition | D4
N-2017-05885 | 2017/03/09 | CLOSED | P#16-31555 (D2O): Workplan not fully signed off - DEC120471 Seismic dike (West Annex) | D3
N-2017-06155 | 2017/03/13 | CLOSED | P# 16-31555 (D2O): Pipe Chase Leak (DEC 123130, HWMB West Annex) | C3-NFE
N-2017-06158 | 2017/03/13 | CLOSED | 16-31555, D2O west annex - 13.8 KV cable install, Review of Contrator's CWP/ITP was found to be Unacceptable. | D3
N-2017-06430 | 2017/03/16 | CLOSED | 16-31555 D2O Delay to Installation of Electrical Equipment | D3
N-2017-06464 | 2017/03/16 | CLOSED | P# 16-31555 (D2O): Design and Construction documentation does not require compliance with CSA N293 (legacy issue) | D3
N-2017-06877 | 2017/03/22 | CLOSED | P#16-31555 (D2O): Delay in Preparing Commissioning Workplans - Documentation Unavailable (HWMB West Annex) | D3
N-2017-06949 | 2017/03/23 | CLOSED | DNRU2 D2O Storage 16-31555: New purchase needed for D2O tanks cover gas pressure regulators | D4
N-2017-06953 | 2017/03/23 | CLOSED | DNRU2 D2O Storage 16-31555: Need supporting documentations for HWMB West Annex Lightning Protection | D4
N-2017-07060 | 2017/03/24 | CLOSED | 16-31555: Report Only back discomfort from faulty chair | D4
N-2017-07070 | 2017/03/24 | CLOSED | 16-31555 D20 Project delay crew stood down due to a first aid call | D4
N-2017-07074 | 2017/03/24 | CLOSED | 16-31555 Delay of X ray work in HWMB | D4
N-2017-07087 | 2017/03/24 | CLOSED | 16-31555 - Worker cut finger; First Aid | D3
N-2017-07329 | 2017/03/28 | CLOSED | D20 Project 16-31555 Job Box fell over | D3
N-2017-07452 | 2017/03/29 | CLOSED | 16-31555 - Keys removed from EWP's | D4
N-2017-07476 | 2017/03/29 | CLOSED | Delayed oversight reporting, D2O Project, 16-31555, Job Box Fell Over, Contract Management Office | D3
N-2017-07548 | 2017/03/30 | CLOSED | 16-31555, D2O West Annex - Review of Contractor CWP/ITP was found to be unacceptable. | D3
N-2017-07617 | 2017/03/30 | CLOSED | 16-31555 - Delay in Processing Step 2 Entries in Oncore | D4
N-2017-07772 | 2017/04/01 | CLOSED | 16-31555, D2O West Annex - Review of Contractor CWP/ITP was found to be unacceptable. | D3
N-2017-08023 | 2017/04/04 | CLOSED | DNRU2 D2O Storage 16-31555: Late deviation request from valve supplier after valve is in service 0-38110-V941 | C3-NFE
N-2017-08286 | 2017/04/06 | CLOSED | 16-31555 D20 Project >Delay to planned work activities | D4
N-2017-08345 | 2017/04/07 | CLOSED | 16-31555, D2O West Annex - Work performed in the field without a work package | D3
N-2017-08348 | 2017/04/07 | CLOSED | 16-31555, D2O West Annex - Anchor installation does not meet manufacturers requirements | D3
N-2017-08526 | 2017/04/10 | CLOSED | 16-31555, D2O - Product Quality Issue - ITP presented to OPG for prior approval and deficiencies were identified. | D3
N-2017-08628 | 2017/04/10 | CLOSED | 16-31555, D2O west Annex - Review of Contractor CWP/ITP was found to be unacceptable. | D3
N-2017-08671 | 2017/04/11 | CLOSED | 16-31555 D2O Storage: In-Storage Maintenance of Pumps Not Documented (HWMB West Annex) | D4
N-2017-08856 | 2017/04/12 | CLOSED | DNRU2 D2O Storage 16-31555: EC 120341 R03 change paper package returned to design contractor | D4
N-2017-08873 | 2017/04/12 | CLOSED | 16-31555 D20 Project >Delay of planned activities | D4
N-2017-08956 | 2017/04/13 | CLOSED | 16-31555 Delay of planned activities ( Duplicate see SCR N-2017-08833 generated earlier to document the issue) | D4
N-2017-09018 | 2017/04/14 | CLOSED | 16-31555, D2O - Product Quality Issue - ITP presented to OPG for prior approval and deficiencies were identified. | D3
N-2017-09108 | 2017/04/15 | CLOSED | 16-31555, D2O West annex - Review of Contractor CWP/ITP was found to be unacceptable. | D3
N-2017-09332 | 2017/04/19 | CLOSED | 16-31555 D2O Cable Tray Riser/Ductwork Interference | D3
N-2017-09882 | 2017/04/25 | CLOSED | P# 16-31555 (D2O): Shielding issues for Cables Installed to HWMB Computer DCU4 | D4
N-2017-13345 | 2017/06/05 | CLOSED | DNRU – Eng Services 16-31555 – PO 234115 for MEC 122797, 88528, 118632, 118880, 119824, 119821, 123676 – Vendor Onsite without PO | D4
N-2017-13570 | 2017/06/07 | CLOSED | 16-31555 Worker locked in building | D4
N-2017-13628 | 2017/06/08 | CLOSED | 16-31555 - Locks cut on Sea Container and tools missing | D3
N-2017-14818 | 2017/06/22 | COMPLETE | P#16-31555 (D2O): Challenges to complete TRF Upgrader Tie-In (EC# 120408, HWMB West Annex) | D3
N-2017-14838 | 2017/06/22 | CLOSED | D2O Project 16-31555 –HWMB WA Pipechase Exploratory Excavation Incident- Water | D4
N-2017-15899 | 2017/07/07 | CLOSED | DNRU2 - EC 120402 close out beyond 6 months - Proj 16-31555 (D2O Storage) | D4
N-2017-18613 | 2017/08/15 | CLOSED | P# 16-31555 (D2O): Diesel Fire suppression equipment differs from Technical Specification (HWMB West Annex) | D3
N-2017-18615 | 2017/08/15 | CLOSED | P#16-31555 (D2O): Stakeholder Concerns about the Vapour Recovery System (HWMB West Annex) | D4
N-2017-20474 | 2017/09/07 | CLOSED | D20 Project 16-31555 Tooling damaged 110v Cord plugged into a 220v Receptacle | D3
N-2017-20695 | 2017/09/11 | CLOSED | 16-31555, D20 West Annex - Installation not as per Design EC requirements | D3
N-2017-20720 | 2017/09/11 | CLOSED | 16-31555, D20 West Annex - Procedural Non-Compliance - Welding without documentation | D3
N-2017-20826 | 2017/09/12 | CLOSED | 16-31555, D20 West Annex - Unapproved material being installed in the field | D3
N-2017-21034 | 2017/09/14 | CLOSED | 16-31555, D20 West Annex - Non-compliance to manufacturers installation requirements for anchoring. | D3
N-2017-21068 | 2017/09/14 | CLOSED | West Annex Building D20 Project 16-31555 MCC Component tipped over during unload to 107 el floor | D2
N-2017-21727 | 2017/09/21 | CLOSED | D20 project 16-31555 rolled ankle | D3
N-2017-22097 | 2017/09/26 | CLOSED | D2O Project #16-31555- Worker felt unwell | D3
N-2017-22325 | 2017/09/28 | CLOSED | West Annex Building D20 Project 16-31555 Nuclear Oversight safety observation - Delay | D3
N-2017-22447 | 2017/09/29 | CLOSED | D20 Project 16-31555 HWMB 1 1/2" NSB3 failed welds | D3
N-2017-22672 | 2017/10/03 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design | D4
N-2017-22678 | 2017/10/03 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design | D4
N-2017-22709 | 2017/10/03 | CLOSED | 16-31555, D20 West Annex - Precast panel roof sealing rework required | D4
N-2017-22809 | 2017/10/04 | CLOSED | 16-31555, HWMB West Annex - No QC Support | D3
N-2017-23411 | 2017/10/12 | CLOSED | 16-31555, D20 West Annex - Unapproved material being installed in the field. Repeat Occurrence | D3
N-2017-23413 | 2017/10/12 | CLOSED | 16-31555, D2O West Annex - Work performed in the field without a work package. Repeat Occurrence | D3
N-2017-24046 | 2017/10/19 | CLOSED | 16-31555, D2O West Annex - Inadequate documentation control | D3
N-2017-25450 | 2017/11/03 | CLOSED | D2O Project 16-31555 scraped knee - late reporting | D3
N-2017-25453 | 2017/11/03 | CLOSED | D2O Project 16-31555 pinch finger | D3
N-2017-25964 | 2017/11/09 | CLOSED | D2O Project 16-31555 bumped shin on scaffold | D3
N-2017-26403 | 2017/11/15 | CLOSED | 16-31555, D2O Storage Facility - Procedure Non-Compliance: Vendor QA by-passed FE Witness Point for FME Inspection in HWMB | CO3
N-2017-26410 | 2017/11/15 | CLOSED | 16-31555, D2O Storage Facility - Human Performance Event: Foreign material discovered in HWMB piping during spool installation. | C3-NFE
N-2017-27148 | 2017/11/23 | CLOSED | Project # 16-31555 - Worker Fell Over Cinder Block When Fobbing Out At End Of Shift | D3
N-2017-27155 | 2017/11/23 | CLOSED | Missing TLD Project 16-31555 | D4
N-2017-27212 | 2017/11/24 | CLOSED | 16-31555, D2O West Annex - Non-compliance to Design | D3
N-2017-27526 | 2017/11/28 | CLOSED | 16-31555, D20 West Annex - Work being performed without a Comprehensive Work Package and Inspection Test Plan. Repeat Occurrence | D3
N-2017-27648 | 2017/11/29 | CLOSED | 16-31555, D2O Storage Facility - Human Performance / Product Quality Issue: QA records incomplete | D3
N-2017-28230 | 2017/12/06 | CLOSED | 16-31555, D20 West Annex - Procedural Non-Compliance: Engineering Documents not being uploaded into Asset Suite | D4
N-2017-28698 | 2017/12/11 | CLOSED | P#16-31555 (D2O): tie-in activity removed from TRF schedule / IPG Scope at T-5 (HWMB West Annex) | D4
N-2017-29029 | 2017/12/14 | CLOSED | D2O Project 16-31555 –Worker Scratches Forehead | D3
N-2017-29269 | 2017/12/18 | CLOSED | D2O Project 16-31555 > Safety Observation | D4
N-2017-29334 | 2017/12/19 | CLOSED | D2O Project 16-31555 –Worker Injures Left Ankle and Left Hip. | D3
N-2017-29605 | 2017/12/21 | CLOSED | P# 16-31555 – Purge Hose found connected during AFS Walkdown (HWMB WA Upgrader Tie-in, D2O Project ) | D4
N-2018-00141 | 2018/01/03 | CLOSED | P#16-31555: Upgrader Tie-in for West Annex - Extension required for turnover to Operations (DEC 120408, D2O Project) | D4
N-2018-00727 | 2018/01/11 | CLOSED | P#16-31555 - Walls 54 & 46 HVU5 Interferences (EC 120343) – D2O Project (West Annex) | D4
N-2018-00729 | 2018/01/11 | CLOSED | P#16-31555 – Lack of Design Detail for Causeway Steel Connection to HWMB – D2O Project (West Annex, EC 120906) | D4
N-2018-00796 | 2018/01/11 | CLOSED | 16-31555 - D20 Project - Worker slips on ice | D3
N-2018-01713 | 2018/01/22 | CLOSED | 16-31555 - D20 Project -Worker experiences pain in stomach | D3
N-2018-01716 | 2018/01/22 | CLOSED | 16-31555 - D20 project - HVAC temporary flexible ductwork flange came apart | C3-NFE
N-2018-01982 | 2018/01/25 | CLOSED | 16-31555, D2O Storage Facility - Procedural Non-Compliance 0-38110-HX6 & HX7 Name Plate removal without Owner and ANI prior approval | D3
N-2018-02458 | 2018/01/30 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design, Rework required | D3
N-2018-02460 | 2018/01/30 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design, Rework required | D3
N-2018-03130 | 2018/02/06 | CLOSED | 16-31555, D2O West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 120784 | D4
N-2018-03345 | 2018/02/08 | CLOSED | 16-31555, D2O Storage Facility - Procedural Non-Compliance - Repair work without OEM involvment and design documentation | D3
N-2018-03476 | 2018/02/09 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design, Rework required | D3
N-2018-03986 | 2018/02/15 | CLOSED | P#16-31555 - Turnover to Operations still outstanding - EC 120408 Upgrader Tie-in | D3
N-2018-03991 | 2018/02/15 | CLOSED | P#16-31555: Missed opportunity to implement recommendation of shielding analysis (D2O Project, HWMB West Annex) | D3
N-2018-04019 | 2018/02/15 | CLOSED | P#16-31555 ECC Non-Compliance: no turnover to Operations for partial tie-in, DEC 120406 (HWMB-WA, D2O Project) | D3
N-2018-04474 | 2018/02/22 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design, Rework required | D3
N-2018-04551 | 2018/02/23 | CLOSED | 16-31555, D2O Storage Facility - P.V. Nameplate removal without approval | D3
N-2018-05127 | 2018/03/01 | CLOSED | D2O Project 16-31555 - 600v welding cable pinched in floor hatchway (HWMB West Annex) | D3
N-2018-05441 | 2018/03/06 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design, Rework required | D3
N-2018-05442 | 2018/03/06 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design, Rework required | D3
N-2018-05654 | 2018/03/08 | CLOSED | 16-31555, D20 West Annex - Non-compliance to Design, Rework required | D3
N-2018-05924 | 2018/03/12 | CLOSED | P#16-31555: Moderator Tie in DEC 120401 Flow Diagram deficiency (D2O Project, HWMB West Annex) | D4
N-2018-07221 | 2018/03/27 | CLOSED | P#16-31555, D2O West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 120479 | D4
N-2018-07304 | 2018/03/28 | CLOSED | 16-31555, D20 West Annex - Work being performed without a Comprehensive Work Package and Inspection Test Plan. Repeat Occurrence | D3
N-2018-07421 | 2018/03/29 | CLOSED | 16-31555, D20 West Annex - Work being performed without a Comprehensive Work Package and Inspection Test Plan. Repeat Occurrence | D3
N-2018-07734 | 2018/04/03 | CLOSED | P#16-31555 D2O Storage Facility DIOTS Valve 1001 Tie-in, Incorrect PG9000 Tag | D4
N-2018-07870 | 2018/04/04 | CLOSED | P#16-31555 Plastic Suits Not Available in HWMB for EPC vendor work (DIOTS Valve 1001 Tie-in, D2O project) | D4
N-2018-08657 | 2018/04/12 | CLOSED | D20 Project 16-31555 misuse / inappropriate handling of TWE tooling | D3
N-2018-08980 | 2018/04/16 | CLOSED | P#16-31555: D2O building Chiller System Skids #1 and #2 - instrument isolation valves missing (HWMB West Annex) | D3
N-2018-09287 | 2018/04/19 | CLOSED | P#16-31555 - Lamp test button on new HVAC Control panel does not test all lamps (HWMB West Annex) | D3
N-2018-09406 | 2018/04/20 | CLOSED | 16-31555, D2O Storage Facility: Product Quality Issue - Change Control process to the ITP has not been maintained. | C3-NFE
N-2018-09427 | 2018/04/20 | CLOSED | 16-31555, D2O Storage Facility: Missing FME cap on Breathing Air prefabricated piping in basement of West Annex. | D3
N-2018-09599 | 2018/04/23 | CLOSED | 16-31555, D2O Storage Facility: Product Quality Issue - Change Control process has not been maintained for ITP. | D3
N-2018-09604 | 2018/04/23 | CLOSED | 16-31555, D2O Storage Facility: Product Quality Issue - QA documentation missing information for scope completion | D4
N-2018-09699 | 2018/04/24 | CLOSED | P#16-31555 - EC 120485 R02 returned on VenDM (HWMB West Annex) | D4
N-2018-10241 | 2018/04/30 | CLOSED | P#16-31555 HWMB West Annex Chiller skids to be shipped prior to OPG acceptance of design deviations | D3
N-2018-10316 | 2018/05/01 | CLOSED | P# 16-31555 (D2O)– EC120488 R003 submitted to OPG prior to completion of MEL update - HWMB West Annex | D4
N-2018-10773 | 2018/05/06 | CLOSED | 16-31555, D2O Storage Facility: Product Quality Issue - Change Control process has not been maintained within ITP | D3
N-2018-11012 | 2018/05/09 | CLOSED | P#16-31555 (D2O Project): Procurement of equipment including radioactive sources did not follow N-PROC-RA-0016 | D4
N-2018-11119 | 2018/05/10 | CLOSED | D2O Project 16-31555 Worker tripped and injured Left Knee | D3
N-2018-11122 | 2018/05/10 | CLOSED | Project # 16-31555 HWMB CAT ID PRD docs do not meet the requirements specific for existing OPG CAT ID | D3
N-2018-11603 | 2018/05/16 | CLOSED | D20 Project 16-31555 West Annex Building Water Ingress during rain event | D3
N-2018-11720 | 2018/05/17 | CLOSED | D20 Project # 16-31555 project oversight observation | D4
N-2018-11978 | 2018/05/22 | CLOSED | Project 16-31555 D2O -Configuration Management Issue - Duplicate MEL tag - EC121320 | D3
N-2018-12029 | 2018/05/22 | CLOSED | D20 Project 16-31555 Steel plate falling object | D3
N-2018-12223 | 2018/05/24 | CLOSED | P#16-31555 (D2O)– Last minute change from OEM caused disruption to OLW Support and EC 121805 R01 approval | D4
N-2018-12448 | 2018/05/28 | CLOSED | P# 16-31555 - Submission of Design EC 120489 for OPG Approval without closing the ITF items (D2O project) | D4
N-2018-12465 | 2018/05/28 | CLOSED | P#16-31555 Discrepancies between EC Change Papers and Manufacturer Documents - chilled water system (D2O Project) | D4
N-2018-12521 | 2018/05/29 | CLOSED | P# 16-31555 - Rework required for sub-contractor calculation NK38-DC-53300-10007 (D2O Project) | D4
N-2018-12925 | 2018/06/04 | CLOSED | DNR: EPC purchased nuclear class components NF-CL1 with no Cat ID. (project # 16-31555) | D4
N-2018-12940 | 2018/06/04 | CLOSED | P#16-31555 Delay to EC 120478 acceptance - Design basis documents not on ADL (D2O project, HWMB West Annex) | D4
N-2018-13469 | 2018/06/11 | CLOSED | D20 Project 16-31555, AR28213106 for NEW item CATID have QA selection Issues | D4
N-2018-13470 | 2018/06/11 | CLOSED | D2O Project # 16-31555 Approved EC 120474 has numerous quality issue in the MEL and BOM udpated by EPC Vendor | D3
N-2018-13679 | 2018/06/13 | CLOSED | P#16-31555 EC 120472 - Design basis documents not on ADL (D2O project, HWMB West Annex) | D4
N-2018-14039 | 2018/06/18 | CLOSED | P# 16-31555 (D2O): Vapour Recovery Dryer - Factory Acceptance Test repeated (HWMB West Annex) | D4
N-2018-14144 | 2018/06/20 | CLOSED | P# 16-31555 (D2O)- Missing info identified during OPG Design Acceptance Phase DEC 121319 (HWMB West Annex) | D4
N-2018-14157 | 2018/06/20 | CLOSED | D2O Project #16-31555 EPC purchased pressure boundary pipe caps without CRN requirement. | D3
N-2018-15962 | 2018/07/18 | CLOSED | Project#16-31555 Employees contaminated leaving site | D4
N-2018-16256 | 2018/07/24 | CLOSED | Project# 16-31555 Employees contaminated, late leaving site | D4
N-2018-16336 | 2018/07/25 | CLOSED | DNRU2 - Project # 16-31555 : Failed Storm Drainage Test ACE-18-13883 (WER) | D3
N-2018-16389 | 2018/07/25 | CLOSED | P#16-31555: Design basis documents not on ADL - EC 120475 (D2O project, HWMB West Annex) | D4
N-2018-16398 | 2018/07/25 | CLOSED | P#16-31555 (D2O): Excavation for SG Cable duct started before new Work Authorization was obtained (DEC 120340, HWMB West Annex) | D3
N-2018-16953 | 2018/08/03 | CLOSED | 16-31555, D2O Lift Plan Not Per Engineer Instructions | D3
N-2018-17453 | 2018/08/13 | CLOSED | Project# 16-31555 Employees late leaving work due to turnstile malfunction | D4
N-2018-17653 | 2018/08/15 | CLOSED | D20 Project 16-31555 Worker feeling unwell end of shift | D3
N-2018-17730 | 2018/08/16 | CLOSED | P#16-31555 (D2O): Open items for Design EC 120494 R01- HVAC Control EC (HWMB West Annex) | D4
N-2018-17747 | 2018/08/16 | CLOSED | D20 Project 16-31555 Worker feeling unwell at workface | D3
N-2018-17791 | 2018/08/17 | CLOSED | 16-31555, D2O Facility: Vendor CWP is missing ITP sign-offs and supporting documentation | D3
N-2018-17890 | 2018/08/20 | CLOSED | 16-31555, D2O Facility: Bypassed FME inspection witness point | D3
N-2018-18272 | 2018/08/24 | CLOSED | 16-31555, D2O West Annex - Lift Plan Deviating from Engineer's Approved methods | D3
N-2018-19247 | 2018/09/11 | CLOSED | 16-31555, D2O - Engineering change control process not followed. | D4
N-2018-19269 | 2018/09/11 | CLOSED | 16-31555, D2O Facility: Vendor CWP is missing ITP sign-offs and supporting documentation | D3
N-2018-19924 | 2018/09/19 | CLOSED | 16-31555, D2O Storage Facility - Backup Power (GEN SET) Cable Installation without the use of protective bushing. | D3
N-2018-19925 | 2018/09/19 | CLOSED | 16-31555 D2O Storage Facility - Improper use of Vendor Procedures, EC: 120477 | D3
N-2018-19929 | 2018/09/19 | CLOSED | 16-31555, D2O- M&TE Pressure Test Gauges returned to FEE in bad condition | D3
N-2018-20042 | 2018/09/20 | CLOSED | D20 Project 16-31555 Worker reports pain in right knee | D3
N-2018-20124 | 2018/09/21 | CLOSED | D2O Facility: Procedural Non-Compliance: Intent changes made to Installation ITP without review process - (16-31555) | D3
N-2018-20129 | 2018/09/21 | CLOSED | 16-31555, D2O Facility: FME Plan missing and FME inspection requirement not identified on Contractor ITP & CWP. | D3
N-2018-20304 | 2018/09/24 | CLOSED | D20 Project 16-31555 Worker experiencing chest tightness | D3
N-2018-20344 | 2018/09/25 | CLOSED | 16-31555 D2O Lift Plan Non-Conforming to Engineer's Instructions | D3
N-2018-20351 | 2018/09/25 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compliance: Contract Partner not in compliance with N-PROC-MP-0090 | D3
N-2018-20664 | 2018/09/28 | CLOSED | 16-31555, Damaged Embedded Ground Cable within Transformer 0-53300-T104.. EC# 120472. | D4
N-2018-20665 | 2018/09/28 | CLOSED | D20 project 16-31555 Worker bumps head | D3
N-2018-20698 | 2018/09/28 | CLOSED | D2O Project 16-31555 - Low Level Musculoskeletal Disorder (MSD) Trend Identified | D3
N-2018-20815 | 2018/10/01 | CLOSED | D20 Project 16-31555 Missing TLD Badge | D4
N-2018-21474 | 2018/10/10 | CLOSED | D2O Employee Chewing Gum Inside PA- Project # 16-31555 | D3
N-2018-21938 | 2018/10/17 | CLOSED | D2O Project 16-31555 Functionality issues found at existing electrical switchgear 0-53800-53-SW 3 | D4
N-2018-22415 | 2018/10/24 | CLOSED | 16-31555, D20 - Field work activities progressing without approved documentation. | D3
N-2018-23366 | 2018/11/06 | CLOSED | D20 Project 16-31555 Lost TLD Badge | D4
N-2018-23776 | 2018/11/12 | CLOSED | D20 Project 16-31555 Delay to schedule due to weather | D4
N-2018-23789 | 2018/11/12 | CLOSED | 16-31555, D2O Facility: Non standard field run hanger installation without design prior approval | D4
N-2018-23836 | 2018/11/13 | CLOSED | 16-31555, D2O Facility - Vendor QA inspections bypassed | D4
N-2018-24215 | 2018/11/19 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compliance: - Vendor QC using whiteout on QA records. | D4
N-2018-24391 | 2018/11/21 | CLOSED | D20 Project 16-31555 Worker feeling unwell | D4
N-2018-24404 | 2018/11/21 | CLOSED | 16-31555, D20 - Work completed prior to Comprehensive Work Package being relased to field. | D3
N-2018-24495 | 2018/11/22 | CLOSED | 16-31555, D20 Storage Facility: Unapproved FME covers used on stainless piping spool pieces | D4
N-2018-24855 | 2018/11/28 | CLOSED | 16-31555, D20 Storage Facility: Human Performance: Procedural Non Adherence – By-passed OPG Witness activity | D3
N-2018-24878 | 2018/11/28 | CLOSED | D2O Project 16-31555 Worker reports lower body injury | D3
N-2018-25675 | 2018/12/10 | CLOSED | D20 Project 16-31555 Damage to beetle drain conduit-rework | D3
N-2018-25692 | 2018/12/10 | CLOSED | 16-31555, D20 Storage Facility: Human Performance: QC Vendor ITP steps signed off without being verified complete in field. | D4
N-2018-26354 | 2018/12/20 | CLOSED | D2O Facility: Procedural Non-compliance - Vendor NCR process not followed - (Project No. 16-31555) | D4
N-2018-26356 | 2018/12/20 | CLOSED | Project No. 16-31555: Procedural Non-compliance - Vendor adding nuclear class material to ITP without appropriate QA activities & prior approvals. | D4
N-2018-26394 | 2018/12/20 | CLOSED | D2O Facility: Manufacturer recommended material storage requirements not being followed for nuclear class valve -(Project 16-31555) | D4
N-2018-26600 | 2018/12/28 | CLOSED | D2O Project 16-31555- Minor Equipment Damage | D4
N-2019-00549 | 2019/01/10 | CLOSED | 16-31555, D2O Facility: Bypassed witness points for OPG as left FME inspection. | D3
N-2019-00640 | 2019/01/11 | CLOSED | 16-31555, D2O Facility: Field Engineering Witness Points Bypassed on Vendors Inspection and Test Plan. | D3
N-2019-00813 | 2019/01/14 | CLOSED | D20 Project 16-31555 Potential Working at Heights violation | D2
N-2019-01105 | 2019/01/18 | CLOSED | D20 Project # 16-31555 Foreign Material entered Tank | D3
N-2019-01909 | 2019/01/29 | CLOSED | 16-31555 - Strength of field cured concrete curb does not meet specified requirement - Delays in providing sufficient details to disposition NCR 261 | D4
N-2019-02133 | 2019/01/31 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compliance: Vendors ITP signed for final inspection with work still outstanding. | D3
N-2019-02612 | 2019/02/06 | CLOSED | P#16-31555, D2O West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 120340 | D4
N-2019-02613 | 2019/02/06 | CLOSED | P#16-31555, D2O West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 120476 | D4
N-2019-02615 | 2019/02/06 | CLOSED | P#16-31555, D2O West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 120488 | D4
N-2019-02616 | 2019/02/06 | CLOSED | P#16-31555, D2O West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 120493 | D4
N-2019-02618 | 2019/02/06 | CLOSED | #16-31555, D2O West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 121146 | D4
N-2019-02980 | 2019/02/12 | CLOSED | 16-31555, D2O Facility: Bypassed witness point for OPG to perform 2nd as left FME inspection during the installation of Valve. | D3
N-2019-02990 | 2019/02/12 | CLOSED | 16-31555, D2O Facility: Pipe Spools require Rework after being accepted during receiving inspection. | D3
N-2019-03075 | 2019/02/13 | CLOSED | 16-31555 -Candy Bar Wrapper found in waste bag from Drum room on the 87m of D2O West Annex | D3
N-2019-03095 | 2019/02/13 | CLOSED | 16-31555 D20 Project -Dropped Object While Traversing Off A Scaffold On The 107' | D3
N-2019-03790 | 2019/02/21 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compliance - Vendor not conforming to nonconformance and corrective action procedures. | D3
N-2019-03793 | 2019/02/21 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compliance - Vendor not conforming to non conformance and corrective action procedures. | D3
N-2019-03823 | 2019/02/21 | CLOSED | Worker Experianced Dizziness And Nausea In RFRISA - D2O West Annex Project#16-31555 | D4
N-2019-03854 | 2019/02/22 | CLOSED | 16-31555, D2O Facility: Vendor bypassed OPG Quality Surveillance (FME) Witness Inspection Activity. | D3
N-2019-03859 | 2019/02/22 | CLOSED | 16-31555, D20 Facility: Foreign Material (FME) identified inside installed Nuclear Class 3 diaphragm valve | D3
N-2019-03870 | 2019/02/22 | CLOSED | 16-31555, D2O Facility: Bypassed witness points for OPG as left FME inspection. | D3
N-2019-04054 | 2019/02/25 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compliance - Vendor not conforming to nonconformance and corrective action procedures. | D4
N-2019-04120 | 2019/02/26 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compleance - Vendor not following their noncorformance process. | D4
N-2019-04122 | 2019/02/26 | CLOSED | D2O Facility: Procedural Non-Compliance - Vendor not conforming to nonconformance procedure for repair/rework & ITP control of new material(16-31555) | D4
N-2019-05307 | 2019/03/13 | CLOSED | 16-31555, D2O Storage Facility: By-passed OPG Witness Activity | D4
N-2019-05310 | 2019/03/13 | CLOSED | 16-31555, D2O Facility - Vendor QA/TSSA/OPG Material inspections bypassed | D4
N-2019-05530 | 2019/03/15 | CLOSED | 16-31555, D2O Facility: Procedural Non-Compliance - Vendor not following their noncorformance process. | D4
N-2019-05535 | 2019/03/15 | CLOSED | 16-31555, D2O Facility: Disposition on Nonconformance did not match Field Conditions | D4
N-2019-05660 | 2019/03/18 | CLOSED | 16-31555 - D20 Project -Worker unwell start of shift | D3
N-2019-05692 | 2019/03/18 | CLOSED | 16-31555 D20 Project Worker Working at Heights exposure | D3
N-2019-05852 | 2019/03/20 | CLOSED | 16-31555 D2O Project - TCR-FAR was not prepared to Demineralized Water Flowsheet update before tie-in | D4
N-2019-05937 | 2019/03/21 | CLOSED | 16-31555: D2O Facility: Bypassed FME inspection witness point. | D4
N-2019-05961 | 2019/03/21 | CLOSED | 16-31555 D20 Project schedule issue - delays | D4
N-2019-06169 | 2019/03/25 | CLOSED | 16-31555 - D2O storage facility - quality documentation do not meet the requirements of the vendor QA manual. | D4
N-2019-06267 | 2019/03/26 | CLOSED | 16-31555 - D2O Storage Facility - Quality documentation does not meet the requirements of the vendor QA manual | D4
N-2019-06513 | 2019/03/28 | CLOSED | 16-31555 D20 Project - EWP(elevated work platform) damaged building lighting fixture | D3
N-2019-06580 | 2019/03/29 | CLOSED | D20 Project 16-31555 - Worker's hard hat comes in contact with electrical box | D3
N-2019-06693 | 2019/04/01 | CLOSED | 16-31555 D2O Storage Facility - ITP non compliance | D3
N-2019-06955 | 2019/04/03 | CLOSED | D20 Project 16-31555 - Falling Object (dropped tape measure) | D3
N-2019-07070 | 2019/04/05 | CLOSED | 16-31555 - D2O Storage Facility - Quality documentation does not meet the requirements of the vendor QA manual | D4
N-2019-07392 | 2019/04/11 | CLOSED | 16-31555, D20 Storage Facility - Control Distribution Frame (CDF) Rack Labeled Incorrectly | D4
N-2019-07510 | 2019/04/12 | CLOSED | Project 16-31555 D2O - Design EC 120670 Part of MEC 119824 proceeded to closeout without OLW statused | D4
N-2019-08352 | 2019/04/29 | CLOSED | 16-31555, Vendor Partner signed off Construction Completion Assurance prior to addressing open items. | D4
N-2019-08355 | 2019/04/29 | CLOSED | 16-31555, Engineering Change (EC) set to Modified prior to Comprehensive Work Package (CWP) Inspection and Test Plan (ITP) sign off. | D4
N-2019-08566 | 2019/05/02 | CLOSED | D20 Project 16-31555 ERT contacted | D4
N-2019-08618 | 2019/05/03 | CLOSED | 16-31555, D2O: Ground wire found removed from terminal block after Quality Control sign off | D3
N-2019-09123 | 2019/05/10 | CLOSED | D20 Project 16-31555 - Employee Proceeded Through WBM At The ASB Without Contacting RP | D3
N-2019-09291 | 2019/05/14 | CLOSED | D20 Project 16-31555 Dropped Object | D3
N-2019-09582 | 2019/05/21 | CLOSED | 16-31555, D2O Facility: Vendor Inspection & Test Plan - TSSA Material inspections witness point bypassed. | D3
N-2019-09648 | 2019/05/22 | CLOSED | 16-31555 HWMB-West Annex - Removal of Maintenance TPARs from Vendor's Scope | D4
N-2019-09649 | 2019/05/22 | CLOSED | 16-31555 HWMB-West Annex - Review of Operating Manuals by the Vendor removed from scope | D4
N-2019-10802 | 2019/06/12 | CLOSED | 16-31555: D2O Facility - Breathing Air tie-ins pressure test failure at weld #279 | D4
N-2019-11108 | 2019/06/18 | CLOSED | 16-31555, D2O Facility: NCR Not Signed by TSSA as required by procedure | D4
N-2019-11110 | 2019/06/18 | CLOSED | 16-31555, D2O Facility: NCR Not Signed by TSSA as required by procedure | D3
N-2019-11343 | 2019/06/20 | CLOSED | Proj 16-31555: MDR deviation required for FAAGM installation in HWMB West Annex | D4
N-2019-11688 | 2019/06/27 | CLOSED | D2O Project 16-31555 Worker reports thumb injury | D3
N-2019-11733 | 2019/06/28 | CLOSED | 16-31555: D2O Facility – Vendor’s ITP sequence steps signed off as partially complete without appropriate documentation | D3
N-2019-12155 | 2019/07/08 | CLOSED | 16-31555, D2O Storage Facility: By-passed OPG Witness Activity | D3
N-2019-12160 | 2019/07/08 | CLOSED | #16-31555, HWMB West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 120494 | D4
N-2019-13090 | 2019/07/25 | CLOSED | 16-31555 - Beetles that are to be installed as per DEC 120493 are too long - Delays | D4
N-2019-13724 | 2019/08/07 | CLOSED | 16-31555 D2O Facility: Vendor Procedural Non-Compliance | D3
N-2019-13811 | 2019/08/08 | CLOSED | Project # 16-31555 : D2O West Annex; Employee felt ill. | D3
N-2019-14064 | 2019/08/14 | CLOSED | Project 16-31555, D2O Storage Facility - Inspection and Test Plan not reflecting current field work status | D3
N-2019-14153 | 2019/08/15 | CLOSED | 16-31555, D20 Storage Facility - Unauthorized use of Fibrous Material Used to Seal Threaded Joints | D3
N-2019-14183 | 2019/08/16 | CLOSED | DNR: Proj 16-31555 HWMB West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 121320 | D4
N-2019-14395 | 2019/08/21 | CLOSED | 16-31555, D20 Storage Facility: Failure to install missing manufacturer's nameplate tag on check valve in accordance with Non-Conformance Report. | D3
N-2019-14475 | 2019/08/22 | CLOSED | Project # 16-31555 D2O Storage Facility: ITP Rejected | D4
N-2019-14480 | 2019/08/22 | CLOSED | Project # 16-31555 D2O Storage Facility: CWP Incomplete | D4
N-2019-14494 | 2019/08/22 | CLOSED | Project # 16-31555 - Loss of quality record (W026 form) for supporting ITP sign-offs | D4
N-2019-14673 | 2019/08/26 | CLOSED | 16-31555 D20 Storage Facility - Quality Documentation Gap Identified | D4
N-2019-14709 | 2019/08/27 | CLOSED | 16-31555, D2O Storage Facility: By-passed ITP Witness Activity | D4
N-2019-14861 | 2019/08/29 | CLOSED | Project # 16-31555 D2O Storage Facility: CWP Incomplete | D4
N-2019-14987 | 2019/09/02 | CLOSED | Project 16-31555, D2O Storage Facility - Inspection and Test Plan not reflecting current field work status. | D4
N-2019-15022 | 2019/09/03 | CLOSED | 16-31555, D20 Storage Facility - Material damaged during installation | D3
N-2019-15049 | 2019/09/03 | CLOSED | 16-31555, D2O Storage Facility - Foreign Material Intrusion identified during Hydrostatic Testing on prefabricated NC3 piping system. | C3-NFE
N-2019-15354 | 2019/09/09 | CLOSED | 16-31555, D2O Storage Facility: By-passed ITP Witness Activity | D3
N-2019-15406 | 2019/09/10 | CLOSED | 16-31555, D20 Storage Facility: Valve bonnet tightened while energized during NCIII Pneumatic Pressure Test | D3
N-2019-15564 | 2019/09/12 | CLOSED | D20 Storage Facility: Test temperature was not recorded on pressure test form Project # 16-31555 | D4
N-2019-15977 | 2019/09/18 | CLOSED | DNR - Proj 16-31555 HWMB West Annex - Pre-agreement for use of FICREQ21 through FICREQ30 in EC 121323 | D4
N-2019-15993 | 2019/09/18 | CLOSED | Project # 16-31555 D2O Storage Facility: CWP Incomplete | D4
N-2019-16123 | 2019/09/20 | CLOSED | Project # 16-31555 D2O Storage Facility: Incomplete NCR/Pressure Testing Procedure Documentation found during NCR closeout review | D4
N-2019-16916 | 2019/10/02 | CLOSED | 16-31555. D20 Storage Facility: FME Condition - FME Plan not in CWP | D3
N-2019-16951 | 2019/10/02 | CLOSED | 16-31555, D20 Storage Facility: FME Plan Not in CWP | D3
N-2019-17041 | 2019/10/03 | CLOSED | 16-31555, D20 Storage Facility: FME - Borescope Inspection Indentified FM in Piping | D3
N-2019-17138 | 2019/10/04 | CLOSED | D20 Storage Facility: FME - Borescope Inspection Indentified FM in Piping 0-38500-L182 Tank 9 Tie-In Connection - (16-31555) | CO3
N-2019-17226 | 2019/10/06 | CLOSED | D20 Storage Facility: FME - Borescope Inspection Indentified FM in Piping 0-38500-L186 Tank 11 Tie-In Connection - (16-31555) | CO3
N-2019-17286 | 2019/10/07 | CLOSED | D20 Storage Facility: FME - Borescope Inspection Indentified FM in Piping/Tank 29 Connection - (16-31555) | CO3
N-2019-17447 | 2019/10/09 | CLOSED | Proj. # 16-31555 Electrical Penetrations through non-fire rated penetrations not being added to the appropriate design document | D4
N-2019-17520 | 2019/10/10 | CLOSED | 16-31555 D2O Project During Commissioning of Instrument Air/Service Air Plugs found not installed on traps | D3
N-2019-17554 | 2019/10/11 | CLOSED | Project #16-31555 D2O Storage Facility: Bypassed QC Hold Point - (16-31555) | D3
N-2019-17926 | 2019/10/17 | CLOSED | D2O Storage Facility: Lack of Attention to Detail - ITP Package Closout - (16-31555) | D4
N-2019-18127 | 2019/10/21 | CLOSED | Project # 16-31555 D2O Storage Facility: Foreign Material Found During Borescope Inspection - (16-31555 ) | D4
N-2019-18134 | 2019/10/21 | CLOSED | Project 16-31555 - D2O Storage Facility: By-passed ITP Witness Activity | D3
N-2019-18150 | 2019/10/21 | CLOSED | Project 16-31555 - D2O Storage Facility: Bypassed ITP Hold Point Inspections | D3
N-2019-18302 | 2019/10/23 | CLOSED | Project #16-31555- vendor workers working in close proximity (adjacent/near) to live exposed electrical apparatus | D3
N-2019-18669 | 2019/10/28 | CLOSED | Project 16-31555, D2O Storage Facility: By-passed ITP Witness Activity | D3
N-2019-18672 | 2019/10/28 | CLOSED | Worker Experienced Sore Knee’s D2O West Annex Project#16-31555 | D3
N-2019-18874 | 2019/10/31 | CLOSED | D2O Storage Facility: Bypassed ITP Hold Point Inspections - (Project 16-31555) | D3
N-2019-19155 | 2019/11/05 | CLOSED | Project #16-31555, D2O Storage Facility - Unapproved FME device used in field | D4
N-2019-19193 | 2019/11/05 | CLOSED | DNR - 16-31555 – P.Eng Stamps for HWMB West Annex Non-Standard Work Protection Isolation Memos | D4
N-2019-19282 | 2019/11/06 | CLOSED | P16-31555: AFS QUORUM FOR DEC 120615 "FIRE PROTECTION STANDPIPE AND HOSE CABINETS" | D4
N-2019-19336 | 2019/11/07 | CLOSED | 16-31555 - D2O Storage Facility: Product Quality Issue: ITP Sign-offs Not Complete - EC 120615 Walkdown | D4
N-2019-19516 | 2019/11/11 | CLOSED | 16-31555 - D2O Storage Facility - By-passed ITP Witness Activity | D3
N-2019-19546 | 2019/11/11 | CLOSED | 16-31555 D2O Storage: IPG Process (timing) not followed for the review and approval of U0 CPC / PIDs Software Installation WPLs | D4
N-2019-19619 | 2019/11/12 | CLOSED | Project # 16-31555, D2O Storage Facility: Work being performed without a CWP and Inspection & Test Plan | D3
N-2019-19966 | 2019/11/18 | CLOSED | Project #16-31555, D2O Storage Facility: By-passed ITP Witness Activity | D3
N-2019-20223 | 2019/11/21 | CLOSED | Project # 16-31555 - ground cable contacted | D3
N-2019-20371 | 2019/11/25 | CLOSED | Project 16-31555: Late Maintenance TPAR Submission | D4
N-2019-20450 | 2019/11/26 | CLOSED | D20 Project 16-31555 Sea-Can - CMS (Combustible Material Safety) issues found | D4
N-2019-20608 | 2019/11/28 | CLOSED | Project 16-31555, D2O Facility: - Vendor’s ITP steps do not reflect field work status - rework | D4
N-2019-20957 | 2019/12/04 | CLOSED | Project 16-31555 - Hilti firestop speed sleeve not fully engaged | D4
N-2019-20967 | 2019/12/04 | CLOSED | Project 16-31555 - Electrical penetrations installed without penetration numbers or location on OPG drawing | D4
N-2019-21034 | 2019/12/05 | CLOSED | Project #16-31555 Minor Wetting D2O | D3
N-2019-21184 | 2019/12/09 | CLOSED | Project # 16-31555-D2O Storage Facility: FME issue | D3
N-2019-21276 | 2019/12/10 | CLOSED | Project #16-31555 - D2O - Bypassed ITP TSSA witness inspection points | D3
N-2019-21290 | 2019/12/10 | CLOSED | Project #16-31555 - D20 false fire alarm | D4
N-2019-21338 | 2019/12/11 | CLOSED | 16-31555 D2O Facility - Bypassed ITP TSSA witness inspection point | D3
N-2019-21361 | 2019/12/11 | CLOSED | Project#16-31555 - D2O Facility - ITP operations not reflecting field work completion | D4
N-2019-21362 | 2019/12/11 | CLOSED | Project#16-31555 - D2O Facility: Bypassed ITP OPG witness inspection point | D4
N-2019-21384 | 2019/12/11 | CLOSED | Project # 16-31555 - D20 Falling object incident | D3
N-2019-21409 | 2019/12/12 | CLOSED | Project #16-31555 - D2O - Bypassed ITP Hold Point Inspection | D4
N-2019-21412 | 2019/12/12 | CLOSED | Project #16-31555 - D2O- Multiple ITPs discovered to be blank or partially completed | D4
N-2019-21433 | 2019/12/12 | CLOSED | Project#16-31555 - D2O Facility - System in service without quality records satisfied | D4
N-2020-00275 | 2020/01/08 | CLOSED | Project # 16-31555 - D2O storage facility - By-pass OPG Hold & Witness Points | D4
N-2020-00276 | 2020/01/08 | CLOSED | Project#16-31555 - D2O Storage facility - ITP Inspection operations signed off with incomplete QA supporting documentation | D4
N-2020-01574 | 2020/01/30 | CLOSED | Project #16-31555 - D2O - Bypassed ITP Hold/Witness Point Inspections | D4
N-2020-01830 | 2020/02/04 | CLOSED | 16-31555 Heavy Water Management Building West Annex - Transfer of Operational Pressure Testing Accountability | D4
N-2020-01835 | 2020/02/04 | CLOSED | Project #16-31555 - D2O: Bypassed (TSSA / OPG / Canatom QC) ITP Witness & Hold Point Inspections | D4
N-2020-01866 | 2020/02/05 | CLOSED | EITER 16-31555 - OPG Field Engineering Inspection HOLD Point By Passed | D3
N-2020-02156 | 2020/02/10 | CLOSED | 16-31555 - Installation of Electrical Cables do not match Approved Design Engineering Change Papers | D3
N-2020-02224 | 2020/02/11 | CLOSED | Project #16-31555 - D2O: Bypassed TSSA ITP Witness Point Inspections | D4
N-2020-02344 | 2020/02/12 | CLOSED | DNR - Project 16-31555: Use of Teflon Tape for threaded joints in HWMB West Annex Instrument and Service Air System | D4
N-2020-02802 | 2020/02/20 | CLOSED | Project # 16-31555, Worker Concern D20 Storage Building Refrigerant R134a | D3
N-2020-02805 | 2020/02/20 | CLOSED | Project # 16-31555, Worker Safety Concern D20 Storage Building Silica | D3
N-2020-02806 | 2020/02/20 | CLOSED | Project # 16-31555, Worker Safety Concern D20 Storage Building Epoxy | D3
N-2020-03045 | 2020/02/25 | CLOSED | Project #16-31555: D2O - Bypassed ITP Hold/Witness Point Inspections | D4
N-2020-03223 | 2020/02/27 | CLOSED | 16-31555: D20 Storage Facility: Final Inspection Walk Down – Installed Component operability is limited | D4
N-2020-04843 | 2020/03/30 | COMPLETE | DNR - Proj 16-31555: Preliminary Results – HWMB West Annex Seismic Dike - Review and Analysis | C3-NFE
N-2020-05033 | 2020/04/03 | COMPLETE | 16-31555 - D2O project - issues with Whole Body Monitor 0-62321-RY603 type Argos 5PB | D4
N-2020-05243 | 2020/04/09 | COMPLETE | Project 16-31555 - D2O Storage Facility: Valve flange seals over torqued during re-assembly of valves | D4
N-2020-05454 | 2020/04/16 | COMPLETE | Project #16-31555 - D2O Facility: Bypassed (TSSA / OPG) ITP Witness Point Inspections | D4
N-2020-05723 | 2020/04/23 | COMPLETE | Project #16-31555 - D2O Facility: Bypassed (TSSA / Vendor QC) ITP Witness Point Inspections | D4
N-2020-06211 | 2020/05/04 | COMPLETE | Project #16-31555 - D2O Facility: Bypassed (TSSA) ITP Witness Point Inspections | D3
N-2020-06685 | 2020/05/14 | COMPLETE | Project #16-31555: D2O Facility-Vendor QC Inspectors performing Visual Weld inspections not qualified/certified in accordance to Vendor's QA program. | D3
N-2020-07197 | 2020/05/27 | COMPLETE | Project #16-31555: D2O Facility - Bypassed ITP Hold/Witness Point Inspections | D4
N-2020-08083 | 2020/06/12 | COMPLETE | 16-31555: INSPECTION OF D2O TANKS BY TSSA - ITPs issues | D3
N-2020-08538 | 2020/06/22 | COMPLETE | 16-31555: 0-38110-RV819 MISSING BOLTS | D3
N-2020-10258 | 2020/07/28 | COMPLETE | DNRU3 - Proj 16-31555: Questions from CNSC on NK38-CORR-00531-21783 | C3-NFE
N-2020-10267 | 2020/07/28 | COMPLETE | Project 16-31555 HMWB West Annex-material received directly instead of via Unit 0 stores | D4
N-2020-10361 | 2020/07/30 | COMPLETE | D2O Project 16-31555: Vendor Tanks provided without CRN’s Identified on the nameplate | D4
N-2020-10874 | 2020/08/10 | COMPLETE | Project # 16-31555 : No fire verification report/certificate for HWMB-WA Standby Generator Building | D4
N-2020-12175 | 2020/09/01 | COMPLETE | Project 16-31555 Subcontractor individual did not serve COVID-19 14 day quarantine | D3
N-2020-14432 | 2020/10/04 | COMPLETE | Project 16-31555 - HWMB RR- As-Found Empty Altair Monitor in D2O West Annex- OPG - delay | D4
N-2020-14822 | 2020/10/09 | COMPLETE | DNRU3 - 16-31555: West Annex Stack Commissioning- Removal Of AI / Cold Fingers From Design | D4
N-2020-15607 | 2020/10/22 | COMPLETE | DNR 16-31555: Missing D2O Project Surplus materials at F6/F8 yards | D3
N-2020-16908 | 2020/11/11 | COMPLETE | Project # 16-31555: D2O Facility - During commissioning (SCI 75110) leak identified downstream of 0-75110-V5010 at threaded fitting. | D4
N-2021-04961 | 2021/03/19 | COMPLETE | P#16-31555: D2O HWMB West Annex - Outstanding Engineering Deliverables | D3
N-2021-05392 | 2021/03/25 | MRM | P#16-31555: Discrepancies between AS7 and SCPR Configuration Report | D4
N-2006-01616 | 05/03/2006 03:53 PM | COMPLETE | Schedule Issue: Threat to the targeted completion date of the Developmental BCS for Project 31555 and 49251 (D2O Storage and Drum Handling Facility) | D 4
N-2006-02642 | 07/27/2006 03:56 PM | COMPLETE | Contract Issue: Contractual Date of Final Report Submittance not met for Project 49251/31555: Pickering/Darlington D2O Storage Project | D 4
D-2006-04357 | 05/03/2006 03:53 PM | COMPLETE | Schedule Issue: Threat to completion of conceptual study for Project 31555 (D2O Storage and Drum Handling Facility) | D 4
N-2007-04049 | 09/12/2007 03:56 PM | COMPLETE | Missed Training | D 4
D-2007-05344 | 05/01/2007 03:46 PM | COMPLETE | Schedule Issue - Technical Evaluation RFP delayed 1 week- D2O Storage Project 16-31555 | D 4
D-2007-05345 | 05/01/2007 03:46 PM | COMPLETE | Schedule Issue - Missed Project Milestones D2O Storage Project 16-31555 | D 4
D-2007-10108 | 09/13/2007 03:53 PM | COMPLETE | Project 31555 D2O Stoarge Facility - Delay to Drilling Geotech bore holes | D 4
N-2008-03760 | 06/17/2008 03:54 PM | CLOSED | Delays caused by implementing CSIP Process. | D 4
N-2012-04396 | 09/07/2012 03:56 PM | CLOSED | Eng Quality Surveillance at RCMT identified issues related to their staff training and qualifications | C 3
N-2012-05071 | 10/15/2012 03:54 PM | CLOSED | Design Quality - Verification Errors, NK38-MDR-38000-10003 | D 4
N-2012-06404 | 12/19/2012 03:46 PM | CLOSED | Difficulty in Arranging Walkdown | C 3
D-2012-07996 | 08/01/2012 03:54 PM | CLOSED | MDR produced by EPC contractor rejected | NE 5
D-2012-10620 | 10/30/2012 03:54 PM | CLOSED | 16-1555: The D2O project team did not meet the scheduling milestone requirements of N-PROC-MA-0022 for T minus 8 | D 4
D-2012-12564 | 12/31/2012 03:54 PM | CLOSED | Discrepancies between Passport and Design Documentation | D 4
D-2013-00472 | 01/16/2013 03:54 PM | COMPLETE | Design deficiencies in Asset Suite (Passport) | C 3
N-2013-00558 | 02/01/2013 03:54 PM | CLOSED | DNGS Refurbishment: Scope addition to existing modification in the EC process Challenges Nuclear Safety Review | D 4
D-2013-00720 | 01/23/2013 03:54 PM | CLOSED | Discrepancy in design documentation for D2O Mnagement Building | D 4
D-2013-02242 | 02/27/2013 03:54 PM | CLOSED | Legacy Configuration Management issue | D 4
N-2013-02295 | 05/06/2013 03:54 PM | CLOSED | West Annex MDR Unvalidated Emission Limit & Dewpoint Calculation | D 4
N-2013-02297 | 05/06/2013 03:54 PM | CLOSED | NR Design Engineering-MDR Rejection by Design SM due to Poor Quality | D 4
N-2013-02561 | 05/17/2013 03:54 PM | CLOSED | Slow Entry through Sally Port | D 4
N-2013-02602 | 05/21/2013 03:53 PM | CLOSED | Challenge to D2O storage bldg project 31555 ( review and approval of workplans) | D 4
N-2013-03258 | 06/18/2013 03:53 PM | CLOSED | Challenge to D2O Storage building Project 31555 | D 4
N-2013-03604 | 07/08/2013 03:54 PM | COMPLETE | WW27 Scheduled Tasks Carried Over to WW28 For D2O Project Work | D 4
N-2013-03630 | 07/09/2013 03:54 PM | COMPLETE | vendor prepared two sets of tech specs for the same e-tag | D 4
D-2013-03876 | 04/12/2013 03:54 PM | CLOSED | S&P clause determining design report requirements is not available | D 4
N-2013-04127 | 08/02/2013 03:54 PM | COMPLETE | Box Drain Sump Pump Out - Odour at Discharge - D2O Project 16 -31555 | D 4
D-2013-04206 | 04/22/2013 03:54 PM | CLOSED | System Engineer review for work plan identified late in review cycle | D 4
N-2013-04430 | 08/22/2013 03:54 PM | COMPLETE | MSA Engineering Contractor QA: No Independent Verification on CSA N286 Documents | D 3
D-2013-04596 | 05/01/2013 03:54 PM | CLOSED | Slow a/r input for Cat ID creation for West Annex Heavy Water Management Building | D 4
D-2013-07624 | 07/30/2013 03:54 PM | COMPLETE | D2O WEST ANNEX POWER SUPPLIES SC CALC SUBMISSION REJECTED | D 4
D-2013-08163 | 08/19/2013 03:54 PM | COMPLETE | Intake fan filter plugged with construction dust | D 4
D-2013-12344 | 09/05/2013 03:54 PM | COMPLETE | Urgent Drawing Office Work Request – EC 120485 | D 4
N-2013-13970 | 09/19/2013 03:53 PM | COMPLETE | 16:31555: Hydraulic Fluid Leak from Zoom Boom | D 4
D-2013-14957 | 09/26/2013 03:54 PM | COMPLETE | Safety Issue ( OPG vehicle being driven in an unsafe manner) | D 4
N-2013-15790 | 10/02/2013 03:53 PM | COMPLETE | 16:31555: D20 Storage Project, Modify LPSW line W/O# 2817137 - Driver Lost TLD | D 4
N-2013-15934 | 10/03/2013 03:54 PM | COMPLETE | Employee sprained left knee | D 4
D-2013-17008 | 10/11/2013 03:54 PM | COMPLETE | MSA/EPC design breakthrough: DEC 123123-R01 FIC4 issued but does not meet engineering standards | D 3
N-2013-17054 | 10/11/2013 03:54 PM | COMPLETE | Quality Issue: Incorrect SCI #s used for electrical systems in MDR NK38-MDR-38000-10003 and subsequent ECs | C 3
D-2013-18217 | 10/22/2013 03:54 PM | COMPLETE | EPC/MSA Breakthrough event: Unsafe non-compliant design installed in the field | C 3
N-2013-18956 | 10/28/2013 03:54 PM | COMPLETE | Project 73360 EPG3 - D20 Project TMOD Interference | D 4
N-2013-19489 | 10/31/2013 03:54 PM | COMPLETE | EPC Issue: No Quality Control Inspection Activities Identified on PB ITP. | D 4
D-2013-20368 | 11/08/2013 03:57 PM | COMPLETE | TRF: Temporary Terminal Point Operation | C 3
D-2013-20799 | 11/13/2013 03:54 PM | COMPLETE | TRF: T1301 Lesson Learned when Shutting Down Heating Steam | D 4
D-2013-22738 | 12/02/2013 03:54 PM | COMPLETE | TRF: T1301: West Annex Project Work, Flowsheets Not Listed on ADL | D 4
N-2014-00467 | 01/07/2014 03:54 PM | COMPLETE | 16- 31555 Delay in Foam Fire testing due to Weather conditions | D 4
D-2014-03000 | 01/28/2014 03:56 PM | COMPLETE | Lost tool (cannot be located after use on D2O Project) PO# 217807 | D 4
D-2014-03305 | 01/30/2014 03:54 PM | COMPLETE | T1301: Delay to TRF Restart due to ACS Project # 16-38401 delays | C 3
D-2014-03963 | 02/04/2014 03:54 PM | COMPLETE | RWPB Geotechnical Work (Bore Hole Drilling) Delayed due to Obstructions in the Building Footprint (RFR Project # 16-73110) | D 4
D-2014-05154 | 02/14/2014 03:54 PM | COMPLETE | TRF- PC1s submitted prior to revision of DIOTS tie in work plan NK38-WPL-38110-0458078 | D 4
N-2014-06240 | 02/24/2014 03:54 PM | COMPLETE | 16 13555- Delay in OPS support of He tie in caused by Transient in TRF | D 4
D-2014-09910 | 03/26/2014 03:54 PM | COMPLETE | Refurbishment Retube Waste Processing Building Geotechnical Work (Bore Hole Excavation) Delayed due to Obstructions in the Building Footprint (C13) | D 4
N-2014-14230 | 05/01/2014 03:54 PM | APPROVED | D2O Annex Design Engineering Change Package Schedule Delays | C 3
D-2014-14588 | 05/05/2014 03:54 PM | COMPLETE | D2O Annex Design Engineering Change Package Schedule Delay - EC 120492 | CO 4
N-2014-16188 | 05/20/2014 03:53 PM | COMPLETE | Schedule Quality, Prj #31555 – D20 Storage Facility -Primavera Level II Float Levels are Inaccuarte | D 4
N-2014-16725 | 05/26/2014 03:53 PM | COMPLETE | 31555 D2O Storage: Workplan Reviews Cancelled due to process not being followed | D 4
N-2014-18575 | 06/13/2014 03:54 PM | COMPLETE | Project 13-49146 Relocatable Structures Demolition - Additional Hours Required | D 4
D-2014-18651 | 06/14/2014 03:57 PM | COMPLETE | TRF Argon supply low. | CO 3
D-2014-19191 | 06/20/2014 03:54 PM | COMPLETE | Protocol required for accessing Construction Safe Work Areas | D 4
D-2014-19262 | 06/20/2014 03:53 PM | COMPLETE | Campus Plan and Infrastructure Project Risks | NE 4