## Sheet1
2-CCC-19 - Summary of Planned vs Actual from 2017 to 2026 by detailed project description and Investment Category
LONDON HYDRO CAPITAL SPENDING DETAILS BY OEB CHAPTER 5 INVESTMENT CATEGORY
Annual Spending Details by Investment Category | 2017 Actual | 2017 OEB Approved | 2018 Actual | 2018 Plan | 2019 Actual | 2019 Plan | 2020 Actual | 2020 Plan | 2021 Bridge | 2022 Test | 2023 Plan | 2024 Plan | 2025 Plan | 2026 Plan
| $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $
System Access
City Road Authority Relocates | 1834243.62 | 2241200 | 694654.42 | 1270700 | 256439.15 | 1119000 | 1160012.39 | 1102500 | 2112000 | 340000 | 1518000 | 1518000 | 1518000 | 1533000
Transit Relocates | 7190.12 | 0 | 143181.87 | 0 | 25196.43 | 0 | 101333.85 | 0 | 1564000 | 7315000 | 2874000 | 3199000 | 1361000 | 1361000
Developer Expansions & Relocations | 969886.92 | 340900 | 1157446.83 | 487000 | 2942735.89 | 973200 | 2138678.26 | 1267000 | 1213600 | 1231900 | 368000 | 382000 | 395000 | 409000
Residential Secondary Service Upgrade | 428492.6 | 355000 | 456358.61 | 363000 | 500149.56 | 370000 | 535130.69 | 377000 | 484000 | 491000 | 551000 | 573000 | 593000 | 613000
Single Family Residential Underground | 4168104.67 | 1090200 | 3716264.59 | 1113900 | 2779583.49 | 1138000 | 2494895.89 | 1161300 | 2718400 | 2759400 | 2772000 | 2785000 | 2797000 | 2812100
Multi-Family Residential Underground | 1789537.73 | 783000 | 1388538.25 | 800400 | 1354947.88 | 817000 | 1884245.86 | 831000 | 1440000 | 1461700 | 1500000 | 1515000 | 1530000 | 1545000
Commercial Distribution Services | 2713549.32 | 1935900 | 1951246.12 | 1960000 | 2247022.2 | 2030000 | 2802836.14 | 2070000 | 2649000 | 2689000 | 2700000 | 2720000 | 2743000 | 2763000
Metering and installations | 1568358.61 | 663200 | 1041521.81 | 657140 | 1303856.39 | 676854 | 1184722.34 | 697159 | 967000 | 970000 | 1015954 | 1041353 | 1062180 | 1083424
Primary metering | 2256.53 | 354000 | 77065.71 | 364620 | -3904.4 | 375558 | 0 | 368825 | 225000 | 229000 | 56000 | 108000 | 57000 | 77000
AMI Communications Renewal | 243660.11 | 649000 | 0 | 699370 | 0 | 720351 | 443905.54 | 741961 | 550000 | 500000 | 350000 | 350000 | 0 | 0
Total System Access | 13725280.23 | 8412400 | 10626278.21 | 7716130 | 11406026.59 | 8219963 | 12745760.96 | 8616745 | 13923000 | 17987000 | 13704954 | 14191353 | 12056180 | 12196524
System Renewal
Substation installations/refurbishments | 0 | 0 | 0 | 0 | 28292.05 | 0 | 103807 | 0 | 330000 | 0 | 0 | 0 | 0 | 0
Battery bank replacements | 11553.28 | 15000 | 12717.34 | 15000 | 15284.25 | 15000 | 12464.04 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 20000
Switchgear modifications | 75.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vault Renewal and RTU Standardization | 0 | 30000 | 85889.81 | 30000 | 93184.31 | 30000 | 0 | 30000 | 0 | 0 | 96000 | 97000 | 98000 | 94100
Misc Substation Rebuild | 0 | 0 | 20079.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Silicone Injection of Underground Cable | 2087270.77 | 2697900 | 1445711.2 | 2029000 | 583842.76 | 1909000 | 251.29 | 2802000 | 0 | 0 | 0 | 0 | 0 | 0
Subdivision Rehabilitation | 32118.26 | 75000 | 134601.92 | 328000 | 1339081.68 | 1334000 | 3074663.53 | 0 | 3443000 | 5846000 | 4415000 | 4386000 | 4400000 | 4425000
Air Insulated SE Replacement | 343423.93 | 293000 | 499659.65 | 866500 | 270350.36 | 689500 | 273412.49 | 398000 | 420000 | 386000 | 445500 | 450000 | 450000 | 450000
Leaking Transformers and Returns | 1007451.38 | 500000 | 1757390.74 | 600000 | -387545.16 | 600000 | 444906.5 | 600000 | 524000 | 499000 | 649000 | 650000 | 675000 | 690000
Rebuild or Convert Vault Areas | 150411.78 | 144000 | 15140.37 | 203000 | 19768.99 | 331000 | 215117.48 | 174000 | 112000 | 160000 | 200000 | 225000 | 226000 | 227000
Underground Conversions | 826763.93 | 556000 | 1464299.4 | 977000 | 2335749.97 | 1382000 | 4731360.12 | 2496000 | 2729000 | 1025000 | 450000 | 500000 | 500000 | 526000
Backup Supply and Fault Indicator Installations | 95.92 | 0 | 34672.09 | 0 | 64974.32 | 0 | 98228.1 | 0 | 180000 | 286000 | 285500 | 300000 | 325000 | 325000
Miscellaneous Subdivision Projects | 35066.69 | 20000 | 59376.26 | 20000 | 169001.41 | 20000 | 140738.7 | 20000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000
Main Feeder Conversions & Ties | 732012.73 | 815000 | 673531.46 | 3042100 | 544582.4 | 653000 | 676564.46 | 1200000 | 516000 | 561000 | 492000 | 504000 | 510000 | 516000
Backup Supply & Civil Structure Installations | 2631827.92 | 2550400 | 5226537.24 | 1500000 | 7438366.02 | 1200000 | 2486079.72 | 200000 | 1505000 | 1224000 | 1225000 | 1230000 | 1241000 | 1252500
Replacement of Network Vaults, Maintenance Holes and Transformers | 1393926.36 | 1014100 | 696183.62 | 1030000 | 1418696.34 | 950000 | 487244.58 | 1050000 | 1068000 | 954000 | 650000 | 655000 | 660000 | 663500
Replacement & Conversion of Primary/Second Network Cable | 607798.24 | 750000 | 589963.26 | 380000 | 2641334.74 | 380000 | 402366.44 | 380000 | 552000 | 525000 | 697000 | 708000 | 713000 | 722000
Maintenance Hole Cable Rebuilds & Fuse Installs | 229915.21 | 300000 | 2198917.43 | 175000 | 1040807.16 | 225000 | 1100781.62 | 225000 | 940000 | 652000 | 269000 | 269000 | 275000 | 279000
Maintenance Hole Cable Protection | 45692.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Replacement of Fully Depreciated/Deteriorated Poles and Poles Susceptible to Fire | 730439.03 | 410000 | 520421.71 | 525000 | 706687.22 | 420000 | 1001443.72 | 575000 | 1250000 | 1250000 | 1400000 | 1425000 | 1450000 | 1475000
Arrestor/Insulator/Other | 523773.8 | 580000 | 510447.69 | 720000 | 403767.16 | 660000 | 500358.84 | 285000 | 365000 | 315000 | 330000 | 330000 | 330000 | 330000
Rebuild Fully Depreciated Overhead Areas | 227992.58 | 260000 | 69789.16 | 314600 | 96389.81 | 1611300 | 26472.27 | 1230000 | 1565000 | 1527000 | 1650000 | 1675000 | 1700000 | 1725000
Reliability/Outage Mitigation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
Overhead Voltage Conversions | 2523835.07 | 3267100 | 2329822.28 | 3947000 | 2635499.59 | 4347600 | 3050211.84 | 4533200 | 1845000 | 2123000 | 2100000 | 2106000 | 2112000 | 2118700
Total System Renewal | 14141444.47 | 14277500 | 18345152.52 | 16702200 | 21458115.38 | 16757400 | 18826472.74 | 16213200 | 17504000 | 17493000 | 15514000 | 15670000 | 15825000 | 15983800
System Service
Relay replacements | 113016.98 | 79600 | 901.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Backup Supply and Fault Indicator Installations | 72753.41 | 90000 | 124094.68 | 90000 | 67375.7 | 20000 | 70864.31 | 20000 | 120000 | 115000 | 50000 | 50000 | 50000 | 50000
Reinforcements | 2497.87 | 0 | 0 | 0 | 0 | 0 | 498.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Recloser Installation | 339455.21 | 195000 | 370563.65 | 195000 | 312020.85 | 195000 | 440303.95 | 195000 | 225000 | 225000 | 208000 | 210000 | 212000 | 213700
Remote Terminal Unit Replacements | 183513.65 | 130000 | 125524.92 | 130000 | 40166.71 | 130000 | 11397.24 | 130000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
Miscellaneous Automation | 249093.98 | 247900 | 61331.47 | 150000 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
SCADA - Cyber Security & Fault Detection | 112878.62 | 100000 | 38108.54 | 100000 | 158163.96 | 100000 | 331121.52 | 100000 | 425000 | 570000 | 375000 | 380000 | 382000 | 385000
Power Quality | 62198.46 | 50000 | 63781.58 | 50000 | 96855.22 | 50000 | 199500.53 | 50000 | 300000 | 200000 | 200000 | 202000 | 205000 | 208500
Total System Service | 1135408.18 | 892500 | 784306.19 | 715000 | 674582.44 | 545000 | 1053685.72 | 545000 | 1095000 | 1135000 | 858000 | 867000 | 874000 | 882200
General Plant
Capital Contribution to Transformer Station | 1875993.24 | 1882000 | 1938202.16 | 1835000 | 0 | 250000 | 0 | 0 | -1750000 | 0 | 0 | 0 | 0 | 0
Vehicles and Major Equipment | 1107046.62 | 1095900 | 1026455.93 | 1104000 | 1492723.5 | 1128000 | 1470038.13 | 1145000 | 1445000 | 1450000 | 1448000 | 1455000 | 1428000 | 1458000
Miscellaneous Operating Equipment | 326167.74 | 319100 | 244022.41 | 300000 | 344566.18 | 300000 | 332033.39 | 300000 | 430000 | 409000 | 418000 | 426000 | 434000 | 443000
Office Furniture & Security Equipment | 115204.73 | 196400 | 290951.97 | 253700 | 409728.68 | 258700 | 270669.1 | 262100 | 825000 | 729000 | 640000 | 355000 | 355000 | 380000
Buildings & Fixtures | 911749.45 | 909400 | 3581742.41 | 991000 | 1804107.14 | 800000 | 1225241.86 | 811000 | 2816000 | 1643000 | 1661000 | 1766000 | 1966000 | 1376000
Computer Hardware and Software | 1041038.04 | 732900 | 777302.04 | 800000 | 396284.09 | 850000 | 1028289.28 | 950000 | 1020000 | 829000 | 800000 | 800000 | 800000 | 800000
Application Development - Regulatory & Sustainment | 586389.1 | 850000 | 853009.47 | 1350000 | 1071038.32 | 950000 | 1048780.7 | 1450000 | 1070000 | 950000 | 1000000 | 1400000 | 1400000 | 1400000
Application Development - System Enhancements | 2303903.78 | 2014200 | 2666080.39 | 1550000 | 2850653.54 | 1400000 | 4031319.98 | 1100000 | 2995000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000
Application Development - New Systems | 641278.08 | 400000 | 639685.99 | 900000 | 1934557.06 | 1500000 | 400485.86 | 2500000 | 238000 | 525000 | 300000 | 300000 | 300000 | 300000
CIS Refresh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 6500000 | 11500000 | 0 | 0 | 0
JD Edwards Upgrade | 539092 | 500000 | 2052217.34 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total General Plant | 9447862.78 | 8899900 | 14069670.11 | 10583700 | 10303658.51 | 7436700 | 9806858.3 | 8518100 | 9589000 | 15935000 | 20667000 | 9402000 | 9583000 | 9057000
Other
Inventory Held for Capital Projects | -790874.83 | 0 | 1433052.26 | 0 | -824042.51 | 0 | 1342092.57 | 0 | -600000 | -500000 | 0 | 0 | 0 | 0
Total Other | -790874.83 | 0 | 1433052.26 | 0 | -824042.51 | 0 | 1342092.57 | 0 | -600000 | -500000 | 0 | 0 | 0 | 0
Total Capital Expenditures before Capital Contributions | 37659120.83 | 32482300 | 45258459.29 | 35717030 | 43018340.41 | 32959063 | 43774870.29 | 33893045 | 41511000 | 52050000 | 50743954 | 40130353 | 38338180 | 38119524
Capital contributions* | -5205870.12 | -3101000 | -4795267.67 | -4795267.67 | -4358519.31 | -4358519.31 | -6838793.12 | -6838793.12 | -6534000 | -4558000 | -4859000 | -4789000 | -4768000 | -4774000
Total | 32453250.71 | 29381300 | 40463191.62 | 30921762.33 | 38659821.1 | 28600543.69 | 36936077.17 | 27054251.88 | 34977000 | 47492000 | 45884954 | 35341353 | 33570180 | 33345524
* Capital Contributions for the 2018, 2019 and 2020 Plan years were not provided in the previous DSP - as a result, these amounts have been presented based on actuals for those years