## DSP Section 3.8, Appendix 2-AB
[21 empty] | File Number: |  | 0
[21 empty] | Exhibit: |  | B
[21 empty] | Tab: |  | 1
[21 empty] | Schedule: |  | 3
Page:
[21 empty] | Date: |  | 2019-06-19
Appendix 2-AB
Table 2 - Capital Expenditure Summary from Chapter 5 Consolidated Distribution System Plan Filing Requirements Distribution System Plan Filing Requirements ($M)
First year of Forecast Period: | 2023
CATEGORY | Historical Period (previous plan1 & actual) | [17 empty] | Forecast Period (planned)
| 2018 |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  | 2023 | 2024 | 2025 | 2026 | 2027
| Plan | Actual | Var | Plan | Q3 YTD Actual | Actual | Var | Plan | Q3 YTD Actual | Actual | Var | Plan | Q3 YTD Actual | As-Filed Forecast | Var (Plan to As-Filed) | Plan | As-Filed Forecast2 | Var (Plan to As-Filed)
|  |  | % |  |  |  | % |  |  |  | % |  |  |  | % |  |  | %
System Access | 175.0938 | 175.0938 | 0% | 147.9457 | 144.083 | 197.3464 | 33.39% | 153.4445 | 141.7412 | 193.6041 | 26.17% | 150.9126 | 162.085 | 171.5254 | 13.66% | 143.0214 | 180.8081 | 26.42% | 239.58 | 240.6414 | 227.0046 | 212.6012 | 204.2616
System Renewal | 219.6941 | 219.6923 | -0.0008366% | 202.27 | 156.281 | 188.9698 | -6.575% | 222.2275 | 162.4781 | 228.6318 | 2.882% | 237.3411 | 176.2488 | 236.0824 | -0.5303% | 256.7262 | 224.9484 | -12.38% | 373.1063 | 410.2959 | 494.1693 | 491.5139 | 497.8344
System Service | 79.0737 | 79.0755 | 0.002291% | 124.0294 | 59.3945 | 112.8322 | -9.028% | 129.3542 | 84.156 | 98.1435 | -24.13% | 144.0643 | 83.684 | 132.5867 | -7.967% | 102.9559 | 153.1683 | 48.77% | 196.4945 | 169.6973 | 229.561 | 192.0298 | 205.921
General Plant | 90.6752 | 90.6752 | 0% | 142.8414 | 9.877 | 114.2881 | -19.99% | 150.2544 | 103.9866 | 178.2286 | 18.62% | 95.2836 | 127.3296 | 173.8461 | 82.45% | 100.4499 | 105.6689 | 5.196% | 195.9254 | 207.3568 | 170.0931 | 175.509 | 162.9324
TOTAL EXPENDITURE | 564.5368 | 564.5368 | -4.676e-06% | 617.0866 | 369.6355 | 613.4366 | -0.5915% | 655.2806 | 492.3619 | 698.6081 | 6.612% | 627.6017 | 549.3475 | 714.0407 | 13.77% | 603.1534 | 664.5937 | 10.19% | 1005.1063 | 1027.9915 | 1120.828 | 1071.6538 | 1070.9494
System OM&A | 544.4 | 558.8 | 2.645% |  |  | 559.6 | -- |  |  | 560.2 | -- | -- | 437.9621 | 531.4 | -- | -- | 535.8 | -- | 597.5 | * | * | * | *
* System OM&A includes Operations, Maintenance and Administration expenses. System OM&A for 2024 - 2027 is determined based on the escalation factor identified in Exhibit A-04-3.
** 2022 is Bridge Year Forecast
Notes to the Table:
1. Historical “previous plan” data is not required unless a plan has previously been filed. However, use the last Board-approved, at least on a Total (Capital) Expenditure basis for the last cost of service rebasing year, and the applicant should include their planned budget in each subsequent historical year up to and including the Bridge Year.
2. Indicate the number of months of 'actual' data included in the last year of the Historical Period (normally a 'bridge' year):
Explanatory Notes on Variances (complete only if applicable)
Notes on shifts in forecast vs. historical budgets by category
For a more detailed explanation of shifts in forecast vs historical expenditures, please see DSP Section 3.9
Notes on year over year Plan vs. Actual variances for Total Expenditures
See DSP Section 3.9 Appendix B "Capital Program Performance Report 2019, 2020"
Notes on Plan vs. Actual variance trends for individual expenditure categories
See DSP Section 3.9 Appendix B "Capital Program Performance Report 2019, 2020"