## EB-2019-0082 C-2-1-2 Table 38
Excerpt from EB-2019-0082, Exhibit C-2-1, Attachment 2
Table 38: Programs with Applicable Variance Explanations - General Plant
| ISD |  |  | Description | 2018 Capital Expenditures ($ Millions) |  |  | 2018 In Service Capital Additions ($ Millions) |  |  | Units
[5 empty] | Approved | Actuals | Variance | Approved | Actuals | Variance | Reportable Unit | Approved | Actuals | Variance | Variance Explanations
Sustaining Capital
Transmission Stations
Site Facilities and Infrastructure
|  |  | S61 | Transmission Site Facilities and Infrastructure | 10.0047 | 16.4433 | 6.4386 | 7.7906 | 17.2082 | 9.4176 | N/A | 0 | 0 | 0% | Emergent Needs
Capital Common Corporate Costs and Other Costs
Transport and Work & Service Equipment
|  |  | CC2 | Transport and Work Equipment (TWE) | 14.1208 | 7.1587 | -6.962 | 14.3179 | 7.163 | -7.1549 | N/A | 677 | 503 | -25.7% | Preliminary Project Definition
Information Technology (including Cornerstone)
|  |  | IT1 | Infra / Tech Refresh Capital | 7.2761 | 4.0392 | -3.2369 | 10.1972 | 5.0991 | -5.0981 | N/A | 0 | 0 | 0% | Preliminary Project Definition
|  |  | IT2 | MFA Infrastructure Technology | 1.7794 | 3.5587 | 1.7793 | 1.7856 | 3.5587 | 1.7731 | N/A | 0 | 0 | 0% | Emergent Needs
|  |  | Other | MFA Client Tech & Periph Refresh | 1.0084 | 3.239 | 2.2307 | 1.0082 | 3.239 | 2.2308 | N/A | 0 | 0 | 0% | Emergent Needs
Facilities & Real Estate
|  |  | CC1 | Facilities Accommodation Improvements | 19.347 | 5.3565 | -13.9905 | 21.0711 | 5.3314 | -15.7397 | N/A | 0 | 0 | 0% | Preliminary Project Definition
|  |  | Other | Station Civil Infrastructure | 2 | 1.6251 | -0.37488 | 3.7275 | 0.02756 | -3.6999 | Number of Stations | 0 | 0 | 0% | Project Delivery Issues

## EB-2019-0082 C-2-1-2 Table 39
Excerpt from EB-2019-0082, Exhibit C-2-1, Attachment 2
Table 39: Projects with Applicable Variance Explanations - General Plant
[5 empty] | 2018 Capital Expenditures ($ Millions) |  |  | 2018 In Service Capital Additions ($ Millions) |  |  |  | Project Status
| ISD |  |  | Project Description | Approved | Actuals | Variance | Approved | Actuals | Variance |  | Approved In Service Date | Approved Status | Actual/ Bridge In Service Date | Status | Variance (in Quarters) | Variance Explanations
Operations Capital
Grid Operating and Control Facilities
|  |  | Other | OGCC Data Centre Remediation | 2.344 | 0.9228 | -1.4212 | 0 | 3.9017 | 3.9017 | 100% | Q1-2018 | Execution | Q4-2018 | Execution | 3 | Preliminary Project Definition
Capital Common Corporate Costs and Other Costs
Information Technology (including Cornerstone)
|  |  | IT3 | Forestry Move to Mobile - Capital | 2.6615 | 3.3244 | 0.66282 | 3.1618 | 3.2019 | 0.040128 | 1.269% | Q1-2019 | Planning | Q4-2019 | Execution | 3 | Project Delivery Issues
|  |  | Other | Source-to-Order Transformation Project | 1.3643 | 1.4509 | 0.086645 | 7.5659 | 6.7873 | -0.7786 | -10.29% | Q2-2018 | Execution | Q2-2018 | Complete | 0 | Emergent Needs
|  |  | Other | Private Cloud Data Center - Capital | 0 | 9.2499 | 9.2499 | 0 | 3.2647 | 3.2647 | 100% | Q4-2019 | N/A | Q4-2019 | Planning | 0 | Accelerated Investments