## I-12-AMPCO-37-Updated
List of Material Capital Investments (EB-2019-0082 Exhibit B-1-1 TSP Section 3.3.6.1)
Table 5 - System Access - Material Capital Investments Proposed |  | EB-2019-0082 (As Filed) |  |  |  |  | EB-2021-0110 (As Filed)
|  | Plan | Plan | Plan | Plan | Plan | Actual | Forecast | Forecast | Forecast | Forecast
ISD | Investment Name | 2020 | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024
SA-01 | Connect New IAMGOLD Mine | 24.9 | 0 | 0 | 0 | 0 | 4.0121 | 15 | 19.4 | 23.3 | 0
SA-02 | Horner TS: Build a Second 230/27.6kV Station | 29.9 | 0 | 0 | 0 | 0 | 31.3097 | 13 | 0.5 | 0 | 0
SA-03 | Halton TS: Build a Second 230/27.6kV Station | 8 | 17.7 | 6 | 0 | 0 | 0 | 0 | -0.000888 | 0 | 5.3944
SA-04 | Connect Metrolinx Traction Substations | 6.5 | 7.9 | 7.1 | 1 | 0 | 0.35056 | 0.3 | 0.3 | 9.958 | 12.244
SA-05 | Future Transmission Load Connection Plans | 0 | 5 | 24.9 | 24.9 | 0 | 0 | 0 | 0 | 5.1969 | 23.9292
SA-06 | Protection and Control Modifications for Distributed Generation | 3.8 | 3.1 | 2.7 | 2.8 | 2.8 | 7.6984 | 5 | 5 | 4 | 4
SA-07 | Secondary Land Use Transmission Asset Modifications | 55.1 | 15 | 13.9 | 15.6 | 3.9 | 15.5941 | 21.7749 | 19.1461 | 9.7626 | 4.9072
System Access Projects & Programs Less Than $3M |  | 27.6 | 9.4 | 8.5 | 7.8 | 9.2 | 31.2144 | 58.6791 | 33.9726 | 105.3691 | 103.834
Total Gross System Access Capital ($M) |  | 155.7 | 58.1 | 63 | 52 | 15.8 | 90.1792 | 113.754 | 78.3179 | 157.5866 | 154.3088
Less Capital Contributions ($M) |  | -130.9 | -46.7 | -51.3 | -39.3 | -11.7 | -70.6325 | -73.6163 | -46.8578 | -78.185 | -83.4261
Total Net System Access Capital ($M) |  | 24.8 | 11.3 | 11.7 | 12.7 | 4.1 | 19.5467 | 40.1377 | 31.4601 | 79.4016 | 70.8827
Table 6 - System Renewal - Material Capital Investments Proposed
ISD | Investment Name | 2020 | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024
SR-01 | Air Blast Circuit Breaker Replacement Projects | 107.5 | 128.4 | 133.5 | 129.2 | 98.7 | 177.8401 | 138.6365 | 130.3516 | 150.3392 | 124.5653
SR-02 | Station Reinvestment Projects | 107 | 125.4 | 120.6 | 87.9 | 53.9 | 121.7134 | 94.7444 | 110.6294 | 100.8044 | 76.5867
SR-03 | Bulk Station Transformer Replacement Projects | 33.2 | 51.8 | 72.5 | 131.5 | 113.8 | 15.1257 | 20.2008 | 63.125 | 107.2251 | 97.02
SR-04 | Bulk Station Switchgear and Ancillary Equipment Replacement Projects | 17.5 | 32.4 | 41.4 | 34.6 | 49.3 | 12.1763 | 12.06 | 47.2036 | 73.0437 | 57.1837
SR-05 | Load Station Transformer Replacement Projects | 91.2 | 132.3 | 129.4 | 178.5 | 200 | 83.906 | 101.0593 | 140.7191 | 156.4193 | 162.865
SR-06 | Load Station Switchgear and Ancillary Equipment Replacement Projects | 19.2 | 30.8 | 47.5 | 58.4 | 77 | 17.8336 | 12.8872 | 22.6334 | 39.0935 | 48.0968
SR-07 | Protection and Automation Replacement Projects | 6.7 | 8.6 | 12.7 | 12.2 | 21.7 | 7.0543 | 7.0455 | 8.8768 | 2.1757 | 1.4832
SR-08 | John Transformer Station Reinvestment Project | 3.5 | 17.9 | 25.6 | 24 | 20.9 | 0.0067016 | 0 | 0 | 0.25026 | 0.42486
SR-09 | Transmission Station Demand and Spares and Targeted Assets | 44.2 | 36.4 | 37 | 37.7 | 38.3 | 61.2671 | 40.1915 | 41.0232 | 43.8549 | 44.6772
SR-10 | Transformer Protection Replacement | 3.8 | 0 | 0 | 0 | 0 | 0.33161 | 0.64188 | 0.62045 | 0 | 0
SR-11 | Legacy SONET System Replacement | 4.1 | 26 | 27.6 | 28.1 | 28.1 | 0.39665 | 0.6 | 4.61 | 19.49 | 29.38
SR-12 | Telecom Performance Improvements | 0 | 0.9 | 5.5 | 3.7 | 0 | 0 | 0 | 0 | 0.97078 | 5.7595
SR-13 | ADSS Fibre Optic Cable Replacements | 7 | 7.1 | 1 | 0 | 0 | 0.50497 | 4.98 | 3.31 | 3.2 | 0
SR-14 | Mobile Radio System Replacement | 2.9 | 6.2 | 6.1 | 4 | 0 | 0 | 0.288 | 2.976 | 5.184 | 6.672
SR-15 | Telecom Fibre IRU Agreement Renewals | 0 | 2.8 | 8.5 | 2.6 | 1.5 | 0 | 2.7996 | 8.5318 | 2.6192 | 1.4626
SR-16 | NERC CIP-014 Physical Security Implementation | 18 | 18 | 18 | 0 | 0 | 24.2186 | 20.6 | 15.067 | 0 | 0
SR-17 | NERC CIP Transient Cyber Asset Project | 3.5 | 0 | 0 | 0 | 0 | 1.0571 | 7.54 | 7.56 | 0 | 0
SR-18 | PSIT Cyber Equipment Replacement | 1 | 5 | 7.7 | 7 | 3.4 | 2.8839 | 6.365 | 8.317 | 0 | 0
SR-19 | Transmission Line Refurbishment - End of Life ACSR, Copper Conductors & Structures | 81.8 | 122.1 | 94.5 | 51 | 75.9 | 43.5305 | 54.6929 | 95.9647 | 46.4527 | 47.4122
SR-20 | Transmission Line Refurbishment - Near End of Life ACSR Conductor | 62.2 | 63.4 | 111.7 | 117.8 | 137.7 | 0.057282 | 5.9411 | 0 | 6.3228 | 61.6592
SR-21 | Wood Pole Structure Replacements | 51 | 52 | 53 | 54.1 | 55.2 | 47.0142 | 48.7658 | 52.7102 | 56.504 | 57.6341
SR-22 | Steel Structure Coating Program | 11.4 | 21.8 | 22.3 | 22.7 | 23.2 | 8.0869 | 21.399 | 22.5545 | 23.63 | 24.07
SR-23 | Tower Foundation Assess/Clean/Coat Program | 11.8 | 22.3 | 22.8 | 23.3 | 23.7 | 8.3845 | 8.5394 | 11.2773 | 10.52 | 10.72
SR-24 | Transmission Line Shieldwire Replacement | 12.3 | 12.6 | 12.8 | 13.1 | 13.4 | 4.5083 | 12.1962 | 12.9167 | 12.054 | 12.2951
SR-25 | Transmission Line Insulator Replacement | 68.3 | 69.7 | 66.3 | 67.6 | 68.9 | 57.0608 | 67.5052 | 68.6013 | 78.4392 | 78.0528
SR-26 | Transmission Line Emergency Restoration | 9.6 | 9.8 | 10 | 10.2 | 10.4 | 11.9983 | 9.7094 | 9.8956 | 10.1874 | 10.3911
SR-27 | C5E/C7E Underground Cable Replacement | 2.1 | 29.8 | 30.9 | 32.2 | 29.2 | 2.7855 | 11.769 | 25.1184 | 38.268 | 23.6805
SR-28 | OPGW Infrastructure Projects | 5.3 | 7.5 | 2.2 | 6.2 | 9.7 | 0.14829 | 1.6634 | 11.1968 | 16.1271 | 10.7232
SR-29 | Physical Security ISL Application Replacement | 5 | 1.1 | 0 | 0 | 0 | 4.2725 | 1.5045 | 0 | 0 | 0
System Renewal Projects & Programs Less Than $3M |  | 77.8 | 67.3 | 60.1 | 44.1 | 41.1 | 98.2753 | 29.8386 | 59.1588 | 180.753 | 237.4809
Total Gross System Renewal Capital ($M) |  | 869.1 | 1109.2 | 1181.1 | 1181.5 | 1194.9 | 812.4383 | 744.1641 | 984.9486 | 1183.9282 | 1230.296
Less Capital Contributions ($M) |  | -3.8 | -6.1 | -8.3 | -4.1 | -1.1 | -8.449 | -4.5454 | -13.4362 | -5.9697 | -1.9512
Total Net System Renewal Capital ($M) |  | 865.2 | 1103.1 | 1172.8 | 1177.4 | 1193.8 | 803.9893 | 739.6187 | 971.5125 | 1177.9585 | 1228.3449
Table 7 - System Service - Material Capital Investments Proposed
ISD | Investment Name | 2020 | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024
SS-01 | Lennox TS: Install 500kV Shunt Reactors | 32.3 | 0 | 0 | 0 | 0 | 21.8353 | 18.95 | 0 | 0 | 0
SS-02 | Wataynikaneyap Line to Pickle Lake Connection | 24.9 | 1.5 | 0 | 0 | 0 | 5.0557 | 22.88 | 4 | 0 | 0
SS-03 | Nanticoke TS: Connect HVDC Lake Erie Circuits | 3 | 10 | 4 | 0 | 0 | 0.00015289 | 0 | 3.057 | 10.2 | 4.08
SS-04 | East-West Tie Connection | 46.3 | 38.8 | 22.6 | 0 | 0 | 68.1104 | 21.53 | 20.03 | 1 | 0
SS-05 | St. Lawrence TS: Phase Shifter Upgrade | 9 | 18 | 9 | 0 | 0 | 0.94103 | 17 | 37.8 | 12 | 0
SS-06 | Merivale TS to Hawthorne TS: 230kV Conductor Upgrade | 5 | 10 | 8.4 | 0 | 0 | 0.26079 | 1 | 9 | 9 | 0
SS-07 | Milton SS: Station Expansion and Connect 230kV Circuits | 0 | 2 | 3 | 69.4 | 119.1 | 0 | 0 | 0 | 0 | 0
SS-08 | Northwest Bulk Transmission Line | 8 | 12.9 | 8.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SS-09 | Barrie Area Transmission Upgrade | 38.1 | 28.2 | 8.5 | 0 | 0 | 13.2081 | 31.2 | 34.6 | 0 | 0
SS-10 | Kapuskasing Area Transmission Reinforcement | 6.7 | 3.8 | 0 | 0 | 0 | 16.6044 | 3.0158 | 2.3 | 0 | 0
SS-11 | South Nepean Transmission Reinforcement | 27.5 | 10.5 | 0 | 0 | 0 | 29.4273 | 17.5918 | 3.2814 | 0 | 0
SS-12 | Alymer-Tillsonburg Area Transmission Reinforcement | 10 | 13.1 | 6.1 | 0 | 0 | 0.69515 | 2.72 | 0.673 | 0 | 0
SS-13 | Leamington Area Transmission Reinforcement | 4.9 | 9.7 | 59.1 | 63.8 | 63.8 | 44.3944 | 99.71 | 27.3 | 0.22 | 0
SS-14 | Southwest GTA Transmission Reinforcement | 10.3 | 7.8 | 6.9 | 3.9 | 2 | 0.55207 | 0.5 | 4.1 | 6.5 | 7.5
SS-15 | Future Transmission Regional Plans | 0 | 0 | 10.5 | 19.6 | 0 | 0 | 0 | 0 | 10.71 | 20.029
SS-16 | Customer Power Quality Program | 3.3 | 3.4 | 3.4 | 3.4 | 3.5 | 1.2463 | 0 | 0 | 0 | 0
System Service Projects & Programs Less Than $3M |  | 9.1 | 8.2 | 9.9 | 14 | 15.9 | 19.5923 | 11.2912 | 16.3596 | 57.4206 | 74.1995
Total Gross System Service Capital ($M) |  | 238.3 | 177.9 | 160.3 | 174.3 | 204.2 | 221.9234 | 247.3888 | 162.501 | 107.0506 | 105.8085
Less Capital Contributions ($M) |  | -34.2 | -29.7 | -8.5 | 0 | 0 | -25.8212 | -23.4882 | -40.4528 | -16.2 | -4.1886
Total Net System Service Capital ($M) |  | 204.1 | 148.2 | 151.8 | 174.3 | 204.2 | 196.1021 | 223.9006 | 122.0483 | 90.8506 | 101.6199
Table 8 - General Plant - Material Capital Investments Proposed
ISD | Investment Name | 2020 | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024
GP-01 | Integrated System Operations Centre - New Facility Development | 32.4 | 12.7 | 0 | 0 | 0 | 28.0996 | 42.1655 | 0 | 0 | 0
GP-02 | Grid Control Network Sustainment | 8 | 6.1 | 6.3 | 6.5 | 6.6 | 3.5863 | 4.37 | 4.37 | 6.4987 | 6.6287
GP-03 | Network Management System Capital Sustainment | 0 | 7.8 | 22.4 | 8.2 | 0 | 5.0193 | 10.4 | 16.6 | 7.6 | 0
GP-04 | Integrated Voice Communications and Telephony System Refresh | 0 | 1.9 | 3.2 | 1.1 | 0 | 0 | 0.998 | 3.1711 | 0.96864 | 0
GP-05 | Transmission Non-Operational Data Management System | 5.2 | 5.3 | 5.4 | 5.5 | 1.1 | 0 | 5.3268 | 5.4281 | 5.5366 | 1.1295
GP-06 | Operating Common IT Infrastructure | 0.8 | 2 | 3.7 | 3.3 | 2.2 | 0 | 1.9975 | 2.0095 | 3.3839 | 2.9609
GP-07 | Hardware/Software Refresh and Maintenance | 2 | 2 | 1.9 | 1.9 | 5.8 | 4.0162 | 2.2156 | 1.7365 | 1.2055 | 2.3645
GP-08 | Corporate Services Transformation - HR / Payroll | 5 | 1.5 | 0 | 0 | 0 | 4.2527 | 5.1896 | 6.2375 | 0 | 0
GP-09 | Corporate Services Transformation - Finance | 1 | 3 | 5 | 6.5 | 5 | 0.050861 | 2.6092 | 0.54172 | 10.0421 | 13.4138
GP-10 | Facility Accommodation & Improvements Service Centres & Admin | 8.1 | 4.9 | 8.2 | 16.4 | 4.3 | 5.2545 | 5.5494 | 5.1906 | 11.7079 | 11.8718
GP-11 | Transmission Facilities & Site Improvements | 9.4 | 9.5 | 9.6 | 9.7 | 9.9 | 11.4141 | 9.5172 | 9.5801 | 9.6882 | 9.882
GP-12 | Transport & Work Equipment | 13.2 | 13.2 | 13.3 | 13.3 | 13.3 | 8.7987 | 12.303 | 9.673 | 20.8456 | 21.3043
General Plant Projects & Programs Less Than $3M |  | 30.2 | 24.3 | 15.8 | 11.1 | 10.7 | 54.2203 | 35.1848 | 38.2489 | 69.3214 | 54.484
Total Gross System Service Capital ($M) |  | 115.4 | 94.4 | 94.7 | 83.6 | 58.9 | 124.7126 | 137.8266 | 102.787 | 146.7986 | 124.0394
Total Net General Plant Capital ($M) |  | 115.4 | 94.4 | 94.7 | 83.6 | 58.9 | 124.7126 | 137.8266 | 102.787 | 146.7986 | 124.0394