## Figure 1 and 2 Underlying Data
| ISD Number EB-2019-0082 | Project Total DRO Plan ($M) | Project Cost Category | Project Total Actual / Forecast ($M) | Project Total Variance ($M) | Cost Variance Category | In-Service DRO Plan | Actual / Forecast In-Service | In-Service Year Variance (days) | In-Service Date Variance Category
System Access
Load Customer Connection
Leamington TS: New 230/27.6 kV DESN | Other | 56.9 | >$50M | 54.6 | -2.3 | 0% to -5% | 2018-05-30 | 2018-05-26 | -4 | Less than 3 mo. early
System Renewal
Integrated Station Investment
Birch TS: Component Replacement | Other | 35.6 | $30 to $50M | 35.5 | -0.1 | 0% to -5% | 2020-04-30 | 2020-04-30 | 0 | Less than 3 mo. late
Chatham SS: Capacitor and Breaker Replacement | Other | 5.1 | $3 to $10M | 5 | -0.1 | 0% to -5% | 2020-06-25 | 2020-05-18 | -38 | Less than 3 mo. early
Chenaux TS EOL Transformer Replacement | Other | 40.2 | $30 to $50M | 41.1 | 0.9 | 0% to 5% | 2021-01-28 | 2021-01-28 | 0 | Less than 3 mo. late
Clarabelle TS: Component Replacement | Other | 6.4 | $3 to $10M | 6.6 | 0.2 | 0% to 5% | 2021-01-28 | 2020-11-30 | -59 | Less than 3 mo. early
Detweiler TS: T2, T4 & Component Replacement | SR-03 | 21.2 | $10 to $30M | 22.1 | 0.9 | 0% to 5% | 2021-09-15 | 2021-06-30 | -77 | Less than 3 mo. early
Dryden TS - ISCR | Other | 38.1 | $30 to $50M | 38.1 | 0 | 0% to -5% | 2021-03-15 | 2021-09-30 | 199 | 6 mo.-1 yr late
Elgin TS; Station Refurbishment | SR-02 | 75.1 | >$50M | 71.3 | -3.8 | 0% to -5% | 2021-11-30 | 2021-11-30 | 0 | Less than 3 mo. late
Gage TS: T3,T4,T5,T6, PCT & Switchyard Reconfiguration | SR-02 | 53.6 | >$50M | 56.8 | 3.2 | 5% to 10% | 2021-12-17 | 2021-12-17 | 0 | Less than 3 mo. late
Hanmer TS: Northern Station Replacement | SR-02 | 83.4 | >$50M | 93.5 | 10.1 | 10% to 15% | 2022-03-15 | 2022-06-30 | 107 | 3-6 mo. late
Hinchinbrooke SS BULK | Other | 22.5 | $10 to $30M | 23.5 | 1 | 0% to 5% | 2020-12-29 | 2021-11-30 | 336 | 6 mo.-1 yr late
King Edward TS T3 and PCT Replacement | SR-05 | 15.9 | $10 to $30M | 15 | -0.9 | -5% to -10% | 2022-01-27 | 2021-10-29 | -90 | Less than 3 mo. early
Kleinburg TS: Component Replacement | Other | 5.6 | $3 to $10M | 7 | 1.4 | 20% to 25% | 2021-03-15 | 2020-12-15 | -90 | Less than 3 mo. early
Leaside TS BULK; Component Replacement | Other | 57.9 | >$50M | 61.2 | 3.3 | 5% to 10% | 2021-03-30 | 2021-03-31 | 1 | Less than 3 mo. late
Leaside TS: 27.6kV Switchyard & Component Replacement | SR-06 | 36.3 | $30 to $50M | 45.4 | 9.1 | 20% to 25% | 2020-12-18 | 2021-09-15 | 271 | 6 mo.-1 yr late
Manby TS – ISCR | Other | 29.8 | $10 to $30M | 31.1 | 1.3 | 0% to 5% | 2021-02-13 | 2021-05-19 | 95 | 3-6 mo. late
Martindale TS: T21/T23 & Component Replacement | SR-02 | 73.8 | >$50M | 71.8 | -2 | 0% to -5% | 2021-12-15 | 2021-12-13 | -2 | Less than 3 mo. early
Meaford TS: Component Replacement | Other | 5.3 | $3 to $10M | 5.4 | 0.1 | 0% to 5% | 2021-06-19 | 2021-03-21 | -90 | Less than 3 mo. early
Minden TS: T1, T2, PCT, 44kV Yard & Component Replacement | SR-05 | 33.2 | $30 to $50M | 34.5 | 1.3 | 0% to 5% | 2021-03-02 | 2021-10-22 | 234 | 6 mo.-1 yr late
Newton TS: T1 & Component Replacement | SR-05 | 3.5 | $3 to $10M | 9.8 | 6.3 | >50% above budget | 2021-04-30 | 2021-04-30 | 0 | Less than 3 mo. late
Runnymede TS: T3, T4 & Switchyard Replacement | SR-02 | 30.2 | $30 to $50M | 35.9 | 5.7 | 15% to 20% | 2021-09-20 | 2021-09-20 | 0 | Less than 3 mo. late
Sheppard TS: T3, T4, PCT, LV Yard & Component Replacement | SR-02 | 40.2 | $30 to $50M | 37.8 | -2.4 | -5% to -10% | 2021-02-25 | 2021-05-20 | 84 | Less than 3 mo. late
St. Thomas TS: Station Decom & W3T, W4T, T11T Reconfiguration | Other | 2.7 | $3 to $10M | 3.7 | 1 | 35% to 40% | 2020-10-15 | 2020-10-15 | 0 | Less than 3 mo. late
Strachan TS T12/T14; T12 & Component Replacement | SR-05 | 13.7 | $10 to $30M | 19.4 | 5.7 | 40% to 45% | 2022-08-26 | 2021-08-26 | -365 | 6 mo.-1 yr early
Transmission Station Renewal - Air Blast Circuit Breakers
Beck 2 TS, ABCB Replacement & Yard Upgrade | SR-01 | 132.4 | >$50M | 128.4 | -4 | 0% to -5% | 2023-03-31 | 2023-07-15 | 106 | 3-6 mo. late
Bruce A 230kV- Replace Breakers & Upgrade Station | SR-01 | 118.6 | >$50M | 118.2 | -0.4 | 0% to -5% | 2021-06-15 | 2020-12-15 | -182 | 6 mo.-1 yr early
Cherrywood TS 230kV BULK; ABCB & Component Replacement | SR-01 | 90.3 | >$50M | 111.6 | 21.3 | 20% to 25% | 2023-06-29 | 2023-06-29 | 0 | Less than 3 mo. late
Lennox TS BULK: ABCB Component Replacement | SR-01 | 108.6 | >$50M | 142.5 | 33.9 | 30% to 35% | 2024-02-08 | 2026-11-30 | 1026 | Over 2 yrs late
Middleport TS ABCB Replacement | SR-01 | 113.4 | >$50M | 119.8 | 6.4 | 5% to 10% | 2025-09-28 | 2025-06-30 | -90 | Less than 3 mo. early
Nanticoke TS ABCB Replacement | SR-01 | 61.2 | >$50M | 66.5 | 5.3 | 5% to 10% | 2025-10-13 | 2025-07-15 | -90 | Less than 3 mo. early
IT Security
ISL Replacement-Discovery-Capital | SR-29 | 11.8 | $10 to $30M | 12.2 | 0.4 | 0% to 5% | 2021-12-20 | 2021-12-31 | 11 | Less than 3 mo. late
Overhead Lines Refurbishment Projects, Component Replacement Programs and Secondary Land Use Projects
D6V/D7V, Guelph North JCT-Fergus TS, Transmission Line Refurbishment | Other | 12.4 | $10 to $30M | 7 | -5.4 | -40% to -45% | 2021-01-31 | 2020-12-15 | -47 | Less than 3 mo. early
CxA, Cameron Falls GS-Alexander G | Other | 7.5 | $3 to $10M | 8.5 | 1 | 10% to 15% | 2020-10-15 | 2021-09-30 | 350 | 6 mo.-1 yr late
D3A, Allanburg TS X ASW Steel CT | SR-19 | 12.9 | $10 to $30M | 13.5 | 0.6 | 0% to 5% | 2020-09-28 | 2020-09-07 | -21 | Less than 3 mo. early
D4Z, Nine Mile JCT-IPB Casey JCT | Other | 3.4 | $3 to $10M | 4 | 0.6 | 15% to 20% | 2021-01-30 | 2020-12-15 | -46 | Less than 3 mo. early
Transmission Line Refurbishment
A7L/R1LB/A6P & 57M1, Alxdr B-Lkhd, Transmission Line Refurbishment | SR-19 | 67.9 | >$50M | 68.3 | 0.4 | 0% to 5% | 2022-11-08 | 2022-08-10 | -90 | Less than 3 mo. early
B3/B4, Horning Mt. - Glanford, Transmission Line Refurbishment | SR-19 | 19.4 | $10 to $30M | 17.3 | -2.1 | -10% to -15% | 2021-01-13 | 2020-12-15 | -29 | Less than 3 mo. early
D6, Des Joachims TS X Petawawa DS, Transmission Line Refurbishment | SR-19 | 41.3 | $30 to $50M | 42.5 | 1.2 | 0% to 5% | 2021-12-29 | 2022-12-15 | 351 | 6 mo.-1 yr late
Protection and Automation
Install DDRs for NERC Compliance | Other | 9.3 | $3 to $10M | 8.3 | -1 | -10% to -15% | 2022-03-31 | 2021-12-31 | -90 | Less than 3 mo. early
Underground Lines Cable Refurbishment & Replacement
HV UG Cable - Replace H7L/H11L | Other | 43 | $30 to $50M | 45.4 | 2.4 | 5% to 10% | 2020-01-03 | 2020-09-30 | 271 | 6 mo.-1 yr late
System Service
Inter Area Network Capability
Lennox TS 500kV Shunt Reactors | SS-01 | 46.2 | $30 to $50M | 47.2 | 1 | 0% to 5% | 2021-11-26 | 2021-11-26 | 0 | Less than 3 mo. late
Local Area Supply Adequacy
Hawthorne TS: Replace 2 Existing Transformers | Other | 20.9 | $10 to $30M | 20.4 | -0.5 | 0% to -5% | 2021-01-31 | 2021-03-30 | 58 | Less than 3 mo. late
Kapuskasing Area Reinforcement | SS-10 | 33.7 | $30 to $50M | 32 | -1.7 | 0% to -5% | 2022-03-16 | 2022-11-23 | 252 | 6 mo.-1 yr late
Performance Enhancement
Port Colborne TS - Outlier Performance Improvement | Other | 6.2 | $3 to $10M | 3.9 | -2.3 | -35% to -40% | 2020-05-30 | 2020-05-29 | -1 | Less than 3 mo. early
Risk Mitigation
L7S - Reliability Performance Mitigation | Other | 3.6 | $3 to $10M | 5.3 | 1.7 | 45% to 50% | 2021-03-18 | 2020-12-18 | -90 | Less than 3 mo. early