## Table2
| Phase | ISD Number EB-2019-0082 | 2020 Capex DRO Plan ($M) | 2020 Capex Actual ($M) | 2020 ISA DRO Plan ($M) | 2020 ISA Actual ($M) | Project Total DRO Plan ($M) | Project Total Actual / Forecast ($M) | Project Total Variance ($M) | In-Service Year DRO Plan | Actual / Forecast In-Service Year | In-Service Year Variance (Years) | Variance Category
System Access
Load Customer Connection
Leamington TS: New 230/27.6 kV DESN | Complete | Other | 2.3 | 3.6 | 2.3 | 3.6 | 56.9 | 54.6 | -2.3 | 2018 | 2018 | 0 | Not a material variance
System Renewal
Integrated Station Investment
Birch TS: Component Replacement | Complete | Other | 1.5 | 0.8 | 3.2 | 2.5 | 35.6 | 35.5 | -0.1 | 2020 | 2020 | 0 | Not a material variance
Chatham SS: Capacitor and Breaker Replacement | Complete | Other | 0.6 | 0.6 | 5.1 | 5 | 5.1 | 5 | -0.1 | 2020 | 2020 | 0 | Not a material variance
Chenaux TS EOL Transformer Replacement | Complete | Other | 5.5 | 7.4 | 21 | 22.5 | 40.2 | 41.1 | 0.9 | 2021 | 2021 | 0 | Not a material variance
Clarabelle TS: Component Replacement | Complete | Other | 1.8 | 1.3 | 4.2 | 3.2 | 6.4 | 6.6 | 0.2 | 2021 | 2020 | -1 | Not a material variance
Detweiler TS: T2, T4 & Component Replacement | Executing | SR-03 | 10.5 | 10.7 | 11.1 | 12.5 | 21.2 | 22.1 | 0.9 | 2021 | 2021 | 0 | Not a material variance
Dryden TS - ISCR | Executing | Other | 3.3 | 0.5 | 4 | 0.7 | 38.1 | 38.1 | 0 | 2021 | 2021 | 0 | Not a material variance
Elgin TS; Station Refurbishment | Executing | SR-02 | 8.5 | 5.2 | 48.8 | 44.7 | 75.1 | 71.3 | -3.8 | 2021 | 2021 | 0 | Not a material variance
Gage TS: T3,T4,T5,T6, PCT & Switchyard Reconfiguration | Executing | SR-02 | 18.5 | 18.4 | 20 | 24.1 | 53.6 | 56.8 | 3.2 | 2021 | 2021 | 0 | Not a material variance
Hanmer TS: Northern Station Replacement | Executing | SR-02 | 10.1 | 20 | 15.5 | 27.8 | 83.4 | 93.5 | 10.1 | 2022 | 2022 | 0 | Execution Factors
Hinchinbrooke SS BULK | Executing | Other | 0.4 | 5.2 | 1.5 | 4.8 | 22.5 | 23.5 | 1 | 2020 | 2021 | 1 | Execution Factors
King Edward TS T3 and PCT Replacement | Executing | SR-05 | 4.8 | 6.3 | 4.6 | 4 | 15.9 | 15 | -0.9 | 2022 | 2021 | -1 | Not a material variance
Kleinburg TS: Component Replacement | Complete | Other | 2.4 | 1.6 | 4.9 | 4.1 | 5.6 | 7 | 1.4 | 2021 | 2020 | -1 | Work Definition
Leaside TS BULK; Component Replacement | Executing | Other | 5.6 | 5.8 | 10.8 | 13.7 | 57.9 | 61.2 | 3.3 | 2021 | 2021 | 0 | Not a material variance
Leaside TS: 27.6kV Switchyard & Component Replacement | Executing | SR-06 | 8.4 | 14.8 | 25.5 | 31.9 | 36.3 | 45.4 | 9.1 | 2020 | 2021 | 1 | Execution Factors
Manby TS – ISCR | Executing | Other | 3.7 | 4.6 | 3.6 | 4.3 | 29.8 | 31.1 | 1.3 | 2021 | 2021 | 0 | Not a material variance
Martindale TS: T21/T23 & Component Replacement | Executing | SR-02 | 11.6 | 9.9 | 14 | 15.2 | 73.8 | 71.8 | -2 | 2021 | 2021 | 0 | Not a material variance
Meaford TS: Component Replacement | Executing | Other | 4.1 | 4.3 | 4.9 | 5.1 | 5.3 | 5.4 | 0.1 | 2021 | 2021 | 0 | Not a material variance
Minden TS: T1, T2, PCT, 44kV Yard & Component Replacement | Executing | SR-05 | 20.8 | 17.9 | 25.1 | 22 | 33.2 | 34.5 | 1.3 | 2021 | 2021 | 0 | Not a material variance
Newton TS: T1 & Component Replacement | Executing | SR-05 | 3.5 | 6.6 | 0 | 5.8 | 3.5 | 9.8 | 6.3 | 2021 | 2021 | 0 | Emergent Needs
Runnymede TS: T3, T4 & Switchyard Replacement | Executing | SR-02 | 17.5 | 17.8 | 19.8 | 22.3 | 30.2 | 35.9 | 5.7 | 2021 | 2021 | 0 | Execution Factors
Sheppard TS: T3, T4, PCT, LV Yard & Component Replacement | Executing | SR-02 | 20 | 15.6 | 39.1 | 33.9 | 40.2 | 37.8 | -2.4 | 2021 | 2021 | 0 | Not a material variance
St. Thomas TS: Station Decom & W3T, W4T, T11T Reconfiguration | Complete | Other | 1.8 | 2.2 | 2.8 | 3.2 | 2.7 | 3.7 | 1 | 2020 | 2020 | 0 | Execution Factors
Strachan TS T12/T14; T12 & Component Replacement | Executing | SR-05 | 3.7 | 5.6 | 6 | 8.7 | 13.7 | 19.4 | 5.7 | 2022 | 2021 | -1 | Execution Factors
Transmission Station Renewal - Air Blast Circuit Breakers
Beck 2 TS, ABCB Replacement & Yard Upgrade | Executing | SR-01 | 15.7 | 11.4 | 17.1 | 10.2 | 132.4 | 128.4 | -4 | 2023 | 2023 | 0 | Not a material variance
Bruce A 230kV- Replace Breakers & Upgrade Station | Complete | SR-01 | 6.8 | 8.5 | 0.8 | 12.1 | 118.6 | 118.2 | -0.4 | 2021 | 2020 | -1 | Not a material variance
Cherrywood TS 230kV BULK; ABCB & Component Replacement | Executing | SR-01 | 20.4 | 26.7 | 26.8 | 31.7 | 90.3 | 111.6 | 21.3 | 2023 | 2023 | 0 | Execution Factors
Lennox TS BULK: ABCB Component Replacement | Executing | SR-01 | 13.6 | 12.5 | 50 | 58.8 | 108.6 | 142.5 | 33.9 | 2024 | 2026 | 2 | Work Definition
Middleport TS ABCB Replacement | Executing | SR-01 | 19.6 | 35.3 | 21 | 19.6 | 113.4 | 119.8 | 6.4 | 2025 | 2025 | 0 | Not a material variance
Nanticoke TS ABCB Replacement | Executing | SR-01 | 10.1 | 16.7 | 0 | 11.4 | 61.2 | 66.5 | 5.3 | 2025 | 2025 | 0 | Not a material variance
IT Security
ISL Replacement-Discovery-Capital | Executing | SR-29 | 4.4 | 4.3 | 6.2 | 6.1 | 11.8 | 12.2 | 0.4 | 2021 | 2021 | 0 | Not a material variance
Overhead Lines Refurbishment Projects, Component Replacement Programs and Secondary Land Use Projects
D6V/D7V, Guelph North JCT-Fergus TS, Transmission Line Refurbishment | Complete | Other | 4.4 | 4.4 | 6.5 | 3.6 | 12.4 | 7 | -5.4 | 2021 | 2020 | -1 | Work Definition
CxA, Cameron Falls GS-Alexander G | Executing | Other | 1.2 | 1.3 | 7.5 | 6.7 | 7.5 | 8.5 | 1 | 2020 | 2021 | 1 | Execution Factors
D3A, Allanburg TS X ASW Steel CT | Complete | SR-19 | -0.8 | 2.8 | 12.1 | 12.6 | 12.9 | 13.5 | 0.6 | 2020 | 2020 | 0 | Not a material variance
D4Z, Nine Mile JCT-IPB Casey JCT | Complete | Other | 2.4 | 3.6 | 4.4 | 4.5 | 3.4 | 4 | 0.6 | 2021 | 2020 | -1 | Execution Factors
Transmission Line Refurbishment
A7L/R1LB/A6P & 57M1, Alxdr B-Lkhd, Transmission Line Refurbishment | Executing | SR-19 | 24.9 | 15 | 0 | 6 | 67.9 | 68.3 | 0.4 | 2022 | 2022 | 0 | Not a material variance
B3/B4, Horning Mt. - Glanford, Transmission Line Refurbishment | Complete | SR-19 | 7.2 | 6.8 | 15.2 | 12.4 | 19.4 | 17.3 | -2.1 | 2021 | 2020 | -1 | Execution Factors
D6, Des Joachims TS X Petawawa DS, Transmission Line Refurbishment | Executing | SR-19 | 4.4 | 16.1 | 2.2 | 12.7 | 41.3 | 42.5 | 1.2 | 2021 | 2022 | 1 | Not a material variance
Protection and Automation
Install DDRs for NERC Compliance | Executing | Other | 4.4 | 3.6 | 4 | 3.8 | 9.3 | 8.3 | -1 | 2022 | 2021 | -1 | Work Definition
Underground Lines Cable Refurbishment & Replacement
HV UG Cable - Replace H7L/H11L | Complete | Other | 3.9 | 4.4 | 40.9 | 41.3 | 43 | 45.4 | 2.4 | 2020 | 2020 | 0 | Not a material variance
System Service
Inter Area Network Capability
Lennox TS 500kV Shunt Reactors | Executing | SS-01 | 18.9 | 21.8 | 22 | 0 | 46.2 | 47.2 | 1 | 2021 | 2021 | 0 | Not a material variance
Local Area Supply Adequacy
Hawthorne TS: Replace 2 Existing Transformers | Executing | Other | 4.7 | 2.4 | 10.3 | 0.1 | 20.9 | 20.4 | -0.5 | 2021 | 2021 | 0 | Not a material variance
Kapuskasing Area Reinforcement | Executing | SS-10 | 15.2 | 16.6 | 11.2 | 11.9 | 33.7 | 32 | -1.7 | 2022 | 2022 | 0 | Not a material variance
Performance Enhancement
Port Colborne TS - Outlier Performance Improvement | Complete | Other | 2.3 | 3.2 | 2.9 | 3.9 | 6.2 | 3.9 | -2.3 | 2020 | 2020 | 0 | Work Definition
Risk Mitigation
L7S - Reliability Performance Mitigation | Complete | Other | 2.1 | 3.7 | 0 | 4.3 | 3.6 | 5.3 | 1.7 | 2021 | 2020 | -1 | Work Definition
Grand Total |  |  | 356.7 | 407.8 | 558.9 | 599.3 | 1750.2 | 1848.9 | 98.7

## Table 3
| ISD Number | 2020 Capex DRO Plan ($M) | 2020 Capex Actual ($M) | Capex Variance ($M) | 2020 ISA DRO Plan ($M) | 2020 ISA Actual ($M) | ISA Variance ($M) | Reportable Unit | 2020 Unit DRO Plan | 2020 Unit Actual | Unit Variance | Variance Category
System Renewal
Overhead Lines Component Replacement Programs and Secondary Land Use Projects
Steel Structure Coating Program | SR-22 | 9.3 | 8.1 | -1.2 | 12 | 10.6 | -1.4 | # of structures | 222 | 222 | 0 | Work Definition
Transmission Line Emergency Restoration | SR-26 | 9.7 | 12 | 2.3 | 8.8 | 12.5 | 3.7 | # of work orders | 108 | 166 | 58 | Emergent Needs
Transmission Line Insulator Replacement | SR-25 | 58.8 | 57.1 | -1.7 | 62.9 | 58.2 | -4.7 | # of circuit structures | 3179 | 2794 | -385 | Not a material variance
Transmission Line Shieldwire Replacement | SR-24 | 10.7 | 4.3 | -6.4 | 10.8 | 2.7 | -8.1 | # of km | 282 | 39 | -243 | Execution Factors
Wood Pole Structure Replacements | SR-21 | 45.3 | 47 | 1.7 | 45.9 | 44.9 | -1 | # of structures | 897 | 796 | -101 | Not a material variance
Tower Foundation Assess/Clean/Coat & Life Extension Program | SR-23 | 10.6 | 9.5 | -1.1 | 12.5 | 9 | -3.5 | # of structures | 1177 | 1060 | -117 | Reprioritization
Tx Transformers Demand and Spares
Online DGA MonitorProgram | Other | 1.4 | 1.6 | 0.2 | 3 | 2.2 | -0.8 | # of units | 3 | 2 | -1 | Execution Factors
Transmission Station Demand, Spares and Targeted Assets | SR-09 | 54.7 | 59.1 | 4.4 | 65.7 | 60.9 | -4.8 | Various | - | - | - | Not a material variance
IT Security
NERC CIP-014 Physical Security Upgrades | SR-16 | 18 | 24.2 | 6.2 | 21.3 | 7.9 | -13.4 | # of sites | 11 | 2 | -9 | Execution Factors
Grand Total |  | 218.5 | 222.9 | 4.4 | 242.9 | 208.9 | -34