## B-03-01_3.9-2AA
[11 empty] | File Number: | 0
[11 empty] | Exhibit: | B
[11 empty] | Tab: | 1
[11 empty] | Schedule: | 2
Page:
[11 empty] | Date: | 2019-06-21
Appendix 2-AA w/ OEB Approved 2018-2022
Capital Projects Table ($M)
Investment | 2018 Plan (DRO) | 2018 | 2019 Plan (DRO) | 2019 | 2020 Plan (DRO) | 2020 | 2021 Plan (DRO) | 2021 Bridge | 2022 Plan (DRO) | 2022 Bridge | 2023 Test | 2024 Test | 2025 Test | 2026 Test | 2027 Test
System Access
D-SA-01 Joint Use and Relocations | 20.4138 | 20.4138 | 16.61 | 28.8386 | 17.7026 | 26.2092 | 17.692 | 21.3847 | 17.8609 | 19.1351 | 24.8384 | 29.0109 | 26.9599 | 26.4976 | 27.2493
D-SA-02 New Load Connections, Upgrades, Cancellations | 121.2148 | 121.2148 | 108.9214 | 141.7441 | 105.6085 | 146.3868 | 104.5562 | 130.6391 | 105.7715 | 141.7482 | 150.7174 | 154.5683 | 158.5047 | 162.5246 | 166.6511
D-SA-03 Customer Demand Distributed Energy Resources | 6.6659 | 6.6659 | 3.8042 | 6.6352 | 2.559 | 2.17 | 1.7418 | 1.9191 | 1.375 | 1.4003 | 1.4151 | 1.4151 | 1.4154 | 1.4157 | 1.416
D-SA-04 Metering Sustainment | 26.7897 | 26.7897 | 18.6101 | 20.1262 | 27.5745 | 18.838 | 26.9226 | 17.5825 | 18.0139 | 18.5245 | 62.6092 | 55.6472 | 40.1246 | 22.1633 | 8.9452
D-SA-Other | 0.0096028 | 0.0096028 | 0 | 0.0024219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total System Access | 175.0938 | 175.0938 | 147.9457 | 197.3464 | 153.4445 | 193.6041 | 150.9126 | 171.5254 | 143.0214 | 180.8081 | 239.58 | 240.6414 | 227.0046 | 212.6012 | 204.2616
System Renewal
D-SR-01 Distribution Stations Demand Capital Program | 6.6381 | 6.6381 | 4.5997 | 5.6139 | 4.7526 | 9.8084 | 4.8387 | 4.929 | 4.9615 | 5.022 | 6.1629 | 6.2862 | 6.4119 | 6.5401 | 6.6709
D-SR-02 Mobile Unit Substation Program | 1.3066 | 1.3066 | 4.923 | 6.9323 | 3.9959 | 3.9918 | 4.758 | 4.1569 | 4.7989 | 4.302 | 3.5092 | 4.239 | 2.8678 | 3.2514 | 4.5902
D-SR-03 Distribution Station Planned Component Replacement Program | 4.9918 | 4.9918 | 6.1956 | 7.6744 | 6.7255 | 8.768 | 6.7633 | 6.9265 | 6.9278 | 7.0937 | 4.5627 | 3.3218 | 1.141 | 1.1638 | 1.1871
D-SR-04 Distribution Station Refurbishment | 11.7479 | 11.7461 | 18.655 | 16.5025 | 14.1821 | 7.3977 | 21.2688 | 6.8682 | 27.5843 | 3.1823 | 44.8214 | 41.4864 | 28.4704 | 32.2753 | 32.0669
D-SR-05 Distribution Lines Trouble Call and Storm Damage Response | 112.6981 | 112.6981 | 75.2528 | 74.5837 | 80.2152 | 118.3908 | 78.6645 | 92.2891 | 79.5128 | 93.806 | 106.0051 | 108.1256 | 110.288 | 112.4937 | 114.7436
D-SR-06 Distribution Lines PCB Equipment Replacement Program | 6.3229 | 6.3228 | 9.9076 | 8.1298 | 10.9553 | 4.7656 | 12.3607 | 9.548 | 12.5222 | 9.4776 | 9.416 | 9.4512 | 9.46 | 0 | 0
D-SR-07 Pole Sustainment Program | 51.9665 | 51.9665 | 53.243 | 44.3485 | 59.6883 | 43.5998 | 58.7665 | 73.4008 | 58.2876 | 60.1383 | 107.885 | 110.6286 | 112.383 | 114.9181 | 116.7929
D-SR-08 Distribution Lines Minor Component Replacement Program | 1.3556 | 1.3556 | 7.3583 | 4.8966 | 4.1063 | 6.3386 | 7.1743 | 12.3509 | 7.6005 | 12.272 | 12.3985 | 14.5362 | 13.5187 | 8.5639 | 7.1429
D-SR-09 Submarine Cable Replacement Program | 3.1843 | 3.1843 | 9.0711 | 6.2675 | 9.6664 | 6.6768 | 9.8055 | 10.8674 | 9.9128 | 11.0883 | 12.2071 | 12.4512 | 12.7002 | 12.9542 | 13.2133
D-SR-10 Distribution Lines Sustainment Initiatives | 7.7512 | 7.7512 | 6.8483 | 8.0914 | 16.5777 | 11.723 | 22.0079 | 10.6912 | 33.769 | 13.6901 | 31.5221 | 30.3239 | 35.2797 | 43.1575 | 42.7461
D-SR-11 Life Cycle Optimization & Operational Efficiency Projects | 9.1434 | 9.1434 | 3.9831 | 3.9326 | 5.0341 | 6.2391 | 5.1165 | 2.4974 | 6.7927 | 0.16763 | 2.8236 | 6.5378 | 7.0719 | 0.82257 | 0.44269
D-SR-12 Advanced Meter Infrastructure 2.0 (AMI 2.0) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71737 | 0 | 3.8529 | 30.9201 | 62.0179 | 153.6686 | 154.4469 | 157.293
D-SR-Other | 2.5878 | 2.5878 | 2.2325 | 1.9968 | 6.3281 | 0.93224 | 5.8164 | 0.83965 | 4.056 | 0.85561 | 0.87272 | 0.89017 | 0.90798 | 0.92613 | 0.94466
Total System Renewal | 219.6941 | 219.6923 | 202.27 | 188.9698 | 222.2275 | 228.6318 | 237.3411 | 236.0824 | 256.7262 | 224.9484 | 373.1063 | 410.2959 | 494.1693 | 491.5139 | 497.8344
System Service
D-SS-01 System Upgrades Driven by Load Growth | 26.4643 | 26.4661 | 64.5351 | 45.1855 | 85.479 | 50.6552 | 98.4161 | 97.1091 | 65.0536 | 108.4691 | 98.1657 | 76.2871 | 127.4844 | 76.1296 | 100.1729
D-SS-02 Reliability Improvements | 1.6853 | 1.6853 | 6.8654 | 4.1342 | 3.457 | 4.5579 | 5.7212 | 3.8023 | 0 | 3.746 | 7.2628 | 0.11295 | 6.4918 | 18.612 | 7.5059
D-SS-03 Demand System Modifications | 7.8986 | 7.8986 | 9.7569 | 11.8196 | 7.3238 | 14.0034 | 10.5786 | 7.48 | 10.5607 | 10.912 | 13.1617 | 13.4081 | 13.672 | 13.8567 | 14.2273
D-SS-04 Energy Storage Solutions | 0.1286 | 0.1286 | 8 | 1.5775 | 0 | 4.9758 | 0 | 3.72 | 0 | 4.25 | 34.33 | 34.98 | 35.64 | 36.31 | 36
D-SS-05 Worst Performing Feeders | 8.3114 | 8.3114 | 14.988 | 21.8768 | 15.7549 | 20.7061 | 15.1544 | 17 | 12.7791 | 22 | 39.644 | 40.9 | 42.1838 | 42.95 | 43.76
D-SS-06 Power Quality and Stray Voltage | 0.9623 | 0.9623 | 0.81195 | 1.337 | 0.86535 | 1.22 | 0.87779 | 3.3287 | 0.88725 | 3.4164 | 3.8007 | 3.8769 | 3.954 | 4.0338 | 4.1144
D-SS-Other | 33.6232 | 33.6232 | 19.072 | 26.9017 | 16.4742 | 2.0251 | 13.3161 | 0.14659 | 13.6753 | 0.37471 | 0.12976 | 0.13236 | 0.13501 | 0.13771 | 0.14046
Total System Service | 79.0737 | 79.0755 | 124.0294 | 112.8322 | 129.3542 | 98.1435 | 144.0643 | 132.5867 | 102.9559 | 153.1683 | 196.4945 | 169.6973 | 229.561 | 192.0298 | 205.921
General Plant Allocated to Distribution
Fleet | 18.0755 | 18.0755 | 27.7698 | 29.0061 | 29.3622 | 25.745 | 28.2636 | 28.3029 | 28.246 | 28.4595 | 50.5924 | 51.6707 | 52.2387 | 52.972 | 54.6889
Facilities & Real Estate | 13.7402 | 13.7402 | 17.6389 | 15.624 | 39.4287 | 45.0497 | 22.534 | 23.7472 | 45.1988 | 26.5087 | 65.3952 | 67.1747 | 44.199 | 39.886 | 35.7062
Information Solutions | 52.3396 | 52.3396 | 61.5988 | 67.4329 | 47.2125 | 76.2298 | 24.6266 | 66.057 | 21.5626 | 43.96 | 62.5004 | 71.6183 | 68.5133 | 78.4574 | 70.2293
System Operations | 5.3176 | 5.3176 | 35.6082 | 4.6733 | 34.2509 | 32.8318 | 19.8594 | 55.739 | 5.4426 | 5.7014 | 15.4375 | 14.6931 | 4.0391 | 3.1736 | 2.3081
System Capability Reinforcement | 2.8747 | 2.8747 | 0.22584 | -0.95541 | 2e-08 | -0.7174 | 0 | 0 | 0 | 1.0394 | 2 | 2.2 | 1.103 | 1.02 | 0
Other | -1.6724 | -1.6724 | 0 | -1.4928 | 0 | -0.91035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total General Plant | 90.6752 | 90.6752 | 142.8414 | 114.2881 | 150.2544 | 178.2286 | 95.2836 | 173.8461 | 100.4499 | 105.6689 | 195.9254 | 207.3568 | 170.0931 | 175.509 | 162.9324
Subtotal (SA, SR, SS) | 473.8616 | 473.8616 | 474.2452 | 499.1485 | 505.0262 | 520.3794 | 532.3181 | 540.1946 | 502.7035 | 558.9248 | 809.1809 | 820.6347 | 950.7349 | 896.1448 | 908.017
Total | 564.5368 | 564.5368 | 617.0866 | 613.4366 | 655.2806 | 698.6081 | 627.6017 | 714.0407 | 603.1534 | 664.5937 | 1005.1063 | 1027.9915 | 1120.828 | 1071.6538 | 1070.9494
Notes:
1 Please provide a breakdown of the major components of each capital project undertaken in each year. Please ensure that all projects below the materiality threshold are included in the miscellaneous line. Add more projects as required.
2 The applicant should group projects appropriately and avoid presentations that result in classification of significant components of the capital budget in the miscellaneous category.