## Attachment 2
Table 5 - Distribution Program Variances (2020)
OEB Category | ISD | ISD Description5 | Net DRO Plan ($M) | Net Actual ($M) | Net Variance ($M) | ISA DRO Plan ($M) | ISA Actual ($M) | ISA Variance ($M) | Units DRO Plan | Units Actual | Unit Variance | Variance Type
System Access | SA-01 | Joint Use and Line Relocations Program # of Poles | 17.7026 | 26.2092 | 8.5067 | 17.6698 | 24.5908 | 6.921 | 1446 | 10735 | 9289 | Emergent Needs
| SA-02 | Meter Infrastructure Sustainment # Devices of Meters | 18.2806 | 18.7419 | 0.46132 | 18.3807 | 21.6113 | 3.2306 | 18000 | 28464 | 10464 | Emergent Needs
| SA-03 | AMI Network Expansion # of Devices | 9.2939 | 0.096599 | -9.1973 | 0 | 0.096599 | 0.096599 | 1194 | 0 | -1194 | Work Definition
| SA-04 | New Load Connections, Service Upgrades, Cancellations and Metering # of Connections, Designs, Upgrades, Cancellations, or Subdivisions | 105.6085 | 146.3868 | 40.7783 | 105.9544 | 147.3271 | 41.3727 | 40290.526 | 40967 | 676.474 | Emergent Needs
System Renewal | SR-01 | Distribution Station Demand Program n/a | 4.7526 | 8.5167 | 3.7641 | 4.653 | 5.1735 | 0.52047 | n/a | n/a | n/a | Emergent Needs
| SR-04 | Distribution Station Component Planned Replacement Program # of Components | 5.0621 | 6.7515 | 1.6895 | 4.7518 | 6.0292 | 1.2773 | 50 | 263 | 213 | Work Definition
| SR-06 | Distribution Station Refurbishments # of Stations | 6.3938 | 7.6932 | 1.2994 | 14.1037 | 7.5875 | -6.5162 | 0 | 1 | 1 | Work Definition
| SR-076 | Distribution Lines Trouble Call and Storm Damage Response Program # of poles/equipment, transformers, or occurrences | 80.2152 | 105.5776 | 25.3624 | 80.2152 | 104.1758 | 23.9606 | 9926 | 1129384 | 1119458 | Emergent Needs
| SR-08 | Distribution Lines PCB Equipment Replacement Program # of Transformers | 10.9553 | 4.7656 | -6.1897 | 10.9553 | 4.7656 | -6.1897 | 2982.9996 | 1026 | -1956.9996 | Execution Factors
| SR-09 | Pole Replacement Program # of Poles | 59.6883 | 43.5998 | -16.0885 | 59.6883 | 43.4593 | -16.2289 | 8158 | 4519 | -3639 | Reprioritization
| SR-10 | Distribution Lines Planned Component Replacement # of crossarms replaced, nest relocated, transformes, or sentinel lights | 4.1063 | 6.3385 | 2.2322 | 4.0837 | 6.2926 | 2.209 | 4069.0016 | 3013 | -1056.0016 | Reprioritization
| SR-11 | Component Replacement Submarine Cable # of Submarine Cables | 9.6664 | 6.6768 | -2.9896 | 9.6664 | 6.6032 | -3.0632 | 230.0628 | 298 | 67.9372 | Reprioritization
| SR-12 | Distribution Lines Sustainment Initiatives n/a | 16.3453 | 11.2201 | -5.1253 | 12.8252 | 9.8055 | -3.0197 | n/a | n/a | n/a | Reprioritization
System Service | SS-04 | Demand Investments n/a | 3.581 | 4.565 | 0.98396 | 3.432 | 4.5689 | 1.1369 | n/a | n/a | n/a | Emergent Needs
| SS-05 | Distribution System Modifications n/a | 3.7428 | 9.4384 | 5.6956 | 5.3516 | 8.3532 | 3.0015 | n/a | n/a | n/a | Emergent Needs
| SS-06 | Worst Performing Feeders Program # of Devices (Mix of Remotely Operable and Fault Location Devices) | 15.8 | 20.7 | 4.9 | 15.7549 | 17.2 | 1.4451 | 786 | 799 | 13 | Reprioritization
5The ISD numbers presented are the ISD numbers presented in the last distribution application.
6A portion of SR‐07 funding is reported in System Service which includes Distribution Capital Post Trouble Call and Distribution Capital Power Quality & Stray Voltage.