## Table 2
Table 2 - 2020 Capital Expenditures and In-Service Additions Greater for General Plant allocated to Transmission
Functional Area | EB-2019-0082 ISD | 2020 Capital Expenditures |  |  | 2020 In-Service Additions |  |  | Variance Explanation
|  | ($M) |  |  | ($M)
|  | DRO Plan | Actual | Variance | DRO Plan | Actual | Variance
Fleet | GP-12 Transport & Work Equipment | 9.1932 | 8.7987 | -0.39447 | 9.1932 | 8.7987 | -0.39447 | No Material Variance
Facilities and Real Estate | GP-10 Facility Accommodation & Improvements Service Centres & Admin | 4.8963 | 6.752 | 1.8557 | 4.472 | 4.8132 | 0.34127 | Reprioritization
| GP-11 Transmission Facilities & Site Improvements | 9.4181 | 12.9426 | 3.5245 | 10.3995 | 12.6016 | 2.2021 | Reprioritization
Information Solutions | GP-07 Hardware/Software Refresh and Maintenance | 4.1052 | 4.0162 | -0.08896 | 6.0037 | 5.9124 | -0.091254 | No Material Variance
| GP-08 Corporate Services Transformation - HR / Payroll | 4.1714 | 4.2527 | 0.081266 | 0 | 0 | 0 | No Material Variance
| Private Cloud Data Center - Capital | 2.8677 | 4.6939 | 1.8263 | 7.1003 | 8.9265 | 1.8263 | Reprioritization
System Operations | GP-01 Integrated System Operating Centre | 40.2985 | 28.0996 | -12.199 | 0 | 0 | 0 | Reprioritization
| GP-03 Network Management System Capital Sustainment | 4.8 | 5.0193 | 0.21934 | 0 | 0 | 0 | No Material Variance
| Synchrophasor Central Site | 3.4429 | 1.7499 | -1.693 | 3.8726 | 0 | -3.8726 | Reprioritization
| Ontario Grid Control Centre Data Centre Remediation | 2.1392 | 2.2578 | 0.11861 | 3.3865 | 3.5049 | 0.11838 | No Material Variance
Other | GP-02 Grid Control Network Sustainment | 3.1865 | 3.5863 | 0.39973 | 3.7849 | 2.9948 | -0.79009 | Reprioritization
| Magnetometer Installation Project | 1.345 | 0.73555 | -0.60942 | 4.5727 | 0.031767 | -4.5409 | Execution Factor
Investments Below Threshold* |  | 21.2154 | 41.808 | 20.5926 | 22.3248 | 32.3296 | 10.0048
Total |  | 111.0794 | 124.7126 | 13.6332 | 75.1101 | 79.9136 | 4.8036
*Rounding errors occurred in the original Table provided in B-4-1, Section 4.9, Attachment 2, Table 2.