## Sheet1
Appendix 2-AA Capital Projects Table ($M)
Projects | 2018 | 2018 Plan | 2019 | 2019 Plan | 2020 | 2020 Plan | 2021 ** | 2021 Plan | 2022 | 2022 Plan | 2023* | 2024* | 2025* | 2026* | 2027*
| Actual |  | Actual |  | Actual |  | Forecast |  | Forecast |  | Test | Test | Test | Test | Test
Reporting Basis | USGAAP |  | USGAAP |  | USGAAP |  | USGAAP |  | USGAAP |  | USGAAP | USGAAP | USGAAP | USGAAP | USGAAP
System Access
Generator Customer Connection | 0.3 | 1.2 | 0.5 |  | 2.2 | 0.8 | 1.3 | 1.5 | - | - | 0 | 0 | 0 | 0 | 0
Load Customer Connection | 28.5 | 18.1 | 40.1 |  | 18.4 | 23.4 | 38.3 | 9.2 | 25.9 | 11.2 | 43.7844 | 71.6441 | 60.0216 | 37.5103 | 51.9129
Overhead Lines Refurbishment Projects, Component Replacement Programs and Secondary Land Use Projects | 4.4 | 5.0 | 5.9 |  | (1.7) | 0.4 | 0.5 | 0.5 | 5.5 | 0.5 | 39.7847 | 2.9591 | 2.9585 | 0.85357 | 0.85357
P&C Enablement for Generation Connections | 0.5 | (0.0) | (0.3) |  | 0.6 | 0.1 | - | - | - | - | 0 | 0 | 0 | 0 | 0
Other | - | - | - |  | 0.0 | - | - | - | - | - | 0 | 0 | 0 | 0 | 0
Sub-Total | 33.7 | 24.3 | 46.2 | - | 19.5 | 24.8 | 40.1 | 11.3 | 31.5 | 11.7 | 83.5691 | 74.6031 | 62.9802 | 38.3638 | 52.7665
System Renewal
Ancillary Systems | 0.7 | 0.5 | 0.1 |  | (15.7) | - | - | - | - | - | 0 | 0 | 0 | 0 | 0
Circuit Breakers | 0.1 | 3.0 | 1.3 |  | 0.5 | 0.2 | - | - | - | - | 0 | 0 | 0 | 0 | 0
Integrated Station Investment | 410.7 | 397.4 | 426.8 |  | 499.7 | 465.6 | 359.8 | 555.3 | 512.5 | 494.6 | 771.8356 | 760.4331 | 736.2907 | 734.9358 | 767.0952
IT Security | 22.9 | 31.3 | 24.5 |  | 35.9 | 36.0 | 40.9 | 39.0 | 34.4 | 34.2 | 0 | 0 | 0 | 0 | 0
Other Power Equipment | 0.3 | 0.2 | 0.2 |  | 0.0 | - | - | - | - | - | 0 | 0 | 0 | 0 | 0
Overhead Lines Refurbishment Projects, Component Replacement Programs | 221.2 | 222.8 | 230.5 |  | 196.0 | 209.8 | 243.8 | 282.7 | 297.2 | 287.4 | 285.4502 | 356.3108 | 427.3341 | 478.973 | 461.3908
Power Transformers | (0.7) | 0.5 | (2.7) |  | (2.5) | - | 0.1 | - | - | - | 0 | 0 | 0 | 0 | 0
Protection and Automation | 21.6 | 26.7 | 18.6 |  | 14.4 | 25.7 | 29.6 | 29.7 | 54.5 | 51.7 | 85.8527 | 93.0604 | 92.0663 | 72.5125 | 37.9808
Site Facilities and Infrastructure | 0.3 | 0.6 | 0.2 |  | 0.3 | - | - | - | - | - | 0 | 0 | 0 | 0 | 0
Tx Transformers Demand and Spares | 82.6 | 67.2 | 78.2 |  | 68.3 | 63.5 | 51.3 | 52.9 | 45.4 | 45.8 | 53.3568 | 54.2222 | 54.9308 | 55.9753 | 56.9388
Underground Lines Cable Refurbishment & Replacement | 16.5 | 30.1 | 14.9 |  | 7.1 | 9.4 | 14.2 | 23.1 | 27.6 | 44.5 | 43.2901 | 28.79 | 6.6916 | 1.9775 | 6.9496
Sub-Total | 776.1 | 780.4 | 792.6 | - | 804.0 | 810.1 | 739.6 | 982.8 | 971.5 | 958.2 | 1239.7854 | 1292.8164 | 1317.3135 | 1344.3741 | 1330.3552
System Service
Inter Area Network Transfer Capability | 48.9 | 39.0 | 57.9 |  | 144.8 | 152.7 | 174.4 | 77.0 | 86.2 | 127.5 | 33.1455 | 26.4131 | 25.7672 | 68.7954 | 63.5203
Local Area Supply Adequacy | 20.7 | 27.8 | 19.7 |  | 41.6 | - | 44.9 | - | 34.1 | - | 57.7373 | 77.9093 | 61.8743 | 27.1297 | 29.1596
Performance Enhancement | 0.0 | 0.3 | 0.6 |  | 3.2 | 38.7 | 0.7 | 66.2 | 1.2 | 20.7 | 2.6312 | 0.52624 | 0.52624 | 0 | 0
Power Quality | 1.4 | 4.1 | 3.1 |  | 1.9 | 2.6 | 0.8 | 0.5 | 0.1 | 0.5 | 0 | 0 | 0 | 0 | 0
Risk Mitigation | 2.6 | 4.5 | 4.2 |  | 4.6 | 1.8 | 3.2 | 0.9 | 0.5 | 0.9 | 2.105 | 2.105 | 2.105 | 2.105 | 2.105
Smart Grid | 0.2 | - | 0.1 |  | 0.0 | 2.6 | - | 3.6 | - | 2.3 | 0 | 0 | 0 | 0 | 0
Sub-Total | 73.9 | 75.6 | 85.6 | - | 196.1 | 198.4 | 223.9 | 148.2 | 122.0 | 151.8 | 95.619 | 106.9536 | 90.2728 | 98.0301 | 94.7849
General Plant
Fleet | 9.3 | 31.3 | 15.0 |  | 13.5 | 17.5 | 14.4 | 14.5 | 14.9 | 17.7 | 27.1833 | 27.7624 | 28.0686 | 28.4619 | 29.383
Facilities & Real Estate | 23.4 | 16.6 | 16.0 |  | 19.7 | 15.8 | 15.4 | 15.1 | 15.5 | 15.1 | 27.4007 | 26.2148 | 18.3779 | 19.1356 | 15.5375
Information Technology | 42.0 | 28.9 | 47.1 |  | 42.2 | 25.7 | 30.1 | 18.3 | 29.1 | 16.1 | 60.4607 | 48.953 | 47.4014 | 45.9691 | 37.7805
System Operations | 3.8 | 13.8 | 6.0 |  | 38.8 | 11.2 | 59.0 | 11.9 | 21.8 | 12.0 | 12.5799 | 4.0067 | 4.3793 | 5.0797 | 4.412
Operating Infrastructure | 5.8 | 29.1 | 8.7 |  | 7.5 | 40.9 | 18.9 | 34.7 | 21.5 | 33.7 | 26.879 | 23.6128 | 21.9702 | 23.32 | 23.4259
Other | (0.7) | - | (0.7) |  | 3.0 | - | - | - | - | - | 0 | 0 | 0 | 0 | 0
Sub-Total | 83.6 | 119.7 | 92.1 | - | 124.7 | 111.1 | 137.8 | 94.4 | 102.8 | 94.7 | 154.5036 | 130.5498 | 120.1974 | 121.9664 | 110.5388
Progressive Productivity |  | - |  |  |  | (17.0) |  | (39.0) | (48.1) | (61.0) | -64.1912 | -64.1912 | -64.1912 | -64.1912 | -64.1912
Other** |  | - |  |  |  | (25.5) |  | (28.4) |  | (29.1)
Total | 967.3 | 1,000.0 | 1,016.5 | - | 1,144.4 | 1,101.9 | 1,141.5 | 1,169.2 | 1,179.7 | 1,126.4 | 1509.2859 | 1540.7318 | 1526.5726 | 1538.5433 | 1524.2542
Less Renewable Generation Facility Assets and Other Non-Rate-Regulated Utility Assets (input as negative)
Total | 967.3 | 1,000.0 | 1,016.5 | - | 1,144.4 | 1,101.9 | 1,141.5 | 1,169.2 | 1,179.7 | 1,126.4 | 1509.2859 | 1540.7318 | 1526.5726 | 1538.5433 | 1524.2542
* The 2023-2027 forecast reflects updated inflation assumptions calculated using the methodology described in Section 2.3 of Exhibit O-01-02.
** This reflects the ‘as filed’ forecast, please refer to Exhibit O-02-01, Attachment 2 for 2021 Actuals