## Sheet1
[18 empty] | File Number: |  | 0
[18 empty] | Exhibit: |  | B
[18 empty] | Tab: |  | 1
[18 empty] | Schedule: |  | 3
Page:
[18 empty] | Date: |  | 2019-06-19
Revised Appendix 2-AB
Table 2 - Distribution Capital Expenditure Summary from Chapter 5 Consolidated Distribution System Plan Filing Requirements ($M)
First year of Forecast Period: | 2023
CATEGORY | Historical Period (previous plan1 & actual) | [14 empty] | Forecast Period (As-Filed) |  |  |  |  | Forecast Period (Updated Inflation)***
| 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 | 2024 | 2025 | 2026 | 2027 | 2023 | 2024 | 2025 | 2026 | 2027
| Plan | Actual | Var | Plan | Actual | Var | Plan | Actual | Var | Plan | As-Filed Forecast | Var | Plan | As-Filed Forecast | Var | bar: Forecast Period (Updated Inflation)*** 2023 to Forecast Period (Updated Inflation)*** 2027
|  |  | % |  |  | % |  |  | % |  |  | % |  |  | %
System Access | 175.0938 | 175.0938 | 0% | 147.9457 | 197.3464 | 33.39% | 153.4445 | 193.6041 | 26.17% | 150.9126 | 171.5254 | 13.66% | 143.0214 | 180.8081 | 26.42% | 239.58 | 240.6414 | 227.0046 | 212.6012 | 204.2616 | 252.1548 | 253.2719 | 238.9193 | 223.7599 | 214.9826
System Renewal | 219.6941 | 219.6923 | -0.0008366% | 202.27 | 188.9698 | -6.575% | 222.2275 | 228.6318 | 2.882% | 237.3411 | 236.0824 | -0.5303% | 256.7262 | 224.9484 | -12.38% | 373.1063 | 410.2959 | 494.1693 | 491.5139 | 497.8344 | 392.6894 | 431.831 | 520.1065 | 517.3117 | 523.9641
System Service* | 79.0737 | 79.0755 | 0.002291% | 124.0294 | 112.8322 | -9.028% | 129.3542 | 98.1435 | -24.13% | 144.0643 | 132.5867 | -7.967% | 102.9559 | 153.1683 | 48.77% | 196.4945 | 169.6973 | 229.561 | 192.0298 | 205.921 | 206.8078 | 178.6042 | 241.6099 | 202.1087 | 216.729
General Plant | 90.6752 | 90.6752 | 0% | 142.8414 | 114.2881 | -19.99% | 150.2544 | 178.2286 | 18.62% | 95.2836 | 173.8461 | 82.45% | 100.4499 | 105.6689 | 5.196% | 195.9254 | 207.3568 | 170.0931 | 175.509 | 162.9324 | 206.2088 | 218.2402 | 179.0207 | 184.7209 | 171.4842
TOTAL EXPENDITURE | 564.5368 | 564.5368 | -4.676e-06% | 617.0866 | 613.4366 | -0.5915% | 655.2806 | 698.6081 | 6.612% | 627.6017 | 714.0407 | 13.77% | 603.1534 | 664.5937 | 10.19% | 1005.1063 | 1027.9915 | 1120.828 | 1071.6538 | 1070.9494 | 1057.8608 | 1081.9472 | 1179.6564 | 1127.9012 | 1127.1598
System O&M** | 544.4 | 558.8 | 2.645% |  | 559.6 | -- |  | 560.2 | -- | -- | 531.4 | -- | -- | 535.8 | -- | 597.5 | * | * | * | * | 628.9 | * | * | * | *
* The 2019-2022 Actuals exclude new transmission line facilities for Chatham and Lakeshore (West of Chatham), Lambton and Chatham (West of London) and Northwest Bulk Transmission Line Project (Waasigan).
** System O&M reflects total Operations, Maintenance and Administration expenses. 2024 - 2027 is determined based on the escalation factor identified in Exhibit A-04-02.
***The 2023-2027 forecast reflects updated inflation assumptions calculated using the methodology described in Section 2.3 of Exhibit O-1-2
Notes to the Table:
1. Historical “previous plan” data is not required unless a plan has previously been filed. However, use the last Board-approved, at least on a Total (Capital) Expenditure basis for the last cost of service rebasing year, and the applicant should include their planned budget in each subsequent historical year up to and including the Bridge Year.
2. Indicate the number of months of 'actual' data included in the last year of the Historical Period (normally a 'bridge' year):
Explanatory Notes on Variances (complete only if applicable)
Notes on shifts in forecast vs. historical budgets by category
For a more detailed explanation of shifts in forecast vs historical expenditures, please see DSP Section 3.9 | bar: Forecast Period (As-Filed) 2023 to Forecast Period (As-Filed) 2027
Notes on year over year Plan vs. Actual variances for Total Expenditures
See DSP Section 3.9 Appendix B "Capital Program Performance Report 2019, 2020" | bar: Forecast Period (As-Filed) 2023 to Forecast Period (As-Filed) 2027
Notes on Plan vs. Actual variance trends for individual expenditure categories
See DSP Section 3.9 Appendix B "Capital Program Performance Report 2019, 2020" | bar: Forecast Period (As-Filed) 2023 to Forecast Period (As-Filed) 2027