## 2.3 Summary of Capital Projects
Capital Projects Table
Reporting Basis | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS
Projects | 2018 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| BA | Actual | Actual | Actual | Actual | Projection | Projection
System Access
Total Projects | 0 | 79865.27 | 155912.15 | 238671.46 | 72545 | 216300 | 40000
Sub-Total System Access | 0 | 79865.27 | 155912.15 | 238671.46 | 72545 | 216300 | 40000
Contributed Captial |  | -60245 | -11125 | -240151 | -3148 | -45000 | -10000
Total System Access | 0 | 19620.27 | 144787.15 | -1479.54 | 69397 | 171300 | 30000
| MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS
System Renewal | 2018 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| BA | Actual | Actual | Actual | Actual | Projection | Projection
Total Projects | 0 | 143563 | 36214.51 | 77544.84 | 110145 | 112225 | 107050
Sub-Total System Renewal | 0 | 143563 | 36214.51 | 77544.84 | 110145 | 112225 | 107050
Contributed Captial |  | 0 | 0 | 0 | 0 | 0 | 0
Total System Renewal | 0 | 143563 | 36214.51 | 77544.84 | 110145 | 112225 | 107050
| MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS
System Service | 2018 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| BA | Actual | Actual | Actual | Actual | Projection | Projection
Total Projects | 0 | 0 | 0 | 11532.05 | 4895 | 6000 | 6000
Sub-Total System Service | 0 | 0 | 0 | 11532.05 | 4895 | 6000 | 6000
Contributed Captial |  | 0 | 0 | 0 | 0 | 0 | 0
Total System Service | 0 | 0 | 0 | 11532.05 | 4895 | 6000 | 6000
| MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS
General Plant | 2018 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
| BA | Actual | Actual | Actual | Actual | Projection | Projection
Total Projects | 0 | 3853.67 | 8494.56 | 4676.45 | 35579.73 | 5700 | 72217.5
Sub-Total General Plant | 0 | 3853.67 | 8494.56 | 4676.45 | 35579.73 | 5700 | 72217.5
Contributed Captial |  | 0 | 0 | 0 | 0 | 0 | 0
Total System Access | 0 | 3853.67 | 8494.56 | 4676.45 | 35579.73 | 5700 | 72217.5
| MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS
| 2018 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023
Capital Investment Net Of Cc | 0 | 227281.94 | 200621.22 | 332424.8 | 223164.73 | 340225 | 225267.5
Total Contributed Capital | 0 | -60245 | -11125 | -240151 | -3148 | -45000 | -10000
Adjustment for Unusal Disposal |  |  |  | 28405
Total Capex | 0 | 167036.94 | 189496.22 | 120678.8 | 220016.73 | 295225 | 215267.5
Reconciliation To Yearly Additions (2.6) |  | 167037.27 | 189496.92 | 120679.27 | 220016.36 | 295225 | 215267.5

## 2.3 System Access
System Access
Reporting Basis | Reporting Basis |  | MIFRS |  | MIFRS |  | MIFRS |  | MIFRS |  | MIFRS |  | MIFRS
Projects | Projects | USoA | 2018 | Note | 2019 | Note | 2020 | Note | 2021 | Note | 2022 | Note | 2023 | Note
System Access | System Access |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023
| Land Substation | 1805 | 6900 | 1
| Expense Surveyor | 1820 | 935 | 2
| New O/H and U/G services | 1855 | 20818.5 | 3
| Centre Urgel Forget Phase II | 1850 | 11685 | 4
| Centre Urgel Forget Phase II | 1845 | 17800 | 5
| New Meters | 1860 | 17551.77 | 6
| Service Pole Installation | 1830 | 4175 | 7
| New O/H and U/G services | 1855 |  |  | 23364 | 8
| Transformer 225 KvA | 1850 |  |  | 14219.13 | 9
| Meter Replacement (Seal Years) | 1860 |  |  | 16371.94 | 10
| Scada Improvement | 1820 |  |  | 33653.3 | 11
| Relocate Line St-Jaques Phase I | 1835 |  |  | 20000 | 12
| New Pole St-Jacques | 1830 |  |  | 2500 | 13
| New Transformer Inventory | 1850 |  |  | 21460.34 | 14
| Engineer Patenaude Subdivision | 1845 |  |  | 2360 | 15
| Enhancement Blais Street | 1835 |  |  | 16240 | 16
| Maintenance Manual New Substation | 1820 |  |  | 5743.44 | 17
| New O/H and U/G services | 1855 |  |  |  |  | 31632.93 | 18
| Versaille III Project | 1850 |  |  |  |  | 23735 | 19
| Versaille III Project | 1845 |  |  |  |  | 66142 | 20
| Patenaude East Subdivision Phase II (Faubourge Ste-Marie Phase II) | 1850 |  |  |  |  | 33425 | 21
| Patenaude East Subdivision Phase II (Faubourge Ste-Marie Phase II) | 1845 |  |  |  |  | 65793.55 | 22
| Meter Replacement (Seal Years) | 1860 |  |  |  |  | 8942.98 | 23
| New Transformers Inventory | 1850 |  |  |  |  | 9000 | 24
| New O/H and U/G services | 1855 | [6 empty] | 38580 | 25
| Meter | 1860 | [6 empty] | 12093 | 26
| New Transformers Inventory | 1850 | [6 empty] | 8465 | 27.28
| Distribution Map | 1845 | [6 empty] | 5615 | 28
| Distribution Map | 1835 | [6 empty] | 2565 | 29
| Pole Testing | 1830 | [6 empty] | 5227
| New O/H and U/G services | 1855 | [8 empty] | 23000 | 30
| Meter | 1860 | [8 empty] | 12000 | 31
| New Transformers Inventory | 1850 | [8 empty] | 8000 | 32
| New O/H and U/G services | 1855
| Meter | 1860
| New Transformers Inventory | 1850
| PCB ransformers Dated Prior to 1985 | 1850
Service Area Amendment (Pending)
| Project Central Park (Transformers) | 1850 | [8 empty] | 50000 | 33
| Project Central Park (Underground Cable and Labour) | 1845 | [8 empty] | 115000 | 33
| Project Central Park(Dip Pole and Labour) | 1830 | [8 empty] | 3800 | 33
| Project Central Park (Pimary Overhead Cable and Labour)) | 1835 | [8 empty] | 4500 | 33
Contributed Capital
| New O/H and U/G services | 1855 | [10 empty] | 20000 | 35
| Meter | 1860 | [10 empty] | 12000 | 36
| New Transformers Inventory | 1850 | [10 empty] | 8000 | 37
| PCB ransformers Dated Prior to 1985 | 1850
| Sub-Total System Access - Contributed Capital |  | -60245 |  | -11125 |  | -240151 |  | -3148 |  | -45000 |  | -10000
Total System Access | Total System Access |  | 79865.27 |  | 155912.15 |  | 238671.46 |  | 72545 |  | 216300 |  | 40000
Explanatory Notes on Projects
Notes on System Access
Note 1
Land Substation:
Scope: Installed two new culverts and repair the ditch
Ojectives: To manage water flow
Capital Cost: (6 900.00$)
Note 2
Surveyor expense:
Scope: Survey on private property
Objective: To installed a guy wire on a primary pole
Capital Cost: (935.00$)
Note 3
Project:New Services
Scope: Installation of overhead and underground for new customer.
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2018.
Capital Cost: (20 819$)
Note 4
Project: Centre Urgel Forget Phase II
Scope: New Faclity extension 24 units
Objective: Transformers purchase to falicitate futur 24 units.
Capital Cost:( 11 685$)
In service date: April 2018
Note 5
Project: Centre Urgel Forget Phase II
Scope: New Faclity extension 24 units
Objective: Installation of secondary and primary cable ,transformer bank.
Capital Cost: (17 800$)
In service date: April 2018
Note 6
Project: New Meter
Scope:Order meter for new connection service
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2018.
Capital Cost: (17 552$)
Note 7
Project: Service Pole Installation
Scope: To facilitate to customer request
Objective: Respond rapidly to customer request a service connection
Capital Cost: (4 175$)
Note 8
Project:New Services
Scope: Installation of overhead and underground for new customer.
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2019.
Capital Cost: (23 364$)
Note 9
Project:Transformer 225 kva
Scope: Transfomer for inventory
Objective: To replace transformer in service (About seven in service none in stock)
Customer: Respond rapidly to customer
Capital Cost: (14 219$)
Note10
Project:Meter Replacement (Seal Year)
Scope: Meter Change due to seal year & New Service
Objective: Have meter in inventory
Customer: Respond rapidly to customer
Capital Cost: (16 372$)
Note 11
Project:Scaida improvment
Scope:Be able to get information
Objective: Run report on each feeder
Customer:more reability on the system
Capital Cost: (33 653$)
Note 12
Project:Relocate Line Phase 1 St-Jacques Road
Scope: As per Distribution System Plan
Objective: Remove backyard line
Customer:more reability on the system
Capital Cost: (20 000$)
Note 13
Project: Pole on St-Jacques
Scope: Replace Pole
Objective:Safety issue
Customer:Protection
Capital Cost: (2 500$)
Note 14
Project: New Transformers
Scope: Have the necesary transfo in stock
Objective: To respond rapidly of transformer failure
Customer: Reliability and efficience
Capital Cost: (21 460$)
Note 15
Project: Patenaude Subdivision Phase II Project
Scope: Engineer drawing verification
Objective: To follow electrical Code
Customer: Safety to futur customers
Capital Cost: (2 360$)
Note 16
Project: Blais Street
Scope: Enhacement of the wire location
Objective:More effient m remove 2 transformer
Customer: Not affected
Capital Cost: (16 240$)
Note 17
Project: Substation T1 -T2
Scope: Develop a Maintenance Manuel
Objective: Easier for CHEI for tenders
Customer:
Capital Cost: (5 743$)
Note 18
Project:New Services
Scope: Installation of overhead and underground for new customer.
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2020
Capital Cost: (31 633$)
Note 19
Project: Versaille III Project
Scope: Transformer for New Subdivion
Objective: Installed transfromers in new subdivision
Customer: To connect new owner in the project
Capital Cost: ($23 735)
Note 20
Project: Versaille III Project
Scope: primary and secondary
Objective: Installed primary and secondary
Customer:To connect new owner in the project
Capital Cost: ($66 142)
Note 21
Project: Patenaude Subdivision Phase II Project
Scope: Transformer for New Subdivion
Objective: Installed transfromers in new subdivision
Customer: To connect new owner in the project
Capital Cost: ($33 425)
Note22
Project: Patenaude Subdivision Phase II Project
Scope: primary and secondary
Objective: Installed primary and secondary
Customer:To connect new owner in the project
Capital Cost: ($65 794)
Note 23
Project:Meter Replacement (Seal Year)
Scope: Meter Change due to seal year & New Service
Objective: Have meter in inventory
Customer: Respond rapidly to customer
Capital Cost: (8 943$)
Note 24
Project: New Transformers
Scope: Have the necesary transfo in stock
Objective: To respond rapidly of transformer failure
Customer: Reliability and efficience
Capital Cost: ($9 000)
Note 25
Project:New Services
Scope: Installation of overhead and underground for new customer.
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2021
Capital Cost: (30 000$)
Note 26
Project: New Meter
Scope:Order meter for new connection service
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2021.
Capital Cost: (12 093$)
Note 27
Project: New Transformers
Scope: Have the necesary transfo in stock
Objective: To respond rapidly of transformer failure
Customer: Reliability and efficience
Capital Cost: (8 425$)
Note 28 - 29
Project: Distribution map
Scope: Update the utility map
Objective: To facilate line crew workers
Customer: Reliability and efficience
Capital Cost: (7 170$)
Note 30
Project:New Services
Scope: Installation of overhead and underground for new customer.
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2022
Capital Cost: (23 000$)
Note 31
Project: New Meter
Scope:Order meter for new connection service
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2022.
Capital Cost: (12 000$)
Note 32
Project: New Transformers
Scope: Have the necesary transfo in stock
Objective: To respond rapidly of transformer failure
Customer: Reliability and efficience
Capital Cost: (8 000$)
Service Area Amendment (Pending)
Note 33
Project: Central Park
Scope: New Subdivision
Objective: Installation distribution system
Customer: 245
Capital Cost: (173 000$)
Service Area Amendment (Pending)
Note 34
Project: Mélanie Construction
Scope: New Subdivision
Objective:Installation distribution system
Customer: 325
Capital Cost: (115 000$)
Note 35
Project:New Services
Scope: Installation of overhead and underground for new customer.
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2023
Capital Cost: (20 000$)
Note 36
Project: New Meter
Scope:Order meter for new connection service
Objective: Respond rapidly to customer request a service connection
Customer Attachments New Connections has been perform during calendar year of 2023.
Capital Cost: (12 000$)
Note 37
Project: New Transformers
Scope: Have the necesary transfo in stock
Objective: To respond rapidly of transformer failure
Customer: Reliability and efficience
Capital Cost: (8 000$)

## 2.3 System Renewal
System Renewal
Reporting Basis | Reporting Basis |  | CGAAP |  | CGAAP |  | CGAAP |  | NEWGAAP |  | NEWGAAP |  | NEWGAAP
Projects | Projects | USoA | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023
System Renewal | System Renewal |  | 2018 | Note | 2019 | Note | 2020 | Note | 2021 | Note | 2022 | Note | 2023 | Note
| Pole Replacement # 81 | 1830 | 7300 | 1
| Pole Replacement # 48 | 1830 | 4800 | 2
| Pole Replacement # 11 | 1830 | 6800 | 3
| Pole Replacement # 108 | 1830 | 6400 | 4
| Pole Replacement # 139 | 1830 | 6500 | 5
| Pole Replacement # 353 | 1830 | 3000 | 6
| Pole Replacement # 415 | 1830 | 4800 | 7
| Pole Replacement # 465 | 1830 | 4200 | 8
| Transformer Replacement # 431 | 1850 | 3195 | 9
| Transformer Replacement # 456 | 1850 | 4689 | 10
| Transformer Replacement # 474 | 1850 | 3977 | 11
| Transformer Replacement # 501 | 1850 | 6675 | 12
| Transformer Replacement # 504 | 1850 | 5695 | 13
| Transformer Replacement # 506 | 1850 | 7390 | 14
| Transformer Replacement # 520 | 1850 | 6213 | 15
| Transformer Replacement # 522 | 1850 | 5577 | 16
| Transformer Replacement # 525 | 1850 | 6390 | 17
| Transformer Replacement # 35 | 1850 | 7390 | 18
| Transformer Replacement # 482 | 1850 | 9277 | 19
| Transformer Program Elbows and Inserts | 1850 | 13113 | 20
| Replace Cutout Arrester 1122 Notre-Dame | 1835 | 1826 | 21
| Replace Solid Blade Switch F1 & F2 Dip Pole St-Jacques | 1835 | 4842 | 22
| Map Upgrade | 1835 | 3557 | 23
| Replace Cutout Arrester & Hardware | 1835 | 2957 | 24
| Installed 1 span of 266 meter Spun Buss 1155 Notre-Dame | 1835 | 2000 | 25
| Installed Spun Buss on Forget and Jeanne D'Arc Street | 18350 | 5000 | 26
| Transformer Program Elbows and Inserts | 1850 |  |  | 10139.01 | 27
| Transformer Replacement # 403 | 1850 |  |  | 7211 | 28
| Transformer Replacement # 412 | 1850 |  |  | 4350 | 29
| Transformer Replacement # 422 | 1850 |  |  | 2000 | 30
| Transformer Replacement # 434 | 1850 |  |  | 4350 | 31
| Transformer Replacement # 440 | 1850 |  |  | 4350 | 32
| 3 Cutt-Off Switch Notre-Dame Street | 1835 |  |  | 2534.5 | 33
| Substation Lightning | 1820 |  |  | 1280 | 34
| Transformer Program Elbows and Inserts | 1850 |  |  |  |  | 21040.5 | 35
| Transformer Replacement # 57 | 1850 |  |  |  |  | 7082.5 | 36
| Transformer Replacement # 58 | 1850 |  |  |  |  | 7082.5 | 37
| Transformer Replacement # 59 | 1850 |  |  |  |  | 7082.5 | 38
| Transformer Replacement # 414 | 1850 |  |  |  |  | 1565.2 | 39
| Transformer Replacement # 427 | 1850 |  |  |  |  | 3624.2 | 40
| Transformer Replacement # 446 | 1850 |  |  |  |  | 1584.78 | 41
| Transformer Replacement # 453 | 1850 |  |  |  |  | 1974.7 | 42
| Transformer Replacement # 478 | 1850 |  |  |  |  | 2084.2 | 43
| Transformer Replacement # 480 | 1850 |  |  |  |  | 1582.2 | 44
| Transformer Replacement # 510 | 1850 |  |  |  |  | 1929.7 | 45
| Transformer Replacement # 513 | 1850 |  |  |  |  | 1335.4 | 46
| Transformer Replacement # 524 | 1850 |  |  |  |  | 1720 | 47
| Transformer Replacement # 544 | 1850 |  |  |  |  | 1431 | 48
| Pole Replacement # 18 | 1830 |  |  |  |  | 4452.5 | 49
| Pole Replacement # 185 | 1830 |  |  |  |  | 6800 | 50
| Pole Replacement # 461 | 1830 |  |  |  |  | 5172.96 | 51
| Transformer Replacement # 405 | 1850 | [6 empty] | 3955 | 52
| Transformer Replacement # 487 | 1850 | [6 empty] | 4300 | 53
| Transformer Replacement # 488 | 1850 | [6 empty] | 4100 | 54
| Transformer Replacement # 489 | 1850 | [6 empty] | 4400 | 55
| Transformer Replacement # 490 | 1850 | [6 empty] | 4400 | 56
| Transformer Replacement # 496 | 1850 | [6 empty] | 4400 | 57
| Transformer Replacement # 508 | 1850 | [6 empty] | 3780 | 58
| Transformer Replacement # 511 | 1850 | [6 empty] | 3725 | 59
| Transformer Replacement # 517 | 1850 | [6 empty] | 4400 | 60
| Transformer Replacement # 521 | 1850 | [6 empty] | 5925 | 61
| Transformer Replacement # 530 | 1850 | [6 empty] | 4400 | 62
| Transformer Replacement # 538 | 1850 | [6 empty] | 4450 | 63
| Pole Replacement # 477 | 1830 | [6 empty] | 4800 | 64
| Pole Replacement # 159 | 1830 | [6 empty] | 5800 | 65
| Pole Replacement # 346 | 1830 | [6 empty] | 7100 | 66
| Pole Replacement # 215 | 1830 | [6 empty] | 8600 | 67
| Bollard Replacement | 1850 | [6 empty] | 4000 | 68
.
| Replacement Of Switch and Arrester | 1850 | [6 empty] | 27610 | 69
| Replacement Of Switch and Arrester | 1850 | [8 empty] | 10000 | 70
| Transformer Replacement # 418 ( Tranfo Bank) | 1850 | [8 empty] | 6525 | 71
| Transformer Replacement # 432 | 1850 | [8 empty] | 9750 | 72
| Transformer Replacement # 448 | 1850 | [8 empty] | 6950 | 73
| Transformer Replacement # 452 | 1850 | [8 empty] | 9750 | 74
| Transformer Replacement # 461 | 1850 | [8 empty] | 4250 | 75
| Transformer Replacement # 470 | 1850 | [8 empty] | 5650 | 76
| Transformer Replacement # 481 | 1850 | [8 empty] | 5650 | 77
| Transformer Replacement # 502 | 1850 | [8 empty] | 6950 | 78
| Transformer Replacement # 509 | 1850 | [8 empty] | 4250 | 79
| Transformer Replacement # 518 | 1850 | [8 empty] | 6950 | 80
| Transformer Replacement # 519 | 1850 | [8 empty] | 6950 | 81
| Transformer Replacement # 527 | 1850 | [8 empty] | 4250 | 82
| Transformer Replacement # 528 | 1850 | [8 empty] | 6950 | 83
| Pole Replacement # 296 | 1830 | [8 empty] | 5800 | 84
| Pole Replacement # 441 | 1830 | [8 empty] | 5800 | 85
| Pole Replacement # 369 | 1830 | [8 empty] | 5800 | 86
87
| Replacement Of Switch and Arrester | 1850 | [10 empty] | 10000 | 87
| Transformer Replacement # 531 | 1850 | [10 empty] | 5650 | 88
| Transformer Replacement # 533 | 1850 | [10 empty] | 4250 | 89
| Transformer Replacement # 535 | 1850 | [10 empty] | 6950 | 90
| Transformer Replacement # 536 | 1850 | [10 empty] | 5650 | 91
| Transformer Replacement # 537 | 1850 | [10 empty] | 4250 | 92
| Transformer Replacement # 539 | 1850 | [10 empty] | 6950 | 93
| Transformer Replacement # 541 | 1850 | [10 empty] | 6950 | 94
| Transformer Replacement # 543 | 1850 | [10 empty] | 5650 | 95
| Transformer Replacement # 545 | 1850 | [10 empty] | 5650 | 96
| Transformer Replacement # 546 | 1850 | [10 empty] | 6950 | 97
| Transformer Replacement # 548 (transfo Bank0 | 1850 | [10 empty] | 10250 | 98
| Transformer Replacement # 551 | 1850 | [10 empty] | 4250 | 99
| Pole Replacement # 1 | 1830 | [10 empty] | 8750 | 100
| Pole Replacement # 258 | 1830 | [10 empty] | 8500 | 101
| Pole Replacement # 304 | 1830 | [10 empty] | 6400 | 102
Contributed Capital
Sub-Total System Renewal - Contributed Capital
Total System Renewal | Total System Renewal |  | 143563 |  | 36214.51 |  | 77544.84 |  | 110145 |  | 112225 |  | 107050
Explanatory Notes on Projects
Notes on System Renewal
Note 1
Pole Replacement # 81
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 11
Capital Cost : 7 300$
In Service Date: December 2018
Note 2
Pole Replacement # 48
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 3
Capital Cost : 4 800$
In Service Date: December 2018
Note 3
Pole Replacement # 11
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 6 800$
In Service Date: December 2018
Note 4
Pole Replacement # 108
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 11
Capital Cost : 6 400$
In Service Date: September 2018
Note 5
Pole Replacement # 139
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 5
Capital Cost : 6 500$
In Service Date: October 2018
Note 6
Pole Replacement # 353
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments:
Capital Cost : 3 000$
In Service Date: September 2018
Note 7
Pole Replacement # 415
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 4 800$
In Service Date: December 2018
Note 8
Pole Replacement # 465
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 4 200$
In Service Date: September 2018
Note 9
Transformer Replacement # 431
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 10
Capital Cost : 3 195$
In Service Date: May 2018
Note 10
Transformer Replacement # 456
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 12
Capital Cost : 4 689$
In Service Date: May 2018
Note11
Transformer Replacement # 474
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 3 977$
In Service Date: May 2018
Note 12
Transformer Replacement # 501
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 13
Capital Cost : 6 675$
In Service Date: May 2018
Note13
Transformer Replacement # 504
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 12
Capital Cost : 5 695$
In Service Date: May 2018
Note 14
Transformer Replacement # 506
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 7 390$
In Service Date: May 2018
Note15
Transformer Replacement # 520
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 12
Capital Cost : 6 213$
In Service Date: May 2018
Note 16
Transformer Replacement # 522
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments:
Capital Cost :
In Service Date:
Note 17
Transformer Replacement # 525
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 6 390$
In Service Date: June 2018
Note 18
Transformer Replacement # 35
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 7 390$
In Service Date: June 2018
Note 19
Transformer Replacement # 482
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 12
Capital Cost : 9 277$
In Service Date: June 2018
Note 20
Transformer Program Elbows and Inserts
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost :13 113$
In Service Date: July-August 2018
Note 21
Replace Cutout Arrester 1122 Notre-Dame
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost :1 826$
In Service Date:April 2018
Note 22
Replace Solid Blade Switch F1 & F2 Dip Pole St-Jacques
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost :4 842$
In Service Date:January 2018
Note 23
Map Update
Scope; Update distributiuon map
Ojective: To have the most recent change for our contractor
Customer attachments: Reability to the distribution system
Capital Cost :3 557$
In Service Date:January 2018
Note 24
Replace Cutout Arrester & Hardware
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost :2 957$
In Service Date:August 2018
Note 25
Installed 1 span of 266 meter Spun Buss 1155 Notre-Dame
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost : 5 000$
In Service Date: December 2018
Note 26
Installed Spun Buss on Forget and Jeanne D'Arc Street
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost : 2 000$
In Service Date: December 2018
Note 27
Transformer Program Elbows and Inserts
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost : 10 139$
In Service Date: July-August 2019
Note 28
Transformer Replacement # 403
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 7 211$
In Service Date: May 2019
Note 29
Transformer Replacement # 412
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 4
Capital Cost : 4 350$
In Service Date: May 2019
Note 30
Transformer Replacement # 422
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 2
Capital Cost : 2 000$
In Service Date: May 2019
Note 31
Transformer Replacement # 434
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 4
Capital Cost : 4 350$
In Service Date: May 2019
Note 32
Transformer Replacement # 440
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 4 350$
In Service Date: May 2019
Note 33
3 Cutt-Off Switch Notre-Dame Street
Scope; Prevent outage
Objective: Old Cut-off Switch prevent power failure to sewer System
Customer Attachments: 1
Capital Cost : 2 535$
In Service Date:July 2019
Note 34
Substation Lightning
Scope: Have more security at the substation
Objective:To prevent vandalism
Customer Attachments: 1
Capital Cost : 1 280$
In Service Date:June 2019
Note 35
Transformer Program Elbows and Inserts
Scope: Failure risk
Ojective: To prevent trouble call
Customer attachments: Reability to the distribution system
Capital Cost : 21 041$
In Service Date: Summer 2020
Note 36
Transformer Replacement # 57
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 10
Capital Cost : 7 083$
In Service Date: Summer 2020
Note 37
Transformer Replacement # 58
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 7 083$
In Service Date: Summer 2020
Note 38
Transformer Replacement # 59
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 5
Capital Cost : 7 083$
In Service Date: Summer 2020
Note 39
Transformer Replacement # 414
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 5
Capital Cost : 1 565$
In Service Date: Summer 2020
Note 40
Transformer Replacement # 427
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 3 624$
In Service Date: Summer 2020
Note 41
Transformer Replacement # 446
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 1 585$
In Service Date: Summer 2020
Note 42
Transformer Replacement # 453
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 1 975$
In Service Date: Summer 2020
Note 43
Transformer Replacement # 478
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 2 084$
In Service Date: Summer 2020
Note 44
Transformer Replacement # 480
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 1 582$
In Service Date: Summer 2020
Note 45
Transformer Replacement # 510
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 1 930$
In Service Date: Summer 2020
Note 46
Transformer Replacement # 513
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 1 335$
In Service Date: Summer 2020
Note 47
Transformer Replacement # 524
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 1 720$
In Service Date: Summer 2020
Note 48
Transformer Replacement # 544
Scope: As per OEB requirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 12
Capital Cost : 1 431$
In Service Date: Summer 2020
Note 49
Pole Replacement # 18
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 4 453$
In Service Date: Fall 2020
Note 50
Pole Replacement # 185
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 6 800$
In Service Date: Fall 2020
Note 51
Pole Replacement # 461
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 5 173$
In Service Date: Fall 2020
Note 52
Transformer Replacement # 405
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 12
Capital Cost :2 875 $
In Service Date: Spring 2021
Note 53
Transformer Replacement # 487
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 5
Capital Cost : 4 300$
In Service Date: Spring 2021
Note 54
Transformer Replacement # 488
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 5
Capital Cost : 4 100$
In Service Date: Spring 2021
Note 55
Transformer Replacement # 489
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 4 400$
In Service Date: Spring 2021
Note 56
Transformer Replacement # 490
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 4 400$
In Service Date: Spring 2021
Note 57
Transformer Replacement # 496
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 5
Capital Cost : 4 400$
In Service Date: Spring 2021
Note 58
Transformer Replacement# 508
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 3 530$
In Service Date: Fall 2021
Note 59
Transformer Replacement # 511
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1
Capital Cost : 3 325$
In Service Date: Fall 2021
Note 60
Transformer Replacement # 517
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 4 050$
In Service Date: Fall 2021
Note 61
Transformer Replacement # 521
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 5 925$
In Service Date: Fall 2021
Note 62
Transformer Replacement # 530
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 4 400$
In Service Date: Fall 2021
Note 63
Transformer Replacement # 538
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 4 450$
In Service Date: Fall 2021
Note 64
Pole Replacement # 477
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removal of older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost :4 800$
In Service Date: Fall 2021
Note 65
Pole Replacement # 159
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 5 800$
In Service Date: Fall 2020
Note 66
Pole Replacement # 346
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 7 100$
In Service Date: Fall 2021
Note 67
Pole Replacement # 215
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 8 600$
In Service Date: Fall 2021
Note 68
Bollard Installation
Scope: To protect padmount transformers
Objective: Prevent MVA and safety
Customer Attachments: 12
Capital Cost : 4 000$
In Service Date: Spring 2021
Note 69
Replacement Cut Switch
Scope: Etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace cut switch and arrester. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 27 610$
In Service Date: Spring-Summer 2021
Note 70
Replacement Cut Switch
Scope: Etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace cut switch and arrester. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 10 000$
In Service Date: 2022
Note 71
Transformer Replacement # 418
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1 (Tranformers Bank)
Capital Cost : 6 525$
In Service Date: 2022
Note 72
Transformer Replacement # 432
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 17
Capital Cost : 9 750$
In Service Date: 2022
Note 73
Transformer Replacement # 448
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 18
Capital Cost : 6 950$
In Service Date: 2022
Note 74
Transformer Replacement # 452
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 10
Capital Cost : 9 750$
In Service Date: 2022
Note 75
Transformer Replacement # 461
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 10
Capital Cost : 4 250$
In Service Date: 2022
Note 76
Transformer Replacement # 470
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 5 650$
In Service Date: 2022
Note 77
Transformer Replacement # 481
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 3
Capital Cost : 6 950$
In Service Date: 2022
Note 78
Transformer Replacement # 502
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 4 250$
In Service Date: 2022
Note 79
Transformer Replacement # 509
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 6 950$
In Service Date: 2022
Note 80
Transformer Replacement # 518
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 6 950$
In Service Date: 2022
Note 81
Transformer Replacement # 519
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 6 950$
In Service Date: 2022
Note 82
Transformer Replacement # 527
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 7
Capital Cost : 4 250$
In Service Date: 2022
Note 83
Transformer Replacement # 528
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 15
Capital Cost : 6 950$
In Service Date: 2022
Note 84
Pole Replacement # 296
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 5 800$
In Service Date:2022
Note 85
Pole Replacement # 441
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 5 800$
In Service Date: 2022
Note 86
Pole Replacement # 461
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 5 800$
In Service Date: 2022
Note 87
Replacement Cut Switch
Scope: Etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace cut switch and arrester. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 10 000$
In Service Date: Spring-Summer 2023
Note 88
Transformer Replacement # 531
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 5 650$
In Service Date: 2023
Note 89
Transformer Replacement # 533
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 4 250$
In Service Date: 2023
Note 90
Transformer Replacement # 535
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 11
Capital Cost : 6 950$
In Service Date: 2023
Note 91
Transformer Replacement # 536
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 9
Capital Cost : 5 650$
In Service Date: 2023
Note 92
Transformer Replacement # 537
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 4 250$
In Service Date: 2023
Note 93
Transformer Replacement # 539
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 12
Capital Cost : 6 950$
In Service Date: 2023
Note 94
Transformer Replacement # 541
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 10
Capital Cost : 6 950$
In Service Date: 2023
Note 95
Transformer Replacement # 543
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 8
Capital Cost : 5 650$
In Service Date: 2023
Note 96
Transformer Replacement # 545
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 10
Capital Cost : 5 650$
In Service Date: 2023
Note 97
Transformer Replacement # 546
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 11
Capital Cost : 6 950$
In Service Date: 2023
Note 98
Transformer Replacement # 548
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 1 (Transformer Bank)
Capital Cost 10 250$
In Service Date: 2023
Note 99
Transformer Replacement # 551
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the remova lof older assets. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: 6
Capital Cost : 4 250$
In Service Date: 2023
Note 100
Pole Replacement # 1
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 8 750$
In Service Date: 2023
Note 101
Pole Replacement # 258
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 8 500$
In Service Date: 2023
Note 102
Pole Replacement # 304
Scope: As per OEBrequirements, etablish a comprehensive Asset Management Plan and replace existing aging assetts
Objective: Improve safety and reliability with the removalof older assets and replace damage pole. Follow the Asset Management Plan and performrequires replacement of aging assets
Customer Attachments: n/a
Capital Cost : 6 400$
In Service Date: 2023

## 2.3 System Service
System Service
Reporting Basis | Reporting Basis |  | CGAAP |  | CGAAP |  | CGAAP |  | NEWGAAP |  | NEWGAAP |  | NEWGAAP
Projects | Projects | USoA | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023
System Service | System Service |  | 2018 | Note | 2019 | Note | 2020 | Note | 2021 | Note | 2022 | Note | 2023 | Note
0
0
| PCB Program Dated Prior to 1985 | 1850 |  |  |  |  | 11532.05 | 1
| PCB Program Dated Prior to 1985 | 1850 | [6 empty] | 4895 | 2
| PCB Program Dated Prior to 1985 | 1850
| PCB Program Dated Prior to 1985 | 1850 | [8 empty] | 6000 | 4
| PCB Program Dated Prior to 1985 | 1850 | [10 empty] | 6000 | 4
Contributed Capital
|  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Sub-Total System Service - Contributed Capital
Total System Service | Total System Service |  | 0 |  | 0 |  | 11532.05 |  | 4895 |  | 6000 |  | 6000
Explanatory Notes on Projects
Notes on System Service
Note 1
Project: PCB Program Dated prior 1985
Scope: Transformer with PCB
Objective: To removed transformer with PCB if any
Customer: Safety
Capital Cost: ($11 532)
Note 2
Project: PCB Program Dated prior 1985
Scope: Transformer with PCB
Objective: To removed transformer with PCB if any
Customer: Safety
Capital Cost: ($4 895)
Note 3
Project: Pole Testing
Scope: Test every pole / 5 years
Objective: To replace pole
Customer: Safety
Capital Cost: ($4 895)
Note 4
Project: PCB Program Dated prior 1985
Scope: Transformer with PCB
Objective: To removed transformer with PCB if any
Customer: Safety
Capital Cost: ($6 000)
Note 5
Project: PCB Program Dated prior 1985
Scope: Transformer with PCB
Objective: To removed transformer with PCB if any
Customer: Safety
Capital Cost: ($6 000)

## 2.3 General Plan
General Plant
Reporting Basis | Reporting Basis |  | CGAAP |  | CGAAP |  | CGAAP |  | NEWGAAP |  | NEWGAAP |  | NEWGAAP
Projects | Projects | USoA | 2018 | Note | 2019 | Note | 2020 | Note | 2021 | Note | 2022 | Note | 2023
General Plant | General Plant |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023
| Software -Billing System | 1611 | 1080.67 | 1
| Office Equipment | 1915 | 2773 | 2
| Software | 1611 |  |  | 2988.02 | 3
| Office Equipment | 1915 |  |  | 908.54 | 4
| Computer Hardware | 1920 |  |  | 1950 | 5
| Computer Hardware | 1920 |  |  | 2648 | 6
| Software | 1611 |  |  |  |  | 628.45 | 7
| Office Equipment | 1915 |  |  |  |  | 3431 | 8
| Computer Hardware | 1920 |  |  |  |  | 617 | 9
| Software | 1611 | [6 empty] | 512.73 | 10
| Web Site | 1611 | [6 empty] | 6500 | 11
| Honeywell Connexo Netsense | 1611 | [6 empty] | 28492 | 12
| Office Equipment | 1915 | [6 empty] | 75 | 13
| Computer Hardware | 1920 | [6 empty] | 0 | 14
| Software | 1611 | [8 empty] | 3000 | 15
| Office Equipment | 1915 | [8 empty] | 1200 | 16
| Computer Hardware | 1920 | [8 empty] | 1500 | 17
| Software | 1611 | [9 empty] | 18 | 3000
| Office Equipment | 1915 | [9 empty] | 19 | 1200
| Computer Hardware | 1920 | [9 empty] | 20 | 1500
| Green Button Software | 1611 | [10 empty] | 66517.5
Contributed Capital
Sub-Total General Plant - Contributed Capital
Total General Plant | Total General Plant |  | 3853.67 |  | 8494.56 |  | 4676.45 |  | 35579.73 |  | 5700 |  | 72217.5
Explanatory Notes on Projects | [6 empty] | 92273.8
Notes on General Plant
Note 1
Software -Billing System
Scope: Upgrade billind system
Objectives: To be able to bill our customer accordily
Capital Cost: 1 081$
Note 2
Office Equipment
Scope: New scanner and photocopier
Objectives:
Capital Cost: 2 773$
Note 3
Software
Scope: Software Northstars/Upgrade Computer Station
Objectives: Bill properly customer/Work proper tool
Capital Cost: 2 988$
Note 4
Office Equipment
Scope: Fan -Table
Objectives:To work in safe environment
Capital Cost: 909$
Note 5
Computer Hardware
Scope: New Comouter Station
Objectives: Work with proper tool
Capital Cost: 1 950$
Note 6
Computer Hardware
Scope: Network Attached Storage
Objectives: To have better backup system
Capital Cost: 2648$
Note 7
Software
Scope: Zoom/Adobe Licence
Objectives:To work with proper tool
Capital Cost: 628$
Note 8
Office Equipment
Scope: New Chair and scanner
Objectives: To work in safe environment and proper tool
Capital Cost: 3 431$
Note 9
Office Equipment
Scope: Headphones for employee and directors
Objectives: To work with proper tool during video conference
Capital Cost: 617$
Note 10
Software
Scope:
Objectives:
Capital Cost: 1 113$
Note 11
Website
Scope:
Objectives:
Capital Cost: 6 500$
Note 12
Software
Scope:
Objectives:
Capital Cost: 28 492$
Note 13
Office Equipment
Scope:
Objectives:
Capital Cost: 750$
Note 14
Computer Hardware
Scope: Network Attached Storage
Objectives: To have better backup system
Capital Cost: 750$
Note 15
Software
Scope:
Objectives:
Capital Cost: 3000$
Note 16
Office Equipment
Scope:
Objectives:
Capital Cost: 1200$
Note 17
Computer Hardware
Scope: Network Attached Storage
Objectives: To have better backup system
Capital Cost: 1500$
Note 18
Software
Scope:
Objectives:
Capital Cost: 3000$
Note 19
Office Equipment
Scope:
Objectives:
Capital Cost: 1200$
Note 20
Computer Hardware
Scope: Network Attached Storage
Objectives: To have better backup system
Capital Cost: 1500$