## 2022 I-03-O-AMPCO-137-01
I-03-O-AMPCO-137-01
Ref: EB-2017-0049, Exhibit I-24-AMPCO-25, Attachment 1
Asset Replacment - Planned
# Asset Units
Asset Category |  | Population | # Replaced 2018 | # Replaced 2019 | # Replaced 2020 | # Replaced 2021 | # Forecast to be Replaced 2022 | # Forecast to be Replaced 2023 | # Forecast to be Replaced 2024 | # Forecast to be Replaced 2025 | # Forecast to be Replaced 2026 | # Forecast to be Replaced 2027
Station Transformers | All | Note 1 | 22 | 21 | 14 | 22 | 2 | 20 | 31 | 23 | 21 | 33
| In Service (Note 8) |  | 20 | 15 | 12 | 19 | 0 | 18 | 29 | 21 | 19 | 31
| Spares |  | 2 | 6 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2
Mobile Unit Substations (Note 6) |  |  | 0 | 3 | 2 | 0 | 2 | 1 | 2 | 2 | 2 | 2
Reclosers (Note 7) | All |  | 46 | 274 | 284 | 298 | 276 | 307 | 244 | 54 | 81 | 126
| Oil |  | Note 2
Vaccum
| Metalclad |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Circuit Breakers | All |  | Note 3
Oil
Vaccum
Metalclad
Switches |  |  | 18 | 23 | 10 | 20 | 19 | 10 | 14 | 12 | 11 | 20
Fuses |  |  | Note 4
Station Structures
Fences
Station Grounding Systems
Station Service Transformers
Insulators
Bus Work
Protection Relays
IEDs
Spill Containment Systems |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MUS Structures |  |  | 10 | 16 | 22 | 23 | 20 | 23 | 26 | 23 | 25 | 34
Poles | All |  | 5982 | 3,984 | 4,519 | 5344 | 5050 | 10300 | 10300 | 10300 | 10300 | 10300
| Wood |  | Note 2
Steel
Concrete
Composite
| Red Pine Wood |  | 1,166 | 1,437 | 1,720 | 1819 | Note 5
Rights of Way | kilometers of line clearing completed |  | 26070 | 28009 | 22716 | 33298 | 33053 | 31364 | 30318 | 30318.9996 | 30320.0004 | 30321.9996
Line Transformers | All |  | 1753 | 1558 | 1093 | 1241 | 1684 | 1555 | 1558 | 1423 | 70 | 20
| Pole Mounted Transformers |  | 1753 | 1539 | 1028 | 1165 | 1453 | 1325 | 1248 | 1153
Pad Mounted Transformers
| Submersible transformers |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| Transclosures and Pole-Trans Transformer |  | 0 | 19 | 65 | 76 | 231 | 230 | 310 | 270 | 70 | 20
Submarine Cables (Note 9) |  |  | 25.1 km | 155 units | 199 units | 163 units | 280 units | 280 units | 280 units | 280 units | 280 units | 280 units
Conductor | All |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| Overhead (metres) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| Underground |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Switches | Air Break & Load Break - 3 Phase |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Reclosers/Regulators | All |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| Hydraulic |  | Note 2
Electronic
Capacitor Banks |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
AMI | All |  | 24513 | 28141 | 29806 | 34707 | 108382 | 116402 | 101030 | 67889 | 40429 | 21725
| Retails Meters |  | 22397 | 25894 | 27833 | 32770 | 106387 | 114402 | 99025 | 65982 | 38871 | 20664
| Collectors |  | 972 | 741 | 778 | 655 | 914 | 917 | 919 | 874 | 714 | 486
| Repeaters |  | 1144 | 1506 | 1195 | 1282 | 1081 | 1083 | 1086 | 1033 | 844 | 575
NA | Not applicable/Not available.
Note 1 | Please refer to Exhibit I-03-B3-AMPCO-65 and Exhibit B1, Tab 1, Schedule 1, DSP Section 3.2 for the population information.
Note 2 | Hydro One does not track plannned replacements to this level of granularity for subtype.
Note 3 | When distribution station breakers are replaced, they are replaced with reclosers.
Note 4 | Hydro One does not track planned replacements to this level of granularity; as these assets are generally addressed as part of the integrated distribution station refurbishments not as individual component replacements.
Note 5 | Hydro One does not have a forecast for red pine poles specifically as they will be addressed based on condition and priority relative to other poles.
Note 6 | The 2023-2027 forecast represent the number of MUS replacements and MUS transformer replacements.
Note 7 | These replacements include the total number replaced under both the component replacement program and station refurbishments.
Note 8 | The 2023-2027 forecast is based on 106 and 12 poor condition transformers identified in SR-04 and SR-11, respectively. The forecast numbers do not include unplanned repalcements due to failures.
Note 9 | 2018 submarine cable replacement units were reported in metres of cable replaced. Since 2019, submarine cable replacement units are reported in number of cables replaced.
Note on G54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AMI numbers have been updated for 2021