## Sheet1
Incremental Capital Module Deferral Accounts
OEB-Approved Compared to Actual/Forecast by Project
|  | OEB-Approved | [5 empty] | Actual/Forecast
Line No. | Particulars ($ millions) | ICM Capital |  | In-Service Date | Total Revenue Requirement | Revenue Collection |  | ICM Capital |  | In-Service Date | Total Revenue Requirement |  | Total Revenue Collected
|  | (a) |  | (b) | (c) | (d) |  | (e) |  | (f) | (g) |  | (h)
ICMDA - EGD Rate Zone
1 | NPS 20 Don River Replacement Project | 30.047 |  | April 2020 | 8.191 | -8.191 |  | 29.8331 |  | April 2020 | 8.2102 |  | -8.1537
2 | NPS 20 Replacement Cherry to Bathurst Project | 126.73 |  | Oct 2022 | 6.149 | -6.149 |  | 126.7299 |  | N/A | 6.1154 |  | -4.1407
ICMDA - Union Rate Zones
3 | Kingsville Transmission Reinforcement Project | 118.183 |  | Nov 2019 | 36.908 | -36.908 |  | 91.845 |  | Oct 2019 | 25.6548 |  | -39.7617
4 | Stratford Reinforcement Project | 1.8 |  | Nov 2019 | 0.55 | -0.55 |  | 1.8 |  | Sep 2019 | - |  | -
5 | Windsor Line Reinforcement Project | 82.9 |  | Nov 2020 | 22.23 | -22.23 |  | 74.183 |  | Sep 2021 | 14.2108 |  | -22.2858
6 | London Lines Replacement Project | 124.039 |  | Dec 2021 | 19.357 | -19.357 |  | 100.163 |  | Dec 2021 | 15.034 |  | -19.248
7 | Total Cumulative OEB-Approved and Actual/Forecast | 483.699 | (j) |  | 93.385 | -93.385 |  | 424.554 | (i) |  | 69.2251 |  | -93.5899
8 | Variance of Actual/Forecast to OEB-Approved | [5 empty] | (i)-(j) | -59.145 |  |  | -24.1599 | (k) | -0.2049
9 | Total Cumulative ICMDA Balance | [10 empty] | (k)+(l) | -24.3648
10 | Cumulative Interest to December 31, 2023 | [11 empty] | -1.283
11 | Total Balance Proposed for Clearance | [11 empty] | -25.6478