## SEC 98
Table 1 - Summary of Material Projects Over $10 million 2013 to 2022 in $'s
Line No. | Project Name | Rate Zone | USP Category | Asset Class | In-Service Year | Source of Forecast | Forecasted Cost | Final Costs | Cost Variance | Variance % over/(under) | Variance Explanation for Projects +/- 10%
1 | Ottawa Reinforcement | EGD | System Access | Growth | 2013 | EB-2012-0099 | 51236000 | 70062162 | 18826162 | 36.74% | Please refer to PCFR for Project Variance Explanations at: https://www.rds.oeb.ca/CMWebDrawer/Record/477849/File/document
2 | Ottawa Innes Road Pipeline Replacement Project | EGD | System Renewal | Distribution Pipe | 2014 | EB-2012-0438/EB-2014-0017/EB-2015-0037 | 7254286 | 10742681.67 | 3488395.67 | 48.09% | Please refer to PCFR for Project Variance Explanations at : https://www.rds.oeb.ca/CMWebDrawer/Record/530250/File/document
3 | GTA Reinforcement Project | EGD | System Access | Growth | 2016 | EB-2012-0451 | 667400000 | 847400000 | 180000000 | 26.97% | Please refer to PCFR for Project Variance Explanations at : https://www.rds.oeb.ca/CMWebDrawer/Record/576741/File/document
4 | Tecumseh new building | EGD | General Plant | Real Estate & Workplace Services | 2016 | Budget | 16584666 | 16305455.63 | -279210.37 | -1.684%
5 | Ashtonbee Station | EGD | System Access | Growth | 2017 | EB-2012-0451/EB-2016-0034 | 14378598 | 22416266 | 8037668 | 55.9% | Please refer to PCFR for Project Variance Explanations at : https://www.rds.oeb.ca/CMWebDrawer/Record/619701/File/document
6 | Canadian Nuclear Laboratories | EGD | System Access | Growth | 2017 | EB-2015-0194 | 15503141 | 15739803.49 | 236662.49 | 1.527%
7 | 5904-2018 CX Pgm | EGD | General Plant | TIS | 2018 | Budget/AMP | 9800000 | 15307197.7 | 5507197.7 | 56.2% | Increased scope of work
8 | Dow Moore Storage Pool Drilling | EGD | System Renewal | TPUS | 2019 | EB-2017-0354 | 8877796 | 10185186 | 1307390 | 14.73% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 2, page 6
9 | 5904-2018 CX Pgm | EGD | General Plant | Integration Capital | 2019 | Budget | 11100000 | 12066293.19 | 966293.19 | 8.705%
10 | TOC Site 1 Expansion | EGD | General Plant | Real Estate & Workplace Services | 2019 | Budget | 12700000 | 12836343.52 | 136343.52 | 1.074%
11 | Don River 30" Pipeline Project* | EGD | System Renewal | Distribution Pipe | 2020 | EB-2019-0194 - ICM | 35400000 | 31013253.9867 | -4386746.0133 | -12.39% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 2, page 19
12 | Fenelon Falls Community Expansion Project | EGD | System Access | Growth | 2020 | EB-2017-0147 | 23055488 | 27910741 | 4855253 | 21.1% | Please refer to Evidence Exhibit 1, Tab 12, Schedule 1, Attachment 1, page 13
13 | Kennedy Road Expansion 2020 | EGD | General Plant | Real Estate & Workplace Services | 2020 | Budget/AMP | 12000000 | 12848080.8419 | 848080.8419 | 7.067%
14 | 2019 CIS HANA Upgrade | EGD | General Plant | Integration Capital | 2020 | Budget | 9000000 | 14141878.71 | 5141878.71 | 57.13% | Increased scope of work due to CIS integration
15 | SCOR:Meter Area-Upgrade (Ph 1-2)* | EGD | System Renewal | Compression Stations | 2021-2022 | Budget/AMP | 53233268.317 | 52156529.0286 | -1076739.2884 | -2.023%
16 | Asset & Work Management System (AWS)* | EGD | General Plant | Integration Capital | 2021-2022 | Budget | 37820211 | 38154113 | 333902 | 0.8829%
17 | NPS 2- Replacement Cherry to Bathurst* | EGD | System Renewal | Distribution Pipe | 2022 | EB-2021-0148 - ICM | 129900000 | 87698894.0092 | -42201105.9908 | -32.49% | Variances to be filed in Post Construction Financial Report, additional costs expected in 2023
18 | Thunder Bay Pipeline Project | UGL | System Renewal | Distribution Pipe | 2013 | EB-2012-0226/EB-2012-0227 | 26726000 | 25373153 | -1352847 | -5.062%
19 | Parkway West Project | UGL | System Access | Compression Stations | 2014 | EB-2012-0433 | 219400000 | 231703000 | 12303000 | 5.608%
20 | Brantford-Kirkwall/Parkway D Projects | UGL | System Access | Compression Stations | 2015 | EB-2013-0074 | 204100000 | 197378000 | -6722000 | -3.293%
21 | Sudbury Expansion Project | UGL | System Access | Growth | 2015 | EB-2015-0120 | 10825000 | 10298046.25 | -526953.75 | -4.868%
22 | CRES - Ed Centre | UGL | General Plant | REWS | 2015 | Budget | 17500000 | 16663401 | -836599 | -4.781%
23 | EAM - Enterprise Asset Management | UGL | General Plant | TIS | 2015 | Budget | 14263500 | 13634274 | -629226 | -4.411%
24 | Sarnia Expansion Project | UGL | System Access | TPUS | 2015 | EB-2014-0333 | 24318000 | 15945947.08 | -8372052.92 | -34.43% | Please refer to PCFR for Project Variance Explanations at : https://www.rds.oeb.ca/CMWebDrawer/Record/501564/File/document
25 | Leamington Pipeline Expansion Project | UGL | System Access | Growth | 2016 | EB-2016-0013 | 12344000 | 11233070.68 | -1110929.32 | -9%
26 | 2016 Dawn-Parkway Growth Project | UGL | System Access | Compression Stations | 2016 | EB-2014-0261 | 390715000 | 347061000 | -43654000 | -11.17% | Please refer to PCFR for Project Variance Explanations at : https://www.rds.oeb.ca/CMWebDrawer/Record/600177/File/document
27 | Burlington-Oakville Pipeline | UGL | System Access | TPUS | 2016 | EB-2014-0182 | 119477000 | 83262000 | -36215000 | -30.31% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 1, page 1
28 | Panhandle NPS16 Replacement Project | UGL | System Renewal | Distribution Pipe | 2016 | EB-2013-0420 | 29597000 | 26052842.37 | -3544157.63 | -11.97% | Please refer to PCFR for Project Variance Explanations at : https://www.rds.oeb.ca/CMWebDrawer/Record/597409/File/document
29 | 2017 Dawn-Parkway Project | UGL | System Access | Compression Stations | 2017 | EB-2015-0200 | 622500000 | 620050000 | -2450000 | -0.3936%
30 | Panhandle Reinforcement | UGL | System Access | TPUS | 2017 | EB-2016-0186 | 264500000 | 228574000 | -35926000 | -13.58% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 1, page 10
31 | Contrax Modernization | UGL | General Plant | TIS | 2017 | Budget | 39800000 | 40831392 | 1031392 | 2.591%
32 | Sudbury Replacement Project | UGL | System Renewal | Distribution Pipe | 2018 | EB-2018-0305 - ICM | 95300000 | 96710070.7309 | 1410070.7309 | 1.48%
33 | Stratford Reinforcement Project | UGL | System Access | Growth | 2019 | EB-2018-0305 - ICM | 28540000 | 25002540.7188 | -3537459.2812 | -12.39% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 2, page 26
34 | Kingsville Transmission* | UGL | System Access | Growth | 2019 | EB-2018-0305 - ICM | 121400000 | 91553885.2192 | -29846114.7808 | -24.58% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 2, page 10
35 | Chatham-Kent Rural Project | UGL | System Access | Growth | 2019 | EB-2018-0188 | 19100000 | 14812201.88 | -4287798.12 | -22.45% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 2, page 23
36 | Owen Sound Reinforcement Project* | UGL | System Service | Growth | 2020 | EB-2019-0183 | 68965000 | 70165009.4159 | 1200009.4159 | 1.74%
37 | Windsor Line Replacement* | UGL | System Renewal | Distribution Pipe | 2021 | EB-2019-0194 - ICM | 106805000 | 83123644.2378 | -23681355.7622 | -22.17% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 2, page 29
38 | London Lines Replacement* | UGL | System Renewal | Distribution Pipe | 2021 | EB-2020-0181 - ICM | 161100000 | 122270345.0621 | -38829654.9379 | -24.1% | Variances to be filed in Post Construction Financial Report
39 | Sarnia Industrial Line Reinforcement* | UGL | System Access | TPUS | 2021 | EB-2020-0181 - ICM | 32900000 | 36966604 | 4066604 | 12.36% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 2, page 32
40 | CIS Integration* | UGL | General Plant | Integration Capital | 2021 | Budget | 45000000 | 48792727 | 3792727 | 8.428%
41 | North Bay Community Expansion Project | UGL | System Access | Growth | 2021 | EB-2019-0188 | 10095250 | 11861640 | 1766390 | 17.5% | Please refer to Exhibit 1, Tab 12, Schedule 1, Attachment 1 , page 17
42 | Dawn-Cuthbert* | UGL | System Service | TPUS | 2022 | EB-2021-0148 - ICM | 24200000 | 20046387.2463 | -4153612.7537 | -17.16% | Project is in-service, additional project closeout costs expected in 2023.
43 | Byron Transmission Reinforcement* | UGL | System Access | Growth | 2022 | EB-2021-0148 - ICM | 20400000 | 24127164.4314 | 3727164.4314 | 18.27% | Initial estimate was created based on the assumption of 1-year project execution; however, the project was extended over 2-years plus resulting in higher contractor cost, inspection cost, IDC & Internal OH. Stopping and tapping cost also not included in original estimate.
44 | Kirkland Lake* | UGL | System Renewal | Distribution Pipe | 2022 | EB-2021-0148 - ICM | 20700000 | 27389720.3747 | 6689720.3747 | 32.32% | Higher than estimated construction costs were realized due to complex Horizontal Directional Drill (HDD) installation across Blanche River. HDD had to be redesigned twice after initial attempts to complete crossing failed as a result of challenging geotechnical conditions.
45 | Greenstone Pipeline Project* | UGL | System Access | Growth | 2022 | EB-2021-0205 | 25777789 | 23508093.1706 | -2269695.8294 | -8.805%
46 | Cost of Gas* | UGL | General Plant | Integration Capital | 2022 | Budget | 26500000 | 17288745.7158 | -9211254.2842 | -34.76% | Change of scope from custom build to migrating EGD into UG SAP platform
(*) Projects inlcude indirect overheads
(1) Final Costs may be different than Post Construction Financial Reporting due to ongoing clean up or restoration costs