## Sheet1
|  | Filed (LTC) |  |  | Updates
Project Name | Docket # | PI (Phase 1) | NPV (Phase 1) $000's | Forecast Capex (before CIAC) $000's | PI (Phase 1) | NPV (Phase 1) $000's | Actual Capex $000's | Notes
Leamington Expansion Pipeline Project | EB-2012-0431 | 1 | 0 | 8200 | 1.02 | 257 | 7895
Parkway West Project | EB-2012-0433 | N/A | N/A | 219400 | N/A | N/A | 231703
Brantford-Kirkwall/Parkway D Project | EB-2013-0074 | 1.46 | 94035 | 204076 | 1.51 | 100150 | 197378
Dawn Parkway 2016 Expansion Project | EB-2014-0261 | 0.39 | -238466 | 390715 | 0.41 | -210917 | 347061
Sarnia Expansion Pipeline Project | EB-2014-0333 | 1.06 | 180 | 24317 | 1.06 | 180 | 15946 | 1
Burlington Oakville Pipeline Project | EB-2014-0182 | N/A | -102600 | 119477 | N/A | -71594 | 83262
Sudbury Expansion Project | EB-2015-0120 | 1 | 0 | 10825 | 1 | 0 | 10298 | 2
Leamington Expansion Pipeline Project (Ph. 2) | EB-2016-0013 | 1.11 | 1538 | 12344 | 1.19 | 2485 | 11233
Panhandle Reinforcement Project | EB-2016-0186 | 0.19 | -212382 | 264468 | 0.2 | -180273 | 228574
2017 Dawn Parkway Project | EB-2015-0200 | 0.43 | -344236 | 622500 | 0.42 | -344324 | 620050
Ottawa Reinforcement Project | EB-2012-0099 | 1.06 | 15485.1534 | 51236 | 0.99346 | -1687 | 70062.162 | 3
GTA Reinforcement Project | EB-2012-0451 | 1.73 | 667432.377 | 652144.124 | 1.4599 | 505490.2422 | 869806.472 | 4,5,6
Ashtonbee Station (Request to Vary from GTA Project) | EB-2012-0451/EB-2016-0034 | N/A | N/A | 14378.598 | N/A | N/A | 22416.266 | 7
Notes:
1 - PI and NPV calculated on the growth portion of the project only - net investment used for feasibility $2,818,000.
2 - PI and NPV calculated on the growth portion of the project only $6,592,000 less CIAC of $4,717,000 for a net investment used for feasibility of $1,875,000.
3 - Original filed PI of 1.02 incorrectly reflected service capital commencing a year early; PI of 1.06 reflects updated profile.
4 - $869.8 million in capex inclusive of Ashtonbee to be comparable to filed LTC feasibilty.
5 - $652.1 million capex stated in 2013 dollars, consistent with LTC PI calculation. Value excludes $3.5 million Ashtonbee Station Request to Vary expenditure, approved post LTC approval.
6 - GTA Reinforcement Project Capex excluding Ashtonbee is $847.4 million.
7 - Included in GTA Reinforcement Project Feasibility figures.