## E-2-1-A1
Filed March 29, 2023, EB-2022-0318, Exhibit E-1-2 Attachment 1, Page 1 of 1
Capital Projects
Note: 1. All the dollar figures listed below are in millions 2. Life to Date Capital Budget is the sum of prior year Capital actuals and current year Capital budget to account for the progressive elaboration of the budget. Life to Date Capital Actual is the sum of prior year Capital actuals and current year Capital actuals.
Change Initiatives/ Projects | 2019 Capital Budget | 2019 Capital Actual | 2020 Capital Budget | 2020 Capital Actual | 2021 Capital Budget | 2021 Capital Actual | 2022 Capital Budget | 2022 Capital Actuals | Life to Date Capital Budget | Life to Date Capital Actuals | Life to Date Capital Variance | Variance Reason | 2023 Capital Budget | 2024 Capital Budget | 2025 Capital Budget | Status
Hub Intranet Redevelopment | [7 empty] | 1.8 | 0 | 1.8 | 1.8 | The original budget was less than $1 million. Through planning activities we identified the need for additional hardware requirements which have led to the increase in project costs. |  |  |  | In-flight - Execution
Replacement of the Settlement Systems | 1.5 | 0.8 | 8.4 | 8.3 | 8.8 | 9.3 | 7 | 10.5 | 25.4 | 28.9 | 3.5 | Increase in spending due to change requests to support software usability that introduced additional hardware and software requirements. | 4.4 | 0.8 | 0.1 | In-flight - Execution
Centralized Alarm Management System Replacement |  |  |  |  | 2.5 | 3.1 | 0.8 | 1.1 | 3.9 | 4.2 | 0.3 | Increase in spending due to additional vendor costs to address technical issues identified during the testing phase. |  |  |  | In-flight - Execution
External Identity Management (Portal) |  | 0.1 | 1.1 | 0.8 | 0.3 | 0.7 |  | 0.1 | 1.6 | 1.7 | 0.1 | Increased spending due to change request to to include additional applications, account types, and functionality in scope. |  |  |  | Closed
SCADA/Energy Management System (EMS) Upgrade |  |  | 5.7 | 5.8 | 5.6 | 3.9 | 1.4 | 2.1 | 11.1 | 11.8 | 0.7 | Increase in spending is due to shift in vendor payments from 2021 to 2022 due to vendor delays in achieving some of the project milestones. |  |  |  | In-flight - Execution
Dynamic Limits in Real-Time |  |  |  |  | 1.1 | 0.04 | 2 | 0.5 | 2.04 | 0.54 | -1.5 | Underspend due to delay in completion of some planning activities including procurement, and achieving some of the project milestones. | 2.8 | 0.2 | 0 | In-flight - Planning
Wide Area Visualization Environment (WAVE) - Phase 2 |  |  | 0.5 | 0.2 | 1.2 | 0.8 | 0.6 | 0.4 | 1.6 | 1.4 | -0.2 | Underspend due to vendor delays in achieving some of the project milestones and internal resource constraints. Payments delayed to subsequent years. | 0.5 | 0.3 | 0 | In-flight - Execution
Long Term Demand Forecast Tool Replacement | [6 empty] | 0.8 | 0 | 0.8 | 0 | -0.8 | Underspend due to delays in project initiation and refinement of estimates during Initiation phase. | 1 | 0.8 | 0 | In-flight - Planning
Network Performance Monitoring and Diagnostic (NPMD) Solution |  | 0.9 |  | 0.4 |  |  | 2.8 | 1.1 | 4.1 | 2.4 | -1.7 | Underspend due to $0.8M cost saving achieved through IESO's competitive procurement process, and shift in spending to 2023 due to supply chain issues. |  |  |  | In-flight - Execution
Core Network Refresh | [6 empty] | 0.5 | 0.3 | 0.5 | 0.3 | -0.2 | Underspend due to extended hardware delivery delay. | 2 | 0.6 | 0 | In-flight - Planning
Market Analysis and Simulation Toolset (MAST) | [6 empty] | 2 | 0.2 | 2 | 0.2 | -1.8 | Underspend due to delays caused by unavailability of critical IESO and vendor resources. | 0.5 | 2.4 | 1 | In-flight - Planning
MIM Technical Refresh | [7 empty] | 2.5 | 0 | 2.5 | 2.5 | Project need was identified only in early 2022 and hence was not part of the 2022 Business Plan. | 1.1 | 0 | 0 | In-flight - Execution
PMU Integration - Phase 3 | 1 | [5 empty] | 0.3 | 0 | 0.3 | 0 | -0.3 | Underspend due to deferral of project to 2023 due to internal resource constraints. | 1 | 1 | 1 | Not Initiated - Plan to start in Q2 2023
Data Excellence Program |  |  | 0.5 | 0.5 | 1.3 | 0.4 | 0.7 | 0.4 | 1.6 | 1.3 | -0.3 | Underspend due to change in strategy to reduce vendor engagement in 2022, and postpone further vendor engagement to 2023. | 0.5 | 0.8 | 0.5 | In-flight - Execution
Enterprise Data Warehouse Optimization |  |  |  |  | 0.5 | 0.1 |  | N/A | 0.1 | N/A | N/A | Project is being reported as part of Data Excellence Program since 2022. |  |  |  | In-flight - Execution
Enabling Resources Program |  |  |  |  | 0.5 | 0 |  | 0 | 0 | 0 | 0 | Underspend is in line with the estimates refined during the Planning Phase. | 0.3 | 0.6 | 3.3 | In-flight - Planning
Addressing Market Surveillance Panel (MSP) Recommendations |  |  |  |  | 1.8 | 0.1 | 0.5 | 0.3 | 0.6 | 0.4 | -0.2 | Underspend especially for Tranmission Rights Market Enhancement and Platform Refresh project due to delay in completion of Planning Phase. | 1.2 | 0.4 | 0.5 | In-flight - Execution
Transmission Rights Market Enhancement and Platform Refresh | [6 empty] | 1 | N/A | 1 | N/A | N/A | Project is being reported as part of MSP Program since 2022. |  |  |  | In-flight - Planning
Enterprise Antivirus Replacement | [5 empty] | 0.01 | 2.3 | 0.3 | 2.31 | 0.31 | -2 | Underspend is in line with the capital baseline approved at the end of Planning Phase based on the revised approach to use a product with subscription based licensing. | 0.3 | 0 | 0 | In-flight - Execution
Resource Adequacy Program |  |  |  |  | 1 | 1.9 | 2 | 1 | 3.9 | 2.9 | -1 | Underspend, especially for the Capacity Auction Enhancements project is in line with the baseline approved at the end of Planning Phase. 2021 Actual has been updated to reflect the $1.7M capital expenditure transfer from the closed Capacity Auction project to this project. | 1 | 1.2 | 1.3 | In-flight - Initiation
Space Needs Program | [7 empty] | 0 | 0 | 0 | 0 |  | 7 | 10 | 13 | Not Initiated - Plan to start in 2023
Space Needs Program - Office Pilot | [7 empty] | 1.6 | 0 | 1.6 | 1.6 | Project was originally estimated to be less than $1 million. Through initiation and planning activities, additional needs were identified that has led to increased costs. |  |  |  | In-flight - Execution
Backup Operating Centre and Backup Data Centre Relocation | [7 empty] | 0 | 0 | 0 | 0 |  | 5 | 5.4 | 0 | In-flight - Initiation
Data Historian Expansion and Upgrade | [6 empty] | 1 | 0 | 1 | 0 | -1 | Underspend due to exclusion of infrastructure costs as it will be funded by a different initiative. |  |  |  | In-flight - Planning
Meter Data Management System Replacement (MDMS) | [7 empty] | 0 | 0 | 0 | 0 |  | 0.3 | 2 | 3.5 | Not Initiated - Plan to start in 2023
Enabling Grid Transformation Program | [7 empty] | 0 | 0 | 0 | 0 |  | 0.1 | 1.1 | 7 | Not Initiated - Plan to start in 2023
Lawson Refresh | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0.2 | 1.9 | Not Initiated - Plan to start in 2023
Firewall Refresh | [7 empty] | 0 | 0 | 0 | 0 |  | 0.2 | 2.8 | 0 | Not Initiated - Plan to start in 2023
Data Loss Prevention (DLP) Phase 2 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 1.5 | 1 | Not Initiated - Plan to start in 2024
Windows Infrastructure Refresh | [7 empty] | 0 | 0 | 0 | 0 |  | 1.9 | 0.1 | 0 | Not Initiated - Plan to start in 2023
LogRhythm SIEM Refresh | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 2.9 | 0.1 | Not Initiated - Plan to start in 2024
Network WAN Infrastructure | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 1.6 | 0.1 | Not Initiated - Plan to start in 2024
Cybectec Refresh | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0.9 | 0.1 | Not Initiated - Plan to start in 2024
Aspen File Server Refresh | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 2.1 | Not Initiated - Plan to start in 2025
Intrusion Prevention System (IPS) Refresh 2025 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 1.4 | Not Initiated - Plan to start in 2025
Projects Closed Prior to 2022 | 10 | 14.5 | 4.4 | 5.9 | 0.2 | -1.4 |  | N/A | N/A | N/A | N/A | Updated 2021 Actual to reflect transfer of $1.7M capital expenditure from the closed Capactiy Auction project to the Resource Adequacy Program - Capacity Auction Enhancements project. |  |  |  | Closed
Subtotal: Capital Projects ($1 million and above) | 12.5 | 16.3 | 20.6 | 21.9 | 24.8 | 18.95 | 25.7 | 24.2 | 82.85 | 81.4 | -1.5 |  | 31.1 | 37.6 | 37.9
Other Initiatives/Projects (Less than $1 million) | 4.8 | 4.3 | 5 | 5.1 | 7.8 | 7.5 | 4.3 | 4 | 21.2 | 20.9 | -0.3 |  | 3.9 | 6 | 5.7
Total Core IESO Capital Portfolio | 17.3 | 20.6 | 25.6 | 27 | 32.6 | 26.3 | 30 | 28.2 | 103.9 | 102.1 | -1.8 |  | 35 | 43.6 | 43.6
Market Renewal Program | 26 | 10.3 | 25.9 | 25 | 44.6 | 24 | 35.4 | 34 | 95.9 | 94.5 | -1.4 | $6.4 million of the variance has been reassigned to future years through the approval of the new baseline for the program; the remaining $1.4 million is due to underspending from shared resources that charge to the program as needed. | 51 | 32.3 | 14.6 | In-flight - Execution
Total Capital Including Market Renewal | 43.3 | 30.9 | 51.5 | 52 | 77.2 | 50.3 | 71.2 | 62.2 | 198.6 | 195.4 | -3.2 |  | 86 | 75.9 | 58.2