## 2AA – Capital Projects FINAL
Appendix 2-AA
Capital Projects Table
| 2017 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 Bridge Year | 2024 Test Year | 2025 | 2026 | 2027 | 2028 | Check
| MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS | MIFRS
| COS Board Approved - Proxy | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Bridge | Test | Forecast | Forecast | Forecast | Forecast
| COS Board Approved - Combined | Year 1 Actual - 2017 Combined | Year 2 Actual - Combined | Year 3 Actual - 2019 | Year 4 Actual - 2020 | Year 5 Actual - 2021 | Year 6 Actual - 2022 | Year 7 Bridge - 2023 | Year 8 Test - 2024
SYSTEM ACCESS
PCB Transformer Replacements (A 01) | 118655 | 70093 | 0 | 122773 | -2519 |  |  |  |  | 0 | 0 | 0 | 0
Customer Recoverable System Modifications (A 02) | 281092 | 690963 | 258086 | 764044 | 1350435 | 1421111 | 1061956.7971 | 420388.8862 | 433903.141 | 2232472.2038 | 349432.8279 | 356421.4844 | 363549.9141
Customer Driven System Expansions (A 11) | 209034 | 82717 | 68784 | 84754 | 53665 | 94060 | 54625.8767 | 63094.7147 | 55498.9676 | 56608.947 | 57741.1259 | 58895.9484 | 60073.8674
Residential Service Connections (A 12) | 480213 | 398439 | 309335 | 381089 | 398015 | 452097 | 332385.4123 | 399623.1846 | 446751.5645 | 455686.5958 | 464800.3277 | 474096.3342 | 483578.2609
General Service Connections (A 13) | 1029898 | 517279.64 | 565596 | 939081 | 488930 | 447137 | 803796.1656 | 513958.6868 | 651832.9587 | 764869.6179 | 780167.0102 | 795770.3504 | 811685.7575
Expansions for Residential Subdivisions (A 14) | 230530 | -51134.02 | 39406 | 577065 | 857507 | -52445.66 | 199066.47 | 140126.6974 | 141196.2288 | 144020.1534 | 146900.5564 | 149838.5676 | 152835.3389
System Relocations (A 15) | 164881 | 0 | 144121 | 1245701 | 34144 | 808330 | 1468409.07 | 266777.4418 | 92552.2195 | 394403.2639 | 716291.3292 | 98217.1558 | 100181.4989
Sentinel Lights (A 19) | 0 | 0 | 1234 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0
Meter Installations (A 21) | 289626 | 221374 | 287214 | 255567 | 118790 | 212496 | 145276.89 | 180710.3029 | 269828.0691 | 275224.6305 | 280729.1231 | 522104 | 357000
Kenora Underground Services | 10000 | 12562 | 14503
Miscellaneous | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Total - System Access | 2813929 | 1942293.62 | 1688491 | 4370074 | 3298967 | 3382785.34 | 4065516.6817 | 1984679.9143 | 2091563.1492 | 4323285.4122 | 2796062.3004 | 2455343.8409 | 2328904.6377
System Access Contributions | -1326298 | -1016596.98 | -1243210.99 | -2517222.4 | -2922524.63 | -2741595.23 | -3415480.56 | -1421568.5283 | -1534422.3928 | -3437204.0206 | -1864813.0575 | -1596413.0575 | -1628341.3186
System Access Net Expenditures | 1487631 | 925696.64 | 445280.01 | 1852851.6 | 376442.37 | 641190.11 | 650036.1217 | 563111.3861 | 557140.7564 | 886081.3915 | 931249.243 | 858930.7834 | 700563.3191
SYSTEM RENEWAL
25 kV Voltage Conversions (B11) | [9 empty] | 764105 | 975387 | 2497539.1659 | 7333619.1669
Spruce/Hemlock Pole Line | 0 | 0 | 2862.954 | 12876 | 54583 | 3305 | 647546.3116
Kingsway/ Walsh Pole Line | 0 |  |  |  | 30921 | 89851 | 881084.1168
20th Side Rd 12 k Rebuild |  |  |  |  | 7103.54
Victor St Pole Line Rebuild |  |  |  |  | 11556.38
Tupper St 4 kV Pole Line |  |  |  |  | 477146.88 | 46
Walsh Pole Line Rebuild |  |  |  |  | 234749.35 | 250132
21F6 PH2 Rebuild |  |  |  |  | 3237
Arthur St 2017 25kV Rebuild | 0 | 5438 | 1016775.1642 | 4000 | 0
25kV Pole Replacements | 584384 | 113617 | 0 | 0 | 0
Walsh-Sprag/Kings |  | 6670 | 12413.2454 | 33694 | 91660 | 206295
Carl-Dublin-Strand Pole |  | 11676 | 18966.8051 | 565002 | 133576
10M1 - Northern-vickers |  | 13732 | 187393.8855 | 232788 | 0
Pineview-Sycamore Pole |  | 10620 | 11479.2936 | 750882 | -832 | 30150
Agate-Amethyst Pole Line |  | 6453 | 15496.0726 | 639 | 0 | 86956 | 685463.3144
Arthur Street Easement |  | 3396 | 8793.9778 | 102 | 0
Edward-William Pole Line |  | 0 | 0 | 26316 | 10304 | 41251 | 571063.5436
Edward/Ironwood Pole Line |  | 0 | 0 | 16083 | 12170 | 56122 | 380147.3231
Central Ave 17M1/3 Pole | [5 empty] | 22773 | 742191.4272
Central Ave 17M 5/6/7 Pole | [5 empty] | 19543 | 1995.8515
University/ Sherbrooke | [5 empty] | 17082 | 99373.8438 | 949890.6476
17M2 PH2 Pole Placement | [6 empty] | 539258.8073 | 1024381.7986
Edward Ironwood 25kV | [7 empty] | 636152.6692
Inglewood-Ashland Pole | [6 empty] | 9107.8482 |  | 1556541.6238
| 584384 | 171602 | 1274181.3983 | 1642382 | 1066175.15 | 823506 | 4557232.3875 | 2610425.1154 | 1556541.6238 | 764105 | 975387 | 2497539.1659 | 7333619.1669
4 kV Line Voltage Conversions (B12) | [9 empty] | 8351443 | 6903173 | 4401254 | 0
Black Bay/Dewe Rebuild | 1174110 | 1304889 | 36 | 0 | 0
Dewe/Rita Rebuild | 1489302 | 1596588 | -2010.1682 | 0 | 0
Donald-Edward Rebuild | 0 | 0 | 0 | 37757 | 174442 | 483326 | 1225639.6918
Ford/ Walnut | 0 | 3884 | 245237.5421 | 438531 | 0
MacDougall /Court | 0 | 0 | 1957.0182 | 111 | 977082 | 937571
Ontario/ Second rebuild | 0 | 0 |  |  |  | 15353 | 93409.4674 |  | 416996.5068
Finlayson- Brodie | 893725 | 1020139 | 0 | 0 | 0
Strathcona Avenue Pole Line | 0 | 0 | 11234.2652 | 636193 | 0
McPherson-Christie | 0 | 0 | 843862.6664 | 0 | 0
Redmond/Egan Rebuild | 0 | 0 | 0 | 433383 | 1124791
Elm/Campbell | 0 | 0 | 11188.1456 | 360070 | 693539
College Tupper Rebuild | 0 | 0 | 0 | 8392 | 37901 | 176817 | 820410.4127 | 1678497.2022
Miles-Edward (Volt Conv) | 0 | 26706 | 814001.5766 | 0 | 0
Cumming - Brodie | 580677 | 549082 | 1744565.5994 | 0 | 0
Northern-Vickers | 0 | 28793 | 554011.7876 | 1379733 | 0
Donald/Mountdale | 310256 | 369281 | 625690.608 | 0 | 0
Court/ Van Horne | 0 |  | 0 | 9246 | 1022497 | 1411654
Algoma/Wolseley Rebuild | 0 |  | 0 | 2018 | 8618
Court-Elgin Rebuild | 0 |  |  |  | 16271.07 | 24134 | 105603.7418 |  | 948732.5896
Court-Wilson Rebuild |  |  |  |  | 7626.75 | 18843 | 159359.6369 | 1106874.4362 | 2398869.3418
21F1 Rebuild and Volt Con |  | 29068 | 42297.4002 | 304334 | 828174 | 652727
21F5 |  |  |  |  | 13629
21F6 |  | 3211 | 0 | 0 | 8710 | 23637 | 19929.9972 | 853441.7036 | 1121603.7123
McDougall/Court PH1-4kV | 549716 | 146824 | 72.0138 | 0 | 0
21F1-Phase 2 - Rebuild | 0 | 0 | 0 | 2122 | 35279 | 353697 | 500697.2963 | 657096.5716
Algoma/Wolseley Rebuild | 0 | 0 | 1283.7495 | 0 | 0 | 786796
MacDougall Court Line Reb PH1-25kV | 0 | 894798 | -20037.7963 | 0 | 0 | 723293
Donald/ Vickers Rebuild | 0 |  |  |  |  | 24523 | 45867.803 | 731607.2346 | 1493244.9174
Tupper/ Dorothy Rebuild | 0 | [5 empty] | 37011.6966 |  | 839867.2289
| 4997786 | 5973263 | 4873390.4081 | 3611890 | 4948559.82 | 5632371 | 3007929.7436 | 5027517.1482 | 7219314.297 | 8351443 | 6903173 | 4401254 | 0
U/G Installations/ Replacements (B14) | 0 | 0 | 0 | ` | 0 |  |  |  |  | 658684.38 | 1528750 | 2537746.281 | 2588501.2066
UG Project Design | 0 | 178 | 407400 | 0 | 0 |  | 361984.1247
2018 UG Project Design | 0 | 1863 | 0 | 0 | 0
Part B 10m2 & 10m5 cable | 0 | 177 | 1143.4905 | 253447 | 0
Underground Project | 0 | 1961 | 18522.3824 | 291076 | 0
Phillips-Anten | 0 | 0 | 0 | 266780 | 4888 | 467817
Phillips-Anten UG Refurb | [5 empty] | 38800
10M4 & 10M6 Cable |  |  |  |  | 14086.15 | 205271
River St 2M2/3 Circuit UG | [5 empty] | 155359
College Park PH2 | [5 empty] | 64128
College Park PH5 | [5 empty] | 112967
James st. Sub UG Refurb PH2 | [6 empty] | 27245.9125 | 500000 | 645769.0974
James st. Sub UG Refurb PH3 | [6 empty] | 7574.0921
River St 2M2/3 Circuit UG | [6 empty] | 670353.7799
| 0 | 4179 | 427065.8729 | 811303 | 18974.15 | 1044342 | 1067157.9092 | 500000 | 645769.0974 | 658684.38 | 1528750 | 2537746.281 | 2588501.2066
Small Pole Replacements (A 16) | 342512 | 564340 | 314476 | 421652 | 258392.2509 | 127668 | 27082.7268 | 614121.9171 | 767108.8372 | 782451.014 | 798100.0342 | 814062.0349 | 830343.2756
Lines Safety Reports (A 17) | 761834 | 644419 | 788986 | 1066477 | 910050.8236 | 1445290 | 842225.8671 | 1267955.4336 | 858848.0878 | 876025.0496 | 893545.5506 | 911416.4616 | 929644.7908
Transformer/ Switch/ Switchgear Replacements (A18) | 756484 | 989713 | 672006 | 781072 | 661570.3745 | 598339 | 807905.1114 | 867570.5322 | 931872.655 | 950510.1081 | 969520.3102 | 988910.7164 | 1008688.9308
Operations Safety Reports (A 22) | 0 | 75773 | 288841 | 108099 | 0
Kenora Overhead Renewal | 140000 | 267340 | 206957
Kenora Proactive Renewal (Inspection and Testing Outcomes) | 302500 | 10691 | 238390 | 0 | 0
Kenora Operations Support |  | 0 | 54321
Kenora MTS Refurb |  | 0 | 0 | 30698 | 0 | 28620 | 49355.8953
Stations Renewal Project |  | 0 | 0 | 0 | 21084 | 17944
Design Work |  | 0 | 0 | 0 | 0 |  | 53318.2491 | 273455 | 193354
Tree Trimming |  | 0 | 0 | 0 | 0 |  |  | 700000 | 416895
Change in Meter & Transformer Spares | 0 | 15634.76 | 79611 | 32251 | 597168 | 292907 | 700535.86
Miscellaneous | 370600 | 30916 | 184939 | 130040 | 191874 | 194301 | 338414.0884 | 123620.9525 | 124334.8406
Sub-Total - System Renewal | 8256100 | 8747870.76 | 9403164.6793 | 8635864 | 8673848.5689 | 10205288 | 11451157.8383 | 11984666.099 | 12714038.4388 | 12383218.5516 | 12068475.895 | 12150928.6598 | 12690797.3707
|  |  |  | 0 | 0
SYSTEM SERVICE
Grid Modernization (A 35) | 60375 | 110765 | 218483 | 146052 | 3667 | 242148 | 141726.1 | 276719.9366 | 323181.2623 | 329645.1198 | 336238.0222 | 342962.7826 | 349822.0383
SCADA | 0 | 40469 | 70041 | 285529 | 83671
Sub-Total - System Service | 60375 | 151234 | 288524 | 431581 | 87338 | 242148 | 141726.1 | 276719.9366 | 323181.2623 | 329645.1198 | 336238.0222 | 342962.7826 | 349822.0383
0
GENERAL PLANT
Rolling Stock | 619826 | 427028 | 622123 | 439982 | 491899 | 689798 | 787953.56 | 325000 | 600000 | 715000 | 715000 | 800000 | 850000
Building Improvements | 155000 | 111818 | 86036 | 40996 | 26061 | 44365 | 55400 | 80000 | 155250 | 158355 | 161522.1 | 164752.542 | 168047.5928
IT (Software and Hardware) | 213000 | 143738 | 114127 | 462976 | 191109 | 451743 | 478451.73 | 419500 | 305000 | 380000 | 365500 | 416000 | 442500
Equipment - Tools, Shop, Testing, Power and Communications | 203000 | 155733 | 244407 | 108043 | 125692 | 84605 | 178133.59 | 277645 | 171170 | 174593.4 | 178085.268 | 181646.9734 | 185279.9128
Office Equipment | [6 empty] | 29230.14 | 54000 | 51000 | 52020 | 53060.4 | 54121.608 | 55204.0402
Miscellaneous | 113191 | 90476 | 25870 | 20799 | 28692 | 2799 |  | 18000
Sub-Total - General Plant | 1304017 | 928793 | 1092563 | 1072796 | 863453 | 1273310 | 1529169.02 | 1174145 | 1282420 | 1479968.4 | 1473167.768 | 1616521.1234 | 1701031.5458
Miscellaneous, Projects Less Than Materiality |  | 0 | 0 | 0
Total | 11108123 | 10753594.4 | 11229531.6893 | 11993092.6 | 10001081.9389 | 12361936.11 | 13772089.08 | 13998642.4217 | 14876780.4575 | 15078913.4629 | 14809130.9282 | 14969343.3492 | 15442214.2739
Check to Financial Reconcilliation |  |  |  | -29939.29 | -1833.8411 | 207392.1856
Notes:
Check to FA Continuity |  | 3.2596e-09 | -0.4107 | -0.41 | 0.2489 | -0.05 | -0.21 | 0 | 0
1 Please provide a breakdown of the major components of each capital project undertaken in each year. Please ensure that all projects below the materiality threshold are included in the miscellaneous line. Add more projects as required.
2 The applicant should group projects appropriately and avoid presentations that result in classification of significant components of the capital budget in the miscellaneous category.
0
Note on K10: Bob Zappitelli: Bell ASHIP 1.8M
Note on C12: Katie Speziale: $72,066 in contributions in kind
Note on F12: Katie Speziale: $145,320 in contributions in kind
Note on H12: Katie Speziale: 93874 in contributions in kind
Note on H13: Katie Speziale: 36049 in contributions in kind
Note on C14: Katie Speziale: Subdivisions were capitalized in prior years based on estimates, when final developer costs came in a reduction to contributions in kind required
Note on E14: Katie Speziale: 490,025 in contributions in kind
Note on F14: Katie Speziale: 661,104 in contributions in kind
Note on G14: Katie Speziale: We capitalized Parkdale Stage 6 based on original estimate, when we got final costs from developer in 2021, had to adjust parkdale stage 6
Note on H14: Katie Speziale: 159504 in contributions in kind
Note on I107: Katie Speziale: need to allocate out 500k addition to projects
Note on A109: Katie Speziale: Added unplanned capital here
Note on G109: Katie Speziale: Adjusted for transformers returned to inventory (not new capital additions)
Note on I123: Katie Speziale: SCADA
Note on G129: Katie Speziale: Contribution on parkdale stage 6 - JE for 2020, closed in 2021