## Summary Chart
Confidential Draft for Illustrative Purposes | [9 empty] | Inc / (Dec) | Inc / (Dec) |  | Inc / (Dec)
CAD $MM | [7 empty] | Rate Case | As of May 2023 | Total Delta from Rate Case | Delta explained in Qtrly Reports | Delta explained in document: | Delta after last Qtrly Report | Delta after last Qtrly Report explained:
NextBridge Project Cost - East West Tie |  | $MM CAD | Comment
Engineering & Construction |  | 614.2385 | As of May 2023 |  |  |  | Engineering & Construction | 614.28 | 614.2385 | -0.041485 | -2.2204e-16 |  | -0.041485
1 | Engineering, Design and Procurement | 9.9753 | As of May 2023 |  |  |  | Engineering, Design and Procurement | 8.5 | 9.9753 | 1.4753 | 1.5 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | -0.024698 | Project completion. No additional engineering expenses were needed
2 | Materials and Equipment | 68.7007 | As of May 2023 |  |  |  | Materials and Equipment | 66.94 | 68.7007 | 1.7607 | 1.7 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | 0.060749 | True up to material costs additional spare material procurement
8 | Site Clearing, Access | 137.1984 | As of May 2023 |  |  |  | Site Clearing, Access | 140.64 | 137.1984 | -3.4416 | -3.4 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | -0.041622 | Project completion. No additional engineering expenses were needed
9 | Construction | 398.3641 | As of May 2023 |  |  |  | Construction | 398.2 | 398.3641 | 0.16409 | 0.2 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 10/21/22; page 12 | -0.035915 | Project completion. No additional engineering expenses were needed
Environmental & Remediation Activities |  | 31.3 | As of May 2023 |  |  |  | Environmental & Remediation Activities | 31.6 | 31.3 | -0.3 | -0.3 |  | 1.0547e-15
3 | Environmental and Regulatory Approvals | 19.1 | As of May 2023 |  |  |  | Environmental and Regulatory Approvals | 19.1 | 19.1 | 0 | 0 |  | 0
10 | Site Remediation | 12.2 | As of May 2023 |  |  |  | Site Remediation | 12.5 | 12.2 | -0.3 | -0.3 | Quarterly OEB report filed 1/20/23; page 12 | 1.0547e-15
Indigenous Activities |  | 24.0831 | As of May 2023 |  |  |  | Indigenous Activities | 23.6 | 24.0831 | 0.48309 | 1.7764e-15 | Quarterly OEB report filed 1/20/23; page 12 | 0.48309
5 | Indigenous Economic Participation | 10.4 | As of May 2023 |  |  |  | Indigenous Economic Participation | 9.7 | 10.4 | 0.7 | 0.1 |  | 0.6 | Increase in legal feels to Support BLP Buy-In
6 | Indigenous Consultation | 13.6831 | As of May 2023 |  |  |  | Indigenous Consultation | 13.9 | 13.6831 | -0.21691 | -0.1 |  | -0.11691 | Project completion. No additional engineering expenses were needed
4 | Land Rights (excludes Aboriginal) | 23.3305 | As of May 2023 |  |  |  | Land Rights (excludes Aboriginal) | 23.8 | 23.3305 | -0.46949 | -0.5 | Quarterly OEB report filed 4/21/22; page 29 | 0.030512 | n/a
7 | Other Consultation | 1.7 | As of May 2023 |  |  |  | Other Consultation | 2.5 | 1.7 | -0.8 | -0.8 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 4/21/22; page 29 | 0 | n/a
11 | Contingency | 0 | As of May 2023 |  |  |  | Contingency | 0 | 0 | 0 | 0 |  | 0 | n/a
12 | Regulatory | 5.4774 | As of May 2023 |  |  |  | Regulatory | 5.4 | 5.4774 | 0.077391 | 0.2 | Quarterly OEB report filed 4/21/22; page 29 | -0.12261 | Project completion. No additional engineering expenses were needed
13 | EWT Management | 5.7651 | As of May 2023 |  |  |  | EWT Management | 4.9 | 5.7651 | 0.86514 | 0.9 | Quarterly OEB report filed 10/22/21; page 28 & Quarterly OEB report filed 4/21/22; page 29 | -0.034864 | Project completion. No additional engineering expenses were needed
Total Project Spend including Spares |  | 705.8946 | As of May 2023 |  |  |  | Total Project Spend including Spares | 706.08 | 705.8946 | -0.18535 | -0.5 | n/a | 0.31465
14 | Interest During Construction (IDC) | 31.3 | As of May 2023 | Category | Amount | Docket Approved in | Interest During Construction (IDC) | 31 | 31.3 | 0.3 | 0.3 | Quarterly OEB report filed 4/21/22; page 28 | 0 | n/a
Total Construction Costs |  | 737.1946 | Approved in D&O from EB-2020-0150 | Construction | 737.1 | EB-2020-0150 | Total Construction Costs | 737.08 | 737.1946 | 0.11465 | -0.2 |  | 0.31465
Development | Development Costs | 31.2 | Approved in D&O from EB-2017-0182 | Development | 31.2 | EB-2017-0182
Phase Shift | Phase Shift Costs | 5.3 | Approved in D&O from EB-2020-0150 | Phase Shift | 5.3 | EB-2020-0150
Total Construction, Development, Phase Shift | COVID | 773.6946 | Approved in D&O from EB-2020-0150
Construction Cost Variance: Wildfire |  | 0 | To be reviewed in 2023; for rate year 2024
Construction Cost Variance: Kama Cliffs |  | 0 | To be reviewed in 2023; for rate year 2024
Construction Cost Variance: White Lake Narrows |  | 0 | To be reviewed in 2023; for rate year 2024
Construction Cost Variance: Delay & Other |  | 0 | To be reviewed in 2023; for rate year 2024
Total Construction Cost Variance |  | 0 | To be reviewed in 2023; for rate year 2024
COVID-19 |  | 0 | To be reviewed in 2023; for rate year 2024
Total Construction Cost Variance & COVID-19 |  | 0 | To be reviewed in 2023; for rate year 2024
Total |  | 773.6946

## Construction Cost Bal
OEB Bucket | Sub Category | Budget
01. Engineering, Design and Procurement | NEER - Engineering | 9.9753
01. Engineering, Design and Procurement Total |  | 9.9753
02. Materials and Equipment | NEER - Conductor/OPGW/OHGW | 26.5475
| NEER - Structures/poles | 42.1532
02. Materials and Equipment Total |  | 68.7007
03. Environmental and Regulatory Approvals | Construction Compliance | 2.6
| Consultation Support | 0.1
| Environment Surveys & Studies | 4.2
| Environmental Permits and licensing | 3.9
| Environmental Project Management - inter | 1
| Environmental Protection and Compensatio | 6.7
| Project Management - consultants | 0.6
03. Environmental and Regulatory Approvals Total |  | 19.1
04. Land Rights (excludes Aboriginal) | Bell Crossing | 0.015809
| Damage Settlements (Crown) - CanACRE | 0.30325
| Damage Settlements (Crown) - Fees | 0.27867
| Damage Settlements (Crown) - Internal la | 0.058624
| Damage Settlements (Private) - CanACRE | 0.63781
| Damage Settlements (Private) - Fees | 1.9061
| Damage Settlements (Private) - Internal | 0.06063
| GIS - CanACRE | 0.42286
| Land Acquisition (Crown) - CanACRE | 0.33943
| Land Acquisition (Crown) - Fees | 2.448
| Land Acquisition (Crown) - Internal labo | 0.2731
| Land Acquisition (Private) - CanACRE | 1.8523
| Land Acquisition (Private) - Fees | 4.9784
| Land Acquisition (Private) - Internal la | 0.29658
| Land permitting - CanACRE | 1.1568
| Market & Timber Valuations | 0.53912
| Project coordination - CanACRE | 0.061635
| Regulatory (External Legal Fee's) | 0.25284
| Surveys - Internal labour | 0.058624
| Surveys costs | 3.1491
| Temporary Work Space (Private) | 1.0795
| Third Party Payments (Agreements) - Fees | 2.0995
| Third Party Payments (Agreements) - Inte | 0.2027
| Trapper Costs | 0.26821
| Open Damage Settlements, permitting, and project coordination - CanACRE | 0.59095
04. Land Rights (excludes Aboriginal) Total |  | 23.3305
05. Indigenous Economic Participation | 28.2 Land Permits - External legal fees | 0.2
| 28.2 Land Permits - MFN | 0.9
| 28.2 Land Permits -ppfn | 1
| AGLP fees | 2
| Bonus fees - MNO | 1.6
| Indigenous Benefits - BLP | 2.7
| Indigenous Benefits - Consultants | 0.1
| Indigenous Benefits - External legal fee | 0.4
| Indigenous Benefits - Internal labour | 0.2
| Indigenous Benefits - MNO | 1.3
05. Indigenous Economic Participation Total |  | 10.4
06. Indigenous Consultation | Capacity Funding Agreements - Consultati | 2.4099
| Capacity Funding Agreements - Fees | 0.17283
| Community Investments - Fees | 0.00027
| Community Investments - Internal labour | 0.0066104
| Construction Phase Management Support - | 0.11658
| Education & Training - Consultants | 1.6279
| Education & Training - Fees | 6e-05
| Education & Training - Internal labour | 0.0066875
| Indigenous Capacity Support - Capacity p | 7.2143
| Indigenous Capacity Support - Consultant | 0.10817
| Indigenous Capacity Support - External l | -0.0038583
| Indigenous Capacity Support - Fees | 0.010463
| Indigenous Capacity Support - Internal L | 0.18938
| Indigenous monitors and tours - Aborigin | 1.5716
| Indigenous monitors and tours - External | 0.022716
| Indigenous monitors and tours - Internal | 0.22951
06. Indigenous Consultation Total |  | 13.6831
07. Other Consultation | Administration - Internal labour | 0.4
| Community Investments - External costs | 0.1
| Engagement events - Internal labour | 0.1
| Government Relations | 0.8
| Notices and newsletters - External costs | 0.3
07. Other Consultation Total |  | 1.7
08. Site Clearing, Access | E&C Atwell | 1.8096
| Valard Construction - Civil Work | 135.3888
08. Site Clearing, Access Total |  | 137.1984
09. Construction | E&C NEER - NEER Internal Labor | 6.9029
| NEER - NEER Construction Services | 8.7897
| NEER - NEER Internal Expense | 0.39579
| Valard Construction - Conductor, OPGW/OH | 86.9734
| Valard Construction - Contractor G&A, Mo | 19.4534
| Valard Construction - Foundations | 122.3047
| Valard Construction - Material Managemen | 7.7489
| Valard Construction - Project Management | 45.8828
| Valard Construction - Reimbursables | 0.35358
| Valard Construction - Structures | 99.5588
09. Construction Total |  | 398.3641
10. Site Remediation | Neutral Footprint | 1
| Site Rem Yards | 10.3
| Site Remediation Env Inspection | 0.8
| Site Remediation Internal Time | 0.1
10. Site Remediation Total |  | 12.2
12. Regulatory | BZA Appeal/Judicial review - Legal | 0.12438
| BZA Appeal/Judicial review-Travel/accomo | 0.00017921
| Crossing application support - Aird & Be | 0.0020277
| Expropriation application (s. 99 OEB Act | 0.0023297
| General regulatory support - Aird & Berl | 0.34476
| General regulatory support - Experts | 0.16363
| General regulatory support - Travel/acco | 0.022694
| Land support (not including expropriatio | 0.027081
| Leave to construct (including intervenor | 1.0346
| Rate case application - Aird & Berlis | 0.5177
| Rate case application - Travel | 0.006841
| Reg BZA Matter - Internal Labour | 0.0068449
| Reg Crossing application support - Inter | 0.0055008
| Reg Expropriation application (s. 99 OEB | 0.035785
| Reg General regulatory support - Interna | 0.68023
| Reg Land support (not including expropri | 0.089016
| Reg Leave to construct (including interv | 0.88285
| Reg Rate case application - hearing intervenor | 0.20291
| Reg Rate case application - Internal la | 1.3281
12. Regulatory Total |  | 5.4774
13. EWT Management | Monthly Reporting/Accounting - external | 0.075982
| OEB Reporting - external consultant | 0.052358
| Office expenses | 0.2442
| Operations & Maintenance - field office | 0.11236
| Operations & Maintenance - field visit | 0.022261
| Operations & Maintenance - Ops lead | 0.3821
| Operations & Maintenance - Studies/prepa | 0.12627
| PMO Interconnection studies - internal l | 0.0053096
| PMO Monthly Reporting/Accounting - inter | 1.4603
| PMO OEB Reporting - internal labour | 0.032526
| PMO Project Management - internal labour | 2.2621
| Project Management - employees T&E | 0.060578
| Project Management - external consultant | 0.7503
| Project Management - government relation | 0.032882
| Regulatory Support - external consultant | -0.17489
| Regulatory Support - internal labour | 0.067334
| Year-end Audit - audit fees | 0.25313
13. EWT Management Total |  | 5.7651
14. Interest During Construction | IDC - construction | 31.3
14. Interest During Construction Total |  | 31.3
Grand Total |  | 737.1946

## CCVA & COVID
Period/Year |  | JAN 2019 - MAY 2023
Company Hierarchy (Auth) |  | CH2TRANS NEE Transmission
Source (CC=10; IO=15; PS=20) |  | Project System
Inputs (S)/Outputs (H) |  | S Inputs
Account(s)
#N/A
Amount-Obj Currency
WBS-Project |  | WBS | Time-Year | 2020 | 2021 | 2022 | 2023
P-4921 | Const Var: NextBridge Construction Final | P-4921-001-09 | Carrying Charge IDC | 134.8 | 133286.83 | 291655.91 |  | IDC on CCVA & last month const's IDC (outside of Rate Case Amount)
|  | P-4921-002-09 | Const Var: Valard Construction - Contrac |  |  | 10133021 |  | Delays
|  | P-4921-002-12 | Const var: Cama Cliffs |  | 9091759.47 | 2977976 |  | Kama Cliffs
|  | P-4921-002-13 | Const var: Forest Fire Construct shutdn |  | 20526459 | 282805 |  | Wildfire
|  | P-4921-003-03 | White Lake Narrow E&C |  |  | 3961420 |  | White Lake Narrows (E&C Valard)
|  | P-4921-003-04 | White Lake Narrow Environmental | 349481.83 | 66718.65 | 82713.41 | -7294.19 | White Lake Narrows (Enviro - Non Valard)
|  | P-4921-003-05 | White Lake Narrow First Nations | 79686.48 |  | 300000 |  | White Lake Narrows (First Nations - Pic Mobert)
|  | P-4921-005-03 | Const Var: Other - BZA Settlement |  | 420000 |  |  | BZA Settlement
P-4837 | COVID-19 | P-4837-001-01 | Eng and Const NEER COVID |  | 0 | 77930 |  | TDI
|  | P-4837-002-01 | Eng and Const Valard COVID |  |  | 110600206 |  | Valard
|  | P-4837-005-01 | FNM Consultation COVID | 126869.26 | -126869.26 | 384110.66 |  | First Nations Consultation (Supercom)
|  | P-4837-006-01 | FNM Participation COVID | 293915.01 | -293915.01 | 640906.56 |  | First Nations Participation (Atwell)
|  | P-4837-009-01 | PMO COVID | 28.24 | -28.24 | -7118.29 |  | Other
|  | P-4837-011-01 | Carry Charge IDC COVID | 295.79 | -295.79 | 7346.8 |  | IDC on COVID & last month const's IDC (outside of Rate Case Amount)

## Development and Phase Shift
|  |  | Permanent | Permanent | Permanent | Permanent | Permanent
|  |  | Designation Decision | All other Development Costs | $5.3M | Write off | $5.3M
|  |  | Reclassed from P-3217 | Reclassed from P-2156 | Reduce Dev | Reduce Dev | Phase Shift
P-4480-001-01 | Development cost | Engineering and Construction - NEER | 8.7125 | 1.5509
P-4480-001-02 | Write - Off | Engineering and Construction - NEER |  |  |  | -0.77147
P-4480-002-01 | Development cost | Engineering and Construction - Valard
P-4480-002-02 | Write - Off | Engineering and Construction - Valard
P-4480-003-01 | Development cost | Environmental | 4.1141 | 3.7884 | -0.46
P-4480-003-02 | Write - Off | Environmental |  |  |  | -1.1494 | 0.46
P-4480-004-01 | Development cost | Land | 2.1905 | 3.61 | -1.439
P-4480-004-02 | Write - Off | Land |  |  |  | -0.0069041
P-4480-004-03 | Land Acquisition (Private) - Internal la | Land |  |  |  |  | 0.20368
P-4480-004-04 | Land Acquisition (Private) - CanACRE | Land |  |  |  |  | 1.2353
P-4480-005-01 | Development cost | FNM - Consultation Support | 1.9911 | 1.2629
P-4480-005-02 | Write - Off | FNM - Consultation Support |  |  |  | -0.0077728
P-4480-006-01 | Development cost | FNM - Participation |  | 3.4322 | -3.4322
P-4480-006-02 | Write - Off | FNM - Participation
P-4480-006-05 | Indigenous Benefits - BLP | FNM - Participation |  |  |  |  | 3.4154
P-4480-006-06 | Indigenous Benefits - Consultants | FNM - Participation |  |  |  |  | 0.017
P-4480-007-01 | Development cost | Stakeholder Relations | 0.9195 | 0.66752
P-4480-007-02 | Write - Off | Stakeholder Relations |  |  |  | -0.17342
P-4480-008-01 | Development cost | Regulatory | 0.93021 | 0.94328
P-4480-008-02 | Write - Off | Regulatory |  |  |  | -0.11427
P-4480-009-01 | Development cost | PMO | 3.5401 | 1.5106
P-4480-009-02 | Write - Off | PMO |  |  |  | -1.1024
P-4480-010-01 | Development cost | Other costs |  | 0.23016
P-4480-010-02 | Write - Off | Other costs |  |  |  | -0.35152
P-4480-011-01 | Development cost | Carrying charges |  | 0.85547
P-4480-011-02 | Write - Off | Carrying charges
Total |  |  | 22.398 | 17.8515 | -5.3312 | -3.6773 | 5.3314 | 8.886
|  |  | Development Spend | 40.2495
|  |  | Construction Cost eligible | -5.3312 | -9.0085
|  |  | Write off | -3.6773
|  |  | Ending Balance After Write Off | 31.241
|  |  | Actual Development Costs | 40.2495
|  |  | Allow Dev costs - Beg bal CWIP | 31.241 | Include Carry Costs
|  |  | Write-off | -9.0085

## P-3217 and P-2156 Pivot
See P-3217_$22.4M_Detail |  |  |  | See P-2156 thru 7-17_Detail
Sum of Value in Obj. Crcy |  |  |  | Sum of Value in Obj. Crcy
Descr. | Object | CO object name | Total | Discipline | Descr. | Object | CO object name | Total
E&C | P-3217-001-04 | NEET | 3180.61 | P-2156-001 | E&C | P-2156-001-01 | Third party | -8.085e-10
| P-3217-001-05 | FPL | 92755.41 |  | E&C | P-2156-001-02 | Enbridge | 1.8758e-12
| P-3217-001-06 | NEER | 1439432.34 |  | E&C | P-2156-001-04 | NEET | 0
| P-3217-001-07 | NEER - Canada | -355.58 |  | E&C | P-2156-001-05 | FPL | 4357.04
| P-3217-001-08 | Tline Design (Contract) | 1698377.18 |  | E&C | P-2156-001-06 | NEER | 732481.44
| P-3217-001-09 | Foundation Design (Contract) | 105750 |  | E&C | P-2156-001-07 | NEER - Canada | -3.5527e-13
| P-3217-001-10 | Structure Design and Testing | 1985606.88 |  | E&C | P-2156-001-08 | Tline Design (Contract) | 589546.63
| P-3217-001-12 | Land Survey and Lidar | 1503229.86 |  | E&C | P-2156-001-09 | Foundation Design (Contract) | 0
| P-3217-001-13 | Geotech (Contract) | 933903.43 |  | E&C | P-2156-001-10 | Structure Design and Testing | -1.5134e-09
| P-3217-001-14 | Third Party Engineering (Contract) | 356786.46 |  | E&C | P-2156-001-12 | Land Survey and Lidar | 108186.22
| P-3217-001-15 | Studies (Contract) | 146000 |  | E&C | P-2156-001-13 | Geotech (Contract) | 36054.68
| P-3217-001-16 | Other - Misc E&C | 131948.62 |  | E&C | P-2156-001-14 | Third Party Engineering (Contract) | 1.3086e-10
| P-3217-001-17 | Other - Misc Project Costs | 315905.78 |  | E&C | P-2156-001-15 | Studies (Contract) | 25351.87
E&C Total |  |  | 8712520.99 |  | E&C | P-2156-001-16 | Other - Misc E&C | 104283.95
Environmental | P-3217-003-02 | Enbridge | 614337.61 |  | E&C | P-2156-001-17 | Other - Misc Project Costs | -72027.21
| P-3217-003-03 | Enbridge - Internal Staff expenses | 39199.41 |  | E&C | P-2156-001-27 | NEE - Project Delay | 22708.02
| P-3217-003-06 | NEER | 341.64 | P-2156-001 Total |  |  |  | 1550942.64
| P-3217-003-07 | NEER - Canada | 637.5 | P-2156-002 | Land | P-2156-002-01 | Third party | 72027.21
| P-3217-003-08 | Environmental Surveys and Studies | 1783967.43 |  | Land | P-2156-002-02 | Enbridge | 0
| P-3217-003-09 | Regulatory Applications | 775017.3 |  | Land | P-2156-002-25 | 3rd party - Project Delay | 12754.27
| P-3217-003-10 | Environmental Protection and Compensatio | 53731.78 | P-2156-002 Total |  |  |  | 84781.48
| P-3217-003-11 | Consultation Support | 143359.82 | P-2156-003 |  |  |  | 3703600.22
| P-3217-003-12 | Project Management | 587451.37 | P-2156-004 | Land | P-2156-004-01 | Third party | 2901559.12
| P-3217-003-22 | Golder Associates | 116036 |  | Land | P-2156-004-02 | Enbridge | 224177.47
Environmental Total |  |  | 4114079.86 |  | Land | P-2156-004-03 | Enbridge - Internal Staff expenses | 11167.4
FNM | P-3217-005-01 | Third party | 669629.69 |  | Land | P-2156-004-04 | NEET | 1.4211e-14
| P-3217-005-02 | Enbridge | 62787.25 |  | Land | P-2156-004-06 | NEER | 4.9738e-14
| P-3217-005-03 | Enbridge - Internal Staff expenses | 5812.64 |  | Land | P-2156-004-07 | NEER - Canada | -1.5987e-14
| P-3217-005-04 | NEET | 932.21 |  | Land | P-2156-004-08 | Survey Notification & Consent (Land Agen | 8460
| P-3217-005-07 | NEER - Canada | 376433.47 |  | Land | P-2156-004-09 | Consultation (Land Agent) | 24930
| P-3217-005-08 | Internal Expenses | 36800.99 |  | Land | P-2156-004-10 | Aird & Berlis - Land Agreements | 51737.33
| P-3217-005-09 | Capacity Funding to Communities | 577431.65 |  | Land | P-2156-004-11 | Option Fee | 134833.33
| P-3217-005-10 | External Legal Counsel | 246434.46 |  | Land | P-2156-004-15 | Review Fee | 200000
| P-3217-005-11 | Aboriginal advisory board | 14805.09 |  | Land | P-2156-004-25 | 3rd party - Project Delay | 4807.72
FNM Total |  |  | 1991067.45 |  | Land | P-2156-004-26 | Enbridge - Project Delay | 44368.24
Interconnect | P-3217-008-01 | Third party | 68005.47 |  | Land | P-2156-004-32 | Reimbursements | 3952.37
| P-3217-008-06 | NEER | 15872.74 | P-2156-004 Total |  |  |  | 3609992.98
Interconnect Total |  |  | 83878.21 | P-2156-005 | FNM | P-2156-005-01 | Third party | 312085.18
Land | P-3217-004-01 | Third party | 1704632.14 |  | FNM | P-2156-005-02 | Enbridge | 7.6398e-10
| P-3217-004-02 | Enbridge | 226458.55 |  | FNM | P-2156-005-03 | Enbridge - Internal Staff expenses | -932.21
| P-3217-004-03 | Enbridge - Internal Staff expenses | 32067.05 |  | FNM | P-2156-005-04 | NEET | 932.21
| P-3217-004-04 | NEET | 1723.05 |  | FNM | P-2156-005-07 | NEER - Canada | 18778.1
| P-3217-004-06 | NEER | 309.38 |  | FNM | P-2156-005-08 | Internal Expenses | 3462.42
| P-3217-004-07 | NEER - Canada | 34.99 |  | FNM | P-2156-005-09 | Capacity Funding to Communities | 752740.83
| P-3217-004-09 | Consultation (Land Agent) | 195249.54 |  | FNM | P-2156-005-10 | External Legal Counsel | 155713.33
| P-3217-004-10 | Aird & Berlis - Land Agreements | 30064.16 |  | FNM | P-2156-005-11 | Aboriginal advisory board | -1.819e-12
Land Total |  |  | 2190538.86 |  | FNM | P-2156-005-25 | 3rd party - Project Delay | 1750.21
PMO | P-3217-009-01 | Third party | 877025.51 |  | FNM | P-2156-005-27 | NEE - Project Delay | 10589.28
| P-3217-009-02 | Enbridge | 125207.36 |  | FNM | P-2156-005-30 | NEE - Pukaskwa Park | 7815.13
| P-3217-009-03 | Enbridge - Internal Staff expenses | 5680.54 | P-2156-005 Total |  |  |  | 1262934.48
| P-3217-009-04 | NEET | 1669598.71 | P-2156-006 | Stakeholders | P-2156-006-01 | Third party | 270146.29
| P-3217-009-05 | FPL | 2188.66 |  | Stakeholders | P-2156-006-02 | Enbridge | 246158.28
| P-3217-009-06 | NEER | 217365.83 |  | Stakeholders | P-2156-006-03 | Enbridge - Internal Staff expenses | 42376.83
| P-3217-009-07 | NEER - Canada | 323714.22 |  | Stakeholders | P-2156-006-04 | NEET | -1.1369e-13
| P-3217-009-08 | 214 King St. W. Off Exp. | 229561.86 |  | Stakeholders | P-2156-006-07 | NEER - Canada | 3.908e-13
| P-3217-009-09 | Safety Review - Labor | 5843.2 |  | Stakeholders | P-2156-006-09 | Chamber of Commerce | 0
PMO Total |  |  | 3456185.89 |  | Stakeholders | P-2156-006-25 | 3rd party - Project Delay | 37679.98
Regulatory | P-3217-007-01 | Third party | 27170.03 |  | Stakeholders | P-2156-006-26 | Enbridge - Project Delay | 71154.86
| P-3217-007-02 | Enbridge | 463410.63 | P-2156-006 Total |  |  |  | 667516.24
| P-3217-007-03 | Enbridge - Internal Staff expenses | 16177.41 | P-2156-007 | Regulatory | P-2156-007-01 | Third party | -2.2737e-12
| P-3217-007-04 | NEET | 12647.26 |  | Regulatory | P-2156-007-02 | Enbridge | 447605.44
| P-3217-007-05 | FPL | 37064.01 |  | Regulatory | P-2156-007-03 | Enbridge - Internal Staff expenses | 11640.81
| P-3217-007-06 | NEER | 16945.84 |  | Regulatory | P-2156-007-04 | NEET | -9.5213e-13
| P-3217-007-07 | NEER - Canada | 10.86 |  | Regulatory | P-2156-007-05 | FPL | -7.3896e-13
| P-3217-007-08 | Aird & Berlis - Leave to Construct | 85107.56 |  | Regulatory | P-2156-007-06 | NEER | -4.7962e-12
| P-3217-007-09 | Concentric | 47794.84 |  | Regulatory | P-2156-007-07 | NEER - Canada | 3.8369e-13
| P-3217-007-10 | Elenchus | 9900 |  | Regulatory | P-2156-007-08 | Aird & Berlis - Leave to Construct | 114734.46
| P-3217-007-11 | Stakeholder costs | 6380.39 |  | Regulatory | P-2156-007-09 | Concentric | 5.8211e-12
| P-3217-007-12 | Aird & Berlis - Rate application | 80287.14 |  | Regulatory | P-2156-007-10 | Elenchus | 1400
| P-3217-007-15 | NEET - Regulatory - Leave to Construct | 20355.77 |  | Regulatory | P-2156-007-11 | Stakeholder costs | 2.2737e-13
| P-3217-007-16 | FPL - Regulatory - Leave to Construct | 25341.26 |  | Regulatory | P-2156-007-12 | Aird & Berlis - Rate application | 867.15
| P-3217-007-17 | NEER - Regulatory - Leave to Construct | 6237.9 |  | Regulatory | P-2156-007-15 | NEET - Regulatory - Leave to Construct | 14350.84
| P-3217-007-18 | NEET - Regulatory - Rate application | 20172.84 |  | Regulatory | P-2156-007-16 | FPL - Regulatory - Leave to Construct | 9.0949e-13
| P-3217-007-19 | FPL - Regulatory - Rate application | 16520.92 |  | Regulatory | P-2156-007-17 | NEER - Regulatory - Leave to Construct | 6030.91
| P-3217-007-21 | Enbridge - Leave to Construct | 85.86 |  | Regulatory | P-2156-007-18 | NEET - Regulatory - Rate application | 1.4779e-12
| P-3217-007-22 | Enbridge - Rate application | 38603.51 |  | Regulatory | P-2156-007-19 | FPL - Regulatory - Rate application | -7.5033e-12
Regulatory Total |  |  | 930214.03 |  | Regulatory | P-2156-007-21 | Enbridge - Leave to Construct | -4.9738e-13
Stakeholders | P-3217-006-01 | Third party | 448944.64 |  | Regulatory | P-2156-007-22 | Enbridge - Rate application | -1.4552e-11
| P-3217-006-02 | Enbridge | 425469.05 |  | Regulatory | P-2156-007-25 | 3rd party - Project Delay | 193992.15
| P-3217-006-03 | Enbridge - Internal Staff expenses | 41292.49 |  | Regulatory | P-2156-007-26 | Enbridge - Project Delay | 147347.66
| P-3217-006-04 | NEET | 974.13 |  | Regulatory | P-2156-007-27 | NEE - Project Delay | 5315.56
| P-3217-006-07 | NEER - Canada | 2583.56 |  | Regulatory | P-2156-007-29 | Enbridge - Pukaskwa Park | 1.4779e-12
| P-3217-006-09 | Chamber of Commerce | 235 | P-2156-007 Total |  |  |  | 943284.98
Stakeholders Total |  |  | 919498.87 | P-2156-008 | Interconnect | P-2156-008-01 | Third party | -19.36
Grand Total |  |  | 22397984.16 |  | Interconnect | P-2156-008-06 | NEER | -4.9738e-13
[5 empty] | Interconnect | P-2156-008-07 | NEER - Canada | -1.5987e-14
|  |  |  | P-2156-008 Total |  |  |  | -19.36
|  |  |  | P-2156-009 | PMO | P-2156-009-01 | Third party | 166571.41
[5 empty] | PMO | P-2156-009-02 | Enbridge | 66373.76
[5 empty] | PMO | P-2156-009-03 | Enbridge - Internal Staff expenses | 7047.03
[5 empty] | PMO | P-2156-009-04 | NEET | 851026.6
[5 empty] | PMO | P-2156-009-05 | FPL | 1136.16
[5 empty] | PMO | P-2156-009-06 | NEER | 34837.39
[5 empty] | PMO | P-2156-009-07 | NEER - Canada | 66088.45
[5 empty] | PMO | P-2156-009-08 | 214 King St. W. Off Exp. | 20415.02
[5 empty] | PMO | P-2156-009-09 | Safety Review - Labor | -1.819e-12
[5 empty] | PMO | P-2156-009-10 | Fibre Optics Opportunity | 0
[5 empty] | PMO | P-2156-009-11 | Overall 3rd Party GIS | 9419.66
[5 empty] | PMO | P-2156-009-25 | 3rd party - Project Delay | 128206.3
[5 empty] | PMO | P-2156-009-26 | Enbridge - Project Delay | 2664
[5 empty] | PMO | P-2156-009-27 | NEE - Project Delay | 155008.76
[5 empty] | PMO | P-2156-009-29 | Enbridge - Pukaskwa Park | 1803.24
|  |  |  | P-2156-009 Total |  |  |  | 1510597.78
|  |  |  | P-2156-011 | Land | P-2156-011-01 | Third party | 16901.95
[5 empty] | Land | P-2156-011-04 | NEET | -40.43
[5 empty] | Land | P-2156-011-07 | NEER - Canada | 2.558e-13
|  |  |  | P-2156-011 Total |  |  |  | 16861.52
|  |  |  | P-2156-012 | FNM part | P-2156-012-01 | Third party | 502526.06
[5 empty] | FNM part | P-2156-012-02 | Enbridge | 176827.47
[5 empty] | FNM part | P-2156-012-03 | Enbridge - Internal Staff expenses | 17530.72
[5 empty] | FNM part | P-2156-012-04 | NEET | 21232.67
[5 empty] | FNM part | P-2156-012-05 | FPL | 0
[5 empty] | FNM part | P-2156-012-07 | NEER - Canada | 378283.63
[5 empty] | FNM part | P-2156-012-08 | External expenses | 15617.9
[5 empty] | FNM part | P-2156-012-09 | External Legal Counsel | 1116540.88
[5 empty] | FNM part | P-2156-012-10 | Capacity Funding to Communities | 1163612.25
[5 empty] | FNM part | P-2156-012-26 | Enbridge - Project Delay | 2739.2
[5 empty] | FNM part | P-2156-012-27 | NEE - Project Delay | 20476.79
|  |  |  | P-2156-012 Total |  |  |  | 3415387.57
|  |  |  | P-2156-013 | Pic River - Other | P-2156-013-01 | Third party | 218788.38
[5 empty] | Pic River - Other | P-2156-013-07 | NEER - Canada | 11374.76
|  |  |  | P-2156-013 Total |  |  |  | 230163.14
|  |  |  | P-2156-014 | Carry Charge | P-2156-014-01 | Carrying Charges | 855473.64
|  |  |  | P-2156-014 Total |  |  |  | 855473.64
|  |  |  | Grand Total |  |  |  | 17851517.31

## Land
Incremental land optioning negotiations | Time | Staff Expenses | External parties | TOTALS
Engineering & construction |  |  |  | 0
Environment |  |  |  | 0
Land | 95584.2685 | 108098.5804 |  | 203682.8489
CanACRE |  |  | 1257702.8255 | 1235316.8255
First Nation Métis |  |  |  | 0
Stakeholder relations |  |  |  | 0
Regulatory |  |  |  | 0
Project Management office |  |  |  | 0
TOTAL | 95584.2685 | 108098.5804 | 1257702.8255 | 1438999.6744
Budget |  |  |  | 460000