## Sheet1
|  | SaskPower I1K Transmission Project | Manitoba - Minnesota Transmission Project (ACTUAL) | West Fort McMurray Project (ACTUAL) | NALCOR Lower Churchill Project (ACTUAL) | Wataynikaneyap Transmission Project - Post Pandemic (ACTUAL - Includes 10% Loss in post-COVID Period) | Comperable Projects Totals / Average (ACTUAL) | East-West Tie Transmission Line Project (BUDGET) | East-West Tie Transmission Line Project (ACTUAL) | East-West Tie Transmission Line - (MANHOURS CALCULATED AT MM RATES) | East-West Tie Transmission Line Project - (PRODUCTIVITY LOSS COMPARED TO MM RATES)
ASSEMBLY | Manhours | 122002.73 | 130927.49 | 395552.12 | 195094 | 64401.8182 | 907978.1582 | 473256 | 639591 | 373112.4263 | 41.66%
| Weight | 4789006.21 | 4083893 | 22151443.9 | 11886401 | 2943894 | 45854638.11 | 18016821 | 18842893 | 18842893
| Assembly (kg per manhour) | 39.2533 | 31.192 | 56.0013 | 60.9265 | 45.7113 | 50.5019 | 38.0699 | 29.4608 | 50.5019
ERECTION | Manhours | 66128.75 | 40346 | 108203.51 | 87424 | 28966.3636 | 331068.6236 | 120181 | 285221 | 135900.0798 | 52.35%
| Weight (kg) | 4789006.21 | 4083892.7382 | 22151443.9 | 11886401 | 2992766 | 45903509.8482 | 18016821 | 18842893 | 18842893
| Erection (kg per manhour) | 72.4194 | 101.2218 | 204.7202 | 135.9627 | 103.3187 | 138.6526 | 149.9141 | 66.0642 | 138.6526
STRINGING | Stringing Hours | 144456.7 | 99366 | 316794.2 | 238254.75 | 94542.7273 | 893414.3773 | 345062 | 310984 | 204161.9098 | 34.35%
| Line length (m) | 267050 | 120430.423 | 508581.806 | 491500 | 470140.5 | 1857702.729 | 445403 | 445403 | 445403
| conductor length (m) | 1335250 | 1324734.653 | 7120145.284 | 3932000 | 1880562 | 15592691.937 | 3563222 | 3563222 | 3563222
| Stringing (meters per manhour by conductor length) | 9.2433 | 13.3319 | 22.4756 | 16.5033 | 19.8911 | 17.4529 | 10.3263 | 11.4579 | 17.4529
[10 empty] | Average | 42.29%